## Version_Control
VERSION CONTROL — EngageOS Sprint Tracker & Traceability
File naming: claude_v<NNN>_<proper file name>_YYYYMMDD_HHMI.xlsx. Companion: EngageOS product workbook v005 (baseline) -> v006 (22:22, S1-S8 dev) -> v007 (22:55, S9-S10 drafts) = backlog source of truth (D12 pattern); its v008 stays planned for the live Meta verification wave.
Version | Date/Time | Author | Change Description | Status
v001 | 2026-09-10 23:06 | Claude for Senthil/KP | THIS FILE — Consolidated live execution tracker for EngageOS (WhatsApp Business Platform, wave-1), created on Senthil's 23:06 instruction to mirror the TeleField v001 tracker pattern. Rebuilds the full record of BOTH prior runs with proper version stamps: v006 run (22:22) = S1-S8 development, 15 modules, 16 suites / 73 tests at 100%x4 coverage (D13), 75 stories Done-in-code + 8 pending-live; v007 run (22:55) = S9-S10 draftable scope, 4 WhatsApp-compliance modules (24h session window, webhook dedupe/burst, opt-in proof, demo mode), 20 suites / 78 tests at 100%x4, 10 stories Drafted + ST-097 In progress. E001-E014 logged; 100-story traceability with per-story version-stamped evidence; rollup formula-verified. Code: engageos_v0.6.0_src.zip + engageos_v0.7.0_src.zip. | Released
v002 | 2026-09-10 23:10 | Claude for Senthil/KP | Live-sweep readiness increment (was planned as live wave; re-scoped — live wave itself is now v003): CloudApiAdapter real WaApi implementation + typed config + runLiveSweep scripted verification + 30-min WABA setup guide + 12-step sweep doc shipped in codebase v0.8.0 (23 suites / 86 tests, 100%x4). E015-E016 logged. No traceability status changes per R2 — Pending-live flips require sweep evidence. Code: engageos_v0.8.0_src.zip. | Released
v003 | 2026-09-11 08:17 | Claude for Senthil/KP | Adversarial cold-review pass (first reviewer) + fixes: 4 defects found and fixed with regression tests (F-001 unconfigured-inbox crash path, F-002 chatbot question-node TypeError, F-003 unbounded webhook dedupe ledger -> FIFO cap 20x queue, F-004 hardcoded template language -> parameterised for hi/ta); 4 further findings logged with dispositions for Senthil (Review_Findings sheet added). Codebase v0.9.0: 23 suites / 90 tests, 100%x4, BUILD_OK. docs/REVIEW_PACK.md added so an EXTERNAL second reviewer can run ST-097 independently — ST-097 stays In progress: same-AI review does not satisfy second-reviewer independence. Live wave rolls to v004. | Released
v004 | 2026-09-11 12:51 | Claude for Senthil/KP | Review-prep completion wave (live wave rolls to v005): ST-089 WCAG flipped Done-in-code via views.ts screen shells + jest-axe suite (24 suites / 94 tests, 100%x4, codebase v0.10.0); ST-068 to In progress on SECURITY_EVIDENCE.md sandbox half; ST-094 to Drafted on ASSET_PLAN.md. E019-E020 logged. Backlog down to 3 truly-external stories (ST-081/099/100). Code: engageos_v0.10.0_src.zip. | Released
v005 | 2026-09-13 09:55 | Claude for Senthil/KP | Cold-review pass 2 + completion wave (live wave rolls to v006). Pass 2: 8 defects fixed with pinned regressions (F-009..F-016; headline = optIn/sessionWindow modules built in v007 but never wired into any send path). Completion wave: ST-081/080/095 Done-in-code, ST-099/100 Code-complete -> BACKLOG ZERO. ENGAGEOS CODE PHASE COMPLETE — 79 Done-in-code / 10 Pending-live / 9 Drafted / 2 In progress / 0 Backlog (309/399 pts; ST-099/100 sit in Pending-live and do not count toward Done points). Codebase v0.11.0: 27 suites / 118 tests at 100%x4, one documented pragma. Cold review complete across all modules. | Released
v006 | 2026-09-13 10:23 | Claude for Senthil/KP | Artifact-gap audit (live wave rolls to v007): 6 gaps found, 2 CRITICAL — no HTTP application and no DB schema existed behind artifacts the setup guide, deploy workflow, k6 harness and retention purge all referenced. Built: router + app (webhook verify/receive, healthz, pricing, help search, status), Node server entry with npm start, X-Hub-Signature-256 verification, 4 ordered migrations with cascade deletes + npm run migrate, signed k6 fixture generator, npm run sweep CLI, docs + pricing drift gates. ST-088/090/092 -> Code-complete. Codebase v0.12.0: 31 suites / 131 tests at 100%x4. Lesson L-E2 logged. Story rollup unchanged at 79 Done-in-code / 309 pts — this was missing plumbing, not new stories. | Released
v007 | 2026-09-13 10:35 | Claude for Senthil/KP | Cold-review pass 3 over the v012 HTTP layer (live wave rolls to v008): 4 defects fixed, 2 CRITICAL — F-017 no multi-tenancy (shared dedupe ledger and session window across every WABA account), F-018 a valid signature treated as proof of installation, F-019 unauthenticated operational detail, F-020 no OAuth CSRF state. New modules tenancy.ts + oauth.ts; /admin/health and detailed /status behind ENGAGEOS_OPERATOR_TOKEN; /oauth/start + /oauth/callback register tenants with single-use 10-minute state. Codebase v0.13.0: 31 suites / 136 tests at 100%x4. Lesson L-E3 logged. Story position unchanged at 79 Done-in-code / 309 pts. | Released
v008 | 2026-09-13 10:38 | Claude for Senthil/KP | External verification sweep vs live Meta/WhatsApp Cloud API documentation (live wave rolls to v009): 6 findings, 2 serious — VER-E5 batched-webhook data loss (only the first message of each envelope was processed) and VER-E1 the commercial model was built on conversation-based pricing, deprecated by Meta on 1 July 2025 in favour of per-message pricing; plus VER-E2 missing authentication template category, VER-E3 unmodelled 72-hour free-entry-point window, VER-E4 ack/retry semantics verified correct-by-design, VER-E6 80 msg/s throughput now limited. New modules messageCost.ts + throughput.ts. Codebase v0.14.0: 32 suites / 144 tests at 100%x4. Lesson L-E4 logged. Story position unchanged at 79 Done-in-code / 309 pts — correctness release. | Released
v009 | 2026-09-13 10:58 | Claude for Senthil/KP | Verification sweep pass 2 — messaging limits and delivery policy (live wave rolls to v010): VER-E7 no messaging-tier awareness in broadcasts (portfolio-wide 250-to-unlimited ladder of unique business-initiated recipients per rolling 24h), VER-E8 service-window replies verified exempt, VER-E9 US marketing freeze unguarded, VER-E10 frequency-cap errors retried when they must not be. New modules messagingTier.ts + sendPolicy.ts, wired into the send path. Codebase v0.15.0: 33 suites / 151 tests at 100%x4. New risk R-E8 (Meta trust ladder gates go-to-market). Story position unchanged at 79 Done-in-code / 309 pts. | Released
v010 | 2026-09-13 11:04 | Claude for Senthil/KP | Verification sweep pass 3 — message handling (live wave rolls to v011): VER-E11 campaign metrics counted API acceptance as delivery while status webhooks were discarded; VER-E12 inbound media dropped (only a media_id arrives); VER-E13 interactive button/list replies unreadable by the chatbot. New modules deliveryStatus.ts, media.ts, interactive.ts; campaign metrics now distinguish acceptance from confirmed delivery. Codebase v0.16.0: 34 suites / 158 tests at 100%x4. Verification sweep COMPLETE across pricing, limits, policy and message handling. Story position unchanged at 79 Done-in-code / 309 pts. | Released
v011 | 2026-09-13 11:13 | Claude for Senthil/KP | State-architecture audit (live wave rolls to v012): GAP-E8 CRITICAL — every correctness guard was process-local while our own blue/green workflow runs two instances; SharedStore boundary + PgStore (database-side atomicity) + one contract suite over both implementations + single-instance invariant documented and guarded. GAP-E7 — migrations 005/006 for the state added after v012. Codebase v0.17.0: 35 suites / 167 tests at 100%x4. New risk R-E9. Story position unchanged at 79 Done-in-code / 309 pts. | Released
v012 | 2026-09-13 11:18 | Claude for Senthil/KP | Wiring release (live wave rolls to v013): v017 built the SharedStore boundary and left it uncalled — the same "built but never wired" class as F-009/F-010, caught by checking before building anything new. Tenant dedupe guard and broadcast tier counter now run through the store, with cross-instance regressions; session windows remain process-local and are logged as OPEN-E1 rather than silently carried. Codebase v0.18.0: 35 suites / 169 tests at 100%x4. Story position unchanged at 79 Done-in-code / 309 pts. | Released
v013 | 2026-09-13 11:24 | Claude for Senthil/KP | Deferred-halves closure (live wave rolls to v014): OPEN-E1 session windows moved onto the shared store — the async ripple through inbox.receive, broadcast, tenancy and the demo seed done as the single deliberate pass the deferral was for; VER-E12 second half — CloudApiAdapter.resolveMedia() implements the real two-step media fetch. Codebase v0.19.0: 35 suites / 171 tests at 100%x4. No deferred code halves remain. Story position unchanged at 79 Done-in-code / 309 pts. | Released
v014 | 2026-09-13 11:31 | Claude for Senthil/KP | Handover consolidation + as-built re-baseline (live wave rolls to v015). New Senthil_Handover sheet: all 10 remaining items ordered by leverage with effort, external lead time, what each unblocks and the exact next action — none of them movable by Claude. Product workbook v020 re-baselines the spec sheets, which had not been touched since 5 Sep: the financial model still assumed conversation-based pricing (retired by Meta 1 Jul 2025), and the non-functional requirements claimed more than the code delivers. No code changes this sitting — 35 suites / 171 tests at 100% unchanged — because there is no codeable work left that does not depend on his inputs. | Released
v015 | 2026-09-13 11:33 | Claude for Senthil/KP | INTEGRITY AUDIT — eight claims verified mechanically against the shipped artifact rather than restated. Five passed; three failed and are fixed here. (a) Release notes had repeatedly claimed "one documented pragma" — there were five; two were dead code and have been REMOVED (chatbot fall-through, delivery-ledger lookup miss), leaving three honest process-bootstrap pragmas and zero logic pragmas. (b) Two Done-in-code rows named their verification vaguely and could not be checked mechanically — both now name real suites, and all 79 Done-in-code rows resolve to files that exist. (c) NINE traceability rows had their story text overwritten with module paths by my own later update scripts — real data loss in the record, now restored from the product backlog with the module path moved to its proper column. New Integrity_Audit sheet documents all eight checks, methods and outcomes. Clean-room rebuild from the zip: npm ci clean, build clean, 35 suites / 171 tests, coverage gate satisfied. | Released
v016 | 2026-09-13 11:38 | Claude for Senthil/KP | Audit pass 2 (live wave rolls to v017): every one of the 37 closed findings probed against the shipped source and all 37 verified present, then converted into a permanent regression suite so a fix cannot silently disappear while the record still claims it closed; pragma guard added as a test; product workbook structure reconciled (Sprint_Board vs backlog, version sequence, statuses); three record defects fixed — Launch_Checklist item 6 was still written against Meta's retired conversation-pricing model, items 2/3/8 were stale, and the original three risks had no IDs. Codebase v0.21.0: 36 suites / 210 tests at 100%. Integrity_Audit sheet now documents 14 checks across both passes. | Released
v017 | 2026-09-13 11:45 | Claude for Senthil/KP | Operator-path rehearsal (live wave rolls to v018): npm run rehearse boots the real server with placeholder secrets, exercises the handshake, signature verification, replay dedupe, auth boundaries and content routes, then runs the sweep in dry mode — executed here with the transcript committed to docs/REHEARSAL_TRANSCRIPT.md and the step added to CI. The risk it retires is not Meta: it is npm start failing on a typo, or the sweep not being runnable, at the moment credentials finally arrive. Statuses unchanged by design. Codebase v0.22.0: 36 suites / 210 tests at 100%. | Released
v018 | 2026-09-13 11:54 | Claude for Senthil/KP | F-022 (live wave rolls to v019): a reachability audit of src/ found views.ts and demoData.ts called only by tests — the third instance of the built-but-unwired class (F-009/F-010, then F-021), and the first where the unwired code sat behind stories already recorded as Done. Screens are now served at /app/* behind an ENGAGEOS_DEMO flag, axe-clean as served, and exercised by the rehearsal script; the findings regression suite pins the wiring so it cannot be undone silently. ST-094 screenshot capture is unblocked — the screens load today; only styling remains. Codebase v0.23.0: 37 suites / 215 tests at 100%. | Released
v019 | 2026-09-13 11:58 | Claude for Senthil/KP | F-023 (live wave rolls to v020): the reachability question asked one level up — not "is the module wired" but "can the product be used" — and the answer was no. No action routes existed, and inbound webhooks were deduped into a buffer nothing drained, so a customer message never became a conversation. Per-tenant WorkspaceRegistry, webhook-to-inbox delivery and an operator-gated action API now make the five MVP features operable; the rehearsal proves the loop end to end, including a reply that fails 502 against the real Cloud API with placeholder credentials. OPEN-E2 logged: per-agent authentication is still a single operator token. Codebase v0.24.0: 38 suites / 224 tests at 100%, zero logic pragmas. | Released
v020 | 2026-09-13 12:04 | Claude for Senthil/KP | F-024/F-025/F-026 — completing F-023 (live wave rolls to v021). A module-by-module reachability sweep found nine src modules imported by nothing in the product, including compliance, whose self-serve export and delete-my-data the published trust page promises. All nine wired: feature routes for flows, opt-in, analytics, billing, support and data rights; the permission matrix and audit log bound at the HTTP boundary so a member is refused sends, billing and deletion and every mutating call is recorded; the throughput limiter and latency budgets finally measuring what they were built to measure. Codebase v0.25.0: 39 suites / 241 tests at 100%. OPEN-E2 narrowed but still open. | Released
v021 | 2026-09-13 16:27 | Claude for Senthil/KP | OPEN-E2 closed (live wave rolls to v022): HMAC-signed agent sessions replace header-asserted identity. Only the operator token mints a session; the signed role governs; tokens expire in 12 hours; a signing secret under 16 characters is refused at boot; the audit log records a verified actor. The rehearsal now shows a member session reading successfully and being refused a send while a header claims owner. Codebase v0.26.0: 40 suites / 250 tests at 100%. No open architectural item remains on the software side; ENGAGEOS_SESSION_SECRET joins the deploy prerequisites. | Released
v022 | 2026-09-13 16:32 | Claude for Senthil/KP | F-027 (live wave rolls to v023): the product was API-only — the screens served since v024 were read-only mockups with inert buttons, so no agent could work in it. A functional workspace is now served at /web covering the inbox (list, open, reply with honest outcome reporting), broadcast test sends and catalog add with payment link, authenticated by the signed session from v0.26.0. The client is written as testable DOM functions and served by stringifying those same functions, so the browser runs exactly what the suite drives. ST-094 is now blocked only by styling. Codebase v0.27.0: 41 suites / 265 tests at 100%. | Released
v023 | 2026-09-13 16:38 | Claude for Senthil/KP | UI completion (live wave rolls to v024). F-028: ST-069 promises self-serve export and deletion and the only path was an operator-token API — not something a customer could use, while the trust page published the right. Export and delete now sit in the agent workspace with confirmation and the 30-day window stated plainly. Also completed: the ST-057 trial banner (always a UI element, previously only an API string), a health panel putting the quality rating and 24-hour messaging limit into actionable sentences, and the first-run checklist. Codebase v0.28.0: 41 suites / 274 tests at 100%. | Released
v024 | 2026-09-13 16:42 | Claude for Senthil/KP | Styling pass (live wave rolls to v025). F-029: the workspace shipped unstyled and I had been returning the styling to Senthil as "a design job", which was avoidance rather than a boundary. Design grounded in the subject — the SME counter and its paper ledger, seen on a mid-range Android in daylight — with ink on cool ledger paper, one type family on a 1.25 scale, colour reserved strictly for conversation status, and the queue as the only element allowed to be loud. The contrast floor is enforced by a test that failed on first run against my own --closed grey (4.19:1) and forced a correction to 5.25:1. Rationale recorded in docs/DESIGN_NOTES.md. ST-094 keeps only the capture session and video production. Codebase v0.29.0: 41 suites / 279 tests at 100%. | Released
v025 | 2026-09-13 16:47 | Claude for Senthil/KP | F-030 (live wave rolls to v026): the Hindi and Tamil packs drafted in v007 were imported by nothing while the listing copy promises a vernacular UI. The workspace now ships in all three languages across every string, with a language switcher, English fallback for missing keys, and drift gates on both pack completeness and the disk files (now generated from the module). Machine translations still need native-speaker review and server-generated messages remain English — both recorded rather than hidden. Codebase v0.30.0: 41 suites / 286 tests at 100%. | Released
v026 | 2026-09-13 16:53 | Claude for Senthil/KP | Listing-claims audit (live wave rolls to v027): five marketing promises were untrue in the shipped product — flows never answered an inbound message, broadcasts never consulted the quality guard, the circuit breaker was unused, plan-limit prompts were never surfaced, and payment links were returned to the agent rather than sent to the customer. All five fixed and pinned as tests named after the claim they defend, so a future copy change without matching code fails the build. Codebase v0.31.0: 42 suites / 296 tests at 100%. | Released
v027 | 2026-09-13 17:24 | Claude for Senthil/KP | Help-centre audit (live wave rolls to v028): the 15 published articles are a specification, and eight of the tasks they walk a customer through had no route or control at all — including the CSV import that is the day-one migration path, while ST-009 and ST-019 read Done-in-code. All eight are now reachable and pinned by tests named after the articles. Codebase v0.32.0: 43 suites / 307 tests at 100%. | Released
v028 | 2026-09-13 17:28 | Claude for Senthil/KP | F-037 (live wave rolls to v029): the drafted template library was diffed against the wire format and the mismatch was live-blocking — 12 of 20 templates carry variables while the adapter shipped none, which Meta rejects outright. Registry, body components, pre-flight validation naming the missing variable, a drift test against the published library, and the template-send route that outside the 24-hour window is the only legitimate way to reach a customer. Codebase v0.33.0: 44 suites / 315 tests at 100%. | Released
v029 | 2026-09-13 18:50 | Claude for Senthil/KP | F-038 (live wave rolls to v030): the launch runbook prescribed controls the product did not have — a feature-flag rollback step with no flags in existence, and a 2-hourly quality check nothing ever performed. Per-capability kill switches with mandatory reasons and attribution, an on-demand quality check that auto-disables broadcasts on a red rating with manual re-enable, and a status page that admits to a degraded capability. The runbook is rewritten around what exists. Codebase v0.34.0: 45 suites / 324 tests at 100%. | Released
v030 | 2026-09-13 18:59 | Claude for Senthil/KP | F-039 (live wave rolls to v031): the incident comms templates and their severity ladder had nowhere to publish — during an outage the customer would have seen a boolean while the written messages sat in a markdown file. Incidents now open, update and resolve; the public status page carries the latest message and still no internals; the documented cadence is enforced with an overdue list in minutes late. Every customer-facing and operator-facing document in this repo has now been diffed against the product. Codebase v0.35.0: 46 suites / 329 tests at 100%. | Released
v031 | 2026-09-13 19:11 | Claude for Senthil/KP | F-040 (live wave rolls to v032): the ninth specification was the product workbook itself. Its screen inventory names nine screens and four did not exist — the home dashboard, the chatbot flows view the sheet calls the differentiator, settings and team, and help and support. All four built in three languages and axe-audited; the Screens_Wireframes sheet now carries as-built status per screen. ST-074, the weekly metrics email, was wired at the same time after sitting uncallable since v006. Codebase v0.36.0: 47 suites / 336 tests at 100%. | Released
v032 | 2026-09-13 19:31 | Claude for Senthil/KP | F-041 (live wave rolls to v033): the scope sheet names vertical templates as this product's differentiation and no vertical existed in the code — one flat list of twenty templates for every business type. Four packs now shape the template set, the welcome wording and the first routing rule, chosen at setup and validated against the registry. ST-082 was unbuilt in the same way: the checklist was a hard-coded array, completing a step did nothing, aha was unreachable and the review ask could never fire — all three are now real. Codebase v0.37.0: 48 suites / 343 tests at 100%. | Released
v033 | 2026-09-13 19:36 | Claude for Senthil/KP | Close-out (live wave rolls to v034). No new capability: the eleven specifications are diffed and fixed, the backlog is zero and nothing remains that can be moved without Senthil. Instead the artifact was verified one final time from the shipped zip in a clean directory — npm ci, build and the 100% gate all reproduce at 48 suites / 344 tests, 60 modules, 61 routes, three bootstrap pragmas and none in logic — and the run's nineteen lessons were rewritten as a portfolio asset rather than a diary. New Lessons_For_Portfolio sheet groups them by the TECHNIQUE that found each defect, because that is the reusable part, with the cheapest way to run each elsewhere. docs/STATE_OF_ENGAGEOS.md states plainly what exists and is proven, what is assumed and not yet true, and why 309 points are Done-in-code while zero are Done. | Released
v034 | 2026-09-13 19:40 | Claude for Senthil/KP | Audit kit extracted and immediately useful (live wave rolls to v035). The three techniques that found what tests could not are now portable scripts usable on any of the other products. On its first run against EngageOS it found F-042: SHARED_STORE=pg documented in three places and implemented nowhere, and the SEO tool unwired despite an earlier finding claiming all nine modules were wired — an overstatement of mine, caught by the tool. Both fixed; the kit gained consumer-directory scanning after producing one false positive. Codebase v0.38.0: 49 suites / 347 tests at 100%. | Released
v035 | 2026-09-13 20:08 | Claude for Senthil/KP | Audits became gates (live wave rolls to v036). audit/claims.json binds all 43 documented promises to the markers that make them true; audit/findings.json is generated from the regression suite so the two cannot drift, with a sync test naming the three probes a file marker cannot express. All three checks run in CI and via npm run audit: 60/60 modules reachable, 43/43 promises kept, 55/55 closed findings still fixed. Audit kit v002 adds consumer-directory scanning. Codebase v0.39.0: 49 suites / 349 tests at 100%. | Released
v036 | 2026-09-13 20:12 | Claude for Senthil/KP | Claims extractor + F-043 (live wave rolls to v037). The kit gained a drafting tool for the claims manifest, which was its whole adoption cost; on its first run it surfaced an incident-template line promising queued delivery and no lost messages, with no outbound queue in existence. Durable retry queue built — held sends, on-demand drain, bounded capacity that drops loudly, dead letters an operator can read — and the template corrected to what is now true. Codebase v0.40.0: 50 suites / 356 tests at 100%. | Released
v037 | 2026-09-13 20:26 | Claude for Senthil/KP | F-044 and manifest reconciliation (live wave rolls to v038). L-E21 prescribed drafting the claims manifest from disk rather than memory; reconciling the extractor output against the hand-written 43 added five claims and found one real gap — the trust page published a security posture that nothing verified, with verifySecurityConfig() written in v006 and never called. The app now refuses to boot when the deployment contradicts the published claims, with a warn-only escape for local work and an admin route to re-check. Three findings recorded in the tracker but absent from the regression array were added, closing a drift between the record and the gate. Codebase v0.41.0: 51 suites / 365 tests at 100%. | Released
v038 | 2026-09-13 20:33 | Claude for Senthil/KP | Audit kit v004 (live wave rolls to v039): a workbook converter feeds spreadsheet specifications to the claims extractor, which matters here because the screen inventory and the stated differentiation both lived in sheets and both described absent features. Two kit defects surfaced while building it — a bare "log" pattern silently excluded Full_Backlog, and first-person user stories were undetected — both fixed and documented as cautions, since a tool that omits the main artifact while reporting success is worse than no tool. Backlog stories cross-checked against the traceability matrix: all 35 present and Done-in-code, so the matrix stays the gate for stories. Codebase v0.42.0: 51 suites / 365 tests at 100%, 49 documented promises kept. | Released
v039 | 2026-09-13 22:49 | Claude for Senthil/KP | Audit kit v1.0.0 (live wave rolls to v040): the kit enforcing quality across the portfolio had three shipped bugs and no tests of its own. Eleven tests added — seven node, four python — with one named for each bug it has shipped, and a fourth misunderstanding corrected while writing them: a test expected an entry module to be exempt automatically, when the correct behaviour is to report it unless the consumer directory is supplied. The kit runs in this product's CI and ships standalone. Codebase v0.43.0: 51 suites / 365 tests at 100%. | Released
v040 |  |  | PLANNED: opens on the first live evidence, disposition or decision from the handover sheet. | Planned

## Sprint_Tracker_Log
SPRINT TRACKER LOG — every execution event, newest last
ID | Date/Time | Sprint | What happened | Refs | State changes | Blockers | Next
E001 | 2026-09-10 22:22 | — | DIRECTIVE RECORDED — Senthil 22:22: continue sprint work on EngageOS from v005 workbook; create sprint tracker + traceability; complete development with 100% automation testing (D13). EngageOS opened as an additional concurrent build while D15 mode (parallel vs re-order) remains unratified; this entry is the R7-style log of that state. | D13,D15 | EngageOS S1 opened from v005 backlog (100 stories / 399 pts) | None | S1 build
E002 | 2026-09-10 22:22 | S1 | S1 FOUNDATION BUILT (workbook v006 run, TypeScript/Node per v005 stack): install.ts — OAuth install w/ empty-code validation, uninstall webhook token purge + 30-day retention-scheduled deletion, re-install restore inside window / RETENTION_EXPIRED beyond, rotation-safe token refresh, listing/search/referral install attribution. | ST-052,ST-055,ST-056 (+ST-051 logic) | 3 S1 stories Done-in-code (8/13 pts); ST-051 Pending-live | ST-051 <2 min dev-store install needs live Meta dev account | E003
E003 | 2026-09-10 22:22 | S2 | F1 PART 1: inbox.ts — one-screen defaults (min-one-agent), happy path w/ keyword-rule + round-robin assignment, custom rules validated against agent list, reply retry via resilience.ts (exp backoff, clear error after exhaustion); roles.ts owner/admin/member matrix + AuditLog. | ST-001..004,053,054 | 6 S2 stories Done-in-code (29/29 pts) | None | E004
E004 | 2026-09-10 22:22 | S3 | F1 PART 2 + F2 START + QUALITY GATE: inbox metrics/pause-safe/CSV import/notifications (notify.ts per-type mute); broadcast.ts campaign create + segment rules + API error retry; ST-085 test-coverage story closed as SUPERSEDED by D13 100% gate (jest coverageThreshold 100x4). | ST-006..014,085 | 10 S3 stories Done-in-code (42/47 pts); ST-005 Pending-live | None | E005
E005 | 2026-09-10 22:22 | S4 | F2 COMPLETE + TELEMETRY + SMOKE: broadcast send w/ test-mode isolation, delivery/failed tracking, metrics, pause-safe, contact import validation; analyticsGuard funnel events (install->setup->aha->habit); telemetry.ts ErrorTracker release tags + window spike alert; tests/smoke.test.ts E2E MVP loop wired into CI on push/PR/deploy. | ST-016..020,071,072,086 | 8 S4 stories Done-in-code (29/34 pts); ST-015 Pending-live | None | E006
E006 | 2026-09-10 22:22 | S5 | F3 + ONBOARDING: chatbot.ts default welcome flow, run engine w/ branch answers, loop + broken-link + missing/invalid-answer detection, node edits, export/import round-trip; onboarding.ts first-run checklist w/ aha (connect+first-reply) <1 day check, EMPTY_STATES registry per screen. | ST-021..024,026..030,078,079 | 11 S5 stories Done-in-code (45/50 pts); ST-025 Pending-live | None | E007
E007 | 2026-09-10 22:22 | S6 | F4 + BILLING CORE: catalog.ts VPA-validated UPI deep links, item CRUD, CSV import, pause-safe, metrics; billing.ts 14-day no-card trial w/ days-remaining banner, mid-cycle proration w/ cycle-cap clamp, selectProvider(marketplace-mandate vs Stripe fallback). | ST-031..034,036..040,057,058 | 11 S6 stories Done-in-code (47/60 pts); ST-035,059 Pending-live | ST-059 mandate check needs verified Meta terms (S0 item) | E008
E008 | 2026-09-10 22:22 | S7 | BILLING HARDENING: dunning state machine (7-day grace, emails day 0/3/6, then read-only), plan-limit prompts at 80%/100%, GST/VAT invoices w/ rate validation, cancellation save-offer(20%) + exit-survey-required path; compliance.ts least-privilege SCOPE_MAP (3 scopes 1:1 features). | ST-060..064 | 5 S7 stories Done-in-code (15/15 pts) | S7 beta-partner activities themselves external | E009
E009 | 2026-09-10 22:22 | S8 | F5 + E6/E7 + QUALITY: analyticsGuard quality-score guard (green/amber/red w/ throttle action), configurable thresholds, health score, heatmap, CSV export; compliance retentionPolicy + verifySecurityConfig + DataRights export/delete; resilience CircuitBreaker; latency.ts p95 budgets api/ui/webhook; chaos degradation via FakeWaApi outage injection. | ST-041..044,046..050,065,067,069,070,073..077,087,091 | 18 S8 stories Done-in-code (69/87 pts); ST-045,066 Pending-live | ST-088 load test + ST-092 deploy drill need live infra | E010
E010 | 2026-09-10 22:22 | Release | WORKBOOK v006 RELEASED 22:22 — D13 GATE MET: 16 suites / 73 automated tests, 100% statements/branches/functions/lines on all 15 modules, gate enforced (jest coverageThreshold fails any commit below); tsc BUILD_OK; Sprint_Tracker_Log + Traceability_Matrix sheets added to product workbook; recalc 169 formulas zero errors. Position: 75 Done-in-code / 8 Pending-live / 17 Backlog (295/399 pts). | D13 | Code: engageos_v0.6.0_src.zip | Live Meta dev account gates the 8 Pending-live | E011
E011 | 2026-09-10 22:55 | S9-S10 | WHATSAPP COMPLIANCE CODE (v007 run): sessionWindow.ts 24-hour customer-service window + template fallback (hard TEMPLATE_REQUIRED error); webhookGuard.ts wamid dedupe + bounded burst queue tested at 50 msg/s shape w/ overflow accounting; optIn.ts consent proof storage + marketing-send gate; demoData.ts sandbox mode seeding inbox/campaign/flow/catalog (ST-083 code half). | LC-5,LC-7,LC-8,ST-083 | Launch checklist #5/#7/#8 Done-in-code, #4 templates Drafted | Live 50/s burst + Meta template approval pending | E012
E012 | 2026-09-10 22:55 | S9-S10 | DRAFTING SPRINT: listing copy A(outcome-led)+B(pain-led), pricing matrix + 5 FAQs from billing.ts PLANS, trust/security page from compliance.ts facts, 2-min demo script, launch-day runbook (T-1/T-0/rollback/comms tree/48h checks), incident comms + severity ladder, 15 help-center articles, k6 harness (10 rps sustained + 50/s burst, p95<500ms), backup/restore drill (RTO<2h RPO<24h), blue/green deploy.yml, hi/ta i18n packs, 20 Meta message templates. | ST-080,083,084,088,090,092,093,095,096,098 | 10 stories Drafted; ST-097 In progress (self dry-run vs Launch_Checklist done) | ST-093 A/B needs Senthil pick; ST-097 needs second reviewer | E013
E013 | 2026-09-10 22:55 | Release | WORKBOOK v007 RELEASED 22:55 — coverage held: 20 suites / 78 tests at 100%x4; Launch_Checklist re-statused honestly; Traceability updated with artifact paths. Position: 75 Done-in-code / 8 Pending-live / 10 Drafted / 1 In progress / 6 Backlog. Sandbox ceiling reached — every remaining item needs Senthil (Meta verification, reviews, vendors, assets, D15). | D13 | Code: engageos_v0.7.0_src.zip | All remaining blockers Senthil-side | E014
E014 | 2026-09-10 23:06 | — | THIS TRACKER CREATED (v001, 23:06) mirroring TeleField tracker pattern: consolidated E-log of both runs with proper version stamps, 100-story traceability w/ version-stamped evidence, formula rollup, RAID seeded from v005 Risk_Register + build findings, D7 completion gate + LC statuses carried from workbook v007. | D12 pattern | Tracker v001 Released | None | v002 = live Meta wave
E015 | 2026-09-10 23:10 | Live-prep | LIVE-SWEEP READINESS BUILT: config.ts typed env loader naming every missing/blank secret; cloudApiAdapter.ts implements WaApi against graph.facebook.com v21.0 (text + template payloads, Bearer auth asserted byte-exact in tests, WA_HTTP_<status> error surface, GREEN/YELLOW/RED quality mapping) — the FakeWaApi/live swap is now one constructor argument; liveSweep.ts runs 6 automated checks identically against fake (tested) and live; docs: LIVE_SETUP_GUIDE.md (submit Meta Business verification FIRST — longest queue), LIVE_VERIFICATION_SWEEP.md (12 steps -> 8 Pending-live stories), .env.example. | LC-1..3,LC-5,LC-7,LC-8 | Codebase v0.8.0: 23 suites / 86 tests, 100%x4 | WABA access (Senthil) | E016
E016 | 2026-09-10 23:10 | Release | TRACKER v002 + WORKBOOK v008 RELEASED 23:10. Statuses deliberately unchanged (R2: code readiness is not live evidence). EngageOS position: 75 Done-in-code / 8 Pending-live / 10 Drafted / 1 In progress / 6 Backlog; every remaining move is Senthil-side. | R2,D13 | Tracker v003 + workbook v009 planned as the live-wave evidence records | WABA access, A/B pick, second reviewer, pen-test, D15 | v003 on live access
E017 | 2026-09-11 08:17 | Review | ADVERSARIAL COLD-REVIEW PASS 1 — probed state machines, parsers, boundary conditions, live-wiring seams. 8 findings: F-001..F-004 fixed same-session with regression tests (unconfigured-inbox crash, question-node TypeError, unbounded dedupe ledger -> FIFO cap, hardcoded template language -> hi/ta parameterised); F-005..F-008 logged with proposed dispositions for Senthil (install-overwrite semantics, UPI payee name, dunning tick cadence, sweep step-1 triviality). Coverage held 100%x4 through all fixes. | F-001..F-008,ST-097 | Codebase v0.9.0: 23 suites / 90 tests; Review_Findings sheet added | None | E018
E018 | 2026-09-11 08:17 | Release | TRACKER v003 + WORKBOOK v009 RELEASED 08:17. docs/REVIEW_PACK.md ships verification steps + claims list + probe targets for an EXTERNAL second reviewer — ST-097 deliberately stays In progress (same-AI review is not second-reviewer independence). Position otherwise unchanged: 75 Done-in-code / 8 Pending-live / 10 Drafted / 1 In progress / 6 Backlog. | ST-097,R2 | F-005 disposition + external review + live wave all Senthil-side | WABA access, external reviewer, A/B pick, D15 | v004 on live access
E019 | 2026-09-11 12:51 | S9-prep | REVIEW-PREP COMPLETION: accessible screen shells for the four core surfaces rendered from live service objects (empty states single-sourced from ST-079 registry) + jest-axe WCAG suite — populated/empty/unassigned/disabled branches all audited, XSS escaping asserted byte-level; SECURITY_EVIDENCE.md compiled (sandbox half of ST-068: scopes, authz deny-by-throw, input gating, egress single-point, data rights, open items for the vendor incl. F-005); ASSET_PLAN.md 5-shot list mapped to shells + demo-data mode with hi/ta subtitle plan. | ST-089,ST-068,ST-094 | ST-089 Done-in-code (+3 pts -> 298/399); ST-068 In progress; ST-094 Drafted; Backlog now 3 (all external) | Vendor pen-test, asset production, styled-UI WCAG | E020
E020 | 2026-09-11 12:51 | Release | TRACKER v004 + WORKBOOK v010 RELEASED 12:51. Codebase v0.10.0: 24 suites / 94 tests, 100%x4, BUILD_OK. Position: 76 Done-in-code / 8 Pending-live / 11 Drafted / 2 In progress / 3 Backlog (ST-081 chat vendor, ST-099 post-launch SEO, ST-100 design partners — nothing left that code can move). | D13,R2 | Every remaining line is Senthil-side | WABA, external reviewer, F-005, A/B, vendors, D15 | v005 on live access
E021 | 2026-09-13 09:55 | Review-2 | COLD-REVIEW PASS 2 over every module pass 1 skipped (billing, compliance, notify, telemetry, analyticsGuard, catalog, inbox importers, broadcast wiring). 8 defects fixed with pinned regressions. Headline F-009/F-010: the opt-in registry and 24-hour session window shipped in v007 were never called by any send path — marketing broadcasts could have gone to non-consented contacts and free-form messages outside the window, both platform violations, and a 100%-coverage suite could not see it because each module was fully exercised by its OWN tests. Also: read-only unenforced, no payment recovery, trial never expiring, deletion never purging, naive CSV split, unbounded ledgers. Shared csv.ts + ledger.ts extracted. Lesson L-E1 logged. | F-009..F-016, L-E1 | 26 suites / 110 tests at 100%; Review_Findings extended | None | E022
E022 | 2026-09-13 09:55 | Completion | COMPLETION WAVE — the last 3 backlog stories plus 2 drafted ones built: ST-081 built-in support chat with a 4-business-hour first-response SLA (business-hours maths excludes nights and weekends; external chat vendor is now an OPTIONAL cost decision, D-E4 flagged); ST-080 ranked help search with a drift gate that fails if the shipped index and the published article headings ever diverge; ST-095 pricing table generated from the enforced billing PLANS with its own drift test; ST-099 SEO iteration engine refusing to act under 100 impressions; ST-100 10-slot partner tracker with stale nudges and honest gate math (only PAYING STRANGERS count toward G-02 — friends and reviews are counted separately). | ST-080,081,095,099,100 | 5 stories moved (+11 Done pts -> 309/399); ST-099/100 land in Pending-live; BACKLOG ZERO | ST-099/100 live halves are his | E023
E023 | 2026-09-13 09:55 | Release | TRACKER v005 + WORKBOOK v011 RELEASED. ENGAGEOS CODE PHASE COMPLETE — backlog zero, cold review complete across all modules. 79 Done-in-code / 10 Pending-live / 9 Drafted / 2 In progress / 0 Backlog (309/399 pts). Codebase v0.11.0: 27 suites / 118 tests at 100%x4, one documented pragma. No further code sprints planned. | D13,R2 | Code: engageos_v0.11.0_src.zip | All remaining work Senthil-side | v006 on live evidence
E024 | 2026-09-13 10:23 | Gap-audit | ARTIFACT-GAP AUDIT — checked every command, route and file the docs, manifest, CI and k6 harness reference against what the repo actually contained. 6 gaps, 2 CRITICAL. GAP-E1: no HTTP application existed at all — 30 domain modules at 100% coverage and nothing that could receive a WhatsApp message; the setup guide told Meta to register a callback URL for a route with no implementation, and the live sweep would have died the moment it needed a running app. GAP-E2: no DB schema behind the backup drill or the F-014 purge. GAP-E3: webhook signatures never verified. GAP-E4: hub.challenge handshake missing, so Meta could not have saved the callback URL in the first place. GAP-E5: unsigned k6 payloads. GAP-E6: ungated pricing doc. All fixed and tested; setup guide and drill rewritten around the real commands (npm run migrate / npm start / npm run sweep). | GAP-E1..E6, L-E2 | ST-088/090/092 Drafted -> Pending-live; 31 suites / 131 tests at 100% | Live run now needs Postgres + WA_APP_SECRET alongside WABA access | E025
E025 | 2026-09-13 10:23 | Release | TRACKER v006 + WORKBOOK v012 RELEASED. The 30-minute live path is executable end to end for the first time: npm ci -> npm run build -> npm run migrate -> npm start -> register /webhook -> npm run sweep. Position: 79 Done-in-code / 13 Pending-live / 6 Drafted / 2 In progress / 0 Backlog (309/399 pts) — unchanged by design, this was missing plumbing rather than new stories. | D13,R2 | Code: engageos_v0.12.0_src.zip | WABA access + Postgres + WA_APP_SECRET; then the sweep flips 13 stories | v007 on live evidence
E026 | 2026-09-13 10:35 | Review-3 | COLD-REVIEW PASS 3 over the HTTP layer built only twelve minutes earlier — deliberately reviewing the new surface rather than treating it as done. Four defects, two critical. F-017: the app held one dedupe ledger and one session window for the entire process, so WABA accounts shared state — account B retrying a wamid could suppress account A's genuine message, one tenant's burst could evict another's events, and a single inbound opened the 24-hour free-form window for every tenant (a compliance hole, not merely isolation). F-018: a valid signature was treated as proof of installation, so messages for numbers we do not serve were queued. F-019: unauthenticated /healthz and /status handed out release, queue depth and error counts. F-020: embedded signup had no CSRF state. Fixed with tenancy.ts, oauth.ts, an operator-token boundary, and per-tenant resolution from metadata.phone_number_id. | F-017..F-020, L-E3 | 31 suites / 136 tests at 100%; docs, .env.example and security evidence updated | None | E027
E027 | 2026-09-13 10:35 | Release | TRACKER v007 + WORKBOOK v013 RELEASED. Codebase v0.13.0. Position unchanged at 79 Done-in-code / 13 Pending-live / 6 Drafted / 2 In progress / 0 Backlog (309/399 pts) — correctness release. Deploy prerequisites now: WABA credentials, DATABASE_URL, WA_APP_SECRET, ENGAGEOS_OPERATOR_TOKEN. | D13,R2 | Code: engageos_v0.13.0_src.zip | All remaining work Senthil-side | v008 on live evidence
E028 | 2026-09-13 10:38 | Verification | EXTERNAL VERIFICATION SWEEP against live Meta/WhatsApp Cloud API documentation — checking our assumptions about the platform rather than our code against our assumptions. Six findings. VER-E5 (data loss): webhook envelopes are batched and the handler processed only the first message of the first change of the first entry, silently dropping the rest and acking 200 so Meta never retried; invisible to every internal pass because our fixtures carried one message. VER-E1 (commercial): the whole plan model was metered in conversations, a unit Meta stopped billing on 1 July 2025 when it moved to per-message pricing; the 1,000-free-conversations allowance is also gone. VER-E2 missing authentication category. VER-E3 the 72-hour free-entry-point window was unmodelled, so ad-sourced conversations were wrongly template-gated and wrongly treated as billable. VER-E4 ack/retry semantics verified correct-by-design and pinned. VER-E6 80 msg/s outbound throughput now limited. | VER-E1..E6, L-E4 | 32 suites / 144 tests at 100%; messageCost.ts + throughput.ts added; pricing docs corrected; R-E7 logged | VER-E1 commercial decision is Senthil's | E029
E029 | 2026-09-13 10:38 | Release | TRACKER v008 + WORKBOOK v014 RELEASED. Codebase v0.14.0. Position unchanged at 79 Done-in-code / 13 Pending-live / 6 Drafted / 2 In progress / 0 Backlog (309/399 pts) — correctness release. New Senthil item: VER-E1 plan-allowance pricing decision (are 1,000/5,000/20,000 template messages right at $29/$49/$99 when per-message rates vary ~13x by market?). | D13,R2 | Code: engageos_v0.14.0_src.zip | Pricing decision, WABA + secrets, reviewer, dispositions, D15 | v009 on live evidence
E030 | 2026-09-13 10:58 | Verification-2 | VERIFICATION SWEEP PASS 2 — messaging limits and delivery policy, checked against live Meta documentation. VER-E7: the product had no concept of Meta's messaging limits. A new unverified portfolio may start conversations with just 250 unique customers per rolling 24 hours, and the cap is shared across every number in the portfolio since Oct 2025 — so the first campaign an SME runs on EngageOS would have been mostly rejected, damaging the very quality rating that unlocks the next tier. Now metered, with skips named TIER_LIMIT_REACHED and an upgrade-readiness explanation. VER-E8: verified that service-window replies are exempt and implemented accordingly, so a busy support inbox never eats broadcast capacity. VER-E9: marketing templates to US numbers have been paused since April 2025 — now guarded; this also caught that our own test-send placeholder was a US number. VER-E10: the per-user frequency-cap error was being retried three times when Meta says wait 24 hours. | VER-E7..E10 | 33 suites / 151 tests at 100%; messagingTier.ts + sendPolicy.ts; R-E8 logged; setup guide and FAQ updated | Business Verification is the single biggest reach unlock and sits on the critical path | E031
E031 | 2026-09-13 10:58 | Release | TRACKER v009 + WORKBOOK v015 RELEASED. Codebase v0.15.0. Position unchanged at 79 Done-in-code / 13 Pending-live / 6 Drafted / 2 In progress / 0 Backlog (309/399 pts) — correctness release. Practical consequence for launch planning: design-partner and first-campaign expectations must be set at 250 unique customers per 24 hours until verification and quality move the tier. | D13,R2,R-E8 | Code: engageos_v0.15.0_src.zip | Pricing decision, WABA + secrets, reviewer, dispositions, D15 | v010 on live evidence
E032 | 2026-09-13 11:04 | Verification-3 | VERIFICATION SWEEP PASS 3 — message handling, against live Meta documentation. Three findings, all real and all invisible to internal review because the fake adapter behaved the way we assumed the platform did. VER-E11: campaign "delivered" counts came from API acceptance while Meta's status webhooks — the only source of actual delivery — were discarded, so a campaign that reached nobody could have reported 100% to the customer. VER-E12: inbound media carries only a media_id, and the inbox treated every message as text, so a photo of a damaged product arrived as an empty conversation. VER-E13: interactive button and list taps arrive as ids, not text, so every chatbot branch answer would have failed as invalid on a real number — the flagship no-code feature would have looked broken to the first customer. Verification sweep now COMPLETE across pricing, messaging limits, delivery policy and message handling. | VER-E11..E13 | 34 suites / 158 tests at 100%; deliveryStatus.ts, media.ts, interactive.ts added | Webhook subscription must include status events | E033
E033 | 2026-09-13 11:04 | Release | TRACKER v010 + WORKBOOK v016 RELEASED. Codebase v0.16.0. Position unchanged at 79 Done-in-code / 13 Pending-live / 6 Drafted / 2 In progress / 0 Backlog (309/399 pts) — correctness release. Three verification passes have now found 13 platform-model defects that three internal review passes at 100% coverage could not, because the fake adapter faithfully reproduced our own assumptions. | D13,R2,L-E4 | Code: engageos_v0.16.0_src.zip | Pricing decision, WABA + secrets, reviewer, dispositions, D15 | v011 on live evidence
E034 | 2026-09-13 11:13 | State-audit | STATE-ARCHITECTURE AUDIT. GAP-E8 (critical): sixteen modules held cross-request state in process-local Maps while our own blue/green deploy workflow runs two instances during a switch — two webhook dedupe ledgers (the same Meta retry processed twice, so a customer receives duplicate auto-replies), two messaging-tier counters (sending past Meta's 24-hour unique-recipient cap and damaging the quality rating that gates the next tier), two session-window views. Fixed with a SharedStore boundary, an InMemoryStore default and a PgStore that pushes atomicity into the database, plus a single contract suite that both implementations must satisfy. Single-instance operation is now an explicit, guarded invariant until SHARED_STORE=pg is wired. GAP-E7: migrations 005/006 give delivery statuses, media refs, tenants and the shared state real tables with cascade deletes, so the retention purge and the restore drill still hold. | GAP-E7, GAP-E8, L-E5 | 35 suites / 167 tests at 100%; store.ts + persistence/pgStore.ts + migrations 005/006; R-E9 logged | Wiring SHARED_STORE=pg is a live-infra step on first deploy | E035
E035 | 2026-09-13 11:13 | Release | TRACKER v011 + WORKBOOK v017 RELEASED. Codebase v0.17.0. Position unchanged at 79 Done-in-code / 13 Pending-live / 6 Drafted / 2 In progress / 0 Backlog (309/399 pts) — architecture release. Deploy prerequisites unchanged; scaling beyond one instance now has a documented path rather than a silent failure mode. | D13,R2,R-E9 | Code: engageos_v0.17.0_src.zip | Pricing decision, WABA + secrets, reviewer, dispositions, D15 | v012 on live evidence
E036 | 2026-09-13 11:18 | Wiring | SELF-CAUGHT REPEAT: before starting anything new this sitting, checked who calls the SharedStore built in v017 — nobody did. That is exactly F-009/F-010, the finding where optIn.ts and sessionWindow.ts shipped in v007 and sat unused until v011: an abstraction that exists but is not on the execution path buys nothing while reading as solved in every document. Wired it: SharedWebhookGuard and SharedTierLimiter over the store, used by TenantRegistry and BroadcastService. The regressions are written as two-instance scenarios — blue and green sharing one store, where green sees the retry as a duplicate rather than processing it again, and where a single 250-recipient tier budget is shared rather than duplicated per instance. Session windows are honestly left process-local and logged as OPEN-E1 with the reason, not quietly carried. | F-021, OPEN-E1, L-E6 | 35 suites / 169 tests at 100%; sharedState.ts added | OPEN-E1 needs a disposition; SHARED_STORE=pg is still a live-infra step | E037
E037 | 2026-09-13 11:18 | Release | TRACKER v012 + WORKBOOK v018 RELEASED. Codebase v0.18.0. Position unchanged at 79 Done-in-code / 13 Pending-live / 6 Drafted / 2 In progress / 0 Backlog (309/399 pts). | D13,R2 | Code: engageos_v0.18.0_src.zip | Pricing decision, WABA + secrets, reviewer, dispositions, D15 | v013 on live evidence
E038 | 2026-09-13 11:24 | Deferred-close | CLOSED BOTH DEFERRED HALVES rather than letting them become permanent. OPEN-E1: the 24-hour customer-service window and 72-hour free-entry-point window now live in the shared store. This required making the inbox receive path async and carrying that through broadcast, tenancy, the demo seed and every affected test — exactly the deliberate pass the deferral was taken for, rather than a half-wiring. A window opened on one instance is now visible to the others, so a blue/green switch can no longer make the product demand a template where free-form was permitted. VER-E12 second half: resolveMedia() implements the genuine two-step fetch — media_id to a short-lived url, then an authenticated download with the same Bearer token, since an unauthenticated fetch of that url fails. Every cross-instance guard (dedupe, tier counting, session windows) now passes through one boundary with one contract. | OPEN-E1, VER-E12 | 35 suites / 171 tests at 100%; no deferred code halves remain | SHARED_STORE=pg wiring is the only remaining live-infra step for this area | E039
E039 | 2026-09-13 11:24 | Release | TRACKER v013 + WORKBOOK v019 RELEASED. Codebase v0.19.0. Position unchanged at 79 Done-in-code / 13 Pending-live / 6 Drafted / 2 In progress / 0 Backlog (309/399 pts). | D13,R2 | Code: engageos_v0.19.0_src.zip | Pricing decision, WABA + secrets, reviewer, dispositions, D15 | v014 on live evidence
E040 | 2026-09-13 11:31 | Handover | HANDOVER CONSOLIDATION + AS-BUILT RE-BASELINE. No code was written this sitting, deliberately: every remaining item depends on Senthil, and adding a twentieth code version would have been motion rather than progress. Instead: a Senthil_Handover sheet ordering all ten remaining items by leverage with effort, external lead time, what each unblocks and the exact command or link to act on — Meta Business verification first because it is both the longest external queue and the messaging-limit unlock, the same gate twice. And an as-built re-baseline of the product workbook spec sheets, untouched since 5 Sep while nineteen versions of execution happened: the financial model still rested on conversation-based pricing that Meta retired in July 2025, and the non-functional requirements claimed WCAG, uptime and SOC2 positions the code does not hold — both corrected, including the places where we do less than was claimed. | Handover, VER-E1, R-E8 | Tracker gains Senthil_Handover; workbook v020 re-baselines Financial_Model, Product_Spec, Metrics_Targets | Everything remaining is Senthil-side by definition | v015 on first input
E041 | 2026-09-13 11:31 | Release | TRACKER v014 + WORKBOOK v020 RELEASED. Codebase unchanged at v0.19.0 (35 suites / 171 tests, 100%). Position 79 Done-in-code / 13 Pending-live / 6 Drafted / 2 In progress / 0 Backlog (309/399 pts). EngageOS is complete to the sandbox ceiling with no deferred halves, no unexecuted findings and no undocumented gaps. | D13,R2 | Code: engageos_v0.19.0_src.zip (unchanged) | Handover sheet lists all 10 | v015 on first input
E042 | 2026-09-13 11:33 | Audit | INTEGRITY AUDIT, run because "properly" means proving claims rather than repeating them. Eight checks executed against the shipped zip and the tracker itself. The code held: a clean-room npm ci and build from engageos_v0.19.0_src.zip reproduced exactly, 35 suites / 171 tests, coverage gate satisfied, tracker and workbook statuses identical across two files, every non-backlog row version-stamped, documented commands all present. The RECORD did not: release notes had claimed one pragma where there were five (two were dead code and are now removed, leaving three process bootstraps and zero logic suppressions), two rows named their verification too vaguely to check, and nine rows had their story text overwritten with module paths by my own later update scripts — data loss in the traceability record, restored from the product backlog. All three fixed here, with the methods and outcomes written into a new Integrity_Audit sheet so the checks can be re-run by anyone. | Integrity_Audit sheet | Codebase v0.20.0 (2 dead-code pragmas removed); 9 traceability rows repaired; 2 evidence cells made verifiable | None | E043
E043 | 2026-09-13 11:33 | Release | TRACKER v015 + WORKBOOK v021 RELEASED. Codebase v0.20.0: 35 suites / 171 tests at 100%, three bootstrap pragmas and zero logic pragmas. Position unchanged at 79 Done-in-code / 13 Pending-live / 6 Drafted / 2 In progress / 0 Backlog (309/399 pts). | D13,R2 | Code: engageos_v0.20.0_src.zip | Handover sheet lists all 10 remaining items | v016 on first input
E044 | 2026-09-13 11:38 | Audit-2 | AUDIT PASS 2, applying the v021 discipline to the parts of the record it had not touched: the findings ledger and the workbooks themselves. Every one of the 37 findings marked closed was probed against the shipped source — not "does the file exist" but "is the fix on the execution path", so F-009 requires the opt-in gate to be CALLED in broadcast.ts. All 37 verified. Those probes are now tests/findingsRegression.test.ts, which runs on every commit, because F-021 already proved that a fix can exist and not be wired while the record reads as closed. A companion guard fails the build if an istanbul pragma appears outside the three documented bootstraps. On the workbook side: Sprint_Board reconciles exactly with the backlog and the version sequence is contiguous, but Launch_Checklist item 6 still asked for testing of conversation-based pricing that Meta retired in July 2025, items 2/3/8 predated decisions already made, and the three original risks had no IDs while later ones did — all corrected. | Integrity_Audit checks 9-14 | Codebase v0.21.0: 36 suites / 210 tests; workbook v022 corrections | None — audit clean after fixes | E045
E045 | 2026-09-13 11:38 | Release | TRACKER v016 + WORKBOOK v022 RELEASED. Codebase v0.21.0: 36 suites / 210 tests at 100%, zero logic pragmas. Position unchanged at 79 Done-in-code / 13 Pending-live / 6 Drafted / 2 In progress / 0 Backlog (309/399 pts). Every claim in both files is now either mechanically verified or explicitly marked as awaiting live evidence. | D13,R2 | Code: engageos_v0.21.0_src.zip | Handover sheet items 1-10 | v017 on first input
E046 | 2026-09-13 11:45 | Rehearsal | OPERATOR-PATH REHEARSAL — proving the claim that has been repeated for a dozen versions without evidence: that the commands in the setup guide actually run. npm run rehearse boots the real compiled server with placeholder secrets and drives it the way Meta will: liveness, the hub.challenge handshake (so the callback URL would save), a correctly signed webhook accepted and queued, the SAME webhook replayed and recognised as a duplicate — which is what stops a customer receiving two replies while Meta retries for hours — an unsigned webhook rejected 401 before any processing, admin routes refusing without the operator token, public status leaking nothing, pricing rendered from the billing plans, help search answering. Then the sweep runs in dry mode, 6 of 6 steps passing, with a banner making clear it is a fake surface. Executed in full, transcript committed, step added to CI so it cannot rot. This retires the real risk on the night credentials arrive, which was never Meta: it was npm start failing on a typo, or the sweep not being runnable. | REHEARSAL_TRANSCRIPT.md | Codebase v0.22.0: 36 suites / 210 tests; CI gains the rehearsal step; handover items 3-4 updated | Statuses unchanged — a fake surface is not evidence | E047
E047 | 2026-09-13 11:45 | Release | TRACKER v017 + WORKBOOK v023 RELEASED. Codebase v0.22.0. Position unchanged at 79 Done-in-code / 13 Pending-live / 6 Drafted / 2 In progress / 0 Backlog (309/399 pts). | D13,R2 | Code: engageos_v0.22.0_src.zip | Handover items 1-10; only Meta verification and credentials block the live sweep | v018 on first input
E048 | 2026-09-13 11:54 | Wiring-2 | REACHABILITY AUDIT of src/, prompted by having found the same class twice already. Result: views.ts and demoData.ts were imported by nothing but their own tests — and unlike the earlier cases, these sat behind ST-089 and ST-083, two stories the record already counted as Done-in-code. The product had accessible screens and a demo mode that no running process could display. Fixed by serving them: /app/inbox, /app/broadcast, /app/catalog, /app/onboarding and /app/inbox/empty render the shells with demo data, behind ENGAGEOS_DEMO so a demo workspace can never appear on a live tenant, axe-audited AS SERVED rather than only as unit-rendered, exercised by the rehearsal script and pinned in the findings regression suite. Practical effect: ST-094 screenshot capture is no longer blocked on the screens existing — they load today; what remains is a styling pass. Lesson L-E7: Done-in-code must mean the running product uses it, not that the module and its tests exist. | F-022, L-E7 | Codebase v0.23.0: 37 suites / 215 tests; evidence updated for ST-083/089/094 | None | E049
E049 | 2026-09-13 11:54 | Release | TRACKER v018 + WORKBOOK v024 RELEASED. Codebase v0.23.0: 37 suites / 215 tests at 100%. Position unchanged at 79 Done-in-code / 13 Pending-live / 6 Drafted / 2 In progress / 0 Backlog (309/399 pts). Every module in src/ is now reachable from the running product. | D13,R2 | Code: engageos_v0.23.0_src.zip | Handover items 1-10 | v019 on first input
E050 | 2026-09-13 11:58 | Wiring-3 | F-023 — the reachability lens turned on the product itself. Not "is the module imported" (F-021) or "is the screen served" (F-022) but "can anyone actually use this". They could not: every route was a GET except the webhook, so no agent could reply, reassign, create a campaign or add a product; and the inbound path verified, deduped and buffered messages that nothing drained into the inbox, so a customer message never became a conversation. The core loop stopped at the front door while 79 stories read as Done-in-code. Fixed with a per-tenant workspace registry, webhook-to-inbox delivery and an operator-gated action API across all five MVP features, plus router path parameters and the inbox reassignment that had never existed. The rehearsal now runs the loop: a signed webhook becomes conversation c1, reassignment succeeds, an unauthenticated call is refused, and a reply reaches the real Cloud API and returns 502 on placeholder credentials — which is exactly the proof that the wiring is real rather than mocked. | F-023, OPEN-E2, L-E8 | Codebase v0.24.0: 38 suites / 224 tests at 100%; two unreachable fallbacks removed rather than pragma-suppressed | OPEN-E2 per-agent auth needs a disposition | E051
E051 | 2026-09-13 11:58 | Release | TRACKER v019 + WORKBOOK v025 RELEASED. Codebase v0.24.0: 38 suites / 224 tests at 100%. Position unchanged at 79 Done-in-code / 13 Pending-live / 6 Drafted / 2 In progress / 0 Backlog (309/399 pts) — the stories were already counted; what changed is that they are now true of the running product. | D13,R2 | Code: engageos_v0.24.0_src.zip | Handover items 1-10 plus OPEN-E2 | v020 on first input
E052 | 2026-09-13 12:04 | Wiring-4 | COMPLETED F-023 instead of leaving it half-finished. A module-by-module sweep found nine src modules that nothing in the product imported. The most serious was compliance: your trust page and retention policy promise self-serve data export and delete-my-data, both implemented since v006 and callable by nobody — a published commitment a customer had no way to exercise. Also unreachable: analytics and the quality guard, the roles permission matrix, support chat, the partner and SEO tools, and both instrumentation modules. All wired. The matrix now binds at the HTTP boundary, so a member is refused campaign sends, billing and deletion with the action named, and every mutating call lands in the tenant audit log. The throughput limiter finally gates sends, and every request is timed against the p95 budget the product has claimed since v006. | F-024, F-025, F-026, L-E9 | Codebase v0.25.0: 39 suites / 241 tests at 100%; findings regression suite now pins 42 findings | OPEN-E2 narrowed: the matrix is enforced but identity is asserted by the trusted caller | E053
E053 | 2026-09-13 12:04 | Release | TRACKER v020 + WORKBOOK v026 RELEASED. Codebase v0.25.0: 39 suites / 241 tests at 100%, three bootstrap pragmas. Position unchanged at 79 Done-in-code / 13 Pending-live / 6 Drafted / 2 In progress / 0 Backlog (309/399 pts). No module in src/ is now unreachable from the running product. | D13,R2 | Code: engageos_v0.25.0_src.zip | Handover items 1-10 plus OPEN-E2 | v021 on first input
E054 | 2026-09-13 16:27 | Auth | OPEN-E2 CLOSED rather than deferred a third time. Agent identity had been a header the caller filled in — fine for a backend authenticated by the operator token, and exactly the defect that landed as a blocker on a sibling product the moment a browser was involved. Sessions are now HMAC-signed in src/auth.ts: only the operator token can mint one, which keeps password handling with the customer's own backend; the signed role and tenant govern, so a member presenting x-agent-role: owner is still refused; tokens expire after 12 hours; tampering, forgery with another secret and malformed bodies are all rejected by constant-time comparison; and the audit log finally records a verified actor instead of a claim. The rehearsal demonstrates the escalation attempt failing. Worth noting: the pragma guard added two sittings ago fired on a suppression I had just written, and the dead code came out instead. | OPEN-E2, L-E6 | Codebase v0.26.0: 40 suites / 250 tests at 100%; ENGAGEOS_SESSION_SECRET added to prerequisites and handover | None | E055
E055 | 2026-09-13 16:27 | Release | TRACKER v021 + WORKBOOK v027 RELEASED. Codebase v0.26.0: 40 suites / 250 tests at 100%. Position unchanged at 79 Done-in-code / 13 Pending-live / 6 Drafted / 2 In progress / 0 Backlog (309/399 pts). No open architectural item remains on the software side — every remaining line in the handover needs Senthil. | D13,R2 | Code: engageos_v0.26.0_src.zip | Handover items 1-10 | v022 on first input
E056 | 2026-09-13 16:32 | UI | F-027 — the reachability question asked about the human rather than the code. The screens wired in F-022 render state and nothing else: their buttons have no handlers, so every action in this product required a curl command carrying an operator token. An SME could not have used EngageOS and a design partner could not have been shown anything they could touch. A working agent workspace is now served at /web: paste the session token an admin issues, see the real conversations, open one, reply and get the outcome reported honestly — including the platform refusal reason rather than a shrug — compose a campaign and run a test send, add a product and receive its UPI payment link. The client is written as ordinary DOM functions that the jsdom suite drives the way an agent drives them, and the script sent to the browser is built by stringifying those same functions, so there is no second untested copy and no bundler to rot. Accessibility is asserted on every rendered state, and the page holds no tenant data of its own — it fetches with the agent's signed session, so it can never display more than that agent may see. | F-027, L-E10 | Codebase v0.27.0: 41 suites / 265 tests at 100%; ST-094 narrowed to styling alone | Unstyled by design — the design pass is his | E057
E057 | 2026-09-13 16:32 | Release | TRACKER v022 + WORKBOOK v028 RELEASED. Codebase v0.27.0: 41 suites / 265 tests at 100%. Position unchanged at 79 Done-in-code / 13 Pending-live / 6 Drafted / 2 In progress / 0 Backlog (309/399 pts) — but for the first time the product is usable by its intended user rather than only by a terminal. | D13,R2 | Code: engageos_v0.27.0_src.zip | Handover items 1-10 | v023 on first input
E058 | 2026-09-13 16:38 | UI-2 | COMPLETED THE UI instead of shipping the easy half. Reading the story wording literally against the surfaces that exist turned up two unkept promises. ST-069 says SELF-SERVE export and deletion, and the trust page publishes that right — but after F-024 both were operator-token API endpoints, reachable by us and not by the customer. They now sit in the agent workspace: export returns immediately, deletion asks for explicit confirmation, states the 30-day window in plain words, and has a tested cancel path. ST-057 describes a trial BANNER with days remaining; that had only ever been a string an API returned, and is now rendered. Added alongside: a health panel that turns the quality rating and the 24-hour messaging limit into sentences an SME can act on rather than raw numbers, and the first-run checklist with its progress line. Every screen is driven in jsdom the way an agent drives it and audited for accessibility in each rendered state. | F-028, L-E11, ST-057, ST-069 | Codebase v0.28.0: 41 suites / 274 tests at 100% | Styling is the only remaining blocker on ST-094 | E059
E059 | 2026-09-13 16:38 | Release | TRACKER v023 + WORKBOOK v029 RELEASED. Codebase v0.28.0: 41 suites / 274 tests at 100%. Position unchanged at 79 Done-in-code / 13 Pending-live / 6 Drafted / 2 In progress / 0 Backlog (309/399 pts). | D13,R2 | Code: engageos_v0.28.0_src.zip | Handover items 1-10 | v024 on first input
E060 | 2026-09-13 16:42 | Design | STYLING PASS — done rather than handed back. For three releases I had named styling as the last ST-094 blocker while calling it "a design job" for someone else; it was within reach, so the honest move was to do it. The visual language comes from the subject rather than from dashboard convention: an SME counter and the paper ledger on it, read on a mid-range Android in daylight by someone with a customer in front of them. Ink-blue on cool ledger paper, one type family on a 1.25 scale, and colour restricted to carrying conversation status so it never competes with emphasis. The queue is the one loud element — full-width rows, the customer number as the largest non-heading type, a status rule down the left edge — while plan, health, checklist and data stay quiet and ruled. One accessory removed, per the usual advice: a brass accent with no job once status colours signalled. The quality floor is tested, not asserted: a contrast check computes WCAG ratios for every text colour against the page and failed on first run against my own --closed grey at 4.19:1, which forced the correction to 5.25:1. Reasoning is written down in docs/DESIGN_NOTES.md so the next person can argue with it. | F-029, L-E12, ST-094 | Codebase v0.29.0: 41 suites / 279 tests at 100%; handover item 8 rewritten | Capture session and video production remain his | E061
E061 | 2026-09-13 16:42 | Release | TRACKER v024 + WORKBOOK v030 RELEASED. Codebase v0.29.0: 41 suites / 279 tests at 100%. Position unchanged at 79 Done-in-code / 13 Pending-live / 6 Drafted / 2 In progress / 0 Backlog (309/399 pts). | D13,R2 | Code: engageos_v0.29.0_src.zip | Handover items 1-10 | v025 on first input
E062 | 2026-09-13 16:47 | i18n | F-030 — the promise in the listing copy that the product did not keep. Hindi and Tamil packs were drafted in v007 and imported by nothing, while Variant A sells "Vernacular UI" to Indian SMEs: a Tamil-speaking shop owner, the core customer, would have opened an English-only screen, and the 30-day deletion promise would have been unreadable to the person it protects. The workspace now ships in English, Hindi and Tamil across all 47 strings with a switcher remembered per device, English fallback so a customer never sees a raw key, and two drift gates — one failing the build if any language is missing or empties a key, another failing if the disk packs disagree with the shipped strings, which are now their source. Limits recorded rather than glossed: the translations are machine-produced and need a native-speaker pass (OPEN-E3), and server-generated messages stay English until the API carries a locale. | F-030, OPEN-E3, L-E13, LC-10 | Codebase v0.30.0: 41 suites / 286 tests at 100%; handover gains the native-speaker review | Native-speaker review is cheap and his | E063
E063 | 2026-09-13 16:47 | Release | TRACKER v025 + WORKBOOK v031 RELEASED. Codebase v0.30.0: 41 suites / 286 tests at 100%. Position unchanged at 79 Done-in-code / 13 Pending-live / 6 Drafted / 2 In progress / 0 Backlog (309/399 pts). | D13,R2 | Code: engageos_v0.30.0_src.zip | Handover items 1-11 | v026 on first input
E064 | 2026-09-13 16:53 | Claims-audit | LISTING-CLAIMS AUDIT. L-E13 said the listing copy is a specification, so rather than wait to trip over the next unkept promise I checked every claim in the listing copy, pricing page and trust page against the shipped product. Five were untrue, and the worst is the flagship: "Answer at 2am with flows" — the chatbot only ran when an agent poked it through the API, so a customer messaging at 2am got silence. Flows now fire on inbound. "Broadcasts that protect your quality rating" — nothing consulted the guard before a send, so a red-rated number could have blasted a segment and lost the number the business runs on; red now refuses the campaign while amber and green proceed. The trust page promised circuit breakers on all platform calls and the breaker had no importer at all; one per tenant now fronts the adapter, so one customer's outage cannot open the circuit for everyone. Plan-limit prompts existed as a function nobody called. And "get paid in-chat" returned the UPI link to the AGENT — it now reaches the customer, priced and formatted, with refusals reported rather than claimed as sent. Four of the five were reachability failures in disguise: reading the marketing copy proved a better bug-finding technique than reading the code. | F-031..F-035, L-E14 | Codebase v0.31.0: 42 suites / 296 tests at 100%; each claim now has a test named after it | None | E065
E065 | 2026-09-13 16:53 | Release | TRACKER v026 + WORKBOOK v032 RELEASED. Codebase v0.31.0: 42 suites / 296 tests at 100%. Position unchanged at 79 Done-in-code / 13 Pending-live / 6 Drafted / 2 In progress / 0 Backlog (309/399 pts) — the stories did not move, but what they claim is now true of the running product. | D13,R2 | Code: engageos_v0.31.0_src.zip | Handover items 1-11 | v027 on first input
E066 | 2026-09-13 17:24 | Help-audit | HELP-CENTRE AUDIT — the claims-audit lens turned on the 15 published articles, which are a specification too: each walks a customer through a task. Eight of those tasks had no route and no control anywhere in the product. The worst is article 5, "Importing contacts & chats (CSV)", which is the competitor-migration path a new customer needs on their first day: the importers existed as library functions with passing tests, ST-009 and ST-019 both read Done-in-code, and a customer following the article would have hunted for an import button that was never built. Also unreachable: bulk close, assignment rules, pause-without-data-loss, catalog price edits and deactivation, chatbot node edits, and notification muting. All eight now have validated, permission-gated routes, and each article's task is pinned by a test named after the article so a future article describing something unbuilt fails the build. | F-036, L-E15, ST-009, ST-019 | Codebase v0.32.0: 43 suites / 307 tests at 100% | None | E067
E067 | 2026-09-13 17:24 | Release | TRACKER v027 + WORKBOOK v033 RELEASED. Codebase v0.32.0: 43 suites / 307 tests at 100%. Position unchanged at 79 Done-in-code / 13 Pending-live / 6 Drafted / 2 In progress / 0 Backlog (309/399 pts). | D13,R2 | Code: engageos_v0.32.0_src.zip | Handover items 1-11 | v028 on first input
E068 | 2026-09-13 17:28 | Template-audit | F-037 — the template library diffed against the wire format, and this one was live-blocking. Twelve of the twenty drafted templates carry variables, and the adapter sent name and language with no body components at all. Meta rejects a template whose placeholders have no matching parameters, so on the first live day order_shipped, appointment_confirm, payment_link and festive_sale would every one have failed — at the platform, surfacing as a bare error code with nothing useful in our own logs. The registry now declares each template with its variables, the adapter ships the components Meta requires, and a send with a missing or unexpected value is refused before the platform sees it with the offending variable named. A drift test fails the build if the published library and the registry disagree in either direction. Also added the template-send route, which had never existed despite being the only legitimate way to reach a customer once the 24-hour window closes. | F-037, L-E16 | Codebase v0.33.0: 44 suites / 315 tests at 100%; LC-4 note updated | Variable names must match the registry when submitting to Meta | E069
E069 | 2026-09-13 17:28 | Release | TRACKER v028 + WORKBOOK v034 RELEASED. Codebase v0.33.0: 44 suites / 315 tests at 100%. Position unchanged at 79 Done-in-code / 13 Pending-live / 6 Drafted / 2 In progress / 0 Backlog (309/399 pts). | D13,R2 | Code: engageos_v0.33.0_src.zip | Handover items 1-11 | v029 on first input
E070 | 2026-09-13 18:50 | Runbook-audit | F-038 — the launch runbook diffed against the product. Its first rollback step reads "feature-flag broadcasts off first if quality score drops to amber", and there was no feature flag anywhere: an operator at 2am, following the ladder as written, would have found nothing between noticing the problem and rolling back the whole deployment. Its monitoring line says check the quality rating every two hours, and nothing ever polled it — the guard ran only mid-broadcast, which is after the damage. Both are now real. Four per-capability kill switches mean the blast radius of turning something off is one capability rather than the product; every disable demands a reason and records who and when, because an unexplained flag discovered weeks later is its own incident. The quality check runs from cron or by hand, disables broadcasts automatically on a red rating, and leaves re-enabling to a human on the grounds that a recovering score is not an understood cause. The public status page now admits to a degraded capability instead of only counting errors. The runbook has been rewritten around the controls that exist. | F-038, L-E17, ST-098 | Codebase v0.34.0: 45 suites / 324 tests at 100% | Schedule the monitor every 2h at deploy time | E071
E071 | 2026-09-13 18:50 | Release | TRACKER v029 + WORKBOOK v035 RELEASED. Codebase v0.34.0: 45 suites / 324 tests at 100%. Position unchanged at 79 Done-in-code / 13 Pending-live / 6 Drafted / 2 In progress / 0 Backlog (309/399 pts). | D13,R2 | Code: engageos_v0.34.0_src.zip | Handover items 1-11 | v030 on first input
E072 | 2026-09-13 18:59 | Comms-audit | F-039 — the last operator document, and the same shape of gap as the seven before it. The incident comms file holds three written customer messages and a severity ladder with update cadences, and there was nowhere to publish any of it: during an outage a customer would have seen degraded:true while the carefully worded "your inbox and data are unaffected" sat unread in markdown, and the 15-minute Sev-1 cadence depended on a stressed human remembering it at 2am. Incidents now open, update and resolve with the full trail kept; the public status page carries the latest message and still leaks no error counts; and the operator view lists everything overdue for its next update with minutes late, so the cadence is enforced rather than remembered. An update with no words is refused, because a status entry that says nothing is worse than none. The external status-page vendor becomes a choice rather than a launch dependency. | F-039, L-E18, ST-084 | Codebase v0.35.0: 46 suites / 329 tests at 100% | None | E073
E073 | 2026-09-13 18:59 | Release | TRACKER v030 + WORKBOOK v036 RELEASED. Codebase v0.35.0: 46 suites / 329 tests at 100%. Position unchanged at 79 Done-in-code / 13 Pending-live / 6 Drafted / 2 In progress / 0 Backlog (309/399 pts). Every customer-facing and operator-facing document in the repo has now been diffed against the product, and each one is pinned by a test. | D13,R2,L-E18 | Code: engageos_v0.35.0_src.zip | Handover items 1-11 | v031 on first input
E074 | 2026-09-13 19:11 | Screens-audit | F-040 — the ninth specification, and it was the product workbook itself. Its Screens_Wireframes sheet names nine screens with a purpose each, and four did not exist: the home dashboard it calls the daily habit surface, the chatbot flows view it calls the DIFFERENTIATOR surface, settings and team, and help and support. A customer could reach neither the feature the sheet says sets this product apart nor the help meant to deflect support load. All four are now built in English, Hindi and Tamil and audited for accessibility in each rendered state — a morning summary of open conversations and number quality, a flows view that creates and test-runs a flow with an empty state explaining why it matters, help search that falls through to a support ticket when nothing matches, and notification controls. ST-074, the weekly metrics email, was wired in the same pass after sitting uncallable since v006; its activation figure now comes from the funnel rather than a spreadsheet. The Screens sheet records as-built status per screen so this cannot drift unnoticed again. | F-040, L-E19, ST-074 | Codebase v0.36.0: 47 suites / 336 tests at 100%; Screens sheet gains an as-built column | None | E075
E075 | 2026-09-13 19:11 | Release | TRACKER v031 + WORKBOOK v037 RELEASED. Codebase v0.36.0: 47 suites / 336 tests at 100%. Position unchanged at 79 Done-in-code / 13 Pending-live / 6 Drafted / 2 In progress / 0 Backlog (309/399 pts). Nine specifications have now been diffed against this product and all nine had gaps. | D13,R2,L-E19 | Code: engageos_v0.36.0_src.zip | Handover items 1-11 | v032 on first input
E076 | 2026-09-13 19:31 | Scope-audit | F-041 — the differentiation itself. The scope sheet states this product's differentiation as vertical templates for retail, clinics and education, and there was no vertical concept anywhere in the code: one flat list of twenty templates, so a clinic was handed order-tracking messages and a shop got appointment reminders. Four packs now exist, each selecting the templates that business actually uses along with a welcome line and a first routing keyword that fit it — choosing clinic at setup rewrites the flow a customer meets at 2am to "Book, reschedule or ask about an appointment" and seeds an appointment routing rule. A validation test fails the build if any pack names a template that does not exist. The GTM sheet has exactly one Eng-owned task, the in-app review ask after aha, and it was unbuilt for a subtler reason: the onboarding checklist was a hard-coded array whose steps did nothing, so aha was never reached and the ask could never fire. Steps complete for real now and the ask appears once, after the win. | F-041, OPEN-E4, ST-082 | Codebase v0.37.0: 48 suites / 343 tests at 100%; handover gains the pack review | Pack contents are a commercial judgement — OPEN-E4 | E077
E077 | 2026-09-13 19:31 | Release | TRACKER v032 + WORKBOOK v038 RELEASED. Codebase v0.37.0: 48 suites / 343 tests at 100%. Position unchanged at 79 Done-in-code / 13 Pending-live / 6 Drafted / 2 In progress / 0 Backlog (309/399 pts). Eleven specifications have now been diffed against this product; every one had at least one gap. | D13,R2 | Code: engageos_v0.37.0_src.zip | Handover items 1-12 | v033 on first input
E078 | 2026-09-13 19:36 | Close-out | CLOSE-OUT. Nothing new was built, deliberately: eleven specifications are diffed and fixed, the backlog is zero, and every remaining item belongs to Senthil. The shipped artifact was verified once more from the zip in a clean directory — npm ci, build and the 100% gate all reproduce, 48 suites / 344 tests, 60 modules, 61 routes, three pragmas all in process bootstraps and none in logic. The run's nineteen lessons were then rewritten for the other products rather than left as a diary: grouped by the TECHNIQUE that found each defect, since that is what transfers. The headline is uncomfortable and worth carrying: 100% coverage was in place from the first release and did not prevent a product that could not be used, four modules nothing called, eleven documents making promises the product did not keep, or thirteen wrong assumptions about the platform. The three techniques that did find them — reachability sweeps, document diffs and platform verification — all start from outside the code. | Lessons_For_Portfolio, STATE_OF_ENGAGEOS.md | No code change; codebase v0.37.1 = v0.37.0 plus the two documents | None — the queue is his | v034 on first input
E079 | 2026-09-13 19:36 | Release | TRACKER v033 RELEASED. EngageOS is closed to further unattended work: 79 Done-in-code / 13 Pending-live / 6 Drafted / 2 In progress / 0 Backlog (309/399 pts), 48 suites / 344 tests at 100%. Zero stories are Done, because Done means listed and paid for. The next version opens on live evidence, a disposition, or a decision from the handover sheet. | D13,R2 | Code: engageos_v0.37.1_src.zip | Handover items 1-12 | v034 on first input
E080 | 2026-09-13 19:40 | Audit-kit | THE TECHNIQUES MADE PORTABLE. The three checks that found what tests could not were bespoke to this repo, so the other eleven products could not use them; they are now three small scripts with per-product manifests and a README that says plainly what they will and will not do. Writing them paid for itself within minutes: on its first run against THIS codebase — already subjected to three cold reviews, a reachability sweep and a claims audit — the kit found that SHARED_STORE=pg had been documented in three places while nothing read the variable, so the Postgres store could not be selected however carefully it had been written and tested; and that the SEO tool was still imported by nothing, despite my own F-024 recording all nine modules as wired. The second one is the more useful result: a tool caught me overstating a finding, which is exactly the failure a lesson written in a spreadsheet does not catch. The kit itself then earned an improvement from being used, gaining consumer-directory scanning after one false positive, because a tool that cries wolf teaches a team to ignore it. | F-042, L-E20, ST-099, ST-100 | Codebase v0.38.0: 49 suites / 347 tests at 100%; audit_kit_v001.zip ships standalone | None | E081
E081 | 2026-09-13 19:40 | Release | TRACKER v034 + WORKBOOK v039 RELEASED. Codebase v0.38.0: 49 suites / 347 tests at 100%. Position unchanged at 79 Done-in-code / 13 Pending-live / 6 Drafted / 2 In progress / 0 Backlog (309/399 pts). | D13,R2 | Code: engageos_v0.38.0_src.zip; audit_kit_v001.zip | Handover items 1-12 | v035 on first input
E082 | 2026-09-13 20:08 | Audit-gates | THE AUDITS BECAME GATES. Each of them had been an exercise I performed once and wrote up; now they run on every commit. The work was in the manifests. audit/claims.json names all 43 promises made across the eleven customer- and operator-facing documents and binds each to the marker that would only exist if the promise were kept — "answer at 2am" is tied to the call site of autoReply, not to anyone remembering it was a commitment. audit/findings.json was GENERATED from the regression suite rather than retyped, so drift between them is impossible, and a test asserts the id sets match while naming the three probes a file marker cannot express, so that gap is a decision rather than an oversight. Today they all pass: 60 of 60 modules reachable, 43 of 43 promises kept, 55 of 55 closed findings still fixed. The pass is not the point. The point is that the next listing bullet written without code behind it fails a build rather than reaching a customer. | audit/claims.json, audit/findings.json | Codebase v0.39.0: 49 suites / 349 tests at 100%; CI runs npm run audit | None | E083
E083 | 2026-09-13 20:08 | Release | TRACKER v035 + WORKBOOK v040 RELEASED. Codebase v0.39.0: 49 suites / 349 tests at 100%. Position unchanged at 79 Done-in-code / 13 Pending-live / 6 Drafted / 2 In progress / 0 Backlog (309/399 pts). | D13,R2 | Code: engageos_v0.39.0_src.zip; audit_kit_v002.zip | Handover items 1-12 | v036 on first input
E084 | 2026-09-13 20:12 | Claims-extractor | A TOOL WRITTEN TWENTY MINUTES EARLIER FOUND A PROMISE NOBODY HAD NOTICED. The audit kit gained a claims extractor, because writing the manifest by hand is the entire adoption cost and it took a full sitting here; it reads the customer- and operator-facing documents and drafts the claim list with markers left blank, since deciding what makes a promise true is the judgement worth spending attention on. Run against this repo it surfaced a line from the incident template: "Sends are queued and will deliver automatically; no messages are lost." There was no outbound queue — an exhausted send was recorded as failed and forgotten, so the sentence we would publish mid-outage, when a customer trusts us least, was false. It had survived the full claims audit because I wrote that manifest from the documents I remembered rather than the documents on disk. F-043 fixed the product rather than the wording: failed sends are held, retried on demand once the outage clears, and dead-lettered with their last error where an operator can see exactly what was lost. | F-043, L-E21 | Codebase v0.40.0: 50 suites / 356 tests at 100%; audit kit v003 | Drain the queue before telling a customer nothing was lost | E085
E085 | 2026-09-13 20:12 | Release | TRACKER v036 + WORKBOOK v041 RELEASED. Codebase v0.40.0: 50 suites / 356 tests at 100%. Position unchanged at 79 Done-in-code / 13 Pending-live / 6 Drafted / 2 In progress / 0 Backlog (309/399 pts). | D13,R2 | Code: engageos_v0.40.0_src.zip; audit_kit_v003.zip | Handover items 1-12 | v037 on first input
E086 | 2026-09-13 20:26 | Posture | DID WHAT L-E21 ACTUALLY PRESCRIBED. That lesson said to draft the claims manifest from the documents on disk rather than the ones I remember, and I had only eyeballed the extractor output before moving on. Reconciling it properly against the hand-written 43 turned up thirteen uncovered candidates: most were covered in substance, five became claims, and one was a real gap. The trust page publishes a security posture — TLS 1.2 or better, AES-256 at rest, secrets in a vault and never in code — and nothing checked any of it; verifySecurityConfig() had been written in v006 and never called. That is the worst shape a security claim can take, because it reads as though it were verified. The fix is a posture check rather than an implementation, deliberately: at-rest encryption and TLS termination belong to the database and the load balancer, and a product that encrypted fields itself while claiming disk encryption would simply be lying differently. What it can honestly do is refuse to start when its own configuration contradicts what we publish. Three findings recorded in this sheet but never added to the regression array were also added — the record and the gate had drifted. | F-044, F-045, L-E21 | Codebase v0.41.0: 51 suites / 365 tests at 100%; 62 modules reachable, 48 promises kept, 58 findings defended | Deploy must set DB_ENCRYPTION_AT_REST, TLS_MIN and SECRETS_SOURCE | E087
E087 | 2026-09-13 20:26 | Release | TRACKER v037 + WORKBOOK v042 RELEASED. Codebase v0.41.0: 51 suites / 365 tests at 100%. Position unchanged at 79 Done-in-code / 13 Pending-live / 6 Drafted / 2 In progress / 0 Backlog (309/399 pts). | D13,R2 | Code: engageos_v0.41.0_src.zip | Handover items 1-12 | v038 on first input
E088 | 2026-09-13 20:33 | Workbook-claims | THE EXTRACTOR COULD NOT READ THE DOCUMENTS THAT MATTER MOST HERE. It handled markdown only, while in this portfolio the richest specifications are spreadsheets — the screen inventory and the stated differentiation both came from sheets, and both described features that did not exist. A converter now feeds the readable sheets into the same pipeline, skipping logs and trackers because a version history records what happened rather than promising anything. Building it produced two bugs in the kit that are worth more than the feature. The converter silently skipped Full_Backlog — the hundred user stories, the largest specification in the file — because a bare "log" pattern matched "Backlog", and it reported success while doing so; and the extractor did not recognise first-person user stories, so even once the sheet was included it would have drafted nothing from it. A tool that cries wolf gets ignored; a tool that quietly omits the main artifact is worse, because it tells you everything is fine. Both fixed, both written into the README as cautions. The 35 stories now surfaced were cross-checked against the traceability matrix: all present, all Done-in-code, so the matrix stays the gate for stories and the manifest stays for prose. | F-046, F-047 | Codebase v0.42.0: 51 suites / 365 tests at 100%; audit kit v004; 49 promises kept | Worth running the converter on the other products' workbooks | E089
E089 | 2026-09-13 20:33 | Release | TRACKER v038 + WORKBOOK v043 RELEASED. Codebase v0.42.0: 51 suites / 365 tests at 100%. Position unchanged at 79 Done-in-code / 13 Pending-live / 6 Drafted / 2 In progress / 0 Backlog (309/399 pts). | D13,R2 | Code: engageos_v0.42.0_src.zip; audit_kit_v004.zip | Handover items 1-12 | v039 on first input
E090 | 2026-09-13 22:49 | Kit-tests | THE KIT THAT ENFORCES QUALITY HAD NONE OF ITS OWN. It had shipped three bugs already and was about to go to eleven other products untested, which is not a position I can defend while using it to argue that other people's code makes claims nothing verifies. It now has eleven tests, and one is named for each bug it has shipped: the reachability false positive, the backlog silently dropped because a bare "log" pattern matched "Backlog" while reporting success, and the first-person user stories it could not see. Exit codes are asserted too, because a check that cannot fail a build is decoration. Writing them caught a fourth error that was mine rather than the tool's — a test expected reachability to exempt an entry module automatically, when the correct behaviour is to report it unless the consumer directory is supplied, which is exactly the false positive the kit had already been fixed for. The contrast is now asserted in both directions so the behaviour is documented rather than assumed. | F-048 | Codebase v0.43.0: 51 suites / 365 tests at 100%; audit kit v1.0.0 with 11 tests in CI | None | E091
E091 | 2026-09-13 22:49 | Release | TRACKER v039 + WORKBOOK v044 RELEASED. Codebase v0.43.0: 51 suites / 365 tests at 100%; audit kit v1.0.0. Position unchanged at 79 Done-in-code / 13 Pending-live / 6 Drafted / 2 In progress / 0 Backlog (309/399 pts). | D13,R2 | Code: engageos_v0.43.0_src.zip; audit_kit_v100.zip | Handover items 1-12 | v040 on first input

## Decisions
DECISIONS (tracker scope)
ID | Decision | Rationale | Decided by | Status
D13 | (Portfolio-wide) Discovery interviews parked; development proceeds with 100% automation test coverage on all code. Supersedes ST-085 >=70% gate. | Senthil 10 Sep 20:45; applied to EngageOS per 22:22 continue directive. Enforced via jest coverageThreshold 100x4. | Senthil | LOCKED
D15 | EngageOS build opened 10 Sep 22:22 as one of multiple concurrent builds while the rank-1 completion gate (listed + 10 paying) is unmet. MODE TO RATIFY: (a) formal parallel builds, or (b) hold-serial with order decision. | Logged per R7-class rule; consolidated across products in the 23:03 portfolio action board. | Senthil (mode ratification pending) | OPEN — pick (a) or (b)
D-E1 | Stack = TypeScript/Node per v005 ReadMe assumption; WhatsApp Cloud API behind WaApi adapter interface with FakeWaApi (failure injection) for sandbox; real HTTP client swaps in at live wiring. | Sandbox has no Meta credentials; adapter isolation means live wiring is one module. Same accepted pattern as TeleField D16. | Claude — flagged | OPEN for ratification
D-E2 | Status taxonomy for this tracker: Done-in-code / Pending-live (WhatsApp) / Drafted / In progress / Backlog. Rollup counts Done-in-code + Done. | R2-class honesty: code complete is not listed/live; drafts are not published. | Claude — flagged | OPEN for ratification
D-E3 | ST-085 recorded as Done-in-code with evidence "superseded by D13 100% gate" rather than deleted. | Preserves backlog integrity + audit trail of the gate change. | Claude | APPLIED

## V006_Build_Board
V006 BUILD BOARD — S1-S8 development run (22:22) — 15 modules, 16 suites / 73 tests, 100%x4
ID | Item | Story refs | Sprint | Owner | Status | Notes / Evidence
B6-01 | Repo scaffold + CI with 100% coverage gate (D13) | — | S1 | Claude | Done | jest coverageThreshold 100x4; .github/workflows/ci.yml runs build+test+smoke on push/PR/deploy. E010.
B6-02 | E1 install lifecycle: OAuth install, uninstall token purge + retention deletion, re-install window, token rotation, attribution | ST-051(logic),052,053,055,056 | S1-S2 | Claude | Done | install.ts + install.test.ts (8 tests incl. RETENTION_EXPIRED, duplicate-install, uninstalled-rotation-block).
B6-03 | Roles matrix + audit log | ST-054,067 + F-perm stories | S2,S8 | Claude | Done | roles.ts 9-action owner/admin/member MATRIX; guard() FORBIDDEN + AuditLog entries.
B6-04 | F1 team inbox: defaults, rule+round-robin assignment, reply retry, bulk, pause-safe, CSV import, metrics, notifications | ST-001..004,006..010 | S2-S3 | Claude | Done | inbox.ts + inbox.test.ts (8 tests); notify.ts per-type mute.
B6-05 | F2 broadcasts: segments, test mode, send retry + failure ledger, metrics, pause-safe, contact import | ST-011..014,016..020 | S3-S4 | Claude | Done | broadcast.ts + broadcast.test.ts (6 tests incl. retry-exhaustion failure recording).
B6-06 | F3 chatbot flows: default flow, run engine, branch/loop/broken-link errors, export/import, metrics | ST-021..024,026..030 | S5 | Claude | Done | chatbot.ts + chatbot.test.ts (5 tests).
B6-07 | F4 catalog + UPI links: VPA validation, CRUD, deep-link format, CSV import, pause-safe, metrics | ST-031..034,036..040 | S6 | Claude | Done | catalog.ts + catalog.test.ts (6 tests); upi://pay deep link asserted byte-exact.
B6-08 | F5 analytics + quality guard: score->status->action, thresholds, funnel, health, heatmap, CSV export | ST-041..044,046..050,071,073,075,076,077 | S8 | Claude | Done | analyticsGuard.ts + suite (5 tests); red status => throttle broadcasts action.
B6-09 | E5 billing: trial, proration+clamp, provider selection, dunning 0/3/6->read-only, limits 80/100, GST invoice, cancellation | ST-057..063 | S6-S7 | Claude | Done | billing.ts + billing.test.ts (9 tests).
B6-10 | E6 compliance: SCOPE_MAP least privilege, retention policy, security-config verify, export/delete-my-data | ST-064,065,066(code),069 | S7-S8 | Claude | Done | compliance.ts + suite (4 tests); docs/DATA_FLOW.md published in repo.
B6-11 | Resilience: exp backoff retry + circuit breaker; chaos degradation | ST-070,091 + per-feature error stories | S8 | Claude | Done | resilience.ts + suite; FakeWaApi outage injection across inbox/broadcast suites.
B6-12 | E7 telemetry: error tracking w/ release tags + spike alert; weekly metrics email | ST-072,074 | S4,S8 | Claude | Done | telemetry.ts + suite.
B6-13 | E8 onboarding: checklist->aha<1day, empty states, review-ask once post-aha | ST-078,079,082 | S5,S11 | Claude | Done | onboarding.ts + suite (4 tests).
B6-14 | EQ: E2E smoke on every deploy; p95 budgets | ST-086,087 | S4,S8 | Claude | Done | tests/smoke.test.ts full MVP loop; latency.ts budgets api/ui/webhook.
B6-15 | Live Meta dev-store install E2E (8 Pending-live stories) | ST-005,015,025,035,045,051,059,066 | S1-S8 | Senthil + Claude | To do | Needs Meta Business verification + WABA production access; evidence: install proof + org id + telemetry row.

## V007_Build_Board
V007 BUILD BOARD — S9-S10 draftable run (22:55) — +4 modules, 20 suites / 78 tests, 100%x4
ID | Item | Story/LC refs | Owner | Status | Notes / Evidence
B7-01 | 24-hour session window + template fallback | LC-7 | Claude | Done | sessionWindow.ts — free-form in-window, template outside, TEMPLATE_REQUIRED_OUTSIDE_24H hard error.
B7-02 | Webhook dedupe + burst queue at 50 msg/s shape | LC-8 | Claude | Done | webhookGuard.ts — wamid dedupe, bounded queue, overflow counter, drain; stats asserted.
B7-03 | Opt-in proof capture + marketing-send gate | LC-5 | Claude | Done | optIn.ts — checkbox-text-required proof, revoke, utility-vs-marketing canSend.
B7-04 | Demo-data sandbox mode seeding all surfaces | ST-083 (code half) | Claude | Done | demoData.ts seeds 2 convos, campaign, flow, 2 catalog items; demoData.test.ts E2E.
B7-05 | Listing copy A/B variants | ST-093 | Claude | Drafted | docs/listing/LISTING_COPY_A_B.md — Senthil to pick; 30-day CVR test plan included.
B7-06 | Pricing matrix + FAQ | ST-095 | Claude | Drafted | docs/listing/PRICING_FAQ.md — 3 plans from billing.ts PLANS; Meta fees pass-through stated.
B7-07 | Security/trust page | ST-096 | Claude | Drafted | docs/listing/TRUST_SECURITY.md — from compliance.ts facts; subprocessor list owed at GA.
B7-08 | 2-min demo video script | ST-083 (script half) | Claude | Drafted | docs/listing/DEMO_VIDEO_SCRIPT.md — production pending.
B7-09 | Launch-day runbook | ST-098 | Claude | Drafted | docs/launch/RUNBOOK.md — T-1/T-0, rollback, comms tree, 48h success checks.
B7-10 | Incident comms + severity ladder | ST-084 | Claude | Drafted | docs/launch/INCIDENT_COMMS.md — status-page vendor setup pending.
B7-11 | 15 help-center articles | ST-080 | Claude | Drafted | docs/help/HELP_CENTER_ARTICLES.md — publish to help-desk vendor at S10.
B7-12 | k6 load harness (10 rps + 50/s burst) | ST-088 | Claude | Drafted | ops/loadtest.k6.js — thresholds p95<500ms, fail<1%; live staging run pending.
B7-13 | Backup/restore drill | ST-090 | Claude | Drafted | ops/BACKUP_RESTORE_DRILL.md — RTO<2h RPO<24h targets; execution needs live infra.
B7-14 | Blue/green deploy workflow | ST-092 | Claude | Drafted | .github/workflows/deploy.yml — provider CLI stubs marked; live verification pending.
B7-15 | 20 Meta message templates (12 utility / 8 marketing) | LC-4 | Claude | Drafted | docs/templates/MESSAGE_TEMPLATES.md — submit after WABA access (LC-1).
B7-16 | Hindi/Tamil i18n string packs | LC-10 | Claude | Drafted | i18n/hi.json + i18n/ta.json (15 core strings each) — native-speaker QA pending.
B7-17 | Submission dry-run vs Launch_Checklist | ST-097 | Claude + reviewer | In progress | Self dry-run done this session (checklist re-statused); second-reviewer pass pending.

## Traceability_Matrix
TRACEABILITY MATRIX — 100 stories: module -> epic -> story -> screen -> verification -> status (edit yellow)
Source: product workbook v007 Full_Backlog (single source of truth, D12 pattern). Evidence rows carry the workbook version + timestamp that closed them (D13). Status per D-E2 taxonomy.
Story ID | Epic | Module / feature | Story | Points | Priority | Sprint | Primary screen | Verification | Status | Evidence
ST-001 | F1 | Team inbox + assignment | As a SME owner, I can set up Team inbox + assignment with sensible defaults in one screen | 5 | P0 | S2 | SCR-3 Inbox workspace | inbox.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — inbox.ts; tests: inbox.test.ts. Team inbox + assignment: one-screen setup with validated defaults
ST-002 | F1 | Team inbox + assignment | As a SME owner, the Team inbox + assignment happy path completes without documentation | 8 | P0 | S2 | SCR-3 Inbox workspace | inbox.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — inbox.ts; tests: inbox.test.ts. Happy path covered end-to-end on fake platform surface
ST-003 | F1 | Team inbox + assignment | As a Marketing person, I can customise Team inbox + assignment rules/conditions for my workflow | 5 | P1 | S2 | SCR-3 Inbox workspace | inbox.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — inbox.ts; tests: inbox.test.ts. Rules/conditions customisation with validation errors
ST-004 | F1 | Team inbox + assignment | As a user, Team inbox + assignment shows clear errors and retry paths on platform API failures | 3 | P0 | S2 | SCR-3 Inbox workspace | inbox.test.ts + resilience.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — inbox.ts + resilience.ts; tests: inbox.test.ts + resilience.test.ts. Retry w/ backoff; clear error after exhausting attempts
ST-005 | F1 | Team inbox + assignment | As a Support agent, Team inbox + assignment works on the web app + WhatsApp Cloud API surface end-to-end | 5 | P0 | S3 | SCR-3 Inbox workspace | inbox.test.ts + live E2E | Pending-live | Logic done v006 22:22 in inbox.ts (inbox.test.ts); live WhatsApp/Meta E2E outstanding. Logic Done vs FakeWaApi; live Cloud API E2E outstanding
ST-006 | F1 | Team inbox + assignment | As a Marketing person, I can see Team inbox + assignment performance metrics and trends | 3 | P1 | S3 | SCR-3 Inbox workspace | inbox.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — inbox.ts; tests: inbox.test.ts. Metrics/trends computed and asserted
ST-007 | F1 | Team inbox + assignment | As a user, Team inbox + assignment respects role permissions and audit logging | 3 | P1 | S3 | SCR-3 Inbox workspace | roles.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — inbox.ts + roles.ts; tests: roles.test.ts. owner/admin/member matrix + AuditLog entries
ST-008 | F1 | Team inbox + assignment | As a SME owner, I can pause/disable Team inbox + assignment without data loss | 2 | P2 | S3 | SCR-3 Inbox workspace | inbox.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — inbox.ts; tests: inbox.test.ts. Pause blocks activity; data retained (asserted)
ST-009 | F1 | Team inbox + assignment | As a Marketing person, I can import/migrate existing data into Team inbox + assignment (CSV + competitor importer) | 5 | P1 | S3 | SCR-3 Inbox workspace | inbox.test.ts | Done-in-code | DONE-IN-CODE v033 17:24 — chat CSV import reachable (POST /api/inbox/import); library-only until now
ST-010 | F1 | Team inbox + assignment | As a user, I get notifications (in-app + email) for key Team inbox + assignment events with per-type mute | 3 | P2 | S3 | SCR-3 Inbox workspace | notify.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — inbox.ts + notify.ts; tests: notify.test.ts. In-app + email with per-type mute
ST-011 | F2 | Broadcast campaigns + segments | As a SME owner, I can set up Broadcast campaigns + segments with sensible defaults in one screen | 5 | P0 | S3 | SCR-4 Broadcast builder | broadcast.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — broadcast.ts; tests: broadcast.test.ts. Broadcast campaigns + segments: one-screen setup with validated defaults
ST-012 | F2 | Broadcast campaigns + segments | As a SME owner, the Broadcast campaigns + segments happy path completes without documentation | 8 | P0 | S3 | SCR-4 Broadcast builder | broadcast.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — broadcast.ts; tests: broadcast.test.ts. Happy path covered end-to-end on fake platform surface
ST-013 | F2 | Broadcast campaigns + segments | As a Marketing person, I can customise Broadcast campaigns + segments rules/conditions for my workflow | 5 | P1 | S3 | SCR-4 Broadcast builder | broadcast.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — broadcast.ts; tests: broadcast.test.ts. Rules/conditions customisation with validation errors
ST-014 | F2 | Broadcast campaigns + segments | As a user, Broadcast campaigns + segments shows clear errors and retry paths on platform API failures | 3 | P0 | S3 | SCR-4 Broadcast builder | broadcast.test.ts + resilience.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — broadcast.ts + resilience.ts; tests: broadcast.test.ts + resilience.test.ts. Retry w/ backoff; clear error after exhausting attempts
ST-015 | F2 | Broadcast campaigns + segments | As a Support agent, Broadcast campaigns + segments works on the web app + WhatsApp Cloud API surface end-to-end | 5 | P0 | S4 | SCR-4 Broadcast builder | broadcast.test.ts + live E2E | Pending-live | Logic done v006 22:22 in broadcast.ts (broadcast.test.ts); live WhatsApp/Meta E2E outstanding. Logic Done vs FakeWaApi; live Cloud API E2E outstanding
ST-016 | F2 | Broadcast campaigns + segments | As a Marketing person, I can see Broadcast campaigns + segments performance metrics and trends | 3 | P1 | S4 | SCR-4 Broadcast builder | broadcast.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — broadcast.ts; tests: broadcast.test.ts. Metrics/trends computed and asserted
ST-017 | F2 | Broadcast campaigns + segments | As a user, Broadcast campaigns + segments respects role permissions and audit logging | 3 | P1 | S4 | SCR-4 Broadcast builder | roles.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — broadcast.ts + roles.ts; tests: roles.test.ts. owner/admin/member matrix + AuditLog entries
ST-018 | F2 | Broadcast campaigns + segments | As a SME owner, I can pause/disable Broadcast campaigns + segments without data loss | 2 | P2 | S4 | SCR-4 Broadcast builder | broadcast.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — broadcast.ts; tests: broadcast.test.ts. Pause blocks activity; data retained (asserted)
ST-019 | F2 | Broadcast campaigns + segments | As a Marketing person, I can import/migrate existing data into Broadcast campaigns + segments (CSV + competitor importer) | 5 | P1 | S4 | SCR-4 Broadcast builder | broadcast.test.ts | Done-in-code | DONE-IN-CODE v033 17:24 — contact CSV import reachable (POST /api/contacts/import)
ST-020 | F2 | Broadcast campaigns + segments | As a user, I get notifications (in-app + email) for key Broadcast campaigns + segments events with per-type mute | 3 | P2 | S4 | SCR-4 Broadcast builder | notify.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — broadcast.ts + notify.ts; tests: notify.test.ts. In-app + email with per-type mute
ST-021 | F3 | No-code chatbot flows | As a SME owner, I can set up No-code chatbot flows with sensible defaults in one screen | 5 | P0 | S5 | SCR-5 Chatbot flows view | chatbot.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — chatbot.ts; tests: chatbot.test.ts. No-code chatbot flows: one-screen setup with validated defaults
ST-022 | F3 | No-code chatbot flows | As a SME owner, the No-code chatbot flows happy path completes without documentation | 8 | P0 | S5 | SCR-5 Chatbot flows view | chatbot.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — chatbot.ts; tests: chatbot.test.ts. Happy path covered end-to-end on fake platform surface
ST-023 | F3 | No-code chatbot flows | As a Marketing person, I can customise No-code chatbot flows rules/conditions for my workflow | 5 | P1 | S5 | SCR-5 Chatbot flows view | chatbot.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — chatbot.ts; tests: chatbot.test.ts. Rules/conditions customisation with validation errors
ST-024 | F3 | No-code chatbot flows | As a user, No-code chatbot flows shows clear errors and retry paths on platform API failures | 3 | P0 | S5 | SCR-5 Chatbot flows view | chatbot.test.ts + resilience.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — chatbot.ts + resilience.ts; tests: chatbot.test.ts + resilience.test.ts. Retry w/ backoff; clear error after exhausting attempts
ST-025 | F3 | No-code chatbot flows | As a Support agent, No-code chatbot flows works on the web app + WhatsApp Cloud API surface end-to-end | 5 | P0 | S5 | SCR-5 Chatbot flows view | chatbot.test.ts + live E2E | Pending-live | Logic done v006 22:22 in chatbot.ts (chatbot.test.ts); live WhatsApp/Meta E2E outstanding. Logic Done vs FakeWaApi; live Cloud API E2E outstanding
ST-026 | F3 | No-code chatbot flows | As a Marketing person, I can see No-code chatbot flows performance metrics and trends | 3 | P1 | S5 | SCR-5 Chatbot flows view | chatbot.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — chatbot.ts; tests: chatbot.test.ts. Metrics/trends computed and asserted
ST-027 | F3 | No-code chatbot flows | As a user, No-code chatbot flows respects role permissions and audit logging | 3 | P1 | S5 | SCR-5 Chatbot flows view | roles.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — chatbot.ts + roles.ts; tests: roles.test.ts. owner/admin/member matrix + AuditLog entries
ST-028 | F3 | No-code chatbot flows | As a SME owner, I can pause/disable No-code chatbot flows without data loss | 2 | P2 | S5 | SCR-5 Chatbot flows view | chatbot.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — chatbot.ts; tests: chatbot.test.ts. Pause blocks activity; data retained (asserted)
ST-029 | F3 | No-code chatbot flows | As a Marketing person, I can import/migrate existing data into No-code chatbot flows (CSV + competitor importer) | 5 | P1 | S5 | SCR-5 Chatbot flows view | chatbot.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — chatbot.ts; tests: chatbot.test.ts. CSV/row import with per-row validation errors
ST-030 | F3 | No-code chatbot flows | As a user, I get notifications (in-app + email) for key No-code chatbot flows events with per-type mute | 3 | P2 | S5 | SCR-5 Chatbot flows view | notify.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — chatbot.ts + notify.ts; tests: notify.test.ts. In-app + email with per-type mute
ST-031 | F4 | Catalog + payment links | As a SME owner, I can set up Catalog + payment links with sensible defaults in one screen | 5 | P0 | S6 | SCR-2 Home / catalog surface | catalog.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — catalog.ts; tests: catalog.test.ts. Catalog + payment links: one-screen setup with validated defaults
ST-032 | F4 | Catalog + payment links | As a SME owner, the Catalog + payment links happy path completes without documentation | 8 | P0 | S6 | SCR-2 Home / catalog surface | catalog.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — catalog.ts; tests: catalog.test.ts. Happy path covered end-to-end on fake platform surface
ST-033 | F4 | Catalog + payment links | As a Marketing person, I can customise Catalog + payment links rules/conditions for my workflow | 5 | P1 | S6 | SCR-2 Home / catalog surface | catalog.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — catalog.ts; tests: catalog.test.ts. Rules/conditions customisation with validation errors
ST-034 | F4 | Catalog + payment links | As a user, Catalog + payment links shows clear errors and retry paths on platform API failures | 3 | P0 | S6 | SCR-2 Home / catalog surface | catalog.test.ts + resilience.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — catalog.ts + resilience.ts; tests: catalog.test.ts + resilience.test.ts. Retry w/ backoff; clear error after exhausting attempts
ST-035 | F4 | Catalog + payment links | As a Support agent, Catalog + payment links works on the web app + WhatsApp Cloud API surface end-to-end | 5 | P0 | S6 | SCR-2 Home / catalog surface | catalog.test.ts + live E2E | Pending-live | Logic done v006 22:22 in catalog.ts (catalog.test.ts); live WhatsApp/Meta E2E outstanding. Logic Done vs FakeWaApi; live Cloud API E2E outstanding
ST-036 | F4 | Catalog + payment links | As a Marketing person, I can see Catalog + payment links performance metrics and trends | 3 | P1 | S6 | SCR-2 Home / catalog surface | catalog.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — catalog.ts; tests: catalog.test.ts. Metrics/trends computed and asserted
ST-037 | F4 | Catalog + payment links | As a user, Catalog + payment links respects role permissions and audit logging | 3 | P1 | S6 | SCR-2 Home / catalog surface | roles.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — catalog.ts + roles.ts; tests: roles.test.ts. owner/admin/member matrix + AuditLog entries
ST-038 | F4 | Catalog + payment links | As a SME owner, I can pause/disable Catalog + payment links without data loss | 2 | P2 | S6 | SCR-2 Home / catalog surface | catalog.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — catalog.ts; tests: catalog.test.ts. Pause blocks activity; data retained (asserted)
ST-039 | F4 | Catalog + payment links | As a Marketing person, I can import/migrate existing data into Catalog + payment links (CSV + competitor importer) | 5 | P1 | S6 | SCR-2 Home / catalog surface | catalog.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — catalog.ts; tests: catalog.test.ts. CSV/row import with per-row validation errors
ST-040 | F4 | Catalog + payment links | As a user, I get notifications (in-app + email) for key Catalog + payment links events with per-type mute | 3 | P2 | S6 | SCR-2 Home / catalog surface | notify.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — catalog.ts + notify.ts; tests: notify.test.ts. In-app + email with per-type mute
ST-041 | F5 | Analytics + quality-score guard | As a SME owner, I can set up Analytics + quality-score guard with sensible defaults in one screen | 5 | P0 | S8 | SCR-8 Analytics | analyticsGuard.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — analyticsGuard.ts; tests: analyticsGuard.test.ts. Analytics + quality-score guard: one-screen setup with validated defaults
ST-042 | F5 | Analytics + quality-score guard | As a SME owner, the Analytics + quality-score guard happy path completes without documentation | 8 | P0 | S8 | SCR-8 Analytics | analyticsGuard.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — analyticsGuard.ts; tests: analyticsGuard.test.ts. Happy path covered end-to-end on fake platform surface
ST-043 | F5 | Analytics + quality-score guard | As a Marketing person, I can customise Analytics + quality-score guard rules/conditions for my workflow | 5 | P1 | S8 | SCR-8 Analytics | analyticsGuard.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — analyticsGuard.ts; tests: analyticsGuard.test.ts. Rules/conditions customisation with validation errors
ST-044 | F5 | Analytics + quality-score guard | As a user, Analytics + quality-score guard shows clear errors and retry paths on platform API failures | 3 | P0 | S8 | SCR-8 Analytics | analyticsGuard.test.ts + resilience.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — analyticsGuard.ts + resilience.ts; tests: analyticsGuard.test.ts + resilience.test.ts. Retry w/ backoff; clear error after exhausting attempts
ST-045 | F5 | Analytics + quality-score guard | As a Support agent, Analytics + quality-score guard works on the web app + WhatsApp Cloud API surface end-to-end | 5 | P0 | S8 | SCR-8 Analytics | analyticsGuard.test.ts + live E2E | Pending-live | Logic done v006 22:22 in analyticsGuard.ts (analyticsGuard.test.ts); live WhatsApp/Meta E2E outstanding. Logic Done vs FakeWaApi; live Cloud API E2E outstanding
ST-046 | F5 | Analytics + quality-score guard | As a Marketing person, I can see Analytics + quality-score guard performance metrics and trends | 3 | P1 | S8 | SCR-8 Analytics | analyticsGuard.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — analyticsGuard.ts; tests: analyticsGuard.test.ts. Metrics/trends computed and asserted
ST-047 | F5 | Analytics + quality-score guard | As a user, Analytics + quality-score guard respects role permissions and audit logging | 3 | P1 | S8 | SCR-8 Analytics | roles.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — analyticsGuard.ts + roles.ts; tests: roles.test.ts. owner/admin/member matrix + AuditLog entries
ST-048 | F5 | Analytics + quality-score guard | As a SME owner, I can pause/disable Analytics + quality-score guard without data loss | 2 | P2 | S8 | SCR-8 Analytics | analyticsGuard.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — analyticsGuard.ts; tests: analyticsGuard.test.ts. Pause blocks activity; data retained (asserted)
ST-049 | F5 | Analytics + quality-score guard | As a Marketing person, I can import/migrate existing data into Analytics + quality-score guard (CSV + competitor importer) | 5 | P1 | S8 | SCR-8 Analytics | analyticsGuard.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — analyticsGuard.ts; tests: analyticsGuard.test.ts. CSV/row import with per-row validation errors
ST-050 | F5 | Analytics + quality-score guard | As a user, I get notifications (in-app + email) for key Analytics + quality-score guard events with per-type mute | 3 | P2 | S8 | SCR-8 Analytics | notify.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — analyticsGuard.ts + notify.ts; tests: notify.test.ts. In-app + email with per-type mute
ST-051 | E1 | Install lifecycle | Marketplace OAuth install completes and lands on welcome state in <2 min | 5 | P0 | S1 | SCR-1 Onboarding | install.test.ts + live E2E | Pending-live | Logic done v006 22:22 in install.ts (install.test.ts); live WhatsApp/Meta E2E outstanding. Install logic + attribution Done; <2 min timing needs live dev store
ST-052 | E1 | Install lifecycle | Uninstall webhook removes tokens, schedules data deletion per policy | 3 | P0 | S1 | SCR-1 Onboarding | install.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — install.ts; tests: install.test.ts. Token purged; deletion scheduled at +30d retention
ST-053 | E1 | Install lifecycle | Re-install restores account within retention window | 3 | P1 | S2 | SCR-1 Onboarding | install.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — install.ts; tests: install.test.ts. Restore inside window; RETENTION_EXPIRED beyond it
ST-054 | E1 | Install lifecycle | Multi-user roles: owner/admin/member permission matrix enforced | 5 | P0 | S2 | SCR-1 Onboarding | roles.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — roles.ts; tests: roles.test.ts. Permission matrix enforced; forbidden actions throw
ST-055 | E1 | Install lifecycle | Session/token refresh survives platform token rotation | 3 | P0 | S1 | SCR-1 Onboarding | install.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — install.ts; tests: install.test.ts. rotateToken survives; uninstalled account rejected
ST-056 | E1 | Install lifecycle | Install telemetry: source attribution (listing/search/referral) captured | 2 | P1 | S1 | SCR-1 Onboarding | install.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — install.ts; tests: install.test.ts. listing/search/referral attribution report
ST-057 | E5 | Billing | 14-day trial without card; banner shows days remaining | 5 | P0 | S6 | SCR-7 Billing | billing.test.ts | Done-in-code | DONE-IN-CODE v029 16:38 — trial banner rendered in the UI with days remaining
ST-058 | E5 | Billing | Upgrade/downgrade mid-cycle prorates correctly | 5 | P0 | S6 | SCR-7 Billing | billing.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — billing.ts; tests: billing.test.ts. Mid-cycle proration incl. cycle-cap clamp
ST-059 | E5 | Billing | Marketplace billing API used where mandated; external Stripe fallback elsewhere | 8 | P0 | S6 | SCR-7 Billing | billing.test.ts + live E2E | Pending-live | Logic done v006 22:22 in billing.ts (billing.test.ts); live WhatsApp/Meta E2E outstanding. selectProvider(mandate) Done; Meta mandate verification outstanding (S0)
ST-060 | E5 | Billing | Failed payment: 7-day grace, 3 dunning emails, then read-only mode | 3 | P1 | S7 | SCR-7 Billing | billing.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — billing.ts; tests: billing.test.ts. 7-day grace, dunning emails day 0/3/6, then read-only
ST-061 | E5 | Billing | Plan limits enforced with upgrade prompts at 80%/100% | 3 | P1 | S7 | SCR-7 Billing | billing.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — billing.ts; tests: billing.test.ts. Prompts at 80% and 100% of plan limit
ST-062 | E5 | Billing | Invoices/receipts downloadable; GST/VAT fields supported | 3 | P2 | S7 | SCR-7 Billing | billing.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — billing.ts; tests: billing.test.ts. Invoice with GST/VAT id + rate validation
ST-063 | E5 | Billing | Cancellation flow with save-offer and exit survey | 3 | P1 | S7 | SCR-7 Billing | billing.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — billing.ts; tests: billing.test.ts. Save-offer (20%) and exit-survey-required paths
ST-064 | E6 | Compliance & security | Scopes requested map 1:1 to shipped features (least privilege doc) | 3 | P0 | S7 | SCR-6 Settings & team | compliance.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — compliance.ts; tests: compliance.test.ts. SCOPE_MAP 1:1; leastPrivilegeReport flags unmapped
ST-065 | E6 | Compliance & security | Data-flow diagram + retention policy published | 3 | P0 | S8 | SCR-6 Settings & team | compliance.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — compliance.ts + docs/DATA_FLOW.md; tests: compliance.test.ts. retentionPolicy() + published data-flow doc
ST-066 | E6 | Compliance & security | Encryption at rest + in transit verified; secrets in vault | 5 | P0 | S8 | SCR-6 Settings & team | compliance.test.ts + live E2E | Pending-live | Logic done v006 22:22 in compliance.ts (compliance.test.ts); live WhatsApp/Meta E2E outstanding. verifySecurityConfig Done; live infra verification outstanding
ST-067 | E6 | Compliance & security | Audit log for admin-sensitive actions | 5 | P1 | S8 | SCR-6 Settings & team | roles.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — roles.ts; tests: roles.test.ts. AuditLog records admin-sensitive actions
ST-068 | E6 | Compliance & security | Pen-test (or platform-required evidence) completed and archived | 8 | P0 | S9 | SCR-6 Settings & team | Vendor pen-test | In progress | IN PROGRESS v010 12:51 — docs/SECURITY_EVIDENCE.md sandbox half; F-005 flagged to vendor; npm audit clean at build
ST-069 | E6 | Compliance & security | Data export + delete-my-data self-serve | 5 | P0 | S9 | SCR-6 Settings & team | compliance.test.ts | Done-in-code | DONE-IN-CODE v029 16:38 — self-serve at last: export and delete in the workspace with confirmation; API-only was not self-serve
ST-070 | E6 | Compliance & security | Rate-limit backoff + circuit breaker on platform APIs | 5 | P0 | S8 | SCR-6 Settings & team | resilience.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — resilience.ts; tests: resilience.test.ts. Exponential backoff + circuit breaker open/half-open/reset
ST-071 | E7 | Telemetry | Activation funnel events (install->setup->aha->habit) in one dashboard | 5 | P0 | S4 | SCR-8 Analytics | analyticsGuard.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — analyticsGuard.ts; tests: analyticsGuard.test.ts. install->setup->aha->habit funnel counts
ST-072 | E7 | Telemetry | Error tracking with release tagging; alert on error-rate spike | 3 | P0 | S4 | SCR-8 Analytics | telemetry.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — telemetry.ts; tests: telemetry.test.ts. ErrorTracker release tags + window spike alert
ST-073 | E7 | Telemetry | Feature-usage heatmap for roadmap decisions | 3 | P2 | S8 | SCR-8 Analytics | analyticsGuard.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — analyticsGuard.ts; tests: analyticsGuard.test.ts. Feature-usage heatmap sorted by count
ST-074 | E7 | Telemetry | Weekly automated metrics email to team | 2 | P2 | S8 | SCR-8 Analytics | telemetry.test.ts | Done-in-code | DONE-IN-CODE v037 19:11 — /admin/metrics/weekly serves the email body for a scheduler; uncallable from v006 until now
ST-075 | E7 | Telemetry | Health score computed per account (usage+billing+support) | 5 | P1 | S8 | SCR-8 Analytics | analyticsGuard.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — analyticsGuard.ts; tests: analyticsGuard.test.ts. healthScore usage+billing+support, clamped
ST-076 | E7 | Telemetry | Metrics export to CSV/warehouse for founder analysis | 3 | P2 | S8 | SCR-8 Analytics | analyticsGuard.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — analyticsGuard.ts; tests: analyticsGuard.test.ts. exportCsv funnel export
ST-077 | E7 | Telemetry | Alert thresholds configurable (activation drop, error spike, churn signal) | 3 | P2 | S8 | SCR-8 Analytics | analyticsGuard.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — analyticsGuard.ts; tests: analyticsGuard.test.ts. configure() thresholds with validation
ST-078 | E8 | Onboarding/docs/support | First-run checklist reaches aha-moment in <1 day | 5 | P0 | S5 | SCR-1 / SCR-9 Help | onboarding.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — onboarding.ts; tests: onboarding.test.ts. Checklist; aha on connect+first-reply; <1 day check
ST-079 | E8 | Onboarding/docs/support | Empty states teach next action on every screen | 3 | P1 | S5 | SCR-1 / SCR-9 Help | onboarding.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — onboarding.ts; tests: onboarding.test.ts. EMPTY_STATES registry per screen
ST-080 | E8 | helpSearch.ts + docs/help | Help center with 15 launch articles + search | 5 | P1 | S10 | SCR-1 / SCR-9 Help | completion.test.ts | Done-in-code | DONE-IN-CODE v011 09:55 — helpSearch.ts ranked search + drift gate vs published headings
ST-081 | E8 | supportChat.ts | In-app chat with <4 business-hr first response | 3 | P0 | S10 | SCR-1 / SCR-9 Help | completion.test.ts | Done-in-code | DONE-IN-CODE v011 09:55 — supportChat.ts built-in chat + 4-business-hour SLA (business-hours calc excludes nights/weekends); chat vendor now optional (D-E4)
ST-082 | E8 | Onboarding/docs/support | In-app review ask after aha-moment (marketplace rating engine) | 3 | P1 | S11 | SCR-1 / SCR-9 Help | onboarding.test.ts | Done-in-code | DONE-IN-CODE v038 19:31 — onboarding completion made real, so aha is reachable and the ask fires once after it
ST-083 | E8 | Onboarding/docs/support | Demo video (2 min) + interactive sandbox/demo data mode | 5 | P1 | S10 | SCR-1 / SCR-9 Help | Review + publish | Drafted | DONE-IN-CODE v024 11:54 — demo mode reachable via ENGAGEOS_DEMO=1 through /app/*; video production still pending
ST-084 | E8 | Onboarding/docs/support | Status page + incident comms template | 2 | P2 | S10 | SCR-1 / SCR-9 Help | Review + publish | Drafted | DRAFTED v036 18:59 — comms publish through /admin/incidents to the public status page with cadence enforcement; external vendor now optional
ST-085 | EQ | Quality engineering | Unit+integration test coverage gate ≥70% on core modules | 5 | P0 | S3 | Cross-cutting | jest.config.js coverageThreshold (all 35 suites) | Done-in-code | DONE-IN-CODE v006 22:22 — jest.config.js; tests: all 16 suites. Superseded by D13: 100% gate (coverageThreshold) > 70%
ST-086 | EQ | Quality engineering | E2E smoke suite runs on every deploy | 5 | P0 | S4 | Cross-cutting | smoke.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — tests/smoke.test.ts + ci.yml; tests: smoke.test.ts. E2E MVP loop; CI runs on push/PR/deploy
ST-087 | EQ | Quality engineering | p95 latency budgets defined and monitored per surface | 3 | P0 | S8 | Cross-cutting | latency.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — latency.ts; tests: latency.test.ts. Budgets api/ui/webhook; p95 check within/breached
ST-088 | EQ | ops/loadtest.k6.js + scripts/make-fixtures.ts | Load test at 5x expected launch traffic | 5 | P1 | S8 | Cross-cutting | fixtures.test.ts + live staging | Pending-live | CODE-COMPLETE v012 10:23 — k6 posts genuine signed webhook envelopes at the real route; live run pending
ST-089 | EQ | views.ts (screen shells) | Accessibility WCAG AA pass on primary flows | 3 | P1 | S9 | Cross-cutting | views.a11y.test.ts | Done-in-code | DONE-IN-CODE v024 11:54 — shells SERVED at /app/* and axe-clean as served (F-022); styled-UI audit remains a launch check
ST-090 | EQ | db/migrations/ + scripts/migrate.sh | Backup + restore drill executed | 3 | P1 | S9 | Cross-cutting | docsDrift.test.ts + live drill | Pending-live | CODE-COMPLETE v012 10:23 — db/migrations 001-004 with cascade deletes + npm run migrate behind the drill
ST-091 | EQ | Quality engineering | Chaos test: platform API outage degrades gracefully with user comms | 3 | P2 | S9 | Cross-cutting | resilience.test.ts + broadcast.test.ts + inbox.test.ts | Done-in-code | DONE-IN-CODE v006 22:22 — resilience.ts + waAdapter.ts; tests: resilience/broadcast/inbox suites. Outage injection degrades gracefully with clear errors
ST-092 | EQ | deploy.yml + src/http/app.ts | Zero-downtime deploy verified (blue/green or rolling) | 3 | P2 | S8 | Cross-cutting | http.test.ts + live switch | Pending-live | CODE-COMPLETE v012 10:23 — deploy health-check now curls a real /healthz route
ST-093 | EL | Listing & launch | Marketplace listing copy A + B variants drafted and reviewed | 3 | P0 | S9 | Marketplace listing (external) | Review + publish | Drafted | DRAFTED v007 22:55 — docs/listing/LISTING_COPY_A_B.md. A (outcome-led) + B (pain-led) drafted; Senthil review pending
ST-094 | EL | Listing & launch | 5 screenshots + 2-min demo video meet platform asset specs | 5 | P0 | S9 | Marketplace listing (external) | Review + produce | Drafted | DRAFTED v030 16:42 — styled; only the capture session and video production remain
ST-095 | EL | pricingPage.ts | Pricing page/plan matrix published with FAQ | 3 | P0 | S10 | Marketplace listing (external) | completion.test.ts | Done-in-code | DONE-IN-CODE v011 09:55 — pricingPage.ts generated from billing PLANS + drift test
ST-096 | EL | Listing & launch | Security/trust page (data handling, subprocessors) live | 3 | P0 | S10 | Marketplace listing (external) | Review + publish | Drafted | DRAFTED v007 22:55 — docs/listing/TRUST_SECURITY.md. Trust page drafted from compliance.ts facts; subprocessor list at GA
ST-097 | EL | Listing & launch | Submission dry-run against platform checklist by second reviewer | 3 | P0 | S10 | Marketplace listing (external) | Second-reviewer pass | In progress | IN PROGRESS v007 22:55 — product workbook v007 Launch_Checklist re-statused as the self dry-run record; second-reviewer pass pending
ST-098 | EL | Listing & launch | Launch-day runbook: monitoring, rollback, comms tree | 3 | P1 | S11 | Marketplace listing (external) | Review + publish | Drafted | DRAFTED v035 18:50 — runbook rewritten around real controls (flags, monitor, status); launch-day execution remains his
ST-099 | EL | seo.ts | Post-launch listing SEO iteration 1 from search-term data | 2 | P2 | S12 | Marketplace listing (external) | completion.test.ts + live data | Pending-live | CODE-COMPLETE v039 19:40 — POST /admin/seo/iterate reachable; live half needs post-listing search data
ST-100 | EL | partners.ts | First 10 design-partner reviews scheduled | 2 | P1 | S11 | Marketplace listing (external) | completion.test.ts + outreach | Pending-live | CODE-COMPLETE v039 19:40 — /admin/partners reachable with honest gate maths; outreach his

## Sprint_Status_Rollup
SPRINT STATUS ROLLUP — live formulas over Traceability_Matrix
Do not edit computed cells. 'Done' counts Done-in-code + Done. Exit criteria from product workbook Sprint_Board.
Sprint | Focus | Stories | Points | Done | Done points | % points done | RAG (manual) | Exit criteria
S1 | Foundation (2 wks) | 4 | 13 | 3 | 8 | 61.54% | AMBER — 3/4 done-in-code; live install is the exit criterion and pending Meta access | App installs cleanly in dev store/org; telemetry firing
S2 | Team inbox pt 1 | 6 | 29 | 6 | 29 | 100% | GREEN — 6/6 done-in-code | Inbox happy path demoable
S3 | Inbox pt 2 + Broadcasts start | 11 | 47 | 10 | 42 | 89.36% | GREEN — 10/11; ST-005 pending-live | Inbox complete with tests; Broadcasts skeleton
S4 | Broadcast campaigns + segments | 9 | 34 | 8 | 29 | 85.29% | GREEN — 8/9; ST-015 pending-live | MVP loop usable end-to-end internally
S5 | Chatbot flows + alpha hardening | 12 | 50 | 11 | 45 | 90% | GREEN — 11/12; ST-025 pending-live; alpha-dogfood exit needs live org | Internal alpha: team dogfoods daily
S6 | Billing + Catalog/payment links | 13 | 60 | 11 | 47 | 78.33% | AMBER — 11/13; billing-mandate check (ST-059) needs verified Meta terms | Can charge a test customer; up/downgrade paths work
S7 | Private beta (design partners) | 5 | 15 | 5 | 15 | 100% | AMBER — code done; beta partners themselves external | 3+ partners active weekly; NPS pulse >30
S8 | Beta iteration + Analytics/guard | 22 | 87 | 18 | 69 | 79.31% | AMBER — 18/22; load test + deploy drill need live infra | Beta cohort WoW retention >60%
S9 | Marketplace review prep | 7 | 30 | 3 | 11 | 36.67% | AMBER — drafts done; pen-test + screenshots external | Review submission accepted into queue
S10 | Review remediation + docs | 7 | 24 | 3 | 11 | 45.83% | AMBER — content drafted; approval cycle external | Marketplace approval obtained
S11 | Launch | 3 | 8 | 1 | 3 | 37.5% | RED — launch gated on everything above | First 10 installs; first 3 reviews; activation >40%
S12 | Iterate & scale decision | 1 | 2 | 0 | 0 | 0% | RED — post-launch only | Growth model doc with CAC/LTV first estimates
TOTAL | (S1-S12) | 100 | 399 | 79 | 309 | 77.44%

## RAID_Carryover
RAID — seeded from product workbook Risk_Register + build findings
ID | Type | Raised | Item | Status | Notes / Mitigation
R-E1 | Risk | v005 | WhatsApp quality-rating drop throttles number (High/Medium) | Mitigated-in-code | Quality-guard live: red status => throttle-broadcasts action (analyticsGuard.ts); opt-in hygiene enforced (optIn.ts marketing gate). Live rating monitoring still owed (LC-3).
R-E2 | Risk | v005 | Meta pricing change squeezes campaign ROI for SMEs (Medium/Medium) | Open | Conversation fees pass-through at cost (pricing page states it); multi-channel fallback (SMS/email) stays roadmap.
R-E3 | Risk | v005 | BSP dependency terms/latency (Medium/Medium) | Open | Cloud API direct path is the built assumption; dual-BSP abstraction possible behind WaApi adapter (one-module swap).
R-E4 | Constraint | 22:22 | Sandbox has no Meta credentials/Postgres — platform behind WaApi adapter w/ FakeWaApi; persistence in-memory | Open | D-E1: real HTTP client + Postgres at live wiring; domain code untouched. TeleField D16 precedent.
R-E5 | Risk | 22:55 | Webhook payload/signature format assumed generic (wamid dedupe) pending Cloud API docs verification at live wiring | Open | Verification isolated in webhookGuard.ts + adapter; format change is one-module.
R-E6 | Risk | 22:55 | Meta may mandate specific billing rails for WABA-linked SaaS (ST-059 fallback logic built both ways) | Open | selectProvider() covers both; verify terms during LC-1 (was an S0 item, S0 parked under D13).
A-E1 | Assumption | 22:22 | D13 applies to EngageOS: discovery parked, 100% coverage; S0 activities (PRD sign-off, terms verify, wireframes) remain owed and NOT marked done | Open | Per 20:45/22:22 directives.
A-E2 | Assumption | 22:22 | D15 mode pending — EngageOS one of multiple concurrent builds; serial rule formally intact until ratified | Open | Senthil to ratify; consolidated in 23:03 portfolio action board.

## Gate_Checklist
COMPLETION GATE (D7) — EngageOS is DONE only when every row is Done
R2: code complete counts for nothing. Gate decision = Senthil. LC items = product workbook Launch_Checklist (v007 statuses).
ID | Gate item | Source | Status
G-01 | App LISTED on WhatsApp/Meta ecosystem (approved + published) | D7 / R2 | Open
G-02 | 10 PAYING installs from strangers | D7 / R2 | Open
G-03 | S12 kill criteria evaluated with evidence pack | D7 / R3 | Open
G-04 | Kill/continue decision recorded by Senthil | R5 / D10 | Open
G-05 | On CONTINUE: next-rank build authorised; EngageOS enters ops floor | N4 / R1 | Open
LC-1 | Meta Business verification + WhatsApp Business Account (WABA) production access | workbook LC #1 | Open
LC-2 | BSP agreement signed (360dialog/Gupshup class) OR Cloud API direct path chosen | workbook LC #2 | Open
LC-3 | Display name approved; phone number quality rating monitoring in place | workbook LC #3 | Open
LC-4 | Message template library (20+ approved across utility/marketing categories) | workbook LC #4 | Drafted — 20 templates in docs/templates/MESSAGE_TEMPLATES.md; Meta approval pending
LC-5 | Opt-in capture flows compliant (checkbox + proof storage) | workbook LC #5 | Done in code — OptInRegistry proof storage + marketing gate; live flow QA pending
LC-6 | Conversation-pricing pass-through billing tested (Meta invoice reconciliation) | workbook LC #6 | Open
LC-7 | 24-hour session logic + template fallback tested | workbook LC #7 | Done in code — SessionWindow 24h logic + template fallback tested; live test pending
LC-8 | Webhook resilience: retry + dedupe at 50 msg/s burst | workbook LC #8 | Done in code — WebhookGuard dedupe + queue, 50/s burst shape tested; live burst pending
LC-9 | Data retention + DPDP(India)/GDPR policy live | workbook LC #9 | Drafted — trust page + DATA_FLOW.md retention; DPDP/GDPR legal review pending
LC-10 | Vernacular UI pack (Hindi/Tamil) QA complete | workbook LC #10 | Drafted — hi/ta string packs in i18n/; native-speaker QA pending

## Review_Findings
REVIEW FINDINGS — adversarial cold-review pass 1 (11 Sep 08:17). Dispositions = Senthil (R5-class).
ID | Severity | Finding | Evidence | Disposition | Status
F-001 | Major | inbox.receive() before setupDefaults() assigned conversations to undefined (NaN round-robin index) and notified nobody | src/inbox.ts pre-fix; repro test now in inbox.test.ts | FIXED — INBOX_NOT_CONFIGURED thrown; regression test added | Closed (fixed v0.9.0)
F-002 | Major | Chatbot question node with options stripped via updateNode crashed with raw TypeError instead of a clean builder error | src/chatbot.ts pre-fix; repro test in chatbot.test.ts | FIXED — INVALID_NODE_NO_OPTIONS:<id>; regression test added | Closed (fixed v0.9.0)
F-003 | Major | WebhookGuard dedupe ledger grew unbounded — memory leak certainty in a long-running live process | src/webhookGuard.ts pre-fix | FIXED — FIFO cap at 20x queue size; eviction + recent-dedupe both asserted | Closed (fixed v0.9.0)
F-004 | Minor | CloudApiAdapter hardcoded template language "en" — the 8 marketing + hi/ta templates would have been unusable at live | src/cloudApiAdapter.ts pre-fix | FIXED — templateLang parameter, default en; hi asserted | Closed (fixed v0.9.0)
F-005 | Minor | Duplicate install() while an account is ACTIVE silently replaces token + attribution source (session-fixation-adjacent; also skews ST-056 attribution) | src/install.ts install() overwrite branch (covered by test "duplicate install while active overwrites cleanly") | LOG — acceptable for sandbox; at live wiring require explicit re-auth confirmation or preserve original source. Senthil to ratify | Open
F-006 | Obs | catalog paymentLink hardcodes payee name pn=EngageOS — merchants will want their own trading name on the UPI sheet | src/catalog.ts | LOG — add merchantName to CatalogService config at live wiring | Open
F-007 | Obs | billing.dunningTick emails depend on tick cadence: if no tick runs between day 3-6, only 2 of 3 emails ever send (grace/read-only unaffected) | billing.test.ts dunning sequence | LOG — live scheduler must tick daily; acceptable as designed | Open
F-008 | Obs | liveSweep step 1 (config valid) is trivially true after loadConfig succeeds — it evidences wiring, not validation | src/liveSweep.ts | LOG — keep: step exists to print phoneNumberId into the evidence record | Open
F-009 | Blocker | optIn.ts existed since v007 but NO send path ever called it — marketing broadcasts could reach contacts with no consent proof (platform violation + the exact risk the module was built to stop) | src/broadcast.ts pre-fix; new regression asserts skipped[] with NO_OPT_IN | FIXED — OptInRegistry is now a required BroadcastService collaborator; campaigns carry a category; non-consented targets recorded as skipped, never silently sent | Closed (fixed v0.11.0)
F-010 | Blocker | sessionWindow.ts likewise never wired — free-form sends outside the 24-hour window would have been rejected by Meta in production; inbox replies had the same hole | src/broadcast.ts + src/inbox.ts pre-fix | FIXED — inbound recorded on receive; reply/send consult the window and use an approved template outside it; out-of-window targets with no template recorded as NO_SESSION_WINDOW rather than aborting the campaign | Closed (fixed v0.11.0)
F-011 | Major | read-only and cancelled billing states were set but enforced nowhere — a non-paying account kept full write access | src/billing.ts pre-fix | FIXED — writeBlocked/assertWritable gate; reads stay open so customers can always export | Closed (fixed v0.11.0)
F-012 | Major | No payment-recovery path: an account in grace or read-only could never return to active even after paying | src/billing.ts pre-fix | FIXED — paymentSucceeded() clears grace, resets dunning, restarts the cycle | Closed (fixed v0.11.0)
F-013 | Major | Trial expiry never enforced — trialEndsAt passed and the account stayed on free trial indefinitely | src/billing.ts pre-fix | FIXED — enforceTrialExpiry() moves an unpaid expired trial to read-only | Closed (fixed v0.11.0)
F-014 | Major | requestDeletion only flagged an account; nothing ever deleted it, so the published 30-day purge was a promise with no mechanism | src/compliance.ts pre-fix | FIXED — runPurge() executes hooks past the purge date, marks purged, is idempotent | Closed (fixed v0.11.0)
F-015 | Major | Both CSV importers used naive split() — any quoted field containing a comma (product names, message text) was corrupted silently | src/inbox.ts + src/catalog.ts pre-fix | FIXED — shared RFC-4180 csv.ts (quotes, escaped quotes, per-row errors) + quoted output helper | Closed (fixed v0.11.0)
F-016 | Minor | Notification, error and funnel ledgers all grew unbounded (same class as F-003, missed on the other three) | src/notify.ts, telemetry.ts, analyticsGuard.ts pre-fix | FIXED — shared FIFO Ledger<T> with drop telemetry | Closed (fixed v0.11.0)
L-E1 | Lesson | 100% coverage proved every LINE of optIn.ts and sessionWindow.ts executed — in their own unit tests. Nothing asserted that production code CALLS them. Coverage measures execution, not integration. | F-009/F-010 root cause | ADOPTED — integration assertions added at the send paths; applies portfolio-wide | Closed
GAP-E1 | Blocker | NO HTTP APPLICATION existed. The setup guide tells Meta to register a /webhook callback, deploy.yml curls /healthz, the k6 harness posts to /webhook — none of those routes, and no server entry or npm start, existed anywhere in the repo | Repo audit: src/ held 30 domain modules and zero transport | FIXED — framework-free Router (async-safe by design: a throwing handler answers 500, it never hangs the connection) + app with 6 routes + Node server entry + npm start | Closed (fixed v0.12.0)
GAP-E2 | Blocker | NO DATABASE SCHEMA existed behind the backup/restore drill, the retention purge (F-014) or any persistence claim; every store was in-memory | ops/BACKUP_RESTORE_DRILL.md referenced tables that were never defined | FIXED — 4 ordered migrations (accounts, contacts, conversations, campaigns, opt_ins, session_windows, webhook_events, catalog_items, subscriptions, invoices, audit_log, support_tickets, funnel_events) with ON DELETE CASCADE so one account delete purges every child row + npm run migrate | Closed (fixed v0.12.0)
GAP-E3 | Blocker | X-Hub-Signature-256 was never verified. The endpoint the guide tells you to publish would have accepted forged inbound messages from anyone who learned the URL | No signature code anywhere in the build | FIXED — HMAC-SHA256 verification with timing-safe compare; unsigned/tampered/wrong-secret requests 401 before any processing | Closed (fixed v0.12.0)
GAP-E4 | Blocker | The GET hub.challenge handshake was missing, so Meta could not save the callback URL at all — webhookVerifyToken was loaded by config.ts and used by nothing | src/config.ts loaded the token; grep found zero readers | FIXED — GET /webhook validates mode + token and echoes the challenge | Closed (fixed v0.12.0)
GAP-E5 | Major | k6 posted an ad-hoc unsigned body — against the real app every request would have 401d and the load test would have measured the rejection path | ops/loadtest.k6.js pre-fix | FIXED — signed fixture generator (npm run loadtest:fixtures) + harness reads real WhatsApp envelopes with valid signatures | Closed (fixed v0.12.0)
GAP-E6 | Minor | PRICING_FAQ.md was hand-written and ungated against billing PLANS — free to drift from what the code charges | docs/listing/PRICING_FAQ.md | FIXED — drift test asserts every plan name, price and limit appears in the published FAQ | Closed (fixed v0.12.0)
L-E2 | Lesson | Coverage over modules proves the modules work, not that a product exists. 30 modules at 100% and no way to receive a single message. | GAP-E1/E2 root cause | ADOPTED — artifact-gap audit (does every referenced command, route and file exist?) added to the close-out routine portfolio-wide | Closed
F-017 | Blocker | NO MULTI-TENANCY in the v012 app: a single WebhookGuard and a single SessionWindow served every WABA account. Tenants shared one dedupe ledger (account B's retry of the same wamid could suppress account A's genuine message), one tenant's 50-message burst could evict another's queued events, and any inbound opened the 24-hour free-form window for ALL tenants — a compliance hole, not just a data-isolation one | src/http/app.ts v012 AppDeps held guard + session directly | FIXED — TenantRegistry with per-tenant guard and session; tenant resolved from metadata.phone_number_id on every webhook; isolation pinned by a regression asserting the same wamid and phone across two tenants stay separate | Closed (fixed v0.13.0)
F-018 | Blocker | A correctly signed payload for a phone_number_id we do not serve was processed and queued. Signature proves Meta sent it, not that the app is installed for that number — an installed-elsewhere account could have been ingested | src/http/app.ts v012 POST /webhook | FIXED — unregistered ids rejected 404 and logged as WEBHOOK_UNKNOWN_TENANT; registration only happens through the OAuth callback, never lazily | Closed (fixed v0.13.0)
F-019 | Major | /healthz and /status were unauthenticated and returned release version, queue depth and error counts — free reconnaissance for anyone who found the host | src/http/app.ts v012 | FIXED — public routes are liveness/degraded-only; release, tenant counts, queue depth and error counts moved behind ENGAGEOS_OPERATOR_TOKEN on /admin/health and the detailed /status view | Closed (fixed v0.13.0)
F-020 | Major | Embedded signup had no CSRF protection — a callback accepting any code lets an attacker complete an install against another user's session (OnCall F-015 / MeetSync M-F15 class) | No OAuth route existed in v012; adding one without state would have repeated the sibling defect | FIXED — OAuthStates issues single-use states with 10-minute expiry, swept on demand; callback validates state, code and account ids before installing and registering the tenant | Closed (fixed v0.13.0)
L-E3 | Lesson | New surfaces inherit old blind spots. The HTTP layer built in v012 reproduced defect classes already found and fixed elsewhere in this same codebase (isolation, auth, replay). Any newly built surface gets its own review pass before it is called done. | F-017..F-020 root cause | ADOPTED — review pass is now part of building a new surface, not a later sitting | Closed
VER-E5 | Blocker | BATCHED WEBHOOK DATA LOSS: entry[], changes[] and messages[] are all arrays and one Meta POST can carry several messages for several phone numbers. The handler read entry[0].changes[0].messages[0] — every message after the first was silently dropped and acked 200, so Meta never retried. Our own fixtures carried a single message, so no test could ever have caught it | Verified against WhatsApp webhook documentation and integration guidance (13 Sep 2026), which names first-element-only parsing as the most common mistake | FIXED — all entries/changes/messages iterated; per-message outcomes returned; a mixed batch keeps the messages we serve and 404s only when none belong to a registered tenant (a whole-batch 404 would have made Meta redeliver messages we had already queued) | Closed (fixed v0.14.0)
VER-E1 | Major | COMMERCIAL MODEL BUILT ON A DEPRECATED UNIT: plans were metered in "conversations/mo" and the pricing page promised to pass through "Meta conversation fees". Meta replaced conversation-based pricing with per-message pricing on 1 July 2025; the old 1,000-free-conversations allowance no longer exists. Billing is now per delivered template message, priced by category and recipient country | Meta pricing documentation (conversation-based pricing marked deprecated) verified 13 Sep 2026 | FIXED IN CODE — plan allowance documented and rendered as delivered template messages; new messageCost.ts encodes the free-vs-billable rules (service messages free; utility templates free inside the 24h window; everything free inside a 72h free-entry-point window) with the rate card as configuration. COMMERCIAL DECISION STILL SENTHIL'S: whether 1,000/5,000/20,000 template messages are the right allowances at $29/$49/$99 given per-message rates vary ~13x by market | Code closed; pricing decision OPEN
VER-E2 | Minor | Only two template categories were modelled (utility, marketing). Meta prices three — marketing, utility and authentication — and authentication has its own international rate in some markets | Meta pricing documentation, 13 Sep 2026 | FIXED — authentication added to the Category union and to the opt-in gate (only marketing requires consent proof) | Closed (fixed v0.14.0)
VER-E3 | Major | The 72-hour FREE ENTRY POINT window was unmodelled: a customer arriving via a Click-to-WhatsApp ad or Page CTA can be messaged freely — templates included, at no charge — for 72 hours. The build applied the 24-hour rule to them, so those conversations were wrongly template-gated and wrongly treated as billable | Meta pricing/window documentation, 13 Sep 2026 | FIXED — recordFreeEntryPoint() opens a distinct 72-hour window that keeps free-form sending open and marks traffic non-billable in the cost model | Closed (fixed v0.14.0)
VER-E4 | Obs | Webhook acknowledgement deadline: sources cite 3-5 seconds before Meta marks delivery failed and retries with backoff for hours to days, producing duplicate deliveries | Verified 13 Sep 2026 | VERIFIED CORRECT-BY-DESIGN — the handler enqueues in memory and acks; no network or DB work on the request path. Pinned as a constraint in the setup guide so it is not regressed when persistence lands | Closed — no change needed
VER-E6 | Minor | Cloud API base outbound throughput is 80 messages/second (raisable on request); broadcasts sent as fast as the loop ran, so a large campaign would have hit platform throttling with no backpressure of our own | Meta Cloud API rate-limit documentation, 13 Sep 2026 | FIXED — ThroughputLimiter (default 80 mps) returns the wait time when the second's budget is spent | Closed (fixed v0.14.0)
L-E4 | Lesson | Three internal review passes at 100% coverage could not find VER-E5 or VER-E1, because both were cases of the code faithfully implementing a WRONG MODEL of the platform. Internal review checks the code against our assumptions; only external verification checks our assumptions against the platform. | VER-E5/VER-E1 root cause | ADOPTED — an external verification sweep against live platform docs is now a required step before any live run, portfolio-wide | Closed
VER-E7 | Blocker | NO MESSAGING-LIMIT AWARENESS: broadcasts iterated the whole segment. Meta caps how many UNIQUE customers a business may start a conversation with per rolling 24 hours — 250 for a new unverified portfolio, then 1,000 / 10,000 / 100,000 / unlimited — and since Oct 2025 the cap is PORTFOLIO-WIDE across every number, so extra numbers buy no extra reach. A 5,000-contact campaign on a young account would have been largely rejected, and the failures would have damaged the quality rating that gates the next tier | Meta messaging-limits documentation verified 13 Sep 2026 | FIXED — MessagingTierLimiter meters unique business-initiated recipients in a rolling 24h window at portfolio level; over-cap targets skip with TIER_LIMIT_REACHED rather than failing at the platform; upgradeReadiness() reports exactly what is missing (quality vs 50%-of-cap volume) | Closed (fixed v0.15.0)
VER-E8 | Obs | Whether replies inside the 24-hour customer-service window count toward the tier cap — if they did, an active support inbox would exhaust the limit | Meta documentation: limits apply to business-initiated messages outside the service window | VERIFIED AND IMPLEMENTED — the limiter is consulted only when the recipient is outside the service window, so inbox replies never consume tier capacity | Closed — verified correct
VER-E9 | Major | US MARKETING FREEZE unguarded: Meta has paused delivery of marketing-category templates to US (+1) numbers since April 2025 with no announced end date. Campaigns would have spent money and quality rating on messages that are not delivered. Also exposed that the built-in test-send placeholder was itself a US number, so a marketing preview would have been blocked by this rule | Meta policy verified 13 Sep 2026 | FIXED — blockedByPolicy() skips US marketing targets as US_MARKETING_PAUSED (utility and authentication still allowed); test-send number is now configurable and no longer a US placeholder | Closed (fixed v0.15.0)
VER-E10 | Major | Error 131049 (per-user marketing frequency cap — users receive roughly two marketing messages a day across ALL brands) was treated as a transient failure by the generic 3x retry. Meta guidance is to wait at least 24 hours; retrying can extend the block | Meta error-code guidance verified 13 Sep 2026 | FIXED — non-retryable codes (131049 and peers) get a single attempt; genuinely transient errors keep the full retry path | Closed (fixed v0.15.0)
VER-E11 | Blocker | CAMPAIGN METRICS OVERSTATED DELIVERY: a contact was counted as delivered the moment the Cloud API accepted the send. Acceptance only means the platform took the request; Meta reports the real outcome asynchronously through status webhooks (sent, delivered, read, or failed with a code), and the app discarded the statuses array entirely. A campaign blocked at every recipient could have reported a 100% delivery rate to the customer | Meta message-status webhook documentation verified 13 Sep 2026; app POST handler ignored value.statuses | FIXED — DeliveryLedger tracks accepted / in-flight / delivered / read / failed per campaign, ignores out-of-order regressions but lets failure win, and records error codes; metrics report acceptanceRate and confirmedDeliveryRate separately, and the broadcast view says plainly that accepted is not delivered | Closed (fixed v0.16.0)
VER-E12 | Major | INBOUND MEDIA LOST: WhatsApp media messages carry only a media_id and mime type — the binary must be fetched separately with an authenticated call and the URL is short-lived. Every message was treated as text, so a customer photo or PDF invoice would have shown as an empty conversation in the shared inbox | Meta media/webhook documentation verified 13 Sep 2026 | FIXED — parseInboundMedia() types the five media kinds with mime and filename, mediaPlaceholder() renders a readable stand-in ([Photo] caption, [Document: invoice.pdf]) so the agent sees the message while the binary fetch is deferred | Closed (fixed v0.16.0)
VER-E13 | Major | INTERACTIVE REPLIES UNREADABLE: a tap on a template button or list item arrives as interactive.button_reply.id or list_reply.id, never as the button text. The chatbot matched answers against typed text only, so on a live number every branch answer would have failed as INVALID_ANSWER — the no-code flows would have appeared broken from the first customer | Meta interactive-message documentation verified 13 Sep 2026 | FIXED — parseReply() resolves interactive, button and text messages to a single value (ids preserved, free text lowercased and trimmed) which is what the flow engine matches on | Closed (fixed v0.16.0)
GAP-E8 | Blocker | ALL CORRECTNESS STATE WAS PROCESS-LOCAL: webhook dedupe, the messaging-tier counter, session windows, OAuth states and the tenant registry each lived in a Map inside one Node process — while .github/workflows/deploy.yml performs a blue/green switch that runs two instances. Consequences on the day: the same Meta retry processed by both instances (a customer gets duplicate auto-replies), the 24-hour unique-recipient cap counted twice so sends go past Meta's limit and damage the quality rating, and free-form sends judged against a session window the other instance owns | Inventory of src/: 16 modules holding cross-request state in Maps; deploy.yml runs GREEN alongside BLUE | FIXED — SharedStore boundary; InMemoryStore (default) and PgStore whose atomicity is the database's (ON CONFLICT DO NOTHING for single-winner claims, xmax=0 to tell insert from update, window pruning in SQL, never read-then-write); ONE contract suite asserts identical behaviour from both, so swapping stores cannot change semantics. Single-instance operation documented as an invariant in the setup guide and guarded in deploy.yml until SHARED_STORE=pg | Closed in code; pg wiring is a live-infra step
GAP-E7 | Major | State added after the v012 schema had nothing behind it: delivery statuses (VER-E11), inbound media references (VER-E12) and the tenant registry (F-017) were all in memory with no tables, so the backup/restore drill would have restored a database that could not hold them | Audit of db/migrations against modules added in v013-v016 | FIXED — migration 005 (shared_claims / shared_windows / shared_timestamps) and 006 (message_statuses with a state CHECK, media_refs, tenants), all with cascade deletes so the F-014 purge still reaches them | Closed (fixed v0.17.0)
L-E5 | Lesson | The deploy workflow and the runtime made contradictory assumptions — one assumed two instances, the other assumed one — and nothing in a module-level test suite can notice a contradiction that lives BETWEEN artifacts. Audit the artifacts against each other, not just the code against its tests. | GAP-E8 root cause | ADOPTED — cross-artifact consistency (workflow vs runtime vs schema vs docs) added to the audit routine | Closed
F-021 | Major | The SharedStore boundary shipped in v017 was called by nothing — the guards it was built for kept using their process-local Maps. Identical to F-009/F-010 (optIn.ts and sessionWindow.ts unused for four versions): a boundary that exists but is not on the path buys nothing and reads as fixed in every document | Grep of v017 for SharedStore consumers: zero outside its own tests | FIXED — SharedWebhookGuard and SharedTierLimiter implemented over the store and wired into TenantRegistry and BroadcastService; regressions prove two instances sharing a store dedupe each other and share one tier budget | Closed (fixed v0.18.0)
OPEN-E1 | Obs | Session windows (24h service window, 72h free entry point) are still process-local. Cross-instance impact is smaller than dedupe or tier counting — a window recorded on instance A is unknown to B, so B would require a template where free-form was allowed, which is conservative and compliant but degrades experience | src/sessionWindow.ts | CLOSED v0.19.0 — session windows moved to SharedSessionWindow over the store; inbox.receive and importCsv became async and the ripple was carried through broadcast, tenancy, demo seed and every affected test in one pass, as the deferral intended. Two-instance regression proves a window opened on blue is seen by green. | Closed (fixed v0.19.0)
L-E6 | Lesson | We repeated our own defect class four versions after naming it. Building a boundary feels like the fix; only wiring it is the fix. Every new abstraction now ends with a grep for its callers before the release is written. | F-021 root cause | ADOPTED — "who calls this?" check added to the release routine | Closed
F-022 | Major | views.ts (behind ST-089, recorded Done-in-code) and demoData.ts (behind ST-083, recorded Done-in-code) were imported by nothing except their own tests. The product had accessible screens and a demo mode that no running process could ever show. Third occurrence of the class after F-009/F-010 and F-021, and the first where the unwired code sat behind stories the record already counted as complete | Reachability grep across src/ for importers of views.ts and demoData.ts: none | FIXED — /app/inbox, /app/broadcast, /app/catalog, /app/onboarding and /app/inbox/empty serve the shells with demo data, gated behind ENGAGEOS_DEMO (off by default so a demo workspace can never surface on a live tenant), axe-audited as served, exercised in the rehearsal script and pinned in the findings regression suite | Closed (fixed v0.23.0)
L-E7 | Lesson | "Done-in-code" has meant "the module exists and its tests pass" three times now when it should mean "the running product uses it". The findings regression suite already tests call sites for past findings; from now a story only counts as Done-in-code when something in the product path imports the module. | F-022 root cause | ADOPTED — reachability grep added to the release routine alongside the who-calls-this check from L-E6 | Closed
F-023 | Blocker | THE PRODUCT COULD NOT BE USED. The running app exposed webhooks, health, pricing, help, status and read-only demo screens — and no action route whatsoever, so nobody could reply to a conversation, reassign it, create or send a campaign, or add a catalog item. Compounding it, an inbound webhook was verified, deduped and pushed into an in-memory buffer that nothing drained, so a customer message never became a conversation: the core loop stopped at the front door while 79 stories read as Done-in-code | Route inventory of app.ts: every route a GET except POST /webhook; grep showed no consumer of the guard buffer | FIXED — WorkspaceRegistry assembles real per-tenant services; the webhook delivers deduped inbound into that tenant's inbox; action API (GET /api/inbox, POST reply, POST assign, POST /api/broadcast, POST send, POST /api/catalog, GET payment-link) behind the operator token, with domain errors answered as 400 and platform failures as 502; router gained path params; InboxService gained the reassignment it never had. Rehearsal proves the loop: signed webhook becomes conversation c1, assign succeeds, unauthenticated calls 401, and a reply reaches the real Cloud API and fails 502 on placeholder credentials | Closed (fixed v0.24.0)
OPEN-E2 | Obs | The action API authenticates with a single operator token rather than per-agent identity, so the roles.ts permission matrix (owner/admin/member) is not enforced at the HTTP boundary — it is enforced only where domain code calls guard() | src/http/app.ts authed() | CLOSED v0.26.0 — src/auth.ts issues HMAC-signed sessions; only the operator token can mint one, so a customer backend authenticates its own staff without this service owning passwords. The signed role and tenant govern: a member session presenting x-agent-role: owner is still refused campaign.send, which the rehearsal demonstrates. 12-hour expiry, tamper and forgery rejected by constant-time comparison, weak secrets refused at boot, audit records the verified agent. | Closed (fixed v0.26.0)
L-E8 | Lesson | Three reachability questions, three defects: is the module imported (F-021), is the screen served (F-022), can the product be operated (F-023). Each was invisible to a 100%-covered suite because tests call modules directly. The test suite proves the parts work; only the running product proves the product works. | F-023 root cause | ADOPTED — the rehearsal script now exercises the product loop, so this class fails a CI run rather than waiting for a reachability audit | Closed
F-024 | Blocker | NINE MODULES UNREACHABLE from the running product: analyticsGuard, compliance, roles, supportChat, partners, seo, latency, throughput (liveSweep is reached from the CLI, so a false positive). The worst is compliance: the trust page and retention policy PROMISE self-serve data export and delete-my-data, both implemented since v006 and callable by nothing — a published commitment with no way for a customer to exercise it | Module-by-module import sweep of src/ after F-023 | FIXED — workspace assembles analytics, data rights, support, billing, onboarding and an audit log; routes added for chatbot flows (create/run/metrics), opt-in capture and revoke, analytics and CSV export, billing trial/status/cancel, support open/respond/SLA, and GET /api/data/export + POST /api/data/delete | Closed (fixed v0.25.0)
F-025 | Major | The owner/admin/member matrix in roles.ts governed nothing at the API: any caller with the operator token could send campaigns, manage billing or delete data, and no mutating call was audited | roles.ts had no importer outside tests | FIXED — mutating routes declare an action; the matrix is checked and a 403 returned with the action named; every permitted call is written to the tenant audit log with actor, role and timestamp, readable at GET /api/audit. Identity is asserted by the trusted operator caller — narrowed OPEN-E2, not closed | Closed (fixed v0.25.0)
F-026 | Major | Both instrumentation modules were inert: the 80 msg/s throughput limiter built for VER-E6 was never consulted when sending, and the p95 budgets defined in v006 measured nothing | throughput.ts and latency.ts had no importers | FIXED — the limiter now gates every outbound send and the caller waits when the second is spent (pinned by a test asserting a real delay); the router times every request and reports p95 against the api budget | Closed (fixed v0.25.0)
F-027 | Major | THE PRODUCT WAS API-ONLY. The four screen shells wired in F-022 render state and nothing else — their buttons carry no handlers — so every action required a curl command with an operator token. An SME could not have used EngageOS, and a design partner could not have been shown anything they could touch | Route and handler inventory after F-024: /app/* render read-only HTML; all mutations live behind /api | FIXED — /web serves a working agent workspace: session token entry, conversation list, open-and-reply with the outcome reported honestly (including the platform refusal reason), broadcast compose and test send, catalog add returning the UPI link. Written as DOM functions the jsdom suite drives as an agent would; the served script is built by stringifying those same functions, so there is no untested copy and no bundler. Accessibility asserted on every rendered state; the page holds no tenant data, fetching everything with the agent's signed session | Closed (fixed v0.27.0)
L-E10 | Lesson | Every reachability finding so far asked whether code was called. F-027 asks the harder version: whether a HUMAN can reach the behaviour. Screens that render but do not act, and an API that works only from a terminal, both pass every reachability grep and still leave the product unusable. | F-027 root cause | ADOPTED — "could the intended user do this unaided?" added to the release routine | Closed
F-028 | Major | ST-069 and the published trust page promise SELF-SERVE data export and delete-my-data. After F-024 both existed as API endpoints gated by the operator token — reachable by the vendor, not by the customer. A published right with no customer-facing path is still an unkept promise, and the same applied to the ST-057 trial banner, which the story describes as a UI element and which existed only as a string an API returned | Story wording ("self-serve", "banner") read against the surfaces that actually existed | FIXED — export and delete buttons in the agent workspace, deletion behind an explicit confirmation with the 30-day window stated in plain words and a cancel path that is tested; trial banner rendered with days remaining; plus a health panel translating quality rating and messaging limit into sentences an SME can act on, and the first-run checklist | Closed (fixed v0.28.0)
L-E11 | Lesson | Story wording carries requirements that code review misses: "self-serve" names WHO must be able to act, and "banner" names WHERE it must appear. Reading acceptance wording literally against the shipped surfaces found two promises that every test and audit had passed over. | F-028 root cause | ADOPTED — acceptance wording is now read against surfaces, not only against behaviour | Closed
F-029 | Minor | The agent workspace shipped unstyled and the styling was repeatedly handed back as "a design job" — a boundary that did not hold up, since the work was within reach and was blocking the last asset story | Three consecutive releases named styling as the remaining ST-094 blocker while treating it as somebody else's | FIXED — design grounded in the subject (SME counter, paper ledger, daylight, one-handed Android use) rather than dashboard defaults: ink on cool ledger paper, one family on a 1.25 scale, colour used only to carry conversation status, and the queue as the single loud element with the customer number as the largest non-heading type. A brass accent was cut once status colours carried the signal. Contrast is enforced by test rather than claimed — it failed on first run against my own --closed grey and forced a correction. docs/DESIGN_NOTES.md records the palette, the audience and what was removed | Closed (fixed v0.29.0)
L-E12 | Lesson | "That needs a designer" was doing the same work as "that needs live credentials", except one was true and the other was not. Worth checking, when handing something back, whether it is genuinely outside reach or merely outside habit. | F-029 root cause | ADOPTED | Closed
F-030 | Major | The Hindi and Tamil string packs drafted in v007 were imported by nothing, while Variant A of the listing copy sells "Vernacular UI" and the product targets Indian SMEs. A Tamil-speaking shop owner — the core customer — would have opened an English-only screen, and the 30-day deletion promise would have been unreadable to the person it protects | Reachability sweep of i18n/: both packs present, zero importers; listing copy checked against the shipped UI | FIXED — src/web/i18n.ts carries all 47 strings in English, Hindi and Tamil; the workspace has a language control remembered per device; missing keys and unknown languages fall back to English rather than showing a raw key; the disk packs are generated from the module and a test fails if they drift; a second test fails if any language is missing a key or has an empty one | Closed (fixed v0.30.0)
OPEN-E3 | Obs | The Hindi and Tamil translations are machine-produced. They are consistent and complete, but tone and terminology in a commercial UI are exactly what a native speaker catches and a machine does not | src/web/i18n.ts | LOGGED — native-speaker review before launch, cheap and quick (47 strings). Also open: server-generated messages (platform errors, payment link text) stay English until the API carries a locale | Open — Senthil disposition
L-E13 | Lesson | The listing copy is a specification. "Vernacular UI" was a promise made to customers in a document nobody diffed against the product. Marketing claims deserve the same drift gate as pricing and help articles already have. | F-030 root cause | ADOPTED — listing claims checked against shipped surfaces at each release | Closed
F-031 | Blocker | "Answer at 2am with flows" — the flagship automation claim. The chatbot engine only ever ran when an agent called it through the API, so a customer messaging at 2am received nothing at all. The no-code flows were a toy, not an auto-responder | Grep for chatbot usage on the inbound path: none | FIXED — autoReply() fires on inbound delivery; a disabled flow or one opening with an end node stays silent rather than sending a broken template; runs are counted so the metrics mean something | Closed (fixed v0.31.0)
F-032 | Blocker | "Broadcasts that protect your quality rating" — nothing consulted the quality guard before sending. A red-rated number could have pushed a full segment and lost the number the whole business runs on, which is the exact failure the guard was built to prevent | Grep for the guard in the send path: absent | FIXED — a red rating refuses the campaign with the reason recorded; amber and green proceed, so the guard throttles rather than blocking the product | Closed (fixed v0.31.0)
F-033 | Major | The trust page states "retry with backoff + circuit breakers on all platform calls". Retry was wired; the breaker built in v006 had no importer, so during a WhatsApp outage every send burned its full retry budget against a dead endpoint | Reachability of CircuitBreaker: no consumers | FIXED — ProtectedWaApi fronts the adapter with one breaker PER TENANT, so a customer's outage cannot open the circuit for everyone else | Closed (fixed v0.31.0)
F-034 | Minor | The pricing page promises usage prompts at 80% and 100% of the plan limit. usagePrompt() existed and was called by nothing, so a customer would have hit their limit unwarned | Reachability of usagePrompt | FIXED — the prompt and the current usage travel with every billing response | Closed (fixed v0.31.0)
F-035 | Major | "Get paid in-chat via UPI" — paymentLink() returned the link to the AGENT. Getting paid in chat requires the link to reach the CUSTOMER, which nothing did | Route inventory: link returned in an API response only | FIXED — POST /api/inbox/:id/payment-link sends the item name, price and UPI link into the conversation, honours the session window and reports a platform refusal as 502 rather than claiming success | Closed (fixed v0.31.0)
L-E14 | Lesson | Four of these five were reachability failures in disguise — a module existed, tests passed, and nothing on the product path called it. The difference is that the claims audit found them by starting from what the CUSTOMER was promised rather than from what the code contains. Reading the marketing copy turned out to be a better bug-finding technique than reading the code. | F-031..F-035 root cause | ADOPTED — claims audit runs at each release, and each claim now has a test named after it | Closed
F-036 | Major | The 15 published help articles walk customers through tasks, and EIGHT of those tasks had no route and no control anywhere: CSV import of contacts and of chats, bulk close, assignment rules, pause-without-data-loss, catalog price edits, deactivation, chatbot node edits and notification muting. A customer following article 5 — the competitor-migration path they need on day one — would have hunted for an import that did not exist, while ST-009 and ST-019 both read Done-in-code because the library functions had tests | Grep of importCsv, bulkClose, mute, deactivate, updateItem, updateNode, addRule, setPaused against routes and UI: zero references for all eight | FIXED — a route for each, validated and permission-gated: contacts/import, inbox/import, inbox/bulk-close, inbox/rules, inbox/pause, catalog/:sku/price, catalog/:sku/deactivate, flows/:id/nodes, notifications/mute. Each article's task is pinned by a test named after the article, so an article describing something unbuilt fails the build | Closed (fixed v0.32.0)
L-E15 | Lesson | Documentation is the third specification, after the backlog and the listing copy — and the one written from the customer's point of view, which is why it found eight gaps the code-first sweeps missed. Anything written FOR the customer is worth diffing against the product: backlog, listing, pricing, trust page, help centre. | F-036 root cause | ADOPTED — all customer-facing documents are diffed against shipped surfaces at each release | Closed
F-037 | Blocker | TEMPLATES WOULD HAVE FAILED ON DAY ONE. Twelve of the twenty drafted templates carry variables — tracking number, appointment date, item and amount, discount percentage, course name — and CloudApiAdapter sent template name and language with no body components. Meta rejects a template send whose placeholders have no matching parameters, so order_shipped, appointment_confirm, payment_link, festive_sale and the rest would all have failed at the platform, surfacing as an error code rather than anything meaningful in our logs. Compounding it, there was no route to send a template into a conversation at all, which is the only legitimate way to reach a customer outside the 24-hour window | Diff of docs/templates/MESSAGE_TEMPLATES.md against the adapter payload | FIXED — src/templates.ts declares all 20 with their variables; the adapter ships components with ordered text parameters; templateParams() refuses a send with a missing or unexpected value and NAMES the variable, before the platform sees it; POST /api/inbox/:id/template added; GET /api/templates lists them. A drift test fails the build if the published library and the registry disagree in either direction | Closed (fixed v0.33.0)
L-E16 | Lesson | Artifacts drafted for a human to read — a template library written for Meta review — are also machine specifications. The library had been sitting in the repo since v007 being treated as copy, when it was actually an interface contract with the platform. | F-037 root cause | ADOPTED — drafted artifacts are diffed against the code that must honour them | Closed
F-038 | Major | THE INCIDENT RUNBOOK PRESCRIBED CONTROLS THAT DID NOT EXIST. Step one of the rollback ladder is "feature-flag broadcasts off first if quality score drops to amber" — there was no feature flag anywhere in the product, so an operator at 2am had nothing between noticing a problem and rolling back the entire deployment. The monitoring line says check the quality rating every two hours; nothing polled it, and the guard only ran mid-broadcast, which is after the damage is done | Diff of docs/launch/RUNBOOK.md against the product | FIXED — FeatureFlags with four per-capability switches (broadcast, chatbot, inbound, payment-links) so one capability can be contained without touching the rest; a disable REQUIRES a reason and records who and when; runQualityCheck() is callable by cron or by POST /admin/monitor/run and auto-disables broadcasts on a red rating with the reason logged, while re-enabling stays manual; /status now reports disabled capabilities publicly without leaking error counts. The runbook is rewritten around these controls | Closed (fixed v0.34.0)
L-E17 | Lesson | An operational document is a specification for the OPERATOR, and the least likely to be read against the code because nobody exercises it until the worst moment. The runbook had been in the repo since v007 describing a rollback ladder whose first rung did not exist. | F-038 root cause | ADOPTED — operational docs are diffed like customer-facing ones | Closed
F-039 | Major | The incident comms document holds three written customer messages and a severity ladder with update cadences, and there was NOWHERE TO PUBLISH ANY OF IT. During an outage the customer would have seen degraded:true while the carefully worded "we are investigating, your inbox and data are unaffected" sat unread in a markdown file — and the cadence promise (Sev-1 every 15 minutes) depended entirely on a stressed human remembering it at 2am | Diff of docs/launch/INCIDENT_COMMS.md against the product: no incident surface existed | FIXED — IncidentLog opens, updates and resolves with the full trail kept; the public /status carries the latest message and still no error counts; the operator view lists every incident overdue for its next update with minutes late, so the cadence is enforced rather than remembered; an update with no words is refused because a status entry saying nothing is worse than none. An external status-page vendor becomes optional rather than a launch dependency | Closed (fixed v0.35.0)
L-E18 | Lesson | Seven documents have now been diffed against this product — backlog, listing copy, pricing page, trust page, help centre, template library, runbook and incident comms — and every single one contained at least one promise the product did not keep. Not one was caught by code review or by a 100%-covered test suite, because tests check the code against itself. The documents were the only artifacts written from outside the code. | F-031..F-039 pattern | ADOPTED — every written artifact is treated as a specification with a test that pins it | Closed
F-040 | Major | FOUR OF THE NINE SPECIFIED SCREENS DID NOT EXIST. The workbook's own Screens_Wireframes sheet names nine surfaces with a purpose each, and the home dashboard ("daily habit surface"), the chatbot flows view ("differentiator surface"), settings and team, and help and support were all missing — so a customer could reach neither the feature the sheet says sets this product apart nor the help meant to deflect support load. ST-074, the weekly metrics email, was in the same condition: written in v006, callable by nothing | Diff of the Screens_Wireframes sheet against the served page | FIXED — all four built in English, Hindi and Tamil and axe-audited in each rendered state: a morning summary of open conversations and number quality; a flows view that creates and test-runs a flow, with an empty state that says why it matters; help search falling through to a support ticket when nothing matches; notification controls. /admin/metrics/weekly serves the email body for a scheduler with activation computed from the funnel. The Screens sheet now records as-built status per screen | Closed (fixed v0.36.0)
L-E19 | Lesson | The ninth specification was the product workbook — the document this whole project is run from. It had been treated as a planning artifact rather than a contract, and its screen inventory went eight days without being read against the product. The closest document was the last one checked. | F-040 root cause | ADOPTED — the workbook's own spec sheets are diffed like any other document | Closed
F-041 | Major | THE DIFFERENTIATION DID NOT EXIST. The ReadMe_Scope sheet states the product's differentiation as "vertical templates (retail / clinics / education)", and there was no vertical anywhere in the code: one undifferentiated list of twenty templates, so a clinic was handed order-tracking messages and a shop got appointment reminders. Separately the GTM sheet has exactly one Eng-owned task — the in-app review ask post-aha, ST-082 — and it was unbuilt because the onboarding checklist was a hard-coded array whose steps did nothing: aha was never reached, so the ask could never fire | Diff of ReadMe_Scope and GTM_Execution against the product | FIXED — four vertical packs (retail, clinic, education, services), each selecting the templates that business uses plus a welcome line and first routing keyword that fit it; POST /api/setup/vertical rewrites the 2am flow and seeds the rule; a validation test fails the build if a pack names an unknown template. Onboarding steps now complete for real, aha is reachable, and the review ask fires exactly once after the win | Closed (fixed v0.37.0)
OPEN-E4 | Obs | Which templates belong to which vertical is a commercial judgement, not an engineering one. The packs are a defensible first cut — a clinic gets appointments and payments, a shop gets orders and campaigns — but an SME owner in each category will have opinions worth more than mine | src/verticals.ts PACKS | LOGGED — worth 20 minutes with one owner per vertical before launch; the packs are data in one file and cheap to change | Open — Senthil disposition
F-042 | Major | Found by the audit kit on its first run, against a codebase that had already had three cold reviews, a reachability sweep and a claims audit. TWO gaps: SHARED_STORE=pg was documented in the setup guide, the deploy workflow and the risk register as the way to run more than one instance, and NOTHING read that variable — the Postgres store, carefully written and contract-tested, could not be selected at runtime. And the SEO tool was still imported by nothing, despite F-024 recording all nine previously-unreachable modules as wired: an overstatement in my own finding, caught by a tool rather than by me | node bin/reachability.js src | FIXED — selectStore() honours SHARED_STORE with named errors for an unknown mode, a missing DATABASE_URL and a missing query function; /admin/seo/iterate and /admin/partners give the two tools a way in. The kit also gained consumer-directory scanning after reporting liveSweep (consumed from scripts/) as unreachable, because a tool that cries wolf teaches a team to ignore it | Closed (fixed v0.38.0)
L-E20 | Lesson | A finding that says "all nine are now wired" is a claim like any other, and mine was wrong. The techniques in this run are worth more as scripts that run every release than as lessons written down — a lesson relies on me remembering; a script does not, and it caught me overstating within minutes of existing. | F-042 root cause | ADOPTED — the kit runs in CI here and ships to the other products | Closed
F-043 | Major | The incident comms template tells customers "sends are queued and will deliver automatically; no messages are lost" — and there was NO OUTBOUND QUEUE. A send whose retries were exhausted was recorded in a failed list and forgotten, so the sentence we would have published mid-outage, when trust is thinnest, was false. Found by the claims extractor written twenty minutes earlier, not by any human reading | node bin/extract-claims.js docs/ — the line surfaced as a candidate claim with no marker | FIXED THE PRODUCT, NOT THE WORDING — during a platform outage durable retry is what a customer needs. Failed sends are held in a bounded queue, retried by POST /admin/outbound/drain once the outage clears, and anything exhausting its attempts is dead-lettered with its message and last error so an operator can see exactly what was lost. The queue drops loudly when full rather than growing without bound. The template now says what is true and warns against promising "no messages are lost" without reading the dead-letter list | Closed (fixed v0.40.0)
L-E21 | Lesson | The most valuable thing built in this run was not a feature but a tool that reads our own promises back to us — and it earned its keep within twenty minutes by finding one that had survived a full claims audit, because I wrote that manifest from the documents I remembered rather than from the documents on disk. | F-043 root cause | ADOPTED — the extractor drafts the manifest from disk on every product, and the drafted list is reviewed rather than recalled | Closed
F-044 | Major | The trust page publishes "TLS 1.2+ in transit; AES-256 at rest; secrets held in a vault, never in code" and NOTHING checked any of it at runtime. verifySecurityConfig() was written in v006 and had no callers, so the published posture rested entirely on somebody configuring the infrastructure correctly and nobody ever discovering if they had not — the worst shape of security claim, because it reads as verified | Reconciling the extractor draft against the hand-written manifest, per L-E21 | FIXED as a posture CHECK rather than an implementation, deliberately: at-rest encryption and TLS termination belong to the database and load balancer, and a product encrypting fields itself while claiming disk encryption would be a different lie. The app refuses to start when its configuration contradicts the trust page — absent or sub-16-character secrets, at-rest flag off, TLS below 1.2, secrets not from a vault — with POSTURE_WARN_ONLY for local work and GET /admin/security-posture to re-check after an infrastructure change | Closed (fixed v0.41.0)
F-045 | Minor | Three findings (F-042, F-043, F-044) had been recorded in this sheet and never added to the regression array, so the gate did not defend them and the ledger generated from that array disagreed with the record | Ledger id-set sync test after adding F-044 | FIXED — all three added; the array is now 61 entries, the generated ledger 58, and the sync test names the three a file marker cannot express | Closed (fixed v0.41.0)
F-046 | Minor | The claims extractor read only markdown, while the richest specifications in this portfolio are spreadsheets: the screen inventory (F-040) and the stated differentiation (F-041) both came from workbook sheets and both described features that did not exist. Anything not converted is not checked | Reviewing what the extractor could see | FIXED — bin/workbook-to-text.py converts readable sheets to markdown, skipping logs and trackers, so the same claims pipeline covers spreadsheets | Closed (kit v004)
F-047 | Major | TWO BUGS IN THE KIT ITSELF, both of the kind that make a team stop trusting tooling. The converter silently skipped Full_Backlog — a hundred user stories, the largest specification in the file — because a bare "log" pattern matched "Backlog", and it reported success while doing it. Separately the extractor did not recognise first-person user stories ("As a shop owner, I can..."), so even with the sheet included it would have drafted nothing from the backlog | Noticed when the workbook run produced two candidate claims instead of dozens | FIXED — sheet titles are normalised before matching and the skip list is word-bounded; the promise pattern recognises first-person stories. Both written into the kit README as cautions, because a tool that quietly omits the main artifact is worse than one that cries wolf: the first reports a pass | Closed (kit v004)
F-048 | Major | THE AUDIT KIT HAD NO TESTS. It had already shipped three bugs — a reachability false positive, a silently skipped Full_Backlog, and undetected first-person user stories — and was about to be applied to eleven other products. Using an untested tool to argue that other code makes unverified claims is not a position worth defending | Asked what the kit itself would fail if pointed at the kit | FIXED — eleven tests (seven node, four python), one named for each shipped bug so the regressions are explicit; the exit codes are asserted too, since a check that cannot fail CI is decoration. Writing them caught a fourth error, mine: a test expected reachability to exempt an entry module automatically, when the correct behaviour is to report it unless the consumer directory is supplied. The contrast is now asserted in both directions | Closed (kit v1.0.0)

## Senthil_Handover
SENTHIL HANDOVER — every remaining EngageOS item, ordered by leverage (13 Sep 2026, 11:31)
Nothing on this list can be moved by Claude. Ordered so the longest external queue starts first. "Unblocks" names what flips the moment it lands.
# | Item | Why it is first/next | Your effort | External lead time | Unblocks | Exact next action
1 | Meta Business verification + WABA production access | Longest queue in the whole chain AND the messaging-limit unlock — the same gate twice. Everything live depends on it | ~30 min of forms | Days (verification review) | 13 pending-live stories; the 250 -> 1,000 tier step; template submission | business.facebook.com -> verify portfolio (needs incorporation or GST doc). Submit before anything else on this list
2 | VER-E1 pricing decision | Only open commercial question. Plan allowances are now template messages, and per-message rates vary ~13x by market, so the same $49 plan has very different margin in India vs Europe | 30-60 min thinking | None | Pricing page, FAQ, financial model ARPU line | Decide: keep 1,000/5,000/20,000 template messages at $29/$49/$99, or re-anchor. Tell me the numbers and I will propagate them through billing, the pricing page and the drift gates
3 | Four secrets + Postgres | Mechanical, but the sweep cannot run without them | 15 min | None | npm run migrate / npm start / npm run sweep | Fill .env: WA_ACCESS_TOKEN, WA_PHONE_NUMBER_ID, WA_WABA_ID, WA_WEBHOOK_VERIFY_TOKEN, WA_APP_SECRET, ENGAGEOS_OPERATOR_TOKEN, ENGAGEOS_SESSION_SECRET (16+ chars), DATABASE_URL. Run `npm run rehearse` first — no credentials needed, and it proves the machine works (docs/REHEARSAL_TRANSCRIPT.md)
4 | Run the 12-step verification sweep | Converts assumption into evidence; flips the largest block of stories in one session | ~30 min once (1) and (3) are done | None | ST-005/015/025/035/045/051/059/066/088/090/092 + LC items | npm ci -> npm run build -> npm run migrate -> npm start -> register /webhook -> WA_TEST_PHONE=+91... npm run sweep. The output format is identical to the rehearsal transcript minus the dry-run banner, so you will know immediately whether a failure is yours or Meta's. Send it to me and I will log it as evidence
5 | External second reviewer | Same-AI review is not independence; ST-097 stays In progress until someone else runs it | Forward one file | Reviewer-dependent | ST-097 | Send docs/REVIEW_PACK.md + the repo to your other-AI loop or a human reviewer. It lists the claims to re-check and the probes my passes may have missed
6 | Dispositions: F-005..F-008, D-E4, D-E1, D-E2 | Cheap decisions blocking nothing technically, but they should not go live undecided. F-005 (duplicate install overwriting token + attribution) is the one that matters before live wiring | 20 min | None | Review_Findings rows move to closed | Read the Review_Findings sheet; tell me fix / accept / defer per row. D-E4 = whether to keep the built-in chat engine and skip a vendor entirely
7 | Pen-test vendor | ST-068 sandbox half is compiled; only a vendor can close it | Procurement | Weeks | ST-068 | Brief a vendor with docs/SECURITY_EVIDENCE.md — it already names the areas to target, including F-005
8 | Listing copy A/B pick + asset capture | Listing copy still needs your pick. Screens are built and styled, so capture is now a session with a real device and your brand mark, not a design project | 1 hr review + capture session | None | ST-093, ST-094 | Pick A (outcome-led) or B (pain-led) in docs/listing/LISTING_COPY_A_B.md; then capture the 5 shots in ASSET_PLAN.md against the styled workspace at /web (ENGAGEOS_DEMO=1 for populated screens)
9 | Design-partner outreach | Only paying strangers count toward the 10-install gate; friends do not | Ongoing | Weeks | ST-100 live half; G-02 | Use the 10-slot tracker; remember the 250-recipient/24h ceiling when promising partners a first campaign
10 | Native-speaker review of the Hindi and Tamil UI strings (47 each) | The UI ships in all three languages; a machine did the translating, and tone in a commercial interface is what a native speaker catches | One decision | None | Whether EngageOS competes with the other builds for your attention | Send i18n/hi.json and i18n/ta.json to a native speaker; return corrections and I will apply them (the disk files are generated from the module, so corrections come back through it)
| Review the four vertical template packs (OPEN-E4) | Which templates a clinic vs a shop vs a coaching centre actually needs is a commercial call; the packs are my first cut |  |  |  | Read src/verticals.ts PACKS with one owner per vertical; corrections are one file and I will apply them

## Integrity_Audit
INTEGRITY AUDIT — claims verified mechanically, not restated (13 Sep 2026, 11:33)
Every check below was executed against the shipped artifact engageos_v0.19.0_src.zip and the tracker itself. Findings were fixed in this version.
# | Check | Method | Result | Action taken
1 | The shipped zip actually builds from scratch | Unpacked engageos_v0.19.0_src.zip into a clean directory, ran npm ci then npm run build | PASS — npm ci clean, tsc build clean | None needed
2 | The 100% coverage gate holds on a clean checkout | npm test in the clean directory (jest coverageThreshold 100 x4 fails the run below threshold) | PASS — 35 suites / 171 tests, gate satisfied | None needed
3 | Coverage is not bought with suppressions | grep for istanbul pragmas across src/ and scripts/ | FAIL — 5 pragmas found, while release notes had repeatedly claimed "one documented pragma" | Two were dead code and were REMOVED rather than suppressed: the chatbot run loop now cannot fall through, and the delivery ledger can no longer miss a state lookup. Three remain and are honest: two process bootstraps (http/index.ts, scripts/run-sweep.ts) and one CLI entry (scripts/make-fixtures.ts), none of which contain testable logic. The claim is corrected to THREE bootstrap pragmas, zero logic pragmas
4 | Every story claimed Done-in-code names a test suite that exists | Parsed all 100 traceability rows, extracted named .test.ts files, checked each against a repo file index | FAIL — 2 rows named suites vaguely ("all 16 suites", "resilience/broadcast/inbox suites") and could not be verified mechanically | Both rewritten to name real files. Re-run result: 78 of the 79 Done-in-code rows resolve to .test.ts files that exist; the 79th is ST-085, whose evidence is correctly jest.config.js — the coverage gate itself is the verification for a coverage story, and that file was checked to exist. Justified exception, recorded here rather than papered over
5 | Traceability story text matches the product backlog | Compared column D of every row against Full_Backlog column C, the single source of truth | FAIL — 9 rows had their STORY TEXT OVERWRITTEN with module paths by my own later updates (ST-080/081/088/089/090/092/095/099/100). Real data loss in the traceability record | All 9 restored from the product backlog; the module path moved to the Module column where it belonged. Root cause: later write scripts targeted column 4 assuming a layout that column 3 actually held
6 | Tracker status agrees with the product workbook | Mapped workbook statuses to tracker taxonomy and compared all 100 rows | PASS — 79 / 13 / 6 / 2 / 0 identical in both files | None needed
7 | Every non-backlog row carries a version stamp in its evidence | Regex for a vNNN stamp across all evidence cells | PASS — every row traceable to the version that moved it | None needed
8 | Documented commands and artifacts exist | docsDrift suite asserts .env.example, db/migrations, scripts/migrate.sh, loadtest, templates and the npm scripts all exist | PASS — runs as part of the suite, so it cannot silently rot | None needed
Summary | 8 checks executed | 5 passed on the first run | 3 failed and were fixed in v0.20.0 / tracker v015 | The failures were all in MY reporting and record-keeping rather than in the product: an overstated pragma claim, two unverifiable evidence cells, and nine rows of overwritten story text. Worth noting plainly — the code held up; the paperwork about the code did not.
AUDIT PASS 2 — 13 Sep 2026, 11:38: the findings ledger and workbook structure
# | Check | Method | Result | Action taken
9 | Every finding recorded as closed is still fixed in the shipped code | One concrete source probe per finding (37 of them) run against the unpacked v0.20.0 zip — e.g. F-009 requires the opt-in gate to be CALLED in broadcast.ts, not merely to exist | PASS — 37 of 37 verified | Converted into tests/findingsRegression.test.ts (39 assertions) so the check runs on every commit. This matters because F-021 was precisely a fix that existed but was not wired, and a record can go stale the same way
10 | Coverage is not quietly bought back with pragmas in future | Walk src/ and scripts/ for istanbul pragmas, allowing only the three documented process bootstraps | PASS after the v021 removals | Added as a test, so a new suppression fails the build rather than being spotted in a later audit
11 | Sprint_Board reconciles with Full_Backlog | Recomputed per-sprint story counts and total points from the backlog and compared against the board | PASS — counts and 399-point total agree exactly | None needed
12 | Product workbook version sequence is contiguous | Listed every Version_Control row in order | PASS — v001-v004 baseline row then v005 onward with no gaps or duplicates | None needed
13 | Launch checklist reflects current reality | Read all 10 items against what the code and decisions now say | FAIL — item 6 still required testing "conversation-pricing pass-through billing", the model Meta retired on 1 Jul 2025 (VER-E1); items 2, 3 and 8 carried statuses predating the Cloud API decision, the quality guard and the store-backed dedupe | Item 6 rewritten as per-message reconciliation; items 2, 3 and 8 re-statused to what is actually true, with the live half named in each
14 | Risk identifiers are consistent across files | Compared Risk_Register entries with the tracker RAID sheet | FAIL — the three original risks had no IDs while later ones were R-E7 onward, so the two files could not be cross-referenced | Original three labelled R-E1..R-E3, matching the tracker RAID; the ledger now reads R-E1 through R-E9 across both files
Summary | 14 checks now executed across two passes | 9 passed first time | 5 failed and were fixed | Both passes found the same shape of problem: the product was sound, the record describing it drifted. The response in each case was to convert the check into something automatic — a test suite for the findings, a pragma guard, a drift gate for the docs — so the next drift fails a build instead of waiting for an audit.

## Lessons_For_Portfolio
LESSONS — written to be applied to the other products, not to be admired here
Nineteen lessons from 38 releases. Grouped by the technique that found the defect, because that is the reusable part. Every defect below occurred with 100% statement, branch, function and line coverage in place the whole time.
Group | What it cost here | The rule | Cheapest way to run it elsewhere
Coverage proves the parts, not the product | Four modules shipped, tested and recorded Done while nothing in the product called them — including the opt-in gate and the 24-hour window, so marketing could have reached non-consented contacts. Separately, every route was a GET except the webhook and inbound messages were deduped into a buffer nothing drained: a customer message never became a conversation while 79 stories read as Done. | A story is Done when the RUNNING PRODUCT imports it, and when the intended user could do the thing unaided. Not when the module and its tests exist. | Two greps at each release: list src modules and check each has an importer outside tests; then read the route table and ask which user action each one serves. Ten minutes.
Every written artifact is a specification | Eleven documents were diffed against the product and ALL ELEVEN contained a promise it did not keep: flows that never answered at 2am, a quality guard never consulted before a broadcast, payment links that went to the agent, a vernacular UI whose language packs had no importer, self-serve data rights reachable only with an operator token, plans metered in a unit Meta stopped billing, eight help articles describing tasks with no control, twelve templates whose variables were never sent, a runbook whose first rollback step did not exist, incident messages with nowhere to publish, four missing screens including the stated differentiator, and the vertical differentiation itself. | Diff every customer-facing and operator-facing document against the product at each release, and pin each promise with a test named after it. | Start with the listing copy and the help centre — they are written from the customer's point of view, which is why they find what code review cannot. An hour per product, and it found more defects here than three cold-review passes.
Internal review cannot check your model of the world | Three adversarial passes at 100% coverage could not find that webhook payloads are batched (every message after the first was silently dropped), that conversation pricing was deprecated in July 2025, that messaging limits cap unique recipients portfolio-wide at 250 for a new account, or that templates need body parameters — because the fake adapter faithfully reproduced our own assumptions. | An external verification sweep against live platform documentation is a required step before any live run. | One session per product, before the first live attempt. Read the platform docs for pricing, limits, payload shapes and error semantics; write one test per finding. Thirteen corrections came out of it here.
Honest status is a discipline, not a sentiment | 309 of 399 points are Done-in-code and ZERO are Done, held for 38 releases. Every release that changed no story status said so. Two audits found the record drifting from the product — an overstated pragma claim, nine rows whose story text had been overwritten by my own scripts — and fixing the record was treated as real work. | Separate "the code does this" from "a stranger paid for this", and audit the record itself, not just the code. | A findings-regression suite (one probe per closed defect) plus a periodic diff of the tracker against the product. Both are cheap and both caught things here.
The one that generalises | Coverage, review passes and audits all check the system against itself. | The three techniques that found what they could not — reachability sweeps, document diffs, platform verification — all start from OUTSIDE the code. | Budget for them explicitly in each product's plan rather than hoping they happen.