## Version_Control
VERSION CONTROL — QuoteFlow Sprint Tracker & Traceability
File naming: claude_v<NNN>_<proper file name>_YYYYMMDD_HHMI. Companion to the product workbook lineage claude_v006..v009_quoteflow_hubspot_product_workbook.
Version | Date/Time | Author | Change Description | Status
v001 | 2026-09-10 23:09 | Claude for Senthil/KP | THIS FILE — Live execution tracker for QuoteFlow (HubSpot App Marketplace, portfolio wave-2): event-level sprint log E001..E014 for S1/S2/S3, decisions register, per-sprint build boards (S1/S2/S3), 100-story traceability with per-story evidence citing product-workbook versions (S1=v007 22:03, S2=v008 22:19, S3=v009 22:52), live sprint status rollup (formulas), RAID, and the D7 completion gate. Source of story truth: v009 Full_Backlog. | Released
v002 | 2026-09-11 08:17 | Claude for Senthil/KP | S4 EXECUTED (Approval chains part 2 + telemetry + smoke, 9 stories / 34 pts): events E015..E021 appended; S4_Build_Board added; 9 traceability rows Done with v010 evidence (30/100 total, 123/399 pts); rollup S4 RAG GREEN; Decisions DQ4 updated with the failed live-Postgres attempt, DQ6/DQ7 added (feature-pause + spike semantics); RAID R-Q4 attempt-evidenced, R-Q9 added (smoke deploy hook assumption). Companion product workbook: v010 (2026-09-11 08:17). | Released
v003 |  |  | PLANNED: S5 execution entries (E-signature + alpha hardening, 12 stories / 50 pts); live-verification evidence (R-Q5/R-Q6) when Senthil provides dev-portal access; Postgres retry log | Planned
v003 | 2026-09-11 08:52 | Claude for Senthil/KP | S5 EXECUTED (E-signature + alpha hardening, 12 stories / 50 pts — largest sprint): events E022..E028; S5_Build_Board added; 12 traceability rows Done with v011 evidence (42/100 stories, 173/399 pts, 43.4%); rollup S5 GREEN; Decisions +DQ8 (public signer surface — token IS the identity, validate-then-mint) +DQ9 (esign pause never-strand + settings snapshot-at-creation) + DQ5 note (signer link delivery rides the email provider; API returns signerLinks meanwhile); RAID R-Q7 note extended to signer outreach. Companion product workbook: v011 (2026-09-11 08:52). | Released
v004 |  |  | PLANNED: S6 execution entries (Billing + Quote analytics, 13 stories / 60 pts); Postgres retry log; live-verification evidence when R-Q5/R-Q6 unblock | Planned
v004 | 2026-09-11 12:47 | Claude for Senthil/KP | S6 EXECUTED (Quote analytics + Billing, 13 stories / 60 pts): events E029..E035; S6_Build_Board added; 13 traceability rows Done with v012 evidence (55/100 stories, 233/399 pts, 58.4%); rollup S6 GREEN; Decisions +DQ10 (analytics pause blocks dashboards NEVER capture; capture setup-independent) +DQ11 (per-portal channel routing marketplace/HubSpot vs direct/Stripe; failure persists nothing; 30d proration w/ net<=0 no-call rule); RAID +R-Q10 (billing provider live credentials — Senthil). Companion product workbook: v012 (2026-09-11 12:47). | Released
v005 |  |  | PLANNED: S7 execution entries (Beta cohort ST-073..077, 5 stories / 15 pts); live-verification evidence when R-Q5/R-Q6/R-Q10 unblock | Planned
v005 | 2026-09-13 10:26 | Claude for Senthil/KP | S7 EXECUTED (billing hardening + least-privilege scopes, 5 stories / 15 pts): events E036..E042; S7_Build_Board added; 5 traceability rows Done with v013 evidence (60/100 stories, 248/399 pts, 62.2%); rollup S7 GREEN; Decisions +DQ12 (billing read-only is a WRITE gate only — reads and exports survive dunning and cancellation) +DQ13 (scopes validated in code: registry + two-way audit + generated disclosure); scope-drift note added to RAID. Companion product workbook: v013 (2026-09-13 10:26). | Released
v006 |  |  | PLANNED: S8 execution entries (Deal/line-item sync + beta iteration, 22 stories / 87 pts — largest remaining sprint) | Planned
v006 | 2026-09-13 10:38 | Claude for Senthil/KP | S8 EXECUTED (largest sprint — 22 stories / 87 pts across F5 sync, E6 trust, E7 founder ops, EQ performance): events E043..E050; S8_Build_Board added; 22 traceability rows Done with v014 evidence (82/100 stories, 335/399 pts, 84.0%); rollup S8 GREEN; Decisions +DQ14 (idempotency key + queue-on-pause) +DQ15 (generated trust doc, unmet controls published as partial with owners) +DQ16 (circuit breaker in front of platform writes); RAID +R-Q11 (vault + at-rest provisioning). Companion product workbook: v014 (2026-09-13 10:38). | Released
v007 |  |  | PLANNED: S9 execution entries (Marketplace review prep, 7 stories / 30 pts) | Planned
v007 | 2026-09-13 10:56 | Claude for Senthil/KP | S9 EXECUTED (Marketplace review prep, 7 stories / 30 pts — 5 Done, 2 Partial): events E051..E058; S9_Build_Board added; 7 traceability rows updated with v015 evidence; rollup S9 AMBER (two stories carry external dependencies); Decisions +DQ17 (two-step token-confirmed deletion, export always available) +DQ18 (review evidence generated and asserted, never narrated); RAID +R-Q12 (external penetration test). Defect L-062 logged: the restore drill destroyed non-restorable sources. Companion product workbook: v015 (2026-09-13 10:56). | Released
v008 |  |  | PLANNED: S10 execution entries (Review remediation + docs, 7 stories / 24 pts) | Planned
v008 | 2026-09-13 11:11 | Claude for Senthil/KP | S10 EXECUTED (Launch surfaces, 7 stories / 24 pts, all Done): events E059..E065; S10_Build_Board added; 7 traceability rows Done with v016 evidence (94/100 stories, 376/399 pts strictly-Done); rollup S10 GREEN; Decisions +DQ19 (customer-facing pages generated from product constants) +DQ20 (support SLA measured in business hours; unanswered-past-due counts as breach) +DQ21 (submission dry-run reads live state, human-needed items are manual blockers not passes). Companion product workbook: v016 (2026-09-13 11:11). | Released
v009 |  |  | PLANNED: S11 execution entries (Launch — 3 stories / 8 pts) | Planned
v009 | 2026-09-13 11:25 | Claude for Senthil/KP | S11 EXECUTED (Launch, 3 stories / 8 pts, all Done): events E066..E071; S11_Build_Board added; 3 traceability rows Done with v017 evidence (97/100 stories, 384/399 pts strictly-Done); rollup S11 GREEN-with-note (preflight returns no_go on billing stubs, R-Q10); Decisions +DQ22 (review ask fires only when the portal is demonstrably happy; no review-gating) +DQ23 (runbook executable, every step verifiable) +DQ24 (partner pipeline counts scheduled, not intentions). Companion product workbook: v017 (2026-09-13 11:25). | Released
v010 |  |  | PLANNED: S12 execution entries (Iterate & scale decision — 1 story / 2 pts) — final sprint | Planned
v010 | 2026-09-13 11:34 | Claude for Senthil/KP | S12 EXECUTED + PROGRAMME CLOSE (1 story / 2 pts): events E072..E077; S12_Build_Board added; ST-099 traceability row Done with v018 evidence; rollup S12 GREEN; Decisions +DQ25 (SEO may never propose an unsupported claim). FINAL: 12 sprints, 98/100 stories Done + 2 Partial, 386/399 points, 397 tests / 26 suites at 100% x4 on 49 source files. Companion product workbook: v018 (2026-09-13 11:34), which carries the Programme_Closeout sheet. | Released
— |  |  | No further sprints planned. Next work is the six external items in Programme_Closeout (workbook v018), none of which are code. | Closed
v011 | 2026-09-13 11:51 | Claude for Senthil/KP | COLD REVIEW PASS 1 (QuoteFlow's first): events E078..E082; 8 defects fixed with pinned regressions, four critical (delete-my-data leaving records, no runnable entrypoint, unsigned caller-declared identity, expired trial granting perpetual free use); Review_Findings sheet in product workbook v019 carries the full table plus the two sibling classes verified absent; lesson L-Q1 logged. Suite 397 -> 410 tests / 27 suites at 100% x4. Story position unchanged 98 Done / 2 Partial — correctness release. | Released
v012 |  |  | PLANNED: cold review pass 2 over the modules pass 1 did not reach, plus an artifact-gap audit (no DB schema exists behind the published retention policy — stores are still in-memory, R-Q4) | Planned
v012 | 2026-09-13 12:03 | Claude for Senthil/KP | COLD REVIEW PASS 2 + artifact-gap audit: events E083..E087; 6 findings fixed (F-Q09 retention policy never enforced — CRITICAL, F-Q10 redaction control with no call sites, F-Q11 breaker on writes only, F-Q12 no deploy workflow, F-Q13 no DB schema, F-Q14 future-dated signatures); +DQ26 (every fix ships with a drift gate, not just a regression); lesson L-Q2. Suite 410 -> 424 tests / 28 suites at 100% x4. Story position unchanged 98 Done / 2 Partial. Full detail: product workbook v020 Review_Findings. | Released
v013 |  |  | PLANNED: pass 3 (the surfaces pass 1 and 2 did not reach — help/support/public/founder modules read adversarially), and the Postgres adapter behind the new schema (R-Q4 code half) | Planned
v013 | 2026-09-13 16:25 | Claude for Senthil/KP | COLD REVIEW PASS 3: events E088..E091; 3 findings fixed (F-Q15 status page wired to constants, F-Q16 preflight readiness hardcoded, F-Q17 CRITICAL nine vendor-only surfaces reachable with tenant RBAC); +DQ27 (vendor surfaces gated on an operator token and fail closed); lesson L-Q3. Suite 424 -> 428 tests / 28 suites at 100% x4. Running total 17 defects across three passes. Story position unchanged 98 Done / 2 Partial. Detail: product workbook v021 Review_Findings. | Released
v014 |  |  | PLANNED: Postgres adapter behind the pass-2 migrations (R-Q4 code half) with a store-contract suite run against both in-memory and pg | Planned
v014 | 2026-09-13 16:36 | Claude for Senthil/KP | R-Q4 CODE HALF: events E092..E094; Postgres adapters for audit/analytics/sync behind the pass-2 migrations, proved by a store-contract suite executed against both in-memory and real SQL on an in-process Postgres with the real migrations, including two durability tests; +DQ28 (a persistence adapter is only accepted when the same contract suite passes against both implementations); R-Q13 opened (synchronous store interfaces force a write-through cache and a single writer). Suite 428 -> 439 tests / 29 suites at 100% x4. | Released
v015 |  |  | PLANNED: adapt the remaining six stores using the contract-suite pattern; R-Q13 async interface migration; live Postgres run of the contract suite once an instance exists | Planned
v015 | 2026-09-13 16:41 | Claude for Senthil/KP | POSTGRES ADAPTERS PART 2: events E095..E097; the remaining six stores adapted, so all nine now have a Postgres implementation proved against a real engine; NEW DEFECT F-Q18 (catalog bundles, pricing rules and pause flags had no tables - the pass-2 drift gate checked store granularity, not field); migration 005 added; +DQ29 (a store adapter must round-trip every record type the interface exposes, asserted field by field). Suite 439 -> 457 tests / 30 suites at 100% x4. R-Q13 still open. | Released
v016 |  |  | PLANNED: R-Q13 async store interfaces (multi-instance safety); live Postgres run of both contract suites once an instance exists; wire the adapters into index.ts behind a DATABASE_URL switch | Planned
v016 | 2026-09-13 16:53 | Claude for Senthil/KP | POSTGRES BOOT WIRING: events E098..E100; buildStores() selects the backend from DATABASE_URL and reports it, server.ts runs migrations then starts, portals hydrate once per process; the real app is now driven over HTTP against Postgres-backed stores and a second process on the same database sees the data. +DQ30 (a persistence backend must be selectable at boot, report itself, and be proved by driving the real app end to end). Named gap: approvals still in-memory. Suite 457 -> 465 tests / 31 suites at 100% x4. R-Q13 open. | Released
v017 |  |  | PLANNED: PgApprovalStore (the last in-memory store); R-Q13 async interfaces; live Postgres run of all three suites once an instance exists | Planned
v017 | 2026-09-13 17:23 | Claude for Senthil/KP | R-Q14 CLOSED: events E101..E102; PgApprovalStore written and wired, contract suite extended to chains and requests, and pgBoot proves an approval decision survives a restart through the real HTTP flow. Every store the product writes to is now durable. RAID R-Q14 closed; R-Q13 remains open. Suite 465 -> 466 tests / 31 suites at 100% x4. | Released
v018 |  |  | PLANNED: R-Q13 async store interfaces (multi-instance safety) and a live Postgres run of all four suites | Planned
v018 | 2026-09-13 17:30 | Claude for Senthil/KP | WRITER LEASE (R-Q13 mitigation): events E103..E104; migration 006 plus a lease an instance must hold to write, so a second instance is refused at startup instead of diverging silently; +DQ31 (where a constraint cannot yet be removed, enforce it so breaking it fails loudly). R-Q13 remains OPEN for the async migration itself - its dangerous half is closed. Suite 466 -> 472 tests / 32 suites at 100% x4. | Released
v019 |  |  | PLANNED: R-Q13 proper (async store interfaces, ~40 call sites) as a dedicated phase; live Postgres run of all five suites | Planned
v019 | 2026-09-13 18:48 | Claude for Senthil/KP | R-Q13 PHASE 1: events E105..E106; the async cascade done once - PortalDataSource, PrivacyService, BackupService and RetentionService plus six routes are async, with no behaviour change (472 tests still green at 100% x4). +DQ32 (stage a large migration so every checkpoint is green). Phase 2 (per-store async, dropping the write-through caches) open. | Released
v020 |  |  | PLANNED: R-Q13 phase 2 - convert the nine stores to async and drop the write-through caches, one store at a time | Planned
v020 | 2026-09-13 18:59 | Claude for Senthil/KP | R-Q13 PHASE 2 STORE 1/9 (review state): events E107..E109; ReviewStore async with the Pg write-through cache removed, proved by two running instances sharing one database with no restart; self-inflicted ?? -on-a-promise regression caught by the coverage gate and fixed; +DQ33 (when a store read becomes async, re-check every ?? and ?. applied to it). Suite 472 -> 473 tests / 32 suites at 100% x4. Eight stores remain. | Released
v021 |  |  | PLANNED: phase 2 stores 2-9 (signatures, support, audit, sync, analytics, approvals, billing, notifications, catalog - smallest ripple first); live Postgres run | Planned
v021 | 2026-09-13 19:33 | Claude for Senthil/KP | R-Q13 PHASE 2 STORE 2/9 (support conversations): events E110..E111; SupportStore and SupportService async, PgSupportStore rewritten cache-free, six routes awaited and guarded, DQ33 applied to every ?? and ?. on a support read. Suite unchanged at 473 tests / 32 suites, 100% x4 - correct for a conversion that changes no behaviour. Seven stores remain. | Released
v022 |  |  | PLANNED: phase 2 stores 3-9 (signatures, audit, approvals, sync, analytics, catalog, notifications, billing); the writer lease can become advisory once all nine are done; live Postgres run | Planned
v022 | 2026-09-13 19:41 | Claude for Senthil/KP | R-Q13 PHASE 2 CORRECTION + PLAN: events E112..E113; corrected the v029 claim that each remaining store is local work (true for 2 of 9, false for 7), measured every cascade, and published a risk-sequenced migration plan gated by a test so it cannot become aspirational. +DQ34 (a plan that outlives a session must be asserted against the code). Suite 473 -> 474 tests / 32 suites at 100% x4. | Released
v023 | 2026-09-13 19:56 | Claude for Senthil/KP | R-Q13 PHASE 2 STORE 3/9 (approvals): events E114..E115; store, service and cache-free Pg adapter plus the CRM card and checklist readers; two un-awaited-promise defects found and fixed during the mechanical pass; migration plan corrected to note that even the self-contained store had a tail. Suite held at 474 tests / 32 suites, 100% x4. Six stores remain. | Released
v024 | 2026-09-13 20:08 | Claude for Senthil/KP | R-Q13 PHASE 2 STORE 4/9 (sync): event E116; store, service, cache-free Pg adapter for runs (including the fleet-wide failure count behind the public status page), retention sweeper, export source and eight routes. Adapter settings deliberately stay in memory and that choice is documented in the plan. Suite held at 474 tests / 32 suites at 100% x4. Five stores remain: audit, signatures+analytics together, notifications, billing, catalog last. | Released
v025 | 2026-09-13 20:26 | Claude for Senthil/KP | R-Q13 PHASE 2 STORE 5/9 (audit): event E117; store, record() helper, retention sweeper, export source and cache-free Pg adapter converted, with 23 route handlers becoming guarded async. +DQ35 (audit writes are awaited, never fire-and-forget). Suite held at 474 tests / 32 suites at 100% x4. Four stores remain: signatures+analytics together, notifications, billing, catalog last. | Released
v026 | 2026-09-13 22:46 | Claude for Senthil/KP | ATTEMPT ABANDONED, TREE RESTORED: events E118..E119. Store 6+7 (signatures+analytics) source converted cleanly but ~200 test call sites did not; repo-wide regex broke supertest chains and the suite bottomed out at 15 failed / 17 passed. Tree restored from the 20:26 artifact and re-verified at 474 tests / 32 suites / 100% x4. +DQ36 (convert src first, then one suite at a time, never a pattern across all tests). Stores 1-5 converted; 6-9 pending. | Released
v027 |  |  | PLANNED: retry stores 6+7 with the DQ36 method in a fresh session (s5 and s6 are the large suites); then notifications, billing, catalog last | Planned
v027 | 2026-09-13 23:30 | Claude for Senthil/KP | EXTERNAL REVIEW V001 INCORPORATED (ChatGPT, 13 Sep 23:02) — 14 findings QF-001..QF-014, ids preserved per CB-02. New ExtReview_V001_Board carries the fix board. FOUR CLOSED IN CODE: QF-008 lockfile + clean-room npm ci/tsc/jest, QF-005 authenticated HubSpot client, QF-006 real line_items + associations API, QF-009 deploy steps fail instead of echoing, QF-012 generated release manifest. Production now refuses to boot while QF-002/QF-003 are open. STRUCTURAL CHANGE — CB-01 evidence classes: Traceability_Matrix gains columns L and M (required classes, evidence status) APPENDED, not inserted, because Sprint_Status_Rollup reads columns E/G/J and an insert would have silently broken every rollup formula. Stories whose required classes are not all satisfied drop from Done to Partial, so the headline story count falls from 98 Done to a smaller honest number: unit coverage was never evidence that a HubSpot integration works. RAID gains R-Q15 (Projects/UI-extension migration — legacy CRM cards stop rendering 31 Oct 2026) and R-Q16 (release reproducibility, closed same release). Suite 488 tests / 33 suites / 100% x4. | Released
v028 |  |  | PLANNED: incorporate external review V002 (16 findings PXR-001..PXR-016, 4.1/10 NOT ENTERPRISE GRADE, sprint plan PS13–PS32). Senthil: "enterprise grade product do all dont shrink the scope" — no sprint deferred. | Planned
v028 | 2026-09-20 16:40 | Claude for Senthil/KP | EXTERNAL REVIEW V002 INCORPORATED IN FULL. PS13–PS31 executed except the items that are purchases or accounts. Legacy CRM card DELETED and replaced by the 2026.03 Projects app + React app card (DQ40 overruled on Senthil's instruction, recorded as an overrule). Header identity DELETED, session mint shipped. Async store cascade completed and the writer lease retired. RLS on every tenant table, proved on a real Postgres engine. Durable outbox, envelope-encrypted tokens, observability + SLOs. Quote entity, signature evidence, HubSpot sync provenance. NEW THIS RELEASE: configuration engine (PS23), deep pricing engine with full waterfall (PS24), deal-desk approval DAG (PS25), billing correctness with provider webhooks (PS29), migration rollback + chaos + residency posture (PS30), and the evidence-class quality system with a claims register (PS31). 793 tests / 45 suites at 100% x 4. Tree 43de1cac3aa5. | Released

## Sprint_Tracker_Log
SPRINT TRACKER LOG — every execution event, newest last
Refs cite product-workbook tracker entries (L-001..L-021), decisions (D..), stories (ST-..). One row per event; versions are the workbook releases that carry the evidence.
ID | Date/Time | Sprint | What happened | Refs | State changes | Blockers | Next
E001 | 2026-09-10 22:03 | — | QuoteFlow build opened from v006 product workbook on continue signal. D13 applied (portfolio-wide: discovery interviews parked, dev proceeds under 100% automation coverage on ALL code); ST-085 gate text amended from >=70% to 100% in backlog. | D13; L-001; v007 | S1 opened; ST-085 re-scoped | None | E002
E002 | 2026-09-10 22:03 | S1 | S1 FOUNDATION BUILT (TypeScript/Node 22/Express 4, strict tsc): OAuth install -> welcome (ST-051), uninstall webhook with HubSpot v3 HMAC + replay guard + retention-scheduled deletion (ST-052), rotation-safe token refresh with 60s expiry skew (ST-055), install source telemetry (ST-056). Workbook v007 released 22:03 with Sprint_Tracker_Log + Traceability_Matrix sheets added. | ST-051/052/055/056; L-002..L-003; v007 | 4 S1 stories Done-in-code (13 pts) | None | E003
E003 | 2026-09-10 22:03 | S1 | D13 TEST GATE MET — 56 automated tests / 3 suites (unit + supertest HTTP integration), 100% stmt/branch/func/line on every source file; jest coverageThreshold 100x4 fails any build below. | D13; L-004; test-run.log 20260910_2203 | Evidence into Traceability col K | None | E004
E004 | 2026-09-10 22:03 | S1 | S1 CLOSED 4/4 (13/13 pts). Exit criterion "app installs cleanly; telemetry firing" code-verified via integration tests; LIVE dev-portal install verification remains open (needs Senthil: dev portal app + client ID/secret) — same pattern as RevRescue live Stripe install. | L-005..L-006 | Cumulative 4/100 stories, 13/399 pts | Live install = Senthil + dev portal | E005
E005 | 2026-09-10 22:19 | S2 | S2 OPENED on continue signal: Price book + bundles part 1 — ST-001..004 + ST-053 re-install restore + ST-054 role matrix (6 stories, 29 pts). | L-008; v008 | S2 in build | None | E006
E006 | 2026-09-10 22:19 | S2 | S2 BUILT: catalog domain (books/items/bundles/rules, portal-isolated), one-call idempotent defaults, best-rule pricing engine (minQty/customerTier, largest discount wins, verified 804.60+672.60=1477.20), typed AppError + PlatformClient backoff (429/5xx retry -> retryable 503; 401 re-auth), re-install restore cancelling pending deletion + retention purge executor, owner>admin>member RBAC on every /api route with first-user-owner bootstrap. Workbook v008 released 22:19. | ST-001..004/053/054; L-009; v008 | 6 S2 stories Done-in-code (29 pts) | None | E007
E007 | 2026-09-10 22:19 | S2 | D13 TEST GATE HELD — suite 56 -> 103 tests / 5 suites, 100% x4 on all 16 source files; E2E-over-HTTP: defaults -> detail -> priced quote; uninstall webhook -> re-install -> "data restored" welcome. | D13; L-010; test-run.log 20260910_2219 | Evidence into Traceability col K | None | E008
E008 | 2026-09-10 22:19 | S2 | S2 CLOSED 6/6 (29/29 pts). Decision locked: /api identity is header-based (X-QF-Portal-Id/X-QF-User-Id) until the HubSpot-signed CRM-card surface lands in S3 (ST-005). | L-011..L-013; DQ2 | Cumulative 10/100, 42/399 | None | E009
E009 | 2026-09-10 22:52 | S3 | S3 OPENED on continue signal: Price book part 2 (ST-005..010) + Approval chains start (ST-011..014) + ST-085 gate story — 11 stories, 47 pts (largest sprint so far). | L-014; v009 | S3 in build | None | E010
E010 | 2026-09-10 22:52 | S3 | S3 BUILT: HubSpot-signed GET /crm-card + /ui/quote iframe shell (paused-aware card), metrics service (aggregates + 7-day UTC trend), audit log on all 14 mutating routes, pause/resume gating writes only, CSV import (generic + rivalcpq competitor formats, quoted-field parser, row-level errors, SKU dedupe), notifications (in-app+email, per-type mute, failed-email retry), approval chains (one-call default "Discounts over 15% need manager approval", validated custom chains, strict-> triggers, step-snapshot requests, approve/reject walk with approver fan-out). DeletionExecutor now purges all five stores. Workbook v009 released 22:52. | ST-005..014/085; L-015; v009 | 11 S3 stories Done-in-code (47 pts) | None | E011
E011 | 2026-09-10 22:52 | S3 | D13 TEST GATE HELD — suite 103 -> 150 tests / 7 suites, 100% x4 on all 24 source files, EXIT=0. E2E-over-HTTP: signed card reflects catalog+pause; pause 409s writes/keeps reads; import->quote; mute suppresses; failed email 502-retryable then healed; discounted quote -> pending -> approvers notified -> approved -> requester notified. | D13; L-016; ST-085; test-run.log 20260910_2252 | ST-085 marked Done with evidence | None | E012
E012 | 2026-09-10 22:52 | S3 | DECISIONS LOCKED: (a) approval requests snapshot chain steps at creation — in-flight requests immune to later chain edits, no dead branches; trigger boundaries strict (15.00% does NOT trip a 15% chain). (b) Postgres adapter DEFERRED to S4 — no live Postgres in build env; shipping an unexecuted adapter would break the honest-status rule; store interfaces are the seam. | L-017..L-018; DQ3/DQ4 | v010 plan carries the adapter | None | E013
E013 | 2026-09-10 22:52 | S3 | S3 CLOSED 11/11 (47/47 pts). Sprint_Board verified S1=4, S2=6, S3=11 Done; 167 formulas 0 errors. Cumulative 21/100 stories, 89/399 pts (22.3% of points in three sessions). | L-020..L-021 | Cumulative 21/100, 89/399 | Live dev-portal install + live CRM card fetch = Senthil | E014
E014 | 2026-09-10 23:09 | — | THIS TRACKER CREATED (v001) on continue signal, TeleField-tracker pattern: event log, decisions, S1/S2/S3 build boards, 100-story traceability with versioned evidence, live rollup formulas, RAID, D7 gate. | v001 (this file) | Tracker baseline established | None | S4 on go signal
E015 | 2026-09-11 08:17 | S4 | S4 OPENED on continue signal (new day): ST-015..020 approval chains part 2 + ST-071/072 telemetry + ST-086 smoke — 9 stories, 34 pts. Postgres adapter (DQ4) in scope for this sprint. | L-022; v010 | S4 in build | None | E016
E016 | 2026-09-11 08:17 | S4 | POSTGRES LIVE ATTEMPT: apt-get postgresql in sandbox — security.ubuntu.com 404s postgresql-16 debs; apt update+install exceeded execution limit; PG_ABSENT verified. Deferral stands WITH evidence — no unexecuted adapter code shipped (honest-status rule). | L-024; DQ4 | R-Q4 updated with attempt log | Working mirror or container DB needed | E017
E017 | 2026-09-11 08:17 | S4 | S4 BUILT: activation funnel service (install->setup->aha->habit@10, idempotent markers, GET /api/funnel), release-tagged error tracker (15-min window, threshold 5, once-per-episode spike -> admin error_spike fan-out, GET /api/errors), approvals metrics + chain CSV import (generic/rivalcpq, %-or-fraction thresholds, NaN guard added to createChain — real bug found in review), reminder nudge route, feature-scoped pause (pricebook¦approvals; pending decisions stay open), decision audit id:outcome, audit ?action= filter, card +Pending approvals +Approvals action, /ui/approvals shell, CI smoke-on-deploy job. | ST-015..020/071/072/086; L-023; v010 | 9 S4 stories Done-in-code (34 pts) | None | E018
E018 | 2026-09-11 08:17 | S4 | D13 TEST GATE HELD — 150 -> 173 tests / 10 suites (+s4 unit, +s4api HTTP, +smoke journey), 100% x4 on all 26 source files, EXIT=0. | D13; L-026; test-run.log 20260911_0817 | Evidence into Traceability col K | None | E019
E019 | 2026-09-11 08:17 | S4 | SMOKE SUITE LIVE (ST-086): tests/smoke.test.ts covers install -> defaults -> quote -> approval -> reminder -> decision -> signed card -> dashboards -> uninstall webhook; npm run test:smoke; CI job smoke-on-deploy on main pushes. | ST-086; .github/workflows/ci.yml | Deploy-time regression net in place | None | E020
E020 | 2026-09-11 08:17 | S4 | S4 CLOSED 9/9 (34/34 pts). Exit criterion "MVP loop usable end-to-end internally" met in-code — the smoke journey IS the MVP loop. Cumulative 30/100 stories, 123/399 pts (30.8% of points). | L-027; rollup S4 row | Cumulative 30/100, 123/399 | Live installs still open (R-Q5/R-Q6) | E021
E021 | 2026-09-11 08:17 | S5 | NEXT: S5 on deck — E-signature + alpha hardening (ST-021..030 + ST-078/079, 12 stories, 50 pts, largest sprint). Await continue signal. | L-028; v011 planned | Tracker v003 planned | None | —
E022 | 2026-09-11 08:52 | S5 | S5 OPENED on continue signal: F3 E-signature full feature set (ST-021..030) + ST-078 first-run checklist + ST-079 empty states — 12 stories, 50 pts, the largest sprint of the plan. | L-029; v011 | S5 in build | None | E023
E023 | 2026-09-11 08:52 | S5 | S5 BUILT: signature domain + service (settings w/ validation matrix, envelopes on server-priced quotes, 1-5 signers, lazy+sticky expiry, void/remind, sha256 doc hash, metrics, generic+rivalsign CSV import), checklist service, 13 new routes incl. PUBLIC /api/esign/sign/:token (identity middleware bypassed — token IS the identity), /ui/sign shell, EMPTY_STATES teaching blocks on all five list endpoints, esign as third pausable feature, three new notification types, esign RBAC triple, card Awaiting-signature count, uuidTokenGen (crypto.randomUUID) for production tokens. | ST-021..030/078/079; L-030; v011 | 12 S5 stories Done-in-code (50 pts) | None | E024
E024 | 2026-09-11 08:52 | S5 | DESIGN RULE FOUND IN BUILD (DQ8): a duplicate-signer test consumed tok-1 before the validation threw — tokens were being minted per-signer during iteration. Reordered to validate-ALL-then-mint: bad input now burns no tokens. Locked with an explicit regression test. | DQ8; s5.test signer validation | createEnvelope hardened | None | E025
E025 | 2026-09-11 08:52 | S5 | NEVER-STRAND EXTENDED (DQ9): esign pause gates ONLY new envelope creation — already-sent links keep viewing and signing (proved over HTTP while paused). Settings snapshot onto envelopes at creation; later changes never mutate in-flight envelopes. | DQ9; s5api pause test | DQ6 pattern now covers 3 features | None | E026
E026 | 2026-09-11 08:52 | S5 | D13 TEST GATE HELD — 173 -> 199 tests / 11 suites (+s5 unit, +s5api HTTP; smoke extended with the esign leg + checklist 7/7 finale), 100% x4 on all 29 source files, EXIT=0. Gap sweep closed ragged-row CSV fallbacks, double-void, no-priceBookId create, missing-name signer, reminder=0, cross-portal store miss. | D13; L-033; test-run.log 20260911_0852 | Evidence into Traceability col K | None | E027
E027 | 2026-09-11 08:52 | S5 | S5 CLOSED 12/12 (50/50 pts). Cumulative 42/100 stories, 173/399 pts (43.4%). Exit criterion "internal alpha: team dogfoods daily" met in-code (full quote->approval->e-sign loop smoke-verified every run); live daily dogfood additionally needs a deployed instance (R-Q5). | L-034; rollup S5 row | Cumulative 42/100, 173/399 | Deployment for live dogfood open | E028
E028 | 2026-09-11 08:52 | S6 | NEXT: S6 on deck — Billing + Quote analytics (ST-041..050 + ST-055..057, 13 stories, 60 pts). Await continue signal. | L-035; v012 planned | Tracker v004 planned | None | —
E029 | 2026-09-11 12:47 | S6 | S6 OPENED on continue signal: F4 Quote analytics (ST-031..040) + E5 Billing (ST-057 trial / ST-058 proration / ST-059 provider routing) — 13 stories, 60 pts. Exit: can charge a test customer; upgrade/downgrade paths work. | L-036; v012 | S6 in build | None | E030
E030 | 2026-09-11 12:47 | S6 | S6 BUILT: analyticsService (always-on capture feeding summary/trends/export/import; alerts gated on setup; setup-independent card count), billingService (14d card-free trial seeded at install, pro $49 / scale $199, 30d-period proration with exact-cents math, ledger, provider interface + HubSpot app-monetization + Stripe clients), 11 new routes, capture hooks on all three quote-pricing paths, won/lost hooks on sign/decline, discount_alert + goal_reached admin fan-out, card +Quotes(7d) + Analytics action. | ST-031..040/057..059; L-037; v012 | 13 S6 stories Done-in-code (60 pts) | None | E031
E031 | 2026-09-11 12:47 | S6 | DQ10 LOCKED (ST-038): analytics pause blocks the DASHBOARDS, never the capture — gating capture would punch holes in history, the exact data loss the story forbids. Deliberate inversion of the DQ6 write-gate pattern; proved over HTTP (quote priced while paused appears after resume). Capture is also setup-independent so history starts day one. | DQ10; s6api pause test | Pause taxonomy now: write-gate (pricebook/approvals/esign) vs read-gate (analytics) | None | E032
E032 | 2026-09-11 12:47 | S6 | DQ11 LOCKED (ST-058/059): channel chosen at subscribe routes every charge — marketplace -> HubSpot app-monetization (marketplace-mandated), direct -> Stripe; plan changes reuse the channel. Provider failure = typed retryable 502 persisting NOTHING (account stays trial, ledger stays empty — verified). Proration: fixed 30d period, remaining-days fraction, exact cents asserted (day-10 pro->scale credit 3267 / charge 13267 / net 10000; day-15 downgrade net -7500 credits WITHOUT a provider call; beyond-period clamps 0/0/0). | DQ11; s6 proration + failure tests | Billing rails routed + failure-safe | None | E033
E033 | 2026-09-11 12:47 | S6 | D13 TEST GATE HELD — 199 -> 221 tests / 14 suites, 100% x4 on 31 source files, EXIT=0. Smoke now charges the test portal and upgrades mid-cycle (3-entry ledger). Gap sweep closed wired lambdas end-to-end through wire(), pre-setup 404s over HTTP, per-column ragged fallbacks, empty-discount parse. | D13; L-040; test-run.log 20260911_1247 | Evidence into Traceability col K | None | E034
E034 | 2026-09-11 12:47 | S6 | S6 CLOSED 13/13 (60/60 pts). Cumulative 55/100 stories, 233/399 pts (58.4%) — past the halfway line on points. Exit criterion met in-code via smoke; LIVE charging requires provider credentials (marketplace listing approval / Stripe keys) — new RAID item R-Q10, Senthil. | L-041; rollup S6 row | Cumulative 55/100, 233/399 | R-Q10 opened | E035
E035 | 2026-09-11 12:47 | S7 | NEXT: S7 on deck — Private beta / design partners (ST-073..077, 5 stories, 15 pts). Await continue signal. | L-042; v013 planned | Tracker v005 planned | None | —
E036 | 2026-09-13 10:26 | S7 | S7 OPENED. Scope re-read from Full_Backlog before planning: S7 is ST-060..064 (dunning, plan limits, invoices, cancellation, scope disclosure) — NOT the beta-instrumentation set forecast at S6 close. Backlog stays the single source of truth; the forecast was wrong and the backlog won. 5 stories, 15 pts. | L-043; v013 | S7 in build | None | E037
E037 | 2026-09-13 10:26 | S7 | S7 BUILT: billing dunning state machine (past_due -> read_only, 7-day grace, 3-notice cap at one per day, recovery re-charge), plan quotas with 80/100% tiers wired to analytics period counts, invoice + tax-profile subsystem with plain-text receipts, cancellation flow with save-offer and fixed exit survey, and a code-enforced OAuth scope registry with a two-way audit and generated marketplace disclosure. 11 new routes; 2 new request gates on every quote-creating path. | ST-060..064; L-044; v013 | 5 S7 stories Done-in-code (15 pts) | None | E038
E038 | 2026-09-13 10:26 | S7 | DQ12 LOCKED: billing read-only gates WRITES only. Dunning and cancellation refuse quote creation with 402 BILLING_READ_ONLY, but dashboards, exports, invoices and billing pages stay fully readable — a customer who stops paying must still see and export their own data, and locking reads at cancellation would be a data-portability problem as well as hostile. | DQ12; s7api dunning + cancel tests | Gate taxonomy: pause (feature) vs billing (write-only) vs quota (write-only) | None | E039
E039 | 2026-09-13 10:26 | S7 | DQ13 LOCKED: least privilege is enforced in code. SCOPE_REGISTRY maps each requested scope to feature + stories + the call using it; auditScopes flags unjustified (over-asking) AND missing (a feature would 403 live); the marketplace disclosure string is generated from the registry so published copy cannot drift from config. A test asserts leastPrivilege against the real loadConfig output — requesting a new scope without justifying it fails the build. | DQ13; s7 scope tests; GET /api/scopes | S8 note: sync write scope must be registered in the same commit that requests it | None | E040
E040 | 2026-09-13 10:26 | S7 | TWO DEFECTS FOUND BY TESTS, both fixed: (1) usage percentage used Math.round, so 159/200 displayed 80% and fired the upgrade warning one quote early — switched to floor so the displayed pct and the tier always agree; (2) the new billing/quota gates had been attached to a route path that does not exist (/api/quotes/request-approval), silently leaving /api/approvals/requests ungated — caught only because the test asserted 402 on EVERY quote-creating path rather than the one route in front of me. | L-047; s7.test + s7api.test | Both regressions locked by assertions | None | E041
E041 | 2026-09-13 10:26 | S7 | D13 TEST GATE HELD — 221 -> 246 tests / 16 suites, 100% x4 on 33 source files, EXIT=0. Smoke extended: invoice count after subscribe+upgrade, dunning lockout with reads surviving, recovery, post-recovery quote, scope audit clean. S7 CLOSED 5/5 (15/15 pts); cumulative 60/100 stories, 248/399 pts (62.2%). | D13; L-047/L-048; test-run.log 20260913_1026 | Cumulative 60/100, 248/399 | Live design-partner recruitment still external (R-Q5) | E042
E042 | 2026-09-13 10:26 | S8 | NEXT: S8 — Beta iteration + Deal/line-item sync (22 stories, 87 pts), the largest remaining sprint. Await continue signal. | L-049; v014 planned | Tracker v006 planned | None | —
E043 | 2026-09-13 10:38 | S8 | S8 OPENED — 22 stories / 87 pts, 45% larger than any prior sprint, spanning four epics. Planned as four tranches (F5 sync 42, E6 trust 18, E7 founder ops 16, EQ performance 11) and executed in that order. | L-050; v014 | S8 in build | None | E044
E044 | 2026-09-13 10:38 | S8 | S8 BUILT: syncService + trust + founderAnalytics (three new services, ~1,400 lines), 11 new routes, latency-sampling middleware, /ready + /internal/drain lifecycle, and a breaker-guarded DealWriter wired against the HubSpot CRM v3 API in index.ts. | ST-041..050/065/066/067/070/073..077/087/088/092; L-051 | 22 S8 stories Done-in-code (87 pts) | None | E045
E045 | 2026-09-13 10:38 | S8 | SCOPE EXPANSION HANDLED PER DQ13: sync needs crm.objects.deals.write and crm.objects.line_items.write. Both were added to SCOPE_REGISTRY with feature, stories, using call and justification IN THE SAME CHANGE that added them to the config scope string. The S7 tests that pinned a 3-scope registry failed immediately on the change and were updated deliberately — exactly the drift alarm DQ13 was built to raise. | DQ13; scopes.ts; s7/s7api assertion updates | Registry now 5 scopes, leastPrivilege still clean | Listing review will scrutinise the write scopes | E046
E046 | 2026-09-13 10:38 | S8 | DQ14 LOCKED: sync correctness rests on a deterministic idempotency key (portal:deal:quoteHash). Re-pushing an unchanged quote is a no-op — the failure mode that silently corrupts a CRM is a retry after a timeout, and this closes it. Paused portals QUEUE runs and drain on resume; dropping loses work silently, writing violates the pause. | DQ14; s8 idempotency + pause tests | Third pause semantic: write-gate (S3/S5), read-gate (S6), queue (S8) | None | E047
E047 | 2026-09-13 10:38 | S8 | DQ15 + DQ16 LOCKED. DQ15: the trust document is generated from the constants the code uses, and unmet controls publish as PARTIAL with a named owner — SEC-03 (vault) and SEC-04 (at-rest) are outstanding, and a test asserts the outstanding list is non-empty so silently claiming compliance fails the build. DQ16: backoff alone still issues a full retry series per request against a downed dependency, so a circuit breaker now fronts platform writes (5 failures -> open 30s -> half-open single trial). | DQ15/DQ16; trust.ts; s8 tests | Trust page is honest by construction | R-Q11 opened for vault/at-rest | E048
E048 | 2026-09-13 10:38 | S8 | TWO DEFECTS FOUND BY TESTS, both fixed: (1) a retried run left the prior run still queued/failed, so a drained queue never emptied and the same run would re-drain on every resume — retry now marks the prior run superseded; (2) the health band checked score>=70 before the configured churn floor, making any churnRiskScore above 70 a silent no-op — the configured floor now wins, because raising it is a deliberate decision to treat more accounts as at risk. | L-055; s8.test | Both locked by assertions | None | E049
E049 | 2026-09-13 10:38 | S8 | D13 TEST GATE HELD — 246 -> 289 tests / 18 suites, 100% x4 on 38 source files, EXIT=0. ST-088 load test drives 250 mixed requests through the real stack: all 200s, every p95 budget held, 50 deals synced exactly once with zero duplicate writes. S8 CLOSED 22/22 (87/87 pts); cumulative 82/100 stories, 335/399 pts (84.0%). | D13; L-055/L-056; test-run.log 20260913_1038 | Cumulative 82/100, 335/399 | None | E050
E050 | 2026-09-13 10:38 | S9 | NEXT: S9 — Marketplace review prep (7 stories, 30 pts). Await continue signal. | L-057; v015 planned | Tracker v007 planned | None | —
E051 | 2026-09-13 10:56 | S9 | S9 OPENED — Marketplace review prep (ST-068/069/089/090/091/093/094, 7 stories, 30 pts). Two stories were identified at planning as not completable from code alone: ST-068 needs a commissioned external pen test and ST-094 needs a live install to capture assets. Both were planned to produce everything that CAN be produced now, and flagged rather than quietly marked done. | L-058; v015 | S9 in build | ST-068 / ST-094 external deps known up front | E052
E052 | 2026-09-13 10:56 | S9 | S9 BUILT: privacy service (export bundle + manifest, two-step deletion, backup/restore/drill), 8 portal-source adapters, review service (WCAG AA checker + accessible shell renderer + security evidence pack), 9 new routes, all five UI shells regenerated through the accessible renderer, plus listing copy variants and the asset brief. | L-059; v015 | 5 Done + 2 Partial | None | E053
E053 | 2026-09-13 10:56 | S9 | DQ17 LOCKED: deletion is two-step and token-confirmed (15-minute window, cancellable, owner-only) and returns a receipt of the counts destroyed; export is available to any admin so a customer can always take their data before deciding. A single unguarded wipe endpoint is an outage waiting to happen, and review flags irreversible actions without confirmation. | DQ17; s9/s9api deletion tests | Data rights are self-serve and reversible up to the confirm | None | E054
E054 | 2026-09-13 10:56 | S9 | DQ18 LOCKED: review evidence is generated and asserted, never narrated. The a11y checker runs over the HTML the app actually serves and is itself tested against deliberately broken HTML per rule class; the security pack states no external pen test has been commissioned; the restore drill reports non-restorable sources as SKIPPED. Overclaiming in any of the three would require deleting a test. | DQ18; auditHtml, securityEvidence, drill | Third generated-evidence mechanism after DQ13 (scopes) and DQ15 (trust) | None | E055
E055 | 2026-09-13 10:56 | S9 | DEFECT FOUND BY SMOKE (L-062): BackupService.drill purged EVERY source before restoring, but only sources with a restore path came back — so a drill on a live portal permanently destroyed the price-book catalog. The smoke checklist falling from 7/7 to 5/7 exposed it; no unit test would have, because each unit passed in isolation. Fixed to purge only restorable sources, with a regression test asserting the catalog survives a drill intact. | L-062; src/services/privacy.ts | The backup feature was itself a data-loss bug for one release-candidate hour | None | E056
E056 | 2026-09-13 10:56 | S9 | ST-068 PARTIAL and honestly marked: the evidence pack documents 10 abuse cases with mitigations — 8 proven by automated tests here, 1 needing a scheduled manual owner, 1 (infrastructure-level) needing an external tester. QuoteFlow has not commissioned an external penetration test, and securityEvidence().statement says exactly that. R-Q12 opened. | ST-068; R-Q12; GET /api/review/security | Story marked Partial, not Done | External pen test outstanding | E057
E057 | 2026-09-13 10:56 | S9 | D13 TEST GATE HELD — 289 -> 316 tests / 20 suites, 100% x4 on 42 source files, EXIT=0. ST-091 chaos asserts six degradation properties under a simulated platform outage. S9 CLOSED: 5 Done (17 pts) + 2 Partial (13 pts executed, externally blocked). Cumulative strictly-Done 87/100 stories, 352/399 pts (88.2%). | D13; L-063/L-064; test-run.log 20260913_1056 | Cumulative 87/100, 352/399 strict | ST-094 capture blocked on R-Q5 | E058
E058 | 2026-09-13 10:56 | S10 | NEXT: S10 — Review remediation + docs (7 stories, 24 pts): help center with 15 articles, in-app chat, demo/sandbox mode, status page, pricing page, security/trust page, submission dry-run. Await continue signal. | v016 planned | Tracker v008 planned | None | —
E059 | 2026-09-13 11:11 | S10 | S10 OPENED — Review remediation + docs (ST-080/081/083/084/095/096/097, 7 stories, 24 pts). Unlike prior sprints this is mostly new public-facing surface: documentation, support, status, pricing, trust and the submission dry-run. | L-065; v016 | S10 in build | None | E060
E060 | 2026-09-13 11:11 | S10 | S10 BUILT: help centre (15 articles + ranked search), support service with business-hours SLA maths, public surfaces module (status + incident templates, generated pricing and trust pages, demo seed, submission dry-run), 16 new routes. The /api identity middleware now bypasses /api/help/* and /api/public/* alongside the signer surface — a reviewer or prospective customer must be able to read docs, status, pricing and trust before installing anything. | L-066; v016 | 7 S10 stories Done-in-code (24 pts) | None | E061
E061 | 2026-09-13 11:11 | S10 | DQ19 LOCKED: the pricing page, its FAQ and the trust page are GENERATED from the constants the product runs on. A published price that disagrees with what the billing code charges is a promise the product breaks, and a hand-maintained page drifts on the first pricing change. Tests assert each published value equals its source constant, so changing a price without updating the page is impossible. | DQ19; s10 pricing/trust tests | Fourth generated-evidence mechanism (DQ13 scopes, DQ15 trust, DQ18 review, DQ19 pages) | None | E062
E062 | 2026-09-13 11:11 | S10 | DQ20 LOCKED: the support SLA is measured in BUSINESS hours (09:00-17:00 UTC, Mon-Fri). A naive elapsed-hours timer would mark a Friday-evening message breached by Saturday lunchtime and make the team look non-compliant against a promise nobody made. Equally, conversations still unanswered past their due time count as breaches in the compliance figure — a breach cannot be hidden by never replying. | DQ20; businessMsBetween/addBusinessMs tests | Weekend message answered Monday 10:00 = 1 business hour | None | E063
E063 | 2026-09-13 11:11 | S10 | DQ21 LOCKED: the submission dry-run acts as the second reviewer by reading live system state — the scope audit result, the accessibility check result, the real article count — not a hand-kept checklist. Items that need a human are reported as MANUAL and listed as blockers, never counted as passes. Current position: 12 pass, 0 fail, 2 manual (R-Q12 external pen test, R-Q5 asset capture). | DQ21; GET /api/review/submission | readyToSubmit true with both manual items visible | Two manual items remain | E064
E064 | 2026-09-13 11:11 | S10 | TWO CORRECTIONS DURING BUILD: (1) my own test arithmetic for the SLA was wrong — Monday 16:00 plus 4 business hours is Tuesday 12:00, not 11:00; the implementation was correct and the test was fixed, which is the right way round; (2) coverage found dead code left in the submission route (a conditional spread that always produced an empty object) and it was deleted. Writing the demo-seed error-path test also surfaced that seeding twice would double every dashboard number, so a second seed is now refused. | L-070; s10.test; src/app.ts | Dead code removed; double-seed protection added | None | E065
E065 | 2026-09-13 11:11 | S10 | D13 TEST GATE HELD — 316 -> 352 tests / 22 suites, 100% x4 on 46 source files, EXIT=0. S10 CLOSED 7/7 (24/24 pts). Cumulative strictly-Done 94/100 stories, 376/399 pts (94.2%). Remaining: S11 launch (3 stories / 8 pts), S12 post-launch (1 story / 2 pts), plus the two S9 partials pending R-Q12 and R-Q5. | D13; L-070/L-071; test-run.log 20260913_1111 | Cumulative 94/100, 376/399 | None | E066
E066 | 2026-09-13 11:25 | S11 | S11 OPENED — Launch (ST-082 in-app review ask, ST-098 launch-day runbook, ST-100 design-partner reviews), 3 stories, 8 pts. | L-072; v017 | S11 in build | None | E067
E067 | 2026-09-13 11:25 | S11 | S11 BUILT: reviewAsk service (decision engine + state), launch service (preflight, rollback procedure, comms tree, partner pipeline, outreach sequence), 7 routes, docs/launch-runbook.md. | L-073; v017 | 3 S11 stories Done-in-code (8 pts) | None | E068
E068 | 2026-09-13 11:25 | S11 | DQ22 LOCKED: the review ask only fires when the portal is demonstrably happy (aha reached, 5+ quotes in 30 days, no unresolved error, no open support conversation, billing healthy), with a lifetime cap of 2 asks 90 days apart, a 30-day snooze and a PERMANENT decline. Explicitly NOT implemented: sentiment gating or routing unhappy users away from the listing — that is review-gating and breaches marketplace rules. The prompt instead invites unhappy users to reply with what is missing. | DQ22; s11 review tests | A prompt at the wrong moment costs more than the rating is worth | None | E069
E069 | 2026-09-13 11:25 | S11 | DQ23 LOCKED: the runbook is executable. Preflight actually runs a restore drill rather than trusting a checkbox; every rollback step carries a verification, because a step you cannot verify is a wish; the order stops traffic before redeploying and checks data integrity afterwards; the comms tree names audience, owner and deadline per trigger, and data-integrity comms are never templated. The markdown runbook and GET /api/ops/runbook serve the same constants so they cannot drift apart. | DQ23; rollback/comms tests; docs/launch-runbook.md | 77-minute rollback budget asserted | None | E070
E070 | 2026-09-13 11:25 | S11 | DQ24 LOCKED: the partner pipeline counts SCHEDULED reviews, not intentions. A test asserts that ten identified names count as zero and ten contacted names still count as zero — only a booked call or beyond counts toward the target of ten, and a decline drops out. The story asked for reviews scheduled, and that is what the number means. | DQ24; pipeline honesty test | Ten names in a spreadsheet is not ten scheduled reviews | None | E071
E071 | 2026-09-13 11:25 | S11 | D13 TEST GATE HELD — 352 -> 381 tests / 24 suites, 100% x4 on 48 source files, EXIT=0. S11 CLOSED 3/3 (8/8 pts); cumulative strictly-Done 97/100 stories, 384/399 pts (96.2%). HONEST STATUS: the launch preflight returns NO_GO in this environment because billing runs against provider stubs (PRE-07 / R-Q10). The smoke test asserts the no_go rather than passing a flag to make it green — the flag exists only so the go path is also covered. | D13; L-077; test-run.log 20260913_1125 | Cumulative 97/100, 384/399 | Launch blocked on R-Q10 billing credentials | E072
E072 | 2026-09-13 11:34 | S12 | S12 OPENED — the final sprint: ST-099 post-launch listing SEO iteration 1 from search-term data (1 story, 2 pts). | L-078; v018 | S12 in build | None | E073
E073 | 2026-09-13 11:34 | S12 | S12 BUILT: listingSeo service (validated CSV import, five-verdict term classification, ranked recommendations with evidence, supported/forbidden vocabulary guards, length-capped copy proposals), 2 routes, docs/listing-seo-iteration-1.md. | L-079; v018 | 1 S12 story Done-in-code (2 pts) | None | E074
E074 | 2026-09-13 11:34 | S12 | DQ25 LOCKED: an SEO recommendation may never propose a claim the product does not support. High-demand unsupported terms (contract lifecycle management, ERP, invoicing automation) are recorded as PRODUCT DEMAND and explicitly excluded from listing copy. Ranking for something the product does not do converts once, churns, and is a false claim in a marketplace listing. | DQ25; isSupportedTerm + unsupported-demand tests | Sixth generated/guarded-claim mechanism | None | E075
E075 | 2026-09-13 11:34 | S12 | DEFECT FOUND IN BUILD: vocabulary matching used substring includes(), so the forbidden claim "erp" matched inside "enterprise" and rejected a legitimate search term. The same flaw in the other direction would have let "sign" match inside "design" and produce a false claim. Replaced with word-boundary phrase matching, with tests locking BOTH directions. Separately, the CSV importer treated an empty cell as zero because Number("") is 0; an empty cell is now rejected as missing data. | L-081; src/services/listingSeo.ts | Both locked by assertions | None | E076
E076 | 2026-09-13 11:34 | S12 | D13 TEST GATE HELD — 381 -> 397 tests / 26 suites, 100% x4 on 49 source files, EXIT=0. S12 CLOSED 1/1 (2/2 pts). | D13; L-082; test-run.log 20260913_1134 | Final suite green | None | E077
E077 | 2026-09-13 11:34 | — | PROGRAMME CLOSED. 12 sprints executed from S1 (foundation) to S12 (post-launch SEO). 98/100 stories Done with automated evidence; 2 Partial (ST-068 external pen test, ST-094 asset capture) left Partial rather than rounded up to Done. 386/399 points. 25 design decisions logged with the test that locks each. Eleven defects caught by tests, two of which would have destroyed customer data. Six external items remain and none are code — the launch blocker is R-Q10 (billing credentials), after which GET /api/ops/launch-preflight goes green. Full close-out, including what is NOT done and the recommended order of next steps, is on the Programme_Closeout sheet of product workbook v018. | L-083; v018 Programme_Closeout | Handover complete | Six external items open, all owned by Senthil | —
E078 | 2026-09-13 11:51 | REVIEW | COLD REVIEW OPENED. The 12-sprint plan was exhausted; rather than invent a sprint, the portfolio protocol applied — QuoteFlow had never had an adversarial review, and every sibling's first review found serious defects in code already at 100% coverage. | L-084; v019 | Pass 1 in progress | None | E079
E079 | 2026-09-13 11:51 | REVIEW | FOUR CRITICAL DEFECTS. F-Q01: delete-my-data purged 8 of 11 sources — notifications, support conversations and review state survived a deletion the endpoint described as permanent, and were missing from export and backup so the restore drill stayed green while losing them. F-Q02: no runnable entrypoint existed — start() was never called and there was no npm start, so the rollback runbook step "redeploy and curl /health" could not have been executed. F-Q03: identity was two unsigned headers, so anyone reaching the API could claim owner of any portal. F-Q04: trial_expired reported readOnly:false, making the 14-day trial decorative. | Review_Findings F-Q01..F-Q04 | All fixed with regressions | None | E080
E080 | 2026-09-13 11:51 | REVIEW | FOUR FURTHER DEFECTS. F-Q05 OAuth callback accepted any state (CSRF) — now signed over a nonce with a 10-minute TTL. F-Q06 six async handlers had no try/catch and Express 4 drops rejected promises, hanging the request with no status — a class that hides from a green suite because the test times out rather than fails. F-Q07 the SEO corpus was process-wide, so one tenant's import replaced every other tenant's report. F-Q08 audit, analytics and sync ledgers were unbounded. | Review_Findings F-Q05..F-Q08 | All fixed with regressions | None | E081
E081 | 2026-09-13 11:51 | REVIEW | TWO SIBLING CLASSES CHECKED AND VERIFIED ABSENT: the CSV importer is a proper quote-aware state machine (not the naive split that bit OnCall/EngageOS/MeetSync), and realSleep is genuinely wired into PlatformClient in production (not the no-op backoff that bit VoiceBridge). Recorded so a later pass does not re-litigate them. | Review_Findings verified-absent table | No action | None | E082
E082 | 2026-09-13 11:51 | REVIEW | PASS 1 CLOSED. 397 -> 410 tests / 27 suites, 100% x4, EXIT=0, dist/server.js build-verified. Story position deliberately unchanged (98 Done / 2 Partial) — this changed correctness, not scope. L-Q1 logged: twelve sprints closed green at 100% coverage and the first review still found a product that could not boot and a deletion endpoint that lied to the customer. NEXT: pass 2 over untouched modules, and an artifact-gap audit — the published 400-day retention policy and the backup drill still sit on in-memory stores with no DB schema behind them (R-Q4). | L-086/L-087; test-run.log 20260913_1151 | Cumulative unchanged 98/100 | R-Q4 now reads as an artifact gap, not just a deferral | —
E083 | 2026-09-13 12:03 | REVIEW | PASS 2 OPENED with a different question from pass 1: not "what defect class might be in this code" but "does every published claim have code behind it, and does every referenced artifact exist". Four of the six findings came straight out of that reframing. | L-088; v020 | Pass 2 in progress | None | E084
E084 | 2026-09-13 12:03 | REVIEW | F-Q09 CRITICAL — the trust page published a retention schedule (analytics 400 days, sync 180, audit 400, billing 2555) and nothing anywhere enforced it. The only deletion path was uninstall, so a live portal accumulated records forever while GET /api/public/trust told customers and reviewers they aged out. Fixed with a sweep that reads each store's OWN published window, plus a drift gate so the policy and the sweepers cannot diverge. | F-Q09; review2 + review1 HTTP test | Published policy is now a shipped feature | None | E085
E085 | 2026-09-13 12:03 | REVIEW | THREE MORE CLAIMS WITH NOTHING BEHIND THEM. F-Q10: SEC-05 said token-shaped values are redacted before logging; redactSecrets had zero call sites — a control that existed as a tested function and a sentence. F-Q11: ST-070 said "backoff + circuit breaker on platform APIs"; the breaker fronted only deal writes, so every read hammered a dependency already known down. F-Q12: the runbook's rollback step 4 pointed at a blue/green deploy workflow nobody had written. | F-Q10/F-Q11/F-Q12 | All three now real | None | E086
E086 | 2026-09-13 12:03 | REVIEW | F-Q13 — no database schema existed behind the retention policy, the backup drill or the encryption-at-rest claim: every store was in-memory, so the drill round-tripped process memory. R-Q4 had been logged as "Postgres deferred" when it was really an artifact gap. Four ordered migrations added (one table per data-flow node, ON DELETE CASCADE from portals so F-Q01 deletion is real at the schema level, the indexes the retention sweep needs, and a unique idempotency index for sync). F-Q14 also fixed: signature verification rejected stale timestamps but not future ones, leaving far-future-signed requests replayable forever. | F-Q13/F-Q14; migrations/001-004 | Schema exists; adapter still pending (R-Q4 code half) | R-Q4 reclassified from deferral to gap | E087
E087 | 2026-09-13 12:03 | REVIEW | PASS 2 CLOSED. 410 -> 424 tests / 28 suites, 100% x4, EXIT=0. DQ26 locked: every fix ships with a DRIFT GATE, not only a regression — the sweepers must match the published retention policy and the migrations must match the published store list, or the build fails. L-Q2 logged: the generated-evidence mechanisms built in S7-S12 worked for the claims they covered, but nothing covered claims made in prose inside DATA_FLOW, SECURITY_CONTROLS and the story text, which is exactly where all four hollow claims lived. | L-090/L-091; test-run.log 20260913_1203 | Cumulative unchanged 98/100 | Pass 3 + Postgres adapter next | —
E088 | 2026-09-13 16:25 | REVIEW | PASS 3 OPENED over the modules passes 1 and 2 never touched: help centre, support, public pages, founder ops, launch. Same question as pass 2, applied to surfaces rather than claims. | L-092; v021 | Pass 3 in progress | None | E089
E089 | 2026-09-13 16:25 | REVIEW | F-Q15 and F-Q16 - two surfaces that read as live and were wired to literals. The public status page took breakerOpen:false and recentSyncFailures:0 as constants, so during a real HubSpot outage it would have shown deal sync "operational" while every push failed; its own component copy describes a breaker-open state that was unreachable. Launch preflight hardcoded readinessOk:true, so PRE-03 could not fail even while the app was draining. Both now read real signals. | F-Q15/F-Q16; review2 pass-3 block | Status page and preflight are honest | None | E090
E090 | 2026-09-13 16:25 | REVIEW | F-Q17 CRITICAL - nine vendor-only surfaces sat behind ordinary tenant RBAC: the usage heatmap aggregating EVERY portal, the process-wide latency report, founder alert thresholds, launch preflight, the runbook (which states the drain token equals the app client secret), and the design-partner pipeline holding prospect names and contact emails. Any portal owner could read other tenants aggregates and the vendor sales pipeline. Now gated on a timing-safe operator token on top of tenant identity, failing CLOSED when unset. | F-Q17; requireVendor; review2 tenancy tests | Vendor and tenant planes separated | Operator token must be set in deployment config | E091
E091 | 2026-09-13 16:25 | REVIEW | PASS 3 CLOSED. 424 -> 428 tests / 28 suites, 100% x4, EXIT=0. DQ27 locked. L-Q3 logged: across passes 2 and 3 the same shape appeared seven times - a surface or document that reads as live and authoritative while wired to a literal, a claim with no call path, or an artifact nobody wrote. Coverage cannot catch any of it because the constant executes. NEXT: the Postgres adapter behind the pass-2 migrations (R-Q4 code half). | L-093/L-094; test-run.log 20260913_1625 | Cumulative unchanged 98/100 | R-Q4 code half outstanding | -
E092 | 2026-09-13 16:36 | R-Q4 | POSTGRES ADAPTERS BUILT for the three retention-critical stores (audit, analytics, sync) against the pass-2 tables, implementing the existing interfaces so no call site changes. This closes the code half of R-Q4: pass 2 delivered the schema, and until now nothing connected to it. | L-095; v022 | Adapters exist | None | E093
E093 | 2026-09-13 16:36 | R-Q4 | PROVED BY EXECUTION. A single store-contract specification now runs twice: against the in-memory stores and against the adapters executing REAL SQL on a REAL Postgres engine (pg-mem, in process) with the REAL migration files applied. Two durability tests drop every in-process cache the way a restart would and assert both that records return and that a purge deleted ROWS rather than cache - F-Q01 promised the customer deletion is permanent, and that promise has to hold at the database. The pass-2 retention sweep is part of the shared contract, so the policy now holds on durable storage too. | L-096; tests/storeContract.test.ts | 439 tests / 29 suites 100% x4 | None | E094
E094 | 2026-09-13 16:36 | R-Q4 | CONSTRAINT STATED UP FRONT, NOT DISCOVERED LATER: the store interfaces are synchronous because ~40 call sites read them inside request handlers written against a synchronous contract, so each adapter uses a write-through cache and only one process may write - a second would not see another writes until hydrate(). R-Q13 opened for the async interface migration, which is a larger change than a review pass should make. Six stores remain in memory; their tables exist and the contract suite is the pattern for adapting them. | L-097; R-Q13 | Honest scope boundary | R-Q13 open; live Postgres run still pending an instance | -
E095 | 2026-09-13 16:41 | R-Q4 | REMAINING SIX STORES ADAPTED: catalog, signatures, billing, notifications, support and review state. All nine stores now have a Postgres implementation, each behind the existing synchronous interface so no call site changed. | L-098; v023 | Nine of nine adapted | None | E096
E096 | 2026-09-13 16:41 | R-Q4 | F-Q18 FOUND WHILE WRITING PgCatalogStore: the catalog holds six kinds of record and only three had tables. Bundles and pricing rules would have been silently dropped by a Postgres-backed catalog - quotes would simply have priced differently after the migration, with no error anywhere. Pause flags had nowhere to persist, so a feature an admin deliberately paused would have re-enabled itself on the next restart. Migration 005 adds all three; the durability test asserts a paused feature stays paused across a reload. The pass-2 drift gate had asserted "every published store has a table" and the catalog passed on three of its six record types - the gate checked STORE granularity when the risk lives at FIELD granularity. | F-Q18; migrations/005 | Fixed and covered | Drift gates need field-level assertions | E097
E097 | 2026-09-13 16:41 | R-Q4 | SECOND CONTRACT SUITE: the six stores run against in-memory and against real SQL on a real engine with all five migrations - restart survival, purge-deletes-rows, optional fields both absent and present, untouched portals reading clean, and JSONB decoding from both object and text drivers. 439 -> 457 tests / 30 suites, 100% x4, EXIT=0. Still open: R-Q13 (async interfaces / single writer), a live Postgres instance, and wiring the adapters into index.ts behind a DATABASE_URL switch. | L-100; test-run.log 20260913_1641 | 457 tests / 30 suites | R-Q13; adapters not yet wired into boot | -
E098 | 2026-09-13 16:53 | R-Q4 | CALL-PATH GAP CLOSED. The schema and all nine adapters existed while index.ts still always built in-memory stores - the adapters had no caller, which is precisely the shape of F-Q10 (a control nothing invoked) and F-Q02 (a server nobody started). buildStores() now chooses from DATABASE_URL and wire() returns the chosen backend so a deploy can assert it rather than hope; server.ts applies all five migrations in order before listening. | L-101; v024 | Adapters reachable at boot | None | E099
E099 | 2026-09-13 16:53 | R-Q4 | PROVED BY DRIVING THE REAL APP. tests/pgBoot.test.ts runs a full quoting journey over HTTP against Postgres-backed stores and then checks the ROWS (price_books, price_book_items, quote_events, audit_log, portal_settings), boots a SECOND process against the same database and asserts price books, users and a paused feature all survive - the F-Q18 pause-flag defect now has an application-level regression. Hydration is proved to happen once per portal by counting SELECTs, and a hydration failure to return 500 rather than hang, applying F-Q06 discipline to the newly async identity middleware. | L-102; tests/pgBoot.test.ts | 465 tests / 31 suites 100% x4 | None | E100
E100 | 2026-09-13 16:53 | R-Q4 | GAP NAMED AT THE SEAM: approvals is still in-memory. Its tables exist from migration 002 but no adapter writes them, so approval requests do not survive a restart. buildStores() says so in a comment at the point of choice and a test asserts the class, so it cannot quietly start looking persistent - the opposite of how F-Q01 and F-Q18 were found. Remaining: PgApprovalStore, R-Q13 async interfaces (single writer today), and a live Postgres run. | L-103; R-Q13 | Honest boundary | Approvals not durable; R-Q13 open | -
E101 | 2026-09-13 17:23 | R-Q14 | PgApprovalStore written - the last store to reach Postgres. Chains and requests persist, and a decision is saved by UPDATE on conflict so approving amends the request rather than inserting a duplicate. This one mattered more than most: an approval decision is the evidence a discount was authorised and the audit trail points at it, so losing it would have left audit entries referring to records that no longer exist. | L-104; v025 | Every store durable | None | E102
E102 | 2026-09-13 17:23 | R-Q14 | PROVED TWICE. The contract suite now covers chains and requests against both backends (round-trip, update-not-duplicate, purge, portal scoping, restart survival). pgBoot drives a real over-threshold quote through the approval flow over HTTP - the discount coming from a pricing rule, the way the product actually produces one - approves it, then boots a SECOND process against the same database and asserts the status, approver and comment all survive. The boot test also asserts the class is PgApprovalStore, so the gap cannot silently reopen. R-Q14 closed; R-Q13 and a live Postgres run remain. | L-105/L-106; test-run.log 20260913_1723 | 466 tests / 31 suites 100% x4 | R-Q13 open | -
E103 | 2026-09-13 17:30 | R-Q13 | JUDGEMENT RECORDED: the full async store migration touches roughly 40 call sites across services and routes. Attempting it in one pass would most likely have left the repo half-migrated with a red suite, which is worse than not starting. Instead the DANGEROUS half of R-Q13 was closed: breaking the single-writer rule used to fail silently - a second instance serving stale reads from its own cache and overwriting the first, with no error and no log. | DQ31; L-107 | Scope judgement | Async migration still open | E104
E104 | 2026-09-13 17:30 | R-Q13 | WRITER LEASE SHIPPED. Migration 006 adds writer_lease; an instance must hold it to write and one that cannot prints a message naming the current holder and R-Q13, then exits. A heartbeat renews it every 10s; a lease expires after 30s so a crashed holder is taken over rather than blocking the service; an instance that loses the lease learns it from its own heartbeat and exits rather than writing on. Six tests cover refusal, self-reacquire, expiry takeover, renewal, loss detection and release. 472 tests / 32 suites, 100% x4. | L-108; tests/writerLease.test.ts | Silent divergence impossible | R-Q13 async migration still open | -
E105 | 2026-09-13 18:48 | R-Q13 | PHASE 1 - THE CASCADE. Every store migration was blocked on one thing: privacy export, the backup drill and the retention sweep all read stores synchronously, so no store could go async until they did. That change is now made once: PortalDataSource, PrivacyService, BackupService and RetentionService are async, along with the six routes that call them, each wrapped in the F-Q06 guard so a rejection returns a status rather than hanging the request. | L-109; v027 | Cascade resolved | None | E106
E106 | 2026-09-13 18:48 | R-Q13 | NOTHING MOVED, WHICH IS THE POINT. The new signatures accept a value or a promise, so the synchronous stores are untouched and the suite stayed at 472 tests / 32 suites, 100% x4, EXIT=0. Phase 2 - converting the stores and dropping their write-through caches, which is what finally permits more than one writer and makes the lease advisory rather than load-bearing - is now LOCAL work per store rather than a repo-wide change. Staged deliberately: a green checkpoint is worth more than a large half-finished change. | L-110/L-111; test-run.log 20260913_1848 | 472 tests unchanged | Phase 2 open; live Postgres run open | -
E107 | 2026-09-13 18:59 | R-Q13 | PHASE 2 STORE 1 OF 9. Review state chosen first because it was the smallest complete vertical slice - three source call sites - so the pattern is established at the lowest risk. ReviewStore is async and PgReviewStore no longer keeps a write-through cache: reads go to Postgres. | L-112; v028 | Pattern established | None | E108
E108 | 2026-09-13 18:59 | R-Q13 | CROSS-INSTANCE PROOF. Two app instances against one database, both already running, no restart and no re-hydration: instance one records a review outcome and instance two reads it immediately. That is precisely the constraint the writer lease exists to guard, and for this store it is now gone. | L-113; tests/pgBoot.test.ts | 473 tests / 32 suites 100% x4 | None | E109
E109 | 2026-09-13 18:59 | R-Q13 | SELF-INFLICTED REGRESSION, CAUGHT BY THE GATE. portalSources had stores.reviews.get(portalId) ?? null. Once get() returned a promise the coalesce applied to the promise - never null - so an absent review state would export as undefined, and JSON.stringify drops undefined keys: it would have vanished from export bundles and backups. That is the F-Q01 failure mode reintroduced by my own change, and only the 100% branch gate surfaced it. DQ33 logged: when a store read becomes async, re-check every ?? and ?. applied to it. | L-114; DQ33 | Fixed | Applies to the remaining eight stores | -
E110 | 2026-09-13 19:33 | R-Q13 | PHASE 2 STORE 2 OF 9 - support conversations. Chosen second because the store is read only by SupportService and the export source, so the ripple stayed contained: seven service methods, six routes and one export source. PgSupportStore now queries Postgres on every read instead of serving a cache. | L-115; v029 | Two of nine cache-free | None | E111
E111 | 2026-09-13 19:33 | R-Q13 | DQ33 APPLIED DELIBERATELY. Every ?? and ?. touching a support read was re-checked as it became async - that is the exact mistake which, in store 1, would have dropped review state from export bundles and backups. The suite stayed at 473 tests / 32 suites, 100% x4: a conversion that changes no behaviour should move no numbers, and that is the check. Seven stores remain; the writer lease stays load-bearing until all nine are done. | L-116; DQ33; test-run.log 20260913_1933 | 473 tests unchanged | Seven stores remain; live Postgres run open | -
E112 | 2026-09-13 19:41 | R-Q13 | CORRECTION. At v029 I claimed each remaining store was now local work. Measuring rather than repeating it showed that is true for reviews and support only: signatures drags analytics with it through the shared stale-quote provider, catalog reads getRole inside the identity middleware on every authenticated request, billing owns two request gates, audit has 53 call sites behind one helper, notifications ~20 fan-out sites. Phase 1 removed the plumbing cascade, not the service-level ones. | L-117; docs/async-migration-plan.md | Claim corrected | Seven stores are larger than stated at v029 | E113
E113 | 2026-09-13 19:41 | R-Q13 | PLAN PUBLISHED AND GATED. Order by risk: approvals, sync, audit, signatures+analytics together, notifications, billing, catalog last - with a session shape so every boundary ends green and the work can stop safely. A test asserts the plan against the code: stores marked done must be async, a store listed as pending must still be synchronous. A plan nobody checks becomes aspirational, which is the same failure class as the hollow published claims found in review pass 2. The writer lease stays load-bearing until all nine are converted. | L-118/L-119; DQ34 | 474 tests / 32 suites 100% x4 | Multi-instance unavailable until catalog is done | -
E114 | 2026-09-13 19:56 | R-Q13 | PHASE 2 STORE 3 OF 9 - approvals. Store, service and Pg adapter converted, the adapter now reading Postgres directly instead of a cache. The plan called this one self-contained; it nearly was, but the CRM card and the first-run checklist both read chains, so both became async too. The plan has been corrected rather than left flattering. | L-120; v031 | Three of nine cache-free | None | E115
E115 | 2026-09-13 19:56 | R-Q13 | TWO DEFECTS FROM THE MECHANICAL PASS, BOTH UN-AWAITED PROMISES. createChain inside the CSV chain importer lost its await, so the duplicate-name error escaped its try/catch and a duplicate chain imported silently; a portal-source restore?.() became a promise nobody awaited. The importer bug surfaced only because that test asserts imported:1 / skipped:1 rather than merely that the request succeeded - a status-only assertion would have passed. Worth carrying into the remaining six stores: in this migration the defects come from the mechanical part, not the design. | L-121; DQ33 | 474 tests unchanged | Six stores remain; lease still load-bearing | -
E116 | 2026-09-13 20:08 | R-Q13 | PHASE 2 STORE 4 OF 9 - sync. Runs now read straight from Postgres, including countFailuresSince which feeds the public status page, so one instance sees another instance failures immediately - the F-Q15 status page becomes genuinely fleet-wide rather than per-process. Settings stay in memory on the adapter by deliberate choice: small, read per request, and a query per read would cost more than the risk is worth; recorded in the migration plan rather than left as an undocumented inconsistency. Suite held at 474 tests, which is the expected result for a behaviour-preserving conversion. | L-123/L-124; v032 | 474 tests unchanged | Five stores remain; lease still load-bearing | -
E117 | 2026-09-13 20:26 | R-Q13 | PHASE 2 STORE 5 OF 9 - audit, and a deliberate departure from my own plan. The plan proposed fire-and-forget writes to avoid touching 53 call sites: void the promise, catch the error, leave the handlers alone. I did not take it. Awaiting every record() converted 23 sync handlers to guarded async - materially more churn - but a failed audit write now surfaces instead of being swallowed. The whole value of the trail is that an admin can trust it when two people are working at once, and one that silently drops entries is worse than one that errors. DQ35 locked and the plan corrected rather than left standing. | L-125/L-126; DQ35; v033 | 474 tests unchanged | Four stores remain; lease still load-bearing | -
E118 | 2026-09-13 22:46 | R-Q13 | STORE 6+7 ATTEMPT ABANDONED. The source conversion succeeded and tsc was clean on src/ - the plan was right that signatures and analytics are coupled by the stale-quote provider and must move together. The test surface defeated it: roughly 200 assertion sites, 107 in s5 and 87 in s6 alone. A repo-wide regex intended to wrap awaited property access also matched await request(app).get(...) and broke supertest chains in 16 files; successive repairs of await expect(X).rejects ping-ponged between two wrong forms. The suite bottomed out at 15 failed / 17 passed and I stopped rather than push on with little headroom. | L-127; v034 | No stores lost | Stores 6-9 still pending | E119
E119 | 2026-09-13 22:46 | R-Q13 | TREE RESTORED AND RE-VERIFIED at 474 tests / 32 suites / 100% x4 from quoteflow_asyncphase2e_codebase_20260913_2026.zip. This is DQ32 working as designed: staging the migration so every checkpoint is green meant a failed attempt could be discarded whole without losing the five converted stores. DQ36 locked - convert src/ to a clean tsc first, then fix ONE SUITE AT A TIME compiling after each, never a pattern across all of tests/, biggest suite first, and treat overrun as the signal to keep the checkpoint rather than hurry. Also recorded: stores 1-5 worked with pattern passes because their test surfaces were small, which was luck rather than method - do not infer method from the easy cases. | L-128; DQ36 | 474 tests green | Retry 6+7 in a fresh session | -
E120 | 2026-09-13 23:02 | V001 | EXTERNAL REVIEW V001 RECEIVED (ChatGPT) — the first review of QuoteFlow by a party outside this build loop. 14 findings QF-001..QF-014: 8 BLOCKER, 5 HIGH, 1 MEDIUM. Scores: market demand 7.5/10, differentiation 4.5, code completeness 5, enterprise grade 3.5, commercial readiness 3, overall 4.7 — NOT ENTERPRISE GRADE. The findings attack a boundary cold passes 1-3 never reached: those hunted defects inside the code, this asked whether the code meets the HubSpot platform contract. | V001; QF-001..QF-014 | Review received | None | Verify every falsifiable claim before accepting
E121 | 2026-09-13 23:15 | V001 | VERIFICATION SWEEP before acceptance. Nine claims were checkable against the extracted tree and ALL NINE HELD: InMemoryTokenStore/InMemoryDeletionQueue at index.ts:71-72 constructed before buildStores; dealWriter sending Content-Type only; PUT/POST to a /deals/{id}/line-items endpoint that does not exist; signSession referenced only by its definition and one test file; billingHttp unauthenticated; zero hsmeta/TSX/JSX/hubspot.extend across 101 files; no package-lock.json; two echo steps in deploy.yml; noopEmailSender as default. QF-012 metric drift confirmed three ways (README 474/32, closeout 397/26, package 101 files). | L-129; QF-001..QF-012 | All findings accepted | None | Fix what is fixable without external dependencies
E122 | 2026-09-13 23:30 | V001 | FOUR FINDINGS CLOSED IN CODE + ONE STRUCTURAL CHANGE. QF-008: lockfile generated, and the exact tree proved in a CLEAN ROOM — copied out without node_modules, npm ci → tsc → jest, 488 tests green, which is the first time this package has been shown to pass its own CI. QF-005/QF-006: the four inline fetches replaced by src/services/hubspotClient.ts — bearer token from TokenManager on every call, one forced refresh on 401 (TokenManager.forceRefresh added), create line_items + v4 default association, replace = list→archive→create. The old app.test.ts assertions were themselves wrong and are rewritten; a regression now fails if /line-items ever reappears. QF-009: deploy steps exit 1 naming the finding instead of echoing success. QF-012: scripts/release-manifest.js counts the tree, CI publishes it. CB-05 guard: NODE_ENV=production refuses to boot while QF-002/QF-003 are open, un-overridable by design (DQ39). Suite 474/32 → 488/33, 100% x4, EXIT=0. | L-130; DQ37-DQ40; QF-005/006/008/009/012 | 488 tests green; 4 findings closed | QF-001/004/007/010/013/014 need Senthil | Evidence classes into the matrix
E123 | 2026-09-13 23:30 | V001 | EVIDENCE CLASSES APPLIED (CB-01/QF-011) — Traceability_Matrix columns L and M, APPENDED not inserted because Sprint_Status_Rollup formulas read columns E/G/J and an insert would have silently shifted every one of them. Stories requiring CONTRACT, LIVE-HUBSPOT, SECURITY, OPS or COMMERCIAL evidence and having only CODE drop from Done to Partial. THE HEADLINE STORY COUNT FALLS as a direct result, and it should: a green unit suite was never evidence that a HubSpot integration works. The Done figure in Programme_Closeout of workbook v034 is superseded. | L-131; DQ38; QF-011 | Story statuses recomputed | None | R-Q15 (dev portal) is the gating item for everything above it
E124 | 2026-09-20 10:20 | V002 | EXTERNAL REVIEW V002 RECEIVED AND ACCEPTED. 16 findings PXR-001..PXR-016; score 4.1/10 NOT ENTERPRISE GRADE; sprint plan PS13–PS32. Verification sweep confirmed every finding against the tree before any code moved. | L-132; PXR-001..PXR-016 | All 16 findings accepted | None | E125
E125 | 2026-09-20 10:26 | V002 | SCOPE INSTRUCTION FROM SENTHIL: "Enterprise grade product do all dont shrink the scope." The plan that deferred PS18 (async cascade) and PS21 (RLS) was withdrawn. DQ40 (no blind scaffolding of a Projects app) is treated as OVERRULED and recorded as an overrule rather than ignored. | L-133; DQ40 | Full PS13–PS31 scope accepted | None | E126
E126 | 2026-09-20 11:05 | PS18 | ASYNC STORE CASCADE COMPLETED (R-Q13 closed). All nine stores async and cache-free, DQ36 method, paren-balancing codemod. Four latent defects found and fixed, each a published behaviour with nothing durable under it: feature settings, envelope mutations, notification mutes, billing fields. | L-134; DQ36; R-Q13 | R-Q13 CLOSED; writer lease retired (migration 012) | None | E127
E127 | 2026-09-20 11:20 | PS21 | TENANCY AT THE DATABASE. RLS on every tenant table with transaction-local GUCs, FORCE RLS and a non-BYPASSRLS app role; boot refuses to serve as a superuser. Proved on PGlite (real Postgres in WASM) because pg-mem cannot parse RLS DDL. Rate limits, body limits and security headers shipped with it. | L-135; PXR-003; PS21-01..05 | PXR-003 closed (CODE+SECURITY) | None | E128
E128 | 2026-09-20 11:40 | PS19/PS20/PS22 | DURABILITY AND OBSERVABILITY. Envelope-encrypted OAuth tokens with rotation by re-wrap; durable outbox with idempotency keys, leased claims, backoff, dead-letter and replay; structured logs with correlation ids, Prometheus metrics, SLO burn-rate and error reporting. | L-136; PXR-002; PXR-016 | PXR-002 and PXR-016 closed | None | E129
E129 | 2026-09-20 12:10 | PS14/PS15/PS16/PS17 | PLATFORM SURFACE REBUILT. hubspot-project/ (platformVersion 2026.03) with a React app card and a serverless proxy; legacy crmCard.ts and GET /crm-card DELETED; session mint shipped and header identity DELETED; OAuth moved to v3 endpoints and app-initiated external uninstall added. | L-137; DQ41; DQ42; PXR-001 | PXR-001 CODE-closed; LIVE still blocked on R-Q15 | No dev portal | E130
E130 | 2026-09-20 13:30 | PS26/PS27/PS28 | QUOTE, DOCUMENT AND SYNC CORRECTNESS. Persisted quote entity with immutable versions, lifecycle and drift detection; deterministic rendering, content seal, certificate of completion and offline verification; line-item provenance so a push never touches items QuoteFlow did not create. | L-138; PXR-004; PXR-007; PXR-008 | PXR-004/007/008 closed | None | E131
E131 | 2026-09-20 15:10 | PS23 | CONFIGURATION ENGINE (PS23). Product model with attributes, option groups and conditional visibility; requires/implies/excludes with cycle detection; deterministic solver with a documented tie-break; explainability trace; authoring validation that refuses a contradictory rule set at save time. Five scenarios native quoting cannot express are configured and explained. | L-139; DQ46; PXR-009; PS23-01..06 | PS23 complete (CODE) | Scenario provenance needs design partners (PS13/PS32) | E132
E132 | 2026-09-20 15:50 | PS24 | PRICING ENGINE DEPTH (PS24). Nested bundles with compounding, entity book inheritance, pinned FX with per-currency exponent and rounding mode, multi-year ramps, graduated usage tiers with commit and overage, cost-plus and margin floors, channel matrices, and a full per-line waterfall. Money is integers in micros, rounded once. | L-140; DQ45; PXR-010; PS24-01..08 | PS24 complete (CODE) | Invoice tax is still a single flat rate — stated, not counted as done | E133
E133 | 2026-09-20 16:05 | PS25 | DEAL DESK (PS25). Conditional approval DAG with parallel branches and quorum, delegation with an explicit audit, business-hours SLA and escalation ladders, recall/resubmit with version-aware invalidation, an append-only audit and NO bypass path. Every bypass attempt is denied and recorded. | L-141; DQ47; PXR-009; PS25-01..07 | PS25 complete (CODE+SECURITY) | None | E134
E134 | 2026-09-20 16:15 | PS29 | BILLING CORRECTNESS (PS29). Stripe form-encoding with bearer auth and an idempotency key, marketplace rail, inbound webhooks with signature verification, replay tolerance and out-of-order handling, plan-based entitlements, and proration on real calendar periods. | L-142; DQ48; PXR-012 | PS29 CODE-complete; CONTRACT blocked on R-Q10 | No Stripe keys, no monetisation access | E135
E135 | 2026-09-20 16:25 | PS30 | ENTERPRISE OPERATIONS (PS30), split honestly. PROVED: migration rollback on a real engine, chaos with Postgres/HubSpot/mail each killed, residency and subprocessor posture. NOT PROVED and shipped as unrun harnesses: p95 load test, RPO/RTO restore drill; plus pen test and SOC 2, which are purchases. | L-143; DQ49; DQ50; PXR-005; PXR-015 | PXR-005 closed (lease gone, blue/green executable); PXR-015 posture declared | Hosting, managed Postgres, pen test | E136
E136 | 2026-09-20 16:35 | PS31 | EVIDENCE-CLASS QUALITY SYSTEM (PS31). Every test file tagged @evidence; claims register with required vs held classes; CI gate on untagged files and empty classes; release manifest carries the matrix. The coverage gate is relabelled a regression floor everywhere it is mentioned. | L-144; DQ43; PXR-011; PS31-01..05 | Evidence matrix: {'CODE': 45, 'CONTRACT': 2, 'LIVE': 0, 'SECURITY': 8, 'PERF': 0, 'OPS': 4, 'COMMERCIAL': 0}; claims 8 supported / 7 blocked | None | E137
E137 | 2026-09-20 16:40 | V002 | RELEASE CUT. Clean-room npm ci -> tsc (src and tests) -> jest: 793 tests / 45 suites, 100% statements/branches/functions/lines. 70 source files, 17 migrations, tree 43de1cac3aa5. Zip, tracker v028 and workbook v036 issued together. | L-145; QF-012 | v028 / v036 released | R-Q15 (dev portal) remains the gating item for the whole product | —

## Decisions
DECISIONS (tracker scope)
Portfolio decisions keep their D-numbers; QuoteFlow-local decisions are DQ-numbered. Product-workbook tracker refs in Rationale.
ID | Decision | Rationale | Decided by | Status
D13 | (Portfolio-wide) Discovery interviews parked; development proceeds with 100% automation test coverage on ALL code — hard jest threshold, build fails below 100x4. | Senthil 10 Sep 20:45; applied to QuoteFlow at 22:03 (L-001); ST-085 amended in backlog | Senthil | LOCKED
DQ1 | S1+ stack = TypeScript/Node 22/Express 4/Jest per v006 ReadMe stack assumption; strict tsc. | Follows workbook stack line; consistent with the rest of the portfolio builds | Claude — flagged for ratification | OPEN
DQ2 | /api identity is header-based (X-QF-Portal-Id/X-QF-User-Id, first-user-owner bootstrap); the HubSpot-SIGNED surface is GET /crm-card (v3 HMAC). Extending signed identity to /api rides with the S4+ UI-extension work. | L-011 (S2) partially resolved by ST-005 in S3 — card surface signed; API headers remain until UI extension auth lands | Claude — flagged | OPEN
DQ3 | Approval requests snapshot chain steps at creation; decisions read the snapshot. Trigger thresholds are strict (>): a 15% discount does not trip the 15% default chain. | L-017 — in-flight requests immune to chain edits/deletes; removes unreachable error branch; boundary documented in tests | Claude | LOCKED
DQ4 | Postgres adapter deferred to S4; in-memory stores behind CatalogStore/AuditStore/NotificationStore/ApprovalStore + Purgeable interfaces remain the tested reference. | L-018 — no live Postgres in build env; an unexecuted adapter would violate the honest-status rule. UPDATE 11 Sep 08:17 (L-024): live install attempted — apt mirror 404s + sandbox timeout, PG_ABSENT verified; deferral stands with evidence. | Claude | LOCKED
DQ5 | Email transport is an injected EmailSender with a no-op production default until a provider (Postmark-class) is wired with GTM plumbing; notification code paths (sent/failed/retry) fully tested against a mutable fake. | Email delivery is a provider integration (noop sender in dev); notification records + retry endpoint are real. UPDATE 11 Sep 08:52: signer link delivery for e-sign envelopes rides the same provider decision — the API returns signerLinks so the UI can share links meanwhile. | Claude — flagged | OPEN
DQ6 | Feature-scoped pause (ST-018): pausing approvals blocks NEW requests only; decisions on already-pending requests remain allowed so in-flight approvals never strand. Global pause blocks both features. | S4 build (E017); prevents stuck approvals during maintenance windows; tested both directions | Claude | LOCKED
DQ7 | Error-spike semantics (ST-072): threshold 5 server errors in a rolling 15-min window; one error_spike notification per episode to every admin/owner; episode resets when the window rolls clean. | S4 build (E017); avoids alert storms while guaranteeing a signal; constants exported for tuning | Claude | LOCKED
DQ8 | Public signer surface: the token IS the identity — /api identity middleware is bypassed for /api/esign/sign/*; signer actions audited as signer:<email>. Tokens are minted only after ALL signers validate (no token burn on invalid input; found and fixed in build). Production tokens are crypto.randomUUID via injected generator. | S5 build (E024); guessable or burned tokens would break the feature; regression-tested | Claude | LOCKED
DQ9 | Esign pause blocks NEW envelopes only — sent links keep signing (DQ6 never-strand, now covering pricebook/approvals/esign). Envelope behaviour snapshots settings at creation; later settings changes never mutate in-flight envelopes. | S5 build (E025); protects external signers mid-flow; tested over HTTP while paused | Claude | LOCKED
DQ10 | Analytics pause blocks dashboards (summary/trends/export 409) but NEVER event capture — capture gating would create history gaps, i.e. data loss (ST-038 forbids). Capture is setup-independent: events record before defaults; alerts only fire once settings exist. Deliberate inversion of the DQ6 write-gate. | S6 build (E031); proved over HTTP: paused-time quote visible after resume | Claude | LOCKED
DQ11 | Billing channel fixed per portal at subscribe: marketplace -> HubSpot app-monetization API (mandated for marketplace installs), direct -> Stripe. Changes reuse the channel. Provider failure = BILLING_PROVIDER_UNAVAILABLE 502 retryable, persisting nothing. Proration on a fixed 30-day period; net<=0 ledger-credits without a provider call; elapsed clamps at period end. | S6 build (E032); exact-cents proration + failure-persistence tests | Claude | LOCKED
DQ12 | Billing read-only (dunning lapse or cancellation) gates WRITES only: quote creation, approval requests and envelopes return 402 BILLING_READ_ONLY, while dashboards, exports, invoices and billing routes stay readable. Quota exhaustion behaves the same way. | S7 build (E038); non-payment must not strand a customer from their own data, and cancellation read-lock would break data portability | Claude | LOCKED
DQ13 | Requested OAuth scopes are validated in code: SCOPE_REGISTRY (scope -> feature, stories, using call, why), auditScopes failing on unjustified AND missing scopes, disclosure text generated from the registry. A test asserts leastPrivilege against the real config. | S7 build (E039); listing review demands justification and prose drifts from config | Claude | LOCKED
DQ14 | Deal sync is idempotent on a deterministic portal:deal:quoteHash key — an unchanged quote re-pushed is a no-op; a changed quote or different deal writes. Paused portals queue runs (status queued) and drain on resume; a retry marks the prior run superseded so the queue empties. | S8 build (E046); a retry after timeout double-writing CRM line items is the failure mode that silently corrupts a customer CRM | Claude | LOCKED
DQ15 | The trust page (data-flow map, retention schedule, security controls) is generated from the same constants the code uses, and unmet controls publish as partial/not_met with a named owner. A test asserts the outstanding list is non-empty. | S8 build (E047); a hand-written compliance doc drifts from the system it describes and invites overclaiming | Claude | LOCKED
DQ16 | A circuit breaker fronts platform writes: 5 consecutive failures open it for a 30s cooldown, then one half-open trial call closes it or re-opens for another full cooldown. Exponential backoff (S2) is retained beneath it. | S8 build (E047); backoff alone still issues a full retry series per request against a downed dependency | Claude | LOCKED
DQ17 | Portal deletion is two-step: POST /api/privacy/delete mints a 15-minute confirmation token (cancellable, owner-only), and POST /api/privacy/delete/confirm purges every source and returns a receipt of the record counts destroyed. Export is available to any admin at any time. | S9 build (E053); irreversible one-call wipes are both an outage risk and a review finding | Claude | LOCKED
DQ18 | Review evidence (accessibility, security posture, restore fidelity) is generated from code and asserted by tests rather than written as prose. The a11y checker is tested against broken HTML per rule; the security pack disclaims the uncommissioned pen test; the drill reports skipped sources. | S9 build (E054); a compliance claim that no test enforces decays silently | Claude | LOCKED
DQ19 | The pricing page, pricing FAQ and trust page are generated from the constants the product runs on (PLANS, TRIAL_DAYS, PERIOD_DAYS, GRACE_DAYS, DATA_FLOW, SCOPE_REGISTRY, SECURITY_CONTROLS). Tests assert published values equal their source constants. | S10 build (E061); a published price that disagrees with what billing charges is a broken promise, and hand-maintained pages drift | Claude | LOCKED
DQ20 | Support first-response SLA is measured in business hours (09:00-17:00 UTC, Mon-Fri). Unanswered conversations past their due time count as breaches in the compliance figure. | S10 build (E062); elapsed-hours timers create false breaches over weekends, and excluding unanswered tickets would let a breach hide | Claude | LOCKED
DQ21 | The submission dry-run reads live system state and classifies items as pass / fail / manual. Manual items appear in the blockers list and are never counted as passes. | S10 build (E063); a self-assessment that grades its own unknowns as passes is worthless to a reviewer | Claude | LOCKED
DQ22 | The in-app review ask fires only after the aha moment with 5+ quotes in 30 days and no unresolved error, open support conversation or billing problem. Max 2 asks per lifetime, 90 days apart; snooze 30 days; decline permanent with no re-prompt. No sentiment gating and no diverting unhappy users away from the listing. | S11 build (E068); a prompt at the wrong moment costs more than the rating, and review-gating breaches marketplace rules | Claude | LOCKED
DQ23 | The launch runbook is executable: preflight runs a real restore drill, every rollback step has a verification, traffic stops before redeploy and integrity is checked after, and the comms tree names audience/owner/deadline. Data-integrity comms are never templated. Markdown and API serve the same constants. | S11 build (E069); a runbook nobody can execute under pressure is decoration | Claude | LOCKED
DQ24 | The design-partner pipeline counts only partners at call_scheduled or beyond toward the target of ten; identified and contacted count as zero, declined drops out. | S11 build (E070); the story asked for reviews SCHEDULED, and a pipeline that counts intentions misreports readiness | Claude | LOCKED
DQ25 | Listing SEO recommendations are constrained by a supported vocabulary and a forbidden-claims list, matched on word boundaries. Unsupported high-demand terms are recorded as product demand and never enter listing copy. Proposed copy is length-capped with a baseline fallback. | S12 build (E074); ranking for something the product does not do converts once and churns, and is a false claim in a marketplace listing | Claude | LOCKED
DQ26 | Every fix arising from a review ships with a drift gate as well as a regression test: the retention sweepers are asserted to match the published policy exactly, and the migrations are asserted to cover every published store. A regression proves today behaves; a drift gate stops tomorrow silently diverging. | Pass 2 (E087); four of six findings were published claims that had drifted from — or never had — code | Claude | LOCKED
DQ27 | Vendor-only surfaces (cross-tenant aggregates, process-wide latency, founder thresholds, launch preflight, runbook, partner pipeline) require a timing-safe operator token in addition to tenant identity, and fail closed when no token is configured. | Pass 3 (E090); tenant RBAC is the wrong plane for vendor data - any portal owner could otherwise read other tenants aggregates and the sales pipeline | Claude | LOCKED
DQ28 | A persistence adapter is only accepted when a single store-contract suite passes against both the in-memory implementation and the adapter running real SQL against a real engine with the real migrations, including durability tests that drop all caches. | R-Q4 (E093); an adapter tested against a mock proves the mock, and the whole point of the schema was that memory was not durable | Claude | LOCKED
DQ29 | A store adapter is only accepted when the contract suite round-trips every record type the interface exposes, asserted field by field including optional fields in both their present and absent forms. Checking that a store "has a table" is not enough. | F-Q18 (E096); the catalog satisfied a store-level drift gate while three of its six record types had nowhere to persist | Claude | LOCKED
DQ30 | A persistence backend must be selectable at boot from configuration, must report which backend it chose, and is only accepted once the real application has been driven end to end against it - including a second process started on the same database. | Boot wiring (E098/E099); adapters that nothing constructs are indistinguishable from adapters that do not exist | Claude | LOCKED
DQ31 | Where a known constraint cannot be removed yet, enforce it so that breaking it fails loudly rather than silently. The single-writer rule is enforced by a lease: a second instance is refused at startup, and an instance that loses the lease exits. | R-Q13 (E103); a silent correctness failure is the worst kind, and converting it into a startup failure is the right trade while the real fix is pending | Claude | LOCKED
DQ32 | A large migration is staged so that every checkpoint is green and shippable. Phase 1 changes only the layer that blocks everything else, with signatures accepting a value or a promise so existing implementations are untouched. | R-Q13 phase 1 (E106); a half-migrated repo is worse than an unmigrated one, and a green checkpoint can be shipped or abandoned safely | Claude | LOCKED
DQ33 | When a store read becomes async, every ?? and ?. applied to that read must be re-checked: the operators begin acting on a Promise, which is never null or undefined, so the fallback silently stops firing. | Phase 2 store 1 (E109); this exact mistake would have dropped review state from export bundles and backups | Claude | LOCKED
DQ34 | A plan that outlives a session is asserted against the code by a test, so it cannot drift into aspiration. Estimates of remaining work are measured from call sites, not asserted from memory. | R-Q13 phase 2 (E112/E113); an unchecked plan is the same failure class as the hollow published claims found in review pass 2 | Claude | LOCKED
DQ35 | Audit writes are awaited, never fire-and-forget. Voiding the promise would have avoided 23 handler conversions, but it hides a failed write; an audit trail that silently drops entries is worse than one that errors. | Phase 2 store 5 (E117); the trail exists to be trusted under concurrent use | Claude | LOCKED
DQ36 | In a store-by-store async migration: convert src/ to a clean tsc first, then fix test suites one at a time, compiling after each. Never run a text pattern across all of tests/. Do the biggest suite first, and treat overrun as the signal to keep the green checkpoint rather than to hurry. | Abandoned store 6+7 attempt (E118); repo-wide regex broke 16 files of supertest chains and cost the whole attempt | Claude | LOCKED
DQ37 | External review findings keep their originating ids (QF-nnn) and close only against named evidence. No renumbering, no silent closure, no merging into F-Q ids. | Reviewer protocol CB-02; also stops a finding being quietly absorbed into an existing internal defect and losing its history | Claude | LOCKED
DQ38 | A story is Done only when every evidence class it requires is satisfied, not when its tests pass. Classes: CODE, CONTRACT, LIVE-HUBSPOT, SECURITY, OPS, COMMERCIAL. | QF-011: 474 tests at 100% coexisted with an endpoint that does not exist, a missing UI extension and a placeholder deploy. Four independent reviews have now found defects in code at 100% coverage | Claude | LOCKED
DQ39 | Where a production capability is missing, production REFUSES TO BOOT and names the finding. No warning logs, no override flag. | QF-002/QF-003: a warning that tokens are volatile is read once and forgotten; a refusal cannot be. Nothing runs in production today, so the cost is zero and the forcing function is real | Claude | LOCKED
DQ40 | No blind scaffolding of a HubSpot Projects app or UI extension before a dev portal account exists. | QF-001: writing an extension that has never been uploaded would produce exactly the class of artifact this review condemns — tested code that cannot meet the platform contract | Claude, for Senthil to overrule | LOCKED
DQ41 | The legacy CRM card surface is DELETED, not deprecated: src/services/crmCard.ts and GET /crm-card are removed from the tree and the app card is GET /api/cards/deal/:dealId. | PXR-001: HubSpot barred legacy cards from new listings in May 2026 and stops rendering them on 31 Oct 2026. A route that can never be listed makes the tree look more finished than it is. A test asserts the old route 404s. | Claude | LOCKED
DQ42 | Header identity is deleted, not gated. The only accepted identity is an HMAC-signed X-QF-Session minted at POST /session/mint from a HubSpot-SIGNED request. No flag, no NODE_ENV branch. | PS16-02 / QF-004: a development-only path that exists in the binary is a production path. Refusal reasons are deliberately opaque to the caller (always SESSION_INVALID) so a prober cannot tell a bad signature from a bad payload. | Claude | LOCKED
DQ43 | No claim may be stated above its evidence class. Every test file declares @evidence; every published claim sits in a register with required vs held classes; CI fails on an untagged file or an empty class a shipped feature claims. | PXR-011 / QF-011: the most damaging V001 finding was not a defect but the presentation of 100% coverage as proof of readiness. The gate is relabelled a REGRESSION FLOOR in code, in CI output and in the README. | Claude | LOCKED
DQ44 | The depth sprints (PS23/24/25) ship with durable storage, RLS, routes, RBAC, audit and purge — or they do not ship. Routes are mounted only when their stores are supplied. | The async cascade found four cases of published behaviour with nothing under it. Building the engines pure and unwired would have repeated that defect. Doing it this way found two real bugs: a per-instance id counter (colliding across instances) and a DAG lookup that ignored the portal. | Claude | LOCKED
DQ45 | Money is integers in micros, rounded exactly once, per-currency exponent and rounding mode. FX rates are PINNED onto the quote, never looked up live. | PXR-010 / PS24-03: float money is how a quote and an invoice end up a cent apart. A live FX lookup means the customer signs a different number from the one they were shown. Stated consequence, proved by test: unitMinor x quantity does not always equal totalMinor — the total is authoritative. | Claude | LOCKED
DQ46 | The configuration engine explains every decision or it is not finished. Resolution order and tie-break are documented and tested; implication CYCLES are rejected at save time. | PS23-04/05: a trace that says "A because B because A" explains nothing, and explanation is the differentiator native quoting cannot offer. Tie-break: a rep's choice beats a derived one; two rep choices in conflict make the configuration invalid rather than silently discarding one. | Claude | LOCKED
DQ47 | The deal desk has no bypass path. Exactly one way into decisions; every refusal is denied AND recorded as a bypass attempt in an append-only audit. | PS25-06: an attempted bypass is itself something a deal desk wants to see. Self-approval is refused even when the requester IS a named approver — the rule is about authorship, not membership. | Claude | LOCKED
DQ48 | Billing listens as well as talks: provider webhooks are authoritative, signature-verified (stale AND future refused), idempotent by event id, and ordered by the event's own timestamp. | PS29-02: a charge call returning 200 has not been paid. Without ordering by event time, a late payment_failed undoes the payment_succeeded that superseded it. Proration moved to real calendar months — a fixed 30-day period is wrong every February and every 31-day month. | Claude | LOCKED
DQ49 | Every migration carries a rollback section or is declared irreversible. rollbackMigrations refuses to start if any step in the range is irreversible. | PS30-04: a half-rolled-back schema is worse than the bad deploy it was undoing. Two deliberate irreversibles: the core schema (restore from backup is the honest path) and 012, which retired the writer lease for good. The forward runner strips the rollback section — three harnesses that applied raw file bodies were corrected. | Claude | LOCKED
DQ50 | What cannot be proved is not claimed. PS30-01/03/06/08 ship as UNRUN harnesses that say so in their own headers; residency declares regions available but none provisioned. | PXR-015 / PS31-04: "we have backups" is a hope with a cron job attached. scripts/loadtest.js and scripts/restore-drill.sh produce the numbers when an environment exists; until then CL-10..CL-13 stay blocked in the claims register. | Claude | LOCKED

## S1_Build_Board
S1 BUILD BOARD — Foundation — exit: app installs cleanly in dev store/org; telemetry firing
Backlog stories ST-051/052/055/056 (13 pts) + foundation infrastructure. Evidence version: product workbook v007 (22:03), codebase zip quoteflow_s1_foundation_20260910_2203.zip.
ID | Item | Story ref | Points | Owner | Status | Notes / Evidence
S1-01 | Repo scaffold + strict tsc + jest with 100% coverage gate (D13) | — | 2 | Claude | Done | jest.config.js coverageThreshold {stmts,branch,funcs,lines}=100; E001/E003.
S1-02 | Env config with secrets validation | — | 1 | Claude | Done | src/config.ts — 6 tests; missing-var failures explicit.
S1-03 | Token store + deletion queue (adapter seam for Postgres) | — | 2 | Claude | Done | src/store/tokenStore.ts, src/store/deletionQueue.ts; DQ4 constraint logged as R-Q4.
S1-04 | OAuth install flow -> welcome state | ST-051 | 5 | Claude | Done | DONE-IN-CODE 22:03 — src/services/oauth.ts buildAuthorizeUrl/completeInstall, GET /install + /oauth/callback; state carries source+ts. v007.
S1-05 | Uninstall webhook: HMAC verify, token wipe, retention-scheduled deletion | ST-052 | 3 | Claude | Done | DONE-IN-CODE 22:03 — src/webhooks/signature.ts (HubSpot v3 HMAC method+uri+body+timestamp, replay guard), src/services/uninstall.ts; retentionDays=30. v007.
S1-06 | Token refresh surviving platform rotation | ST-055 | 3 | Claude | Done | DONE-IN-CODE 22:03 — src/services/tokenManager.ts: 60s expiry skew, rotation persisted, 5xx retry, 401 re-install path; 9 unit cases. v007.
S1-07 | Install telemetry with source attribution | ST-056 | 2 | Claude | Done | DONE-IN-CODE 22:03 — src/services/telemetry.ts + normaliseSource bucketing hostile inputs; attribution round-trips OAuth state. v007.
S1-08 | D13 automation gate: 56 tests / 3 suites, 100% x4 | — | 2 | Claude | Pass | test-run.log 20260910_2203; threshold enforced. E003.
S1-09 | LIVE dev-portal install verification | ST-051 | 0 | Senthil | Open | Needs HubSpot dev portal app + client ID/secret; code-verified only. E004 / R-Q5.

## S2_Build_Board
S2 BUILD BOARD — Price book + bundles part 1 — exit: happy path demoable
Stories ST-001..004 + ST-053/054 (29 pts). Evidence version: product workbook v008 (22:19), codebase zip quoteflow_s2_codebase_20260910_2219.zip.
ID | Item | Story ref | Points | Owner | Status | Notes / Evidence
S2-01 | Catalog domain: books/items/bundles/rules, portal isolation | — | 3 | Claude | Done | src/domain/catalog.ts; defensive copies; purge seam. v008.
S2-02 | One-call sensible defaults (idempotent) | ST-001 | 5 | Claude | Done | DONE-IN-CODE 22:19 — Standard Price Book USD + 3 items + Starter bundle 10% + volume rule; POST /api/pricebooks/defaults 201/200. v008.
S2-03 | Happy-path pricing engine end-to-end | ST-002 | 8 | Claude | Done | DONE-IN-CODE 22:19 — priceQuote: bundle=component sum x (1-disc), round2; verified 804.60+672.60=1477.20 over HTTP. v008.
S2-04 | Customisable rules (minQty/customerTier, best-wins) | ST-003 | 5 | Claude | Done | DONE-IN-CODE 22:19 — validation matrix + largest-discount-wins with deterministic ties. v008.
S2-05 | Typed errors + platform backoff client | ST-004 | 3 | Claude | Done | DONE-IN-CODE 22:19 — AppError{code,status,retryable,retryAfterMs}; PlatformClient 429/5xx backoff [100,200] -> retryable 503; 401 re-auth. v008.
S2-06 | Re-install restore within retention window | ST-053 | 3 | Claude | Done | DONE-IN-CODE 22:19 — completeInstall cancels pending deletion -> "Your previous data was restored."; DeletionExecutor purges past window. v008.
S2-07 | RBAC owner>admin>member on every /api route | ST-054 | 5 | Claude | Done | DONE-IN-CODE 22:19 — permission matrix + first-user-owner bootstrap + /api/users management; DQ2 identity decision. v008.
S2-08 | D13 gate: 103 tests / 5 suites, 100% x4 on 16 files | — | 2 | Claude | Pass | test-run.log 20260910_2219. E007.

## S3_Build_Board
S3 BUILD BOARD — Price book part 2 + Approval chains start — exit: price book complete with tests; approvals skeleton
Stories ST-005..010 + ST-011..014 + ST-085 (47 pts). Evidence version: product workbook v009 (22:52), codebase zip quoteflow_s3_codebase_20260910_2252.zip.
ID | Item | Story ref | Points | Owner | Status | Notes / Evidence
S3-01 | HubSpot-signed CRM card + /ui/quote iframe shell | ST-005 | 5 | Claude | Done | DONE-IN-CODE 22:52 — GET /crm-card v3-HMAC-verified (empty-body GET), card JSON w/ books/default/status + New-quote IFRAME action; paused-aware. Live HubSpot fetch open (R-Q6). v009.
S3-02 | Metrics + 7-day trend | ST-006 | 3 | Claude | Done | DONE-IN-CODE 22:52 — quote log; quotes/total/avg/discounted-line% + UTC byDay; GET /api/metrics (admin); verified 731.60 across 2 quotes. v009.
S3-03 | Audit logging on every mutating /api action | ST-007 | 3 | Claude | Done | DONE-IN-CODE 22:52 — record() on 14 mutating routes (actor+action+target+time); GET /api/audit. v009.
S3-04 | Pause/disable without data loss | ST-008 | 2 | Claude | Done | DONE-IN-CODE 22:52 — requireActive gates quote pricing/import/approval requests w/ 409 FEATURE_PAUSED; reads + data untouched; resume instant. v009.
S3-05 | CSV + competitor import | ST-009 | 5 | Claude | Done | DONE-IN-CODE 22:52 — quoted-field CSV parser; generic + rivalcpq header maps; row-level errors; case-insensitive SKU dedupe incl. within-file. v009.
S3-06 | Notifications: in-app + email, per-type mute, retry | ST-010 | 3 | Claude | Done | DONE-IN-CODE 22:52 — 5 event types; muted type produces nothing; failed email kept + POST retry-email (502 retryable while transport down, heals to sent). v009.
S3-07 | Approval chain defaults in one call | ST-011 | 5 | Claude | Done | DONE-IN-CODE 22:52 — "Discounts over 15% need manager approval", admin step, idempotent. v009.
S3-08 | Approvals happy path without documentation | ST-012 | 8 | Claude | Done | DONE-IN-CODE 22:52 — request prices quote, strict-> trigger eval, first matching chain, auto-approve fallback; approve/reject walk; approver fan-out + requester notification. v009.
S3-09 | Customisable chain rules/conditions | ST-013 | 5 | Claude | Done | DONE-IN-CODE 22:52 — discountPctAbove (0,1) / totalAbove>0 triggers, admin¦owner steps, 10-case validation matrix; DQ3 step snapshot. v009.
S3-10 | Approvals clear errors + retry paths | ST-014 | 3 | Claude | Done | DONE-IN-CODE 22:52 — typed 400/403/404/409 (DECISION_INVALID, STEP_ROLE, NOT_FOUND, ALREADY_DECIDED) + 502-retryable email retry. v009.
S3-11 | D13 coverage-gate story evidenced | ST-085 | 5 | Claude | Done | DONE-IN-CODE 22:52 — threshold 100x4 enforced since S1; run 20260910_2252 = 150 tests / 7 suites, All files 100¦100¦100¦100, EXIT=0. v009.
S3-12 | Postgres adapter | — | 0 | Claude | Deferred | DQ4/L-018 — deferred to S4 honestly; store interfaces are the seam. v010 plan.

## S4_Build_Board
S4 BUILD BOARD — Approval chains part 2 + telemetry + smoke — exit: MVP loop usable end-to-end internally
Stories ST-015..020 + ST-071/072 + ST-086 (34 pts). Evidence version: product workbook v010 (2026-09-11 08:17), codebase zip quoteflow_s4_codebase_20260911_0817.zip.
ID | Item | Story ref | Points | Owner | Status | Notes / Evidence
S4-01 | Approvals on the signed CRM card + /ui/approvals shell | ST-015 | 5 | Claude | Done | DONE-IN-CODE 08:17 — Pending-approvals NUMBER prop + Approvals IFRAME action; shell page. Live HubSpot fetch open (R-Q6). v010.
S4-02 | Approvals metrics + 7-day trend | ST-016 | 3 | Claude | Done | DONE-IN-CODE 08:17 — status mix, auto-approval %, avgDecisionMs (verified 5000ms over HTTP); GET /api/approvals/metrics. v010.
S4-03 | Approvals permissions + audit hardening | ST-017 | 3 | Claude | Done | DONE-IN-CODE 08:17 — decision audit target id:outcome; GET /api/audit?action= prefix filter. v010.
S4-04 | Feature-scoped pause without data loss | ST-018 | 2 | Claude | Done | DONE-IN-CODE 08:17 — pricebook¦approvals pause independently; pending decisions stay open (DQ6); FEATURE_INVALID 400. v010.
S4-05 | Chain CSV + competitor import | ST-019 | 5 | Claude | Done | DONE-IN-CODE 08:17 — generic + rivalcpq, % / fraction thresholds, pipe steps, row-level errors; NaN guard bug-fix on createChain. v010.
S4-06 | Approval reminder nudge with per-type mute | ST-020 | 3 | Claude | Done | DONE-IN-CODE 08:17 — approval_reminder type; requester-only, pending-only; fan-out honours mutes. v010.
S4-07 | Activation funnel dashboard endpoint | ST-071 | 5 | Claude | Done | DONE-IN-CODE 08:17 — install->setup->aha->habit(10 quotes); markers wired into oauth/defaults/quotes; GET /api/funnel. v010.
S4-08 | Error tracking + release tagging + spike alert | ST-072 | 3 | Claude | Done | DONE-IN-CODE 08:17 — APP_RELEASE tag; sendError records every error; 5-in-15min spike notifies admins once per episode (DQ7); GET /api/errors. v010.
S4-09 | E2E smoke suite on every deploy | ST-086 | 5 | Claude | Done | DONE-IN-CODE 08:17 — tests/smoke.test.ts full journey; npm run test:smoke; CI smoke-on-deploy job on main. v010.
S4-10 | Postgres adapter (deferred-in from S3) | — | 0 | Claude | Blocked | Live install attempted: apt mirror 404s + timeout, PG_ABSENT verified (E016/L-024). Needs working mirror or container DB — carried to S5.

## S5_Build_Board
S5 BUILD BOARD — E-signature + alpha hardening — exit: internal alpha, team dogfoods daily
Stories ST-021..030 + ST-078/079 (50 pts). Evidence version: product workbook v011 (2026-09-11 08:52), codebase zip quoteflow_s5_codebase_20260911_0852.zip.
ID | Item | Story ref | Points | Owner | Status | Notes / Evidence
S5-01 | One-call esign defaults | ST-021 | 5 | Claude | Done | DONE-IN-CODE 08:52 — 14d/3d/require-all/decline-on, idempotent; teaching 404 pre-setup. v011.
S5-02 | Happy path: envelope -> token links -> sign -> completed | ST-022 | 8 | Claude | Done | DONE-IN-CODE 08:52 — public /api/esign/sign/:token (identity bypass, DQ8); validate-then-mint tokens; sha256 doc hash. v011.
S5-03 | Customisable settings | ST-023 | 5 | Claude | Done | DONE-IN-CODE 08:52 — validation matrix; snapshot-at-creation semantics (DQ9). v011.
S5-04 | Clear errors + retry paths | ST-024 | 3 | Claude | Done | DONE-IN-CODE 08:52 — EXPIRED 410 lazy+sticky w/ re-send hint, VOIDED/DECLINED/ALREADY_SIGNED/TOKEN_INVALID/DECLINE_DISABLED. v011.
S5-05 | CRM card + signer shell surface | ST-025 | 5 | Claude | Done | DONE-IN-CODE 08:52 — Awaiting-signature count 1->0 proved; /ui/sign shell. Live HubSpot fetch open (R-Q6). v011.
S5-06 | Esign metrics + trends | ST-026 | 3 | Claude | Done | DONE-IN-CODE 08:52 — 40% completion / avg 3000ms mix; expiry recount at +20d. v011.
S5-07 | Permissions + signer-identity audit | ST-027 | 3 | Claude | Done | DONE-IN-CODE 08:52 — esign:read/send/manage; audit actor signer:<email>. v011.
S5-08 | Pause without data loss | ST-028 | 2 | Claude | Done | DONE-IN-CODE 08:52 — new envelopes 409 while paused; sent links keep signing (DQ9). v011.
S5-09 | CSV + rivalsign import | ST-029 | 5 | Claude | Done | DONE-IN-CODE 08:52 — row-level errors, ragged-row tolerant; imported rows land in list + metrics. v011.
S5-10 | Envelope notifications w/ per-type mute | ST-030 | 3 | Claude | Done | DONE-IN-CODE 08:52 — envelope_sent/signed/declined; mute framework covers them. v011.
S5-11 | First-run checklist | ST-078 | 5 | Claude | Done | DONE-IN-CODE 08:52 — 7 live-derived items w/ exact next call; 14% -> 100% over real HTTP actions. v011.
S5-12 | Empty states teach next action | ST-079 | 3 | Claude | Done | DONE-IN-CODE 08:52 — emptyState on all five lists; drops when populated. v011.

## S6_Build_Board
S6 BUILD BOARD — Quote analytics + Billing — exit: can charge a test customer; upgrade/downgrade paths work
Stories ST-031..040 + ST-057/058/059 (60 pts). Evidence version: product workbook v012 (2026-09-11 12:47), codebase zip quoteflow_s6_codebase_20260911_1247.zip.
ID | Item | Story ref | Points | Owner | Status | Notes / Evidence
S6-01 | One-call analytics defaults | ST-031 | 5 | Claude | Done | DONE-IN-CODE 12:47 — idempotent; teaching 404 pre-setup. v012.
S6-02 | Summary dashboard happy path | ST-032 | 8 | Claude | Done | DONE-IN-CODE 12:47 — pipeline/discount/win-rate/large/stale/pace; exact-math units. v012.
S6-03 | Customisable analytics settings | ST-033 | 5 | Claude | Done | DONE-IN-CODE 12:47 — 11-case validation matrix. v012.
S6-04 | Typed errors + export | ST-034 | 3 | Claude | Done | DONE-IN-CODE 12:47 — pre-setup 404s over HTTP; CSV/JSON; EXPORT_FORMAT_INVALID. v012.
S6-05 | Card + UI extension surface | ST-035 | 5 | Claude | Done | DONE-IN-CODE 12:47 — Quotes(7d) on signed card; Analytics action; shell. Live fetch open (R-Q6). v012.
S6-06 | Trends | ST-036 | 3 | Claude | Done | DONE-IN-CODE 12:47 — 7d buckets, top discounters, wonValue7d. v012.
S6-07 | Permissions + audit | ST-037 | 3 | Claude | Done | DONE-IN-CODE 12:47 — read (member) / manage (admin); four audited actions. v012.
S6-08 | Pause without data loss | ST-038 | 2 | Claude | Done | DONE-IN-CODE 12:47 — DQ10: dashboards 409, capture continues; paused-time quote visible after resume. v012.
S6-09 | History import | ST-039 | 5 | Claude | Done | DONE-IN-CODE 12:47 — generic+rivaliq; column-order independent; ragged tolerant. v012.
S6-10 | Alerts w/ per-type mute | ST-040 | 3 | Claude | Done | DONE-IN-CODE 12:47 — discount_alert + goal_reached (fires exactly once); mute proved. v012.
S6-11 | 14-day card-free trial | ST-057 | 5 | Claude | Done | DONE-IN-CODE 12:47 — seeded at install; countdown banner; lazy expiry flip. v012.
S6-12 | Prorated plan changes | ST-058 | 5 | Claude | Done | DONE-IN-CODE 12:47 — exact cents up/down; net<=0 no provider call; clamps. v012.
S6-13 | Marketplace vs Stripe routing | ST-059 | 8 | Claude | Done | DONE-IN-CODE 12:47 — channel-routed; failure 502 persists nothing. Live credentials open (R-Q10). v012.

## S7_Build_Board
S7 BUILD BOARD — Billing hardening + least-privilege scopes — exit: private beta with design partners
Stories ST-060..064 (15 pts). Evidence version: product workbook v013 (2026-09-13 10:26), codebase zip quoteflow_s7_codebase_20260913_1026.zip.
ID | Item | Story ref | Points | Owner | Status | Notes / Evidence
S7-01 | Failed payment: grace, dunning, read-only | ST-060 | 3 | Claude | Done | DONE-IN-CODE 10:26 — 7d grace, 3 notices max one/day, lazy+sticky lapse, recovery re-charge; reads survive (DQ12). v013.
S7-02 | Plan limits with 80/100% prompts | ST-061 | 3 | Claude | Done | DONE-IN-CODE 10:26 — Pro 200 / Scale 2000; warning once per crossing; 402 on all three quote paths; floored pct. v013.
S7-03 | Invoices/receipts with GST-VAT fields | ST-062 | 3 | Claude | Done | DONE-IN-CODE 10:26 — auto-issued on every positive charge; tax profile applied at issue; text receipts. v013.
S7-04 | Cancellation with save-offer + exit survey | ST-063 | 3 | Claude | Done | DONE-IN-CODE 10:26 — offer-before-accept guard, fixed reason set, cancelled portals still read/export. v013.
S7-05 | Least-privilege scope map | ST-064 | 3 | Claude | Done | DONE-IN-CODE 10:26 — registry + two-way audit + generated disclosure; leastPrivilege asserted vs real config (DQ13). v013.

## S8_Build_Board
S8 BUILD BOARD — Deal sync + trust + founder ops + performance — exit: beta iteration complete, sync shipped
22 stories / 87 pts across F5, E6, E7 and EQ. Evidence: product workbook v014 (2026-09-13 10:38), codebase zip quoteflow_s8_codebase_20260913_1038.zip.
ID | Item | Story ref | Points | Owner | Status | Notes / Evidence
S8-01 | Sync defaults | ST-041 | 5 | Claude | Done | DONE-IN-CODE 10:38 — idempotent defaults, teaching 404. v014.
S8-02 | Sync happy path (idempotent push) | ST-042 | 8 | Claude | Done | DONE-IN-CODE 10:38 — replace/append + amount; repeat push writes nothing (DQ14). v014.
S8-03 | Sync rules and conditions | ST-043 | 5 | Claude | Done | DONE-IN-CODE 10:38 — mode/strategy/amount/skipStages/minTotal, all skip paths write nothing. v014.
S8-04 | Errors + retry paths | ST-044 | 3 | Claude | Done | DONE-IN-CODE 10:38 — 502 + admin alert + retry w/ supersede. v014.
S8-05 | Card / UI extension surface | ST-045 | 5 | Claude | Done | DONE-IN-CODE 10:38 — /ui/sync shell; billing read-only gate. Live fetch open (R-Q6). v014.
S8-06 | Sync metrics + trends | ST-046 | 3 | Claude | Done | DONE-IN-CODE 10:38 — mix, success rate, topErrors, real durations. v014.
S8-07 | Permissions + audit | ST-047 | 3 | Claude | Done | DONE-IN-CODE 10:38 — sync:read/push/manage; four audited actions. v014.
S8-08 | Pause without data loss | ST-048 | 2 | Claude | Done | DONE-IN-CODE 10:38 — queue-and-drain (DQ14), nothing written while paused. v014.
S8-09 | Sync history import | ST-049 | 5 | Claude | Done | DONE-IN-CODE 10:38 — generic+rivalsync, 6-row error matrix, ragged tolerant. v014.
S8-10 | Sync notifications | ST-050 | 3 | Claude | Done | DONE-IN-CODE 10:38 — sync_failed admin fan-out + sync_completed. v014.
S8-11 | Data-flow diagram + retention | ST-065 | 3 | Claude | Done | DONE-IN-CODE 10:38 — 7 stores declared as data, asserted by tests (DQ15). v014.
S8-12 | Encryption + secrets posture | ST-066 | 5 | Claude | Partial | CODE DONE 10:38 — controls published; SEC-03 vault and SEC-04 at-rest reported PARTIAL, owner Senthil (R-Q11). v014.
S8-13 | Admin-sensitive audit log | ST-067 | 5 | Claude | Done | DONE-IN-CODE 10:38 — GET /api/audit/admin filters to security/money/access. v014.
S8-14 | Rate-limit backoff + circuit breaker | ST-070 | 5 | Claude | Done | DONE-IN-CODE 10:38 — breaker fronts platform writes (DQ16); open/half-open/close proven. v014.
S8-15 | Feature-usage heatmap | ST-073 | 3 | Claude | Done | DONE-IN-CODE 10:38 — ranked uses + unused-feature list. v014.
S8-16 | Weekly metrics email | ST-074 | 2 | Claude | Done | DONE-IN-CODE 10:38 — digest subject/body incl. revenue + breaches. Scheduler is deployment-side. v014.
S8-17 | Account health score | ST-075 | 5 | Claude | Done | DONE-IN-CODE 10:38 — usage/billing/support blend w/ reasons; funnel-milestone activity chain. v014.
S8-18 | Metrics export to CSV/warehouse | ST-076 | 3 | Claude | Done | DONE-IN-CODE 10:38 — GET /api/ops/export, text/csv. v014.
S8-19 | Configurable alert thresholds | ST-077 | 3 | Claude | Done | DONE-IN-CODE 10:38 — activation drop / error spike / churn, severity escalation. v014.
S8-20 | p95 latency budgets per surface | ST-087 | 3 | Claude | Done | DONE-IN-CODE 10:38 — 5 budgets, middleware sampling, breach detection. v014.
S8-21 | Load test at 5x launch traffic | ST-088 | 5 | Claude | Done | DONE-IN-CODE 10:38 — 250 mixed requests, budgets held, 50 deals synced once each. v014.
S8-22 | Zero-downtime deploy verified | ST-092 | 3 | Claude | Done | DONE-IN-CODE 10:38 — /ready 503 on drain, /health green, in-flight completes. v014.

## S9_Build_Board
S9 BUILD BOARD — Marketplace review prep — exit: submission-ready evidence pack
7 stories / 30 pts. Evidence: product workbook v015 (2026-09-13 10:56), codebase zip quoteflow_s9_codebase_20260913_1056.zip.
ID | Item | Story ref | Points | Owner | Status | Notes / Evidence
S9-01 | Pen-test evidence archived | ST-068 | 8 | Claude + Senthil | Partial | CODE DONE 10:56 — 10 abuse cases (8 automated / 1 manual / 1 external); pack states no external pen test commissioned. R-Q12 opened. v015.
S9-02 | Data export + delete-my-data self-serve | ST-069 | 5 | Claude | Done | DONE-IN-CODE 10:56 — full bundle + manifest; two-step token-confirmed deletion w/ receipt (DQ17). v015.
S9-03 | WCAG AA pass on primary flows | ST-089 | 3 | Claude | Done | DONE-IN-CODE 10:56 — all 5 shells pass 11 automated AA rules; checker tested against broken HTML. Manual audit scoped out explicitly. v015.
S9-04 | Backup + restore drill executed | ST-090 | 3 | Claude | Done | DONE-IN-CODE 10:56 — round-trip byte-compare; skipped sources surfaced; lossy source detected. Drill data-loss defect found and fixed (L-062). v015.
S9-05 | Chaos: platform outage degrades gracefully | ST-091 | 3 | Claude | Done | DONE-IN-CODE 10:56 — six properties asserted incl. signer never stranded, no partial state, readiness stays green. v015.
S9-06 | Listing copy A + B variants | ST-093 | 3 | Claude | Done | DONE-IN-CODE 10:56 — two full variants, every claim maps to a Done story, length limits asserted. v015.
S9-07 | 5 screenshots + 2-min demo video | ST-094 | 5 | Claude + Senthil | Partial | BRIEF DONE 10:56 — specs, 5-shot list, timed 1:55 script, checklist. CAPTURE blocked on live install (R-Q5). v015.

## S10_Build_Board
S10 BUILD BOARD — Launch surfaces: docs, support, public pages — exit: submission-ready
7 stories / 24 pts. Evidence: product workbook v016 (2026-09-13 11:11), codebase zip quoteflow_s10_codebase_20260913_1111.zip.
ID | Item | Story ref | Points | Owner | Status | Notes / Evidence
S10-01 | Help centre: 15 articles + search | ST-080 | 5 | Claude | Done | DONE-IN-CODE 11:11 — public endpoints; ranked search; feature-coverage test means shipping without docs fails the build. v016.
S10-02 | In-app chat with <4 business-hr response | ST-081 | 3 | Claude | Done | DONE-IN-CODE 11:11 — business-hours SLA (DQ20), deflection articles at open, overdue counted. Staffing the queue is operational. v016.
S10-03 | Demo video + interactive sandbox mode | ST-083 | 5 | Claude | Done | DONE-IN-CODE 11:11 — sandbox seeds realistic data, double-seed refused. Video script delivered in S9 brief; recording needs live install (R-Q5). v016.
S10-04 | Status page + incident comms template | ST-084 | 2 | Claude | Done | DONE-IN-CODE 11:11 — live-signal component roll-up; four pre-written templates. v016.
S10-05 | Pricing page/plan matrix + FAQ | ST-095 | 3 | Claude | Done | DONE-IN-CODE 11:11 — generated from PLANS (DQ19); 7-entry FAQ; values asserted against billing constants. v016.
S10-06 | Security/trust page live | ST-096 | 3 | Claude | Done | DONE-IN-CODE 11:11 — generated from DATA_FLOW/SCOPE_REGISTRY/SECURITY_CONTROLS; subprocessors listed; unmet controls published with owners. v016.
S10-07 | Submission dry-run by second reviewer | ST-097 | 3 | Claude | Done | DONE-IN-CODE 11:11 — 14 checklist items read from live state; 12 pass / 0 fail / 2 manual (DQ21). v016.

## S11_Build_Board
S11 BUILD BOARD — Launch — exit: live on the marketplace
3 stories / 8 pts. Evidence: product workbook v017 (2026-09-13 11:25), codebase zip quoteflow_s11_codebase_20260913_1125.zip.
ID | Item | Story ref | Points | Owner | Status | Notes / Evidence
S11-01 | In-app review ask after aha-moment | ST-082 | 3 | Claude | Done | DONE-IN-CODE 11:25 — happy-portal gates, lifetime cap, permanent decline, no review-gating (DQ22). v017.
S11-02 | Launch-day runbook: monitoring, rollback, comms | ST-098 | 3 | Claude | Done | DONE-IN-CODE 11:25 — live preflight incl. real restore drill, 7 verified rollback steps (77 min), comms tree (DQ23). v017.
S11-03 | First 10 design-partner reviews scheduled | ST-100 | 2 | Claude | Done | DONE-IN-CODE 11:25 — pipeline + outreach sequence; counts scheduled not intentions (DQ24). Contacting real partners is Senthil. v017.

## S12_Build_Board
S12 BUILD BOARD — Iterate & scale decision — exit: growth model with first CAC/LTV estimates
1 story / 2 pts. Evidence: product workbook v018 (2026-09-13 11:34), codebase zip quoteflow_s12_codebase_20260913_1134.zip. Note: the board exit criterion mentions a CAC/LTV growth model; the backlog carries only ST-099 for S12, and the backlog is the single source of truth — no growth model was invented to match the criterion.
ID | Item | Story ref | Points | Owner | Status | Notes / Evidence
S12-01 | Listing SEO iteration 1 from search-term data | ST-099 | 2 | Claude | Done | DONE-IN-CODE 11:34 — import + five-verdict classification + ranked recommendations; unsupported demand excluded from copy (DQ25); substring-matching defect found and fixed. Iteration against REAL numbers needs post-launch console data (R-Q5/R-Q10). v018.

## Review_Pass1_Board
COLD REVIEW PASS 1 — fix board (13 Sep 2026 11:51)
Full finding detail is on the Review_Findings sheet of product workbook v019. Code: quoteflow_review1_codebase_20260913_1151.zip.
Ref | Severity | Area | Status | Regression test
F-Q01 | CRITICAL | Privacy / backup — delete-my-data left 3 sources behind | Fixed | review1 F-Q01 + S9 assertions 8->11
F-Q02 | CRITICAL | Deployability — no entrypoint, no npm start | Fixed | review1 F-Q02
F-Q03 | CRITICAL | Identity — unsigned caller-declared headers | Fixed | review1 F-Q03 (4 rejection paths)
F-Q04 | CRITICAL | Billing — expired trial not read-only | Fixed | review1 F-Q04
F-Q05 | HIGH | OAuth — callback accepted any state | Fixed | review1 F-Q05
F-Q06 | HIGH | HTTP — async handler rejections hang the request | Fixed | review1 F-Q06
F-Q07 | MEDIUM | Tenancy — SEO corpus shared across portals | Fixed | review1 F-Q07
F-Q08 | MEDIUM | Memory — unbounded ledgers | Fixed | review1 F-Q08

## Review_Pass2_Board
COLD REVIEW PASS 2 — published claims vs code, and missing artifacts (13 Sep 2026 12:03)
Full detail on the Review_Findings sheet of product workbook v020. Code: quoteflow_review2_codebase_20260913_1203.zip.
Ref | Severity | Area | Status | Gate shipped with the fix
F-Q09 | CRITICAL | Retention — published schedule enforced by nothing | Fixed | Drift gate: sweepers must equal the published age-bounded stores
F-Q10 | HIGH | Redaction control with zero call sites (SEC-05) | Fixed | Regression on error-route and telemetry-prop redaction
F-Q11 | MEDIUM | Circuit breaker on writes only despite ST-070 claim | Fixed | Regression: open breaker means reads never reach the platform
F-Q12 | MEDIUM | No deploy workflow behind the rollback runbook | Fixed | Order gate: drain precedes cutover precedes verify
F-Q13 | MEDIUM | No DB schema behind retention / backup / at-rest claims | Fixed | Drift gate: every published store has a table + cascade + sweep index
F-Q14 | MEDIUM | Future-dated signatures replayable forever | Fixed | Regression: beyond-skew refused, modest skew tolerated

## Review_Pass3_Board
COLD REVIEW PASS 3 - surfaces wired to constants, and a tenancy boundary (13 Sep 2026 16:25)
Detail on Review_Findings in product workbook v021. Code: quoteflow_review3_codebase_20260913_1625.zip.
Ref | Severity | Area | Status | Gate shipped with the fix
F-Q15 | HIGH | Public status page wired to hardcoded false/0 | Fixed | Regression: real failed run degrades, open breaker escalates to outage
F-Q16 | MEDIUM | Preflight readiness hardcoded true | Fixed | Regression: draining flips PRE-03 and the decision to no_go
F-Q17 | CRITICAL | Nine vendor surfaces reachable with tenant RBAC | Fixed | Regression: tenant creds refused, wrong same-length token refused, unset = closed

## ExtReview_V001_Board
EXTERNAL REVIEW V001 — fix board (ChatGPT, 13 Sep 2026 23:02)
First review from outside this build loop. Full detail on Review_Findings in product workbook v035. Code: quoteflow_extreview1_codebase_20260913_2330.zip. Ids preserved verbatim (CB-02) — nothing renumbered, nothing closed without evidence.
Ref | Severity | Area | Status | Gate shipped with the fix / what closure needs
QF-001 | BLOCKER | No HubSpot Projects or UI-extension artifact exists | Open | Needs a dev portal (R-Q15). Legacy CRM cards stop rendering 31 Oct 2026 — this is the deadline that matters most.
QF-002 | BLOCKER | OAuth tokens always in-memory | Mitigated, not fixed | Production refuses to boot naming QF-002. Real fix is PgTokenStore with encrypted refresh tokens.
QF-003 | BLOCKER | Retention deletion queue in-memory | Mitigated, not fixed | Same refusal. Real fix is a durable outbox with idempotent claim/lease/retry/DLQ.
QF-004 | BLOCKER | No production session mint path | Open | Blocked on QF-001 — the session must be exchanged from a verified extension context.
QF-005 | BLOCKER | HubSpot calls carried no Authorization header | Fixed | Regression: every /crm/ call carries Bearer; 401 forces one refresh then demands re-install.
QF-006 | BLOCKER | Line items posted to an endpoint that does not exist | Fixed | Regression: create line_items + v4 association; replace archives first; /line-items must never reappear.
QF-007 | BLOCKER | Billing providers unauthenticated, running on stubs | Open | Duplicates R-Q10. Needs test-mode credentials before the call shape is worth rewriting.
QF-008 | BLOCKER | No lockfile while CI runs npm ci | Fixed | Clean room: npm ci → tsc → jest all green from the exact tree with no node_modules.
QF-009 | HIGH | Deploy workflow echoed its two most important steps | Fixed (honesty) | Both steps exit 1 with ::error::QF-009 when unconfigured. A real deploy still needs a hosting target.
QF-010 | HIGH | Email transport is a no-op in production wiring | Mitigated, not fixed | Refusal covers it; provider choice is Senthil (R-Q7).
QF-011 | HIGH | Coverage used as a proxy for external correctness | Structural fix landed | Evidence classes on Traceability_Matrix cols L/M; Done now requires the classes, not just green tests.
QF-012 | HIGH | Three different metric truths across README/workbook/package | Fixed | scripts/release-manifest.js counts the tree; CI publishes it; closeout figures regenerated.
QF-013 | HIGH | Native HubSpot CPQ erodes the feature moat | Open — strategy | Matches R-Q1, raised at v006 and never mitigated. Design-partner evidence, not code.
QF-014 | MEDIUM | Financial model is assumption-led | Open | Needs low/base/high scenarios with each input citing a source or experiment id.

## Traceability_Matrix
TRACEABILITY MATRIX — 100 stories: module -> epic -> story -> sprint -> verification -> evidence
Source: v009 Full_Backlog (single source of truth). Status "Done" = Done-in-code under the D13 100% gate; Evidence cites the product-workbook version + test run carrying the proof. Rollup formulas read cols E/G/J.
Story ID | Epic | Module / feature | Story | Points | Priority | Sprint | Primary screen | Verification | Status | Evidence | Required evidence classes (CB-01) | Evidence status (V001)
ST-001 | F1 | Price book + bundles | As a Sales manager, I can set up Price book + bundles with sensible defaults in one screen | 5 | P0 | S2 | SCR-3 Price book workspace | Automated: unit + HTTP integration (supertest) | Done | v008 22:19 — priceBookService.setupDefaults idempotent + POST /api/pricebooks/defaults; s2 + s2api suites; 100% x4 (run 2219) | CODE | CODE satisfied — the only class this story requires. Stays Done.
ST-002 | F1 | Price book + bundles | As a Sales manager, the Price book + bundles happy path completes without documentation | 8 | P0 | S2 | SCR-3 Price book workspace | Automated: unit + HTTP integration (supertest) | Done | v008 22:19 — priceQuote engine (bundle maths 804.60+672.60=1477.20) + quotes/price E2E over HTTP; 100% x4 (run 2219) | CODE | CODE satisfied — the only class this story requires. Stays Done.
ST-003 | F1 | Price book + bundles | As a RevOps, I can customise Price book + bundles rules/conditions for my workflow | 5 | P1 | S2 | SCR-3 Price book workspace | Automated: unit + HTTP integration (supertest) | Done | v008 22:19 — addRule validation + best-discount-wins engine; 7-case matrix + tiered HTTP quote; 100% x4 (run 2219) | CODE | CODE satisfied — the only class this story requires. Stays Done.
ST-004 | F1 | Price book + bundles | As a user, Price book + bundles shows clear errors and retry paths on platform API failures | 3 | P0 | S2 | SCR-3 Price book workspace | Automated: unit + HTTP integration (supertest) | Done | v008 22:19 — AppError + PlatformClient backoff [100,200]; 6 unit + 7 HTTP platform/check cases; 100% x4 (run 2219) | CODE | CODE satisfied — the only class this story requires. Stays Done.
ST-005 | F1 | Price book + bundles | As a Rep, Price book + bundles works on the HubSpot CRM card + UI extension surface end-to-end | 5 | P0 | S3 | SCR-3 Price book workspace | Automated: unit + HTTP integration (supertest) | Partial | v028 20 Sep — legacy CRM card DELETED; dealCard.ts + GET /api/cards/deal/:dealId over an authenticated session | CODE + CONTRACT + LIVE-HUBSPOT | CODE satisfied. MISSING: CONTRACT, LIVE-HUBSPOT — the app card has never been rendered by HubSpot (R-Q15).
ST-006 | F1 | Price book + bundles | As a RevOps, I can see Price book + bundles performance metrics and trends | 3 | P1 | S3 | SCR-3 Price book workspace | Automated: unit + HTTP integration (supertest) | Partial | v009 22:52 — metricsService aggregates + 7-day UTC trend + GET /api/metrics; bucket-boundary units + 731.60 HTTP case; 100% x4 (run 2252) | CODE + OPS | CODE satisfied. MISSING: OPS — no live portal, provider or external assessment exists yet.
ST-007 | F1 | Price book + bundles | As a user, Price book + bundles respects role permissions and audit logging | 3 | P1 | S3 | SCR-3 Price book workspace | Automated: unit + HTTP integration (supertest) | Partial | v009 22:52 — audit.ts + record() on 14 mutating routes + GET /api/audit; actor/target HTTP assertions; 100% x4 (run 2252) | CODE + SECURITY | CODE satisfied. MISSING: SECURITY — no live portal, provider or external assessment exists yet.
ST-008 | F1 | Price book + bundles | As a Sales manager, I can pause/disable Price book + bundles without data loss | 2 | P2 | S3 | SCR-3 Price book workspace | Automated: unit + HTTP integration (supertest) | Done | v009 22:52 — catalog paused flag + requireActive 409 gate + settings routes; writes-blocked/reads-intact/resume E2E; 100% x4 (run 2252) | CODE | CODE satisfied — the only class this story requires. Stays Done.
ST-009 | F1 | Price book + bundles | As a RevOps, I can import/migrate existing data into Price book + bundles (CSV + competitor importer) | 5 | P1 | S3 | SCR-3 Price book workspace | Automated: unit + HTTP integration (supertest) | Done | v009 22:52 — importService quoted-CSV parser + generic/rivalcpq maps + row-level errors; 6-row error matrix + import->quote E2E; 100% x4 (run 2252) | CODE | CODE satisfied — the only class this story requires. Stays Done.
ST-010 | F1 | Price book + bundles | As a user, I get notifications (in-app + email) for key Price book + bundles events with per-type mute | 3 | P2 | S3 | SCR-3 Price book workspace | Automated: unit + HTTP integration (supertest) | Done | v009 22:52 — notifications domain+service (per-type mute, failed-email retry) + 5 routes; mute-suppression + 502-retryable->healed E2E; 100% x4 (run 2252) | CODE | CODE satisfied — the only class this story requires. Stays Done.
ST-011 | F2 | Approval chains | As a Sales manager, I can set up Approval chains with sensible defaults in one screen | 5 | P0 | S3 | SCR-4 Approval chains builder | Automated: unit + HTTP integration (supertest) | Done | v009 22:52 — approvalService.setupDefaults (15% admin chain, idempotent) + defaults route; 201/200 + member-403 cases; 100% x4 (run 2252) | CODE | CODE satisfied — the only class this story requires. Stays Done.
ST-012 | F2 | Approval chains | As a Sales manager, the Approval chains happy path completes without documentation | 8 | P0 | S3 | SCR-4 Approval chains builder | Automated: unit + HTTP integration (supertest) | Done | v009 22:52 — requestApproval strict-> eval + decide walk + fan-out; full E2E pending->notified->approved->requester-notified; 100% x4 (run 2252) | CODE | CODE satisfied — the only class this story requires. Stays Done.
ST-013 | F2 | Approval chains | As a RevOps, I can customise Approval chains rules/conditions for my workflow | 5 | P1 | S3 | SCR-4 Approval chains builder | Automated: unit + HTTP integration (supertest) | Done | v009 22:52 — createChain 10-case validation + DQ3 step snapshot; owner-step-blocks-admin E2E; 100% x4 (run 2252) | CODE | CODE satisfied — the only class this story requires. Stays Done.
ST-014 | F2 | Approval chains | As a user, Approval chains shows clear errors and retry paths on platform API failures | 3 | P0 | S3 | SCR-4 Approval chains builder | Automated: unit + HTTP integration (supertest) | Done | v009 22:52 — typed 400/403/404/409 approval errors + NOTIFICATION_EMAIL_RETRY_FAILED 502 retryable; error-shape HTTP cases; 100% x4 (run 2252) | CODE | CODE satisfied — the only class this story requires. Stays Done.
ST-015 | F2 | Approval chains | As a Rep, Approval chains works on the HubSpot CRM card + UI extension surface end-to-end | 5 | P0 | S4 | SCR-4 Approval chains builder | Automated: unit + HTTP integration (supertest) | Partial | v010 08:17 — crmCard +pending prop +Approvals action + /ui/approvals; signed-card HTTP case pending=1; smoke card step; 100% x4 (run 0817). Live fetch OPEN (R-Q6) | CODE + CONTRACT + LIVE-HUBSPOT | CODE satisfied. MISSING: CONTRACT, LIVE-HUBSPOT — no live portal, provider or external assessment exists yet.
ST-016 | F2 | Approval chains | As a RevOps, I can see Approval chains performance metrics and trends | 3 | P1 | S4 | SCR-4 Approval chains builder | Automated: unit + HTTP integration (supertest) | Partial | v010 08:17 — approvalService.metrics; unit avg 2000ms/25% auto + HTTP 5000ms/50% auto; 100% x4 (run 0817) | CODE + OPS | CODE satisfied. MISSING: OPS — no live portal, provider or external assessment exists yet.
ST-017 | F2 | Approval chains | As a user, Approval chains respects role permissions and audit logging | 3 | P1 | S4 | SCR-4 Approval chains builder | Automated: unit + HTTP integration (supertest) | Partial | v010 08:17 — decision audit ":approved" target + ?action= filter HTTP cases; 100% x4 (run 0817) | CODE + SECURITY | CODE satisfied. MISSING: SECURITY — no live portal, provider or external assessment exists yet.
ST-018 | F2 | Approval chains | As a Sales manager, I can pause/disable Approval chains without data loss | 2 | P2 | S4 | SCR-4 Approval chains builder | Automated: unit + HTTP integration (supertest) | Done | v010 08:17 — feature pause map + requireActive(feature); approvals-paused-blocks-new/decisions-proceed E2E; 100% x4 (run 0817) | CODE | CODE satisfied — the only class this story requires. Stays Done.
ST-019 | F2 | Approval chains | As a RevOps, I can import/migrate existing data into Approval chains (CSV + competitor importer) | 5 | P1 | S4 | SCR-4 Approval chains builder | Automated: unit + HTTP integration (supertest) | Done | v010 08:17 — importChainsCsv 7-row error matrix + rivalcpq + NaN guard; imported chain governs live request E2E; 100% x4 (run 0817) | CODE | CODE satisfied — the only class this story requires. Stays Done.
ST-020 | F2 | Approval chains | As a user, I get notifications (in-app + email) for key Approval chains events with per-type mute | 3 | P2 | S4 | SCR-4 Approval chains builder | Automated: unit + HTTP integration (supertest) | Done | v010 08:17 — remind route fan-out honouring mutes; NOT_OWN/NOT_PENDING/404 guards; 100% x4 (run 0817) | CODE | CODE satisfied — the only class this story requires. Stays Done.
ST-021 | F3 | E-signature | As a Sales manager, I can set up E-signature with sensible defaults in one screen | 5 | P0 | S5 | SCR-5 E-signature view | Automated: unit + HTTP integration (supertest) | Partial | v011 08:52 — defaults idempotent + teaching 404; 100% x4 (run 0852) | CODE + SECURITY | CODE satisfied. MISSING: SECURITY — no live portal, provider or external assessment exists yet.
ST-022 | F3 | E-signature | As a Sales manager, the E-signature happy path completes without documentation | 8 | P0 | S5 | SCR-5 E-signature view | Automated: unit + HTTP integration (supertest) | Partial | v011 08:52 — HTTP journey create->view->sign->completed (672.6 carried), docHash determinism, DQ8 validate-then-mint; 100% x4 (run 0852) | CODE + SECURITY | CODE satisfied. MISSING: SECURITY — no live portal, provider or external assessment exists yet.
ST-023 | F3 | E-signature | As a RevOps, I can customise E-signature rules/conditions for my workflow | 5 | P1 | S5 | SCR-5 E-signature view | Automated: unit + HTTP integration (supertest) | Partial | v011 08:52 — 9-case validation matrix + snapshot-at-creation; 100% x4 (run 0852) | CODE + SECURITY | CODE satisfied. MISSING: SECURITY — no live portal, provider or external assessment exists yet.
ST-024 | F3 | E-signature | As a user, E-signature shows clear errors and retry paths on platform API failures | 3 | P0 | S5 | SCR-5 E-signature view | Automated: unit + HTTP integration (supertest) | Partial | v011 08:52 — all typed refusals over HTTP; sticky-expiry clock-rewind unit; 100% x4 (run 0852) | CODE + SECURITY | CODE satisfied. MISSING: SECURITY — no live portal, provider or external assessment exists yet.
ST-025 | F3 | E-signature | As a Rep, E-signature works on the HubSpot CRM card + UI extension surface end-to-end | 5 | P0 | S5 | SCR-5 E-signature view | Automated: unit + HTTP integration (supertest) | Partial | v011 08:52 — card count 1->0; /ui/sign shell. Live fetch OPEN (R-Q6); 100% x4 (run 0852) | CODE + CONTRACT + LIVE-HUBSPOT + SECURITY | CODE satisfied. MISSING: CONTRACT, LIVE-HUBSPOT, SECURITY — no live portal, provider or external assessment exists yet.
ST-026 | F3 | E-signature | As a RevOps, I can see E-signature performance metrics and trends | 3 | P1 | S5 | SCR-5 E-signature view | Automated: unit + HTTP integration (supertest) | Partial | v011 08:52 — mix 40% / 3000ms; +20d expiry recount; 100% x4 (run 0852) | CODE + SECURITY + OPS | CODE satisfied. MISSING: SECURITY, OPS — no live portal, provider or external assessment exists yet.
ST-027 | F3 | E-signature | As a user, E-signature respects role permissions and audit logging | 3 | P1 | S5 | SCR-5 E-signature view | Automated: unit + HTTP integration (supertest) | Partial | v011 08:52 — perm matrix + signer:<email> audit; 100% x4 (run 0852) | CODE + SECURITY | CODE satisfied. MISSING: SECURITY — no live portal, provider or external assessment exists yet.
ST-028 | F3 | E-signature | As a Sales manager, I can pause/disable E-signature without data loss | 2 | P2 | S5 | SCR-5 E-signature view | Automated: unit + HTTP integration (supertest) | Partial | v011 08:52 — paused create 409, sent link completes (DQ9); 100% x4 (run 0852) | CODE + SECURITY | CODE satisfied. MISSING: SECURITY — no live portal, provider or external assessment exists yet.
ST-029 | F3 | E-signature | As a RevOps, I can import/migrate existing data into E-signature (CSV + competitor importer) | 5 | P1 | S5 | SCR-5 E-signature view | Automated: unit + HTTP integration (supertest) | Partial | v011 08:52 — error matrix + ragged rows + rivalsign; 100% x4 (run 0852) | CODE + SECURITY | CODE satisfied. MISSING: SECURITY — no live portal, provider or external assessment exists yet.
ST-030 | F3 | E-signature | As a user, I get notifications (in-app + email) for key E-signature events with per-type mute | 3 | P2 | S5 | SCR-5 E-signature view | Automated: unit + HTTP integration (supertest) | Partial | v011 08:52 — three envelope types observed over HTTP; 100% x4 (run 0852) | CODE + SECURITY | CODE satisfied. MISSING: SECURITY — no live portal, provider or external assessment exists yet.
ST-031 | F4 | Quote analytics | As a Sales manager, I can set up Quote analytics with sensible defaults in one screen | 5 | P0 | S6 | SCR-8 Analytics | Automated: unit + HTTP integration (supertest) | Done | v012 12:47 — defaults idempotent + 404; 100% x4 (run 1247) | CODE | CODE satisfied — the only class this story requires. Stays Done.
ST-032 | F4 | Quote analytics | As a Sales manager, the Quote analytics happy path completes without documentation | 8 | P0 | S6 | SCR-8 Analytics | Automated: unit + HTTP integration (supertest) | Done | v012 12:47 — exact-math summary + HTTP w/ stale wiring; 100% x4 (run 1247) | CODE | CODE satisfied — the only class this story requires. Stays Done.
ST-033 | F4 | Quote analytics | As a RevOps, I can customise Quote analytics rules/conditions for my workflow | 5 | P1 | S6 | SCR-8 Analytics | Automated: unit + HTTP integration (supertest) | Done | v012 12:47 — 11-case matrix; 100% x4 (run 1247) | CODE | CODE satisfied — the only class this story requires. Stays Done.
ST-034 | F4 | Quote analytics | As a user, Quote analytics shows clear errors and retry paths on platform API failures | 3 | P0 | S6 | SCR-8 Analytics | Automated: unit + HTTP integration (supertest) | Done | v012 12:47 — pre-setup 404s + export shapes; 100% x4 (run 1247) | CODE | CODE satisfied — the only class this story requires. Stays Done.
ST-035 | F4 | Quote analytics | As a Rep, Quote analytics works on the HubSpot CRM card + UI extension surface end-to-end | 5 | P0 | S6 | SCR-8 Analytics | Automated: unit + HTTP integration (supertest) | Partial | v012 12:47 — card [4]=Quotes(7d)=1; 3 actions; shell. R-Q6 open; 100% x4 (run 1247) | CODE + CONTRACT + LIVE-HUBSPOT | CODE satisfied. MISSING: CONTRACT, LIVE-HUBSPOT — no live portal, provider or external assessment exists yet.
ST-036 | F4 | Quote analytics | As a RevOps, I can see Quote analytics performance metrics and trends | 3 | P1 | S6 | SCR-8 Analytics | Automated: unit + HTTP integration (supertest) | Partial | v012 12:47 — buckets + discounter ranking; 100% x4 (run 1247) | CODE + OPS | CODE satisfied. MISSING: OPS — no live portal, provider or external assessment exists yet.
ST-037 | F4 | Quote analytics | As a user, Quote analytics respects role permissions and audit logging | 3 | P1 | S6 | SCR-8 Analytics | Automated: unit + HTTP integration (supertest) | Partial | v012 12:47 — 403 matrix + audit; 100% x4 (run 1247) | CODE + SECURITY | CODE satisfied. MISSING: SECURITY — no live portal, provider or external assessment exists yet.
ST-038 | F4 | Quote analytics | As a Sales manager, I can pause/disable Quote analytics without data loss | 2 | P2 | S6 | SCR-8 Analytics | Automated: unit + HTTP integration (supertest) | Done | v012 12:47 — DQ10 proof: paused-time quote visible after resume; 100% x4 (run 1247) | CODE | CODE satisfied — the only class this story requires. Stays Done.
ST-039 | F4 | Quote analytics | As a RevOps, I can import/migrate existing data into Quote analytics (CSV + competitor importer) | 5 | P1 | S6 | SCR-8 Analytics | Automated: unit + HTTP integration (supertest) | Done | v012 12:47 — error matrix + per-column fallbacks + rivaliq; 100% x4 (run 1247) | CODE | CODE satisfied — the only class this story requires. Stays Done.
ST-040 | F4 | Quote analytics | As a user, I get notifications (in-app + email) for key Quote analytics events with per-type mute | 3 | P2 | S6 | SCR-8 Analytics | Automated: unit + HTTP integration (supertest) | Done | v012 12:47 — goal-once + mute suppression over HTTP; 100% x4 (run 1247) | CODE | CODE satisfied — the only class this story requires. Stays Done.
ST-041 | F5 | Deal/line-item sync | As a Sales manager, I can set up Deal/line-item sync with sensible defaults in one screen | 5 | P0 | S8 | SCR-3 + HubSpot deal record | Automated: unit + HTTP integration (supertest) | Partial | v014 10:38 — defaults + pre-setup 404; 100% x4 (run 1038) | CODE + CONTRACT + LIVE-HUBSPOT | CODE satisfied. MISSING: CONTRACT, LIVE-HUBSPOT — no live portal, provider or external assessment exists yet.
ST-042 | F5 | Deal/line-item sync | As a Sales manager, the Deal/line-item sync happy path completes without documentation | 8 | P0 | S8 | SCR-3 + HubSpot deal record | Automated: unit + HTTP integration (supertest) | Partial | v014 10:38 — push writes lines + amount; repeat is a no-op (DQ14); 100% x4 (run 1038) | CODE + CONTRACT + LIVE-HUBSPOT | CODE satisfied. MISSING: CONTRACT, LIVE-HUBSPOT — no live portal, provider or external assessment exists yet.
ST-043 | F5 | Deal/line-item sync | As a RevOps, I can customise Deal/line-item sync rules/conditions for my workflow | 5 | P1 | S8 | SCR-3 + HubSpot deal record | Automated: unit + HTTP integration (supertest) | Partial | v014 10:38 — 8-case matrix; all skip paths write nothing; 100% x4 (run 1038) | CODE + CONTRACT + LIVE-HUBSPOT | CODE satisfied. MISSING: CONTRACT, LIVE-HUBSPOT — no live portal, provider or external assessment exists yet.
ST-044 | F5 | Deal/line-item sync | As a user, Deal/line-item sync shows clear errors and retry paths on platform API failures | 3 | P0 | S8 | SCR-3 + HubSpot deal record | Automated: unit + HTTP integration (supertest) | Partial | v014 10:38 — 502 + alert + retry/supersede; re-failed retry still 502; 100% x4 (run 1038) | CODE + CONTRACT + LIVE-HUBSPOT | CODE satisfied. MISSING: CONTRACT, LIVE-HUBSPOT — no live portal, provider or external assessment exists yet.
ST-045 | F5 | Deal/line-item sync | As a Rep, Deal/line-item sync works on the HubSpot CRM card + UI extension surface end-to-end | 5 | P0 | S8 | SCR-3 + HubSpot deal record | Automated: unit + HTTP integration (supertest) | Partial | v014 10:38 — /ui/sync shell; read-only 402; R-Q6 open; 100% x4 (run 1038) | CODE + CONTRACT + LIVE-HUBSPOT | CODE satisfied. MISSING: CONTRACT, LIVE-HUBSPOT — no live portal, provider or external assessment exists yet.
ST-046 | F5 | Deal/line-item sync | As a RevOps, I can see Deal/line-item sync performance metrics and trends | 3 | P1 | S8 | SCR-3 + HubSpot deal record | Automated: unit + HTTP integration (supertest) | Partial | v014 10:38 — success rate, topErrors across 3 codes, real durations; 100% x4 (run 1038) | CODE + CONTRACT + LIVE-HUBSPOT + OPS | CODE satisfied. MISSING: CONTRACT, LIVE-HUBSPOT, OPS — no live portal, provider or external assessment exists yet.
ST-047 | F5 | Deal/line-item sync | As a user, Deal/line-item sync respects role permissions and audit logging | 3 | P1 | S8 | SCR-3 + HubSpot deal record | Automated: unit + HTTP integration (supertest) | Partial | v014 10:38 — perm matrix + audited actions; 100% x4 (run 1038) | CODE + CONTRACT + LIVE-HUBSPOT + SECURITY | CODE satisfied. MISSING: CONTRACT, LIVE-HUBSPOT, SECURITY — no live portal, provider or external assessment exists yet.
ST-048 | F5 | Deal/line-item sync | As a Sales manager, I can pause/disable Deal/line-item sync without data loss | 2 | P2 | S8 | SCR-3 + HubSpot deal record | Automated: unit + HTTP integration (supertest) | Partial | v014 10:38 — queued writes nothing, drains on resume; 100% x4 (run 1038) | CODE + CONTRACT + LIVE-HUBSPOT | CODE satisfied. MISSING: CONTRACT, LIVE-HUBSPOT — no live portal, provider or external assessment exists yet.
ST-049 | F5 | Deal/line-item sync | As a RevOps, I can import/migrate existing data into Deal/line-item sync (CSV + competitor importer) | 5 | P1 | S8 | SCR-3 + HubSpot deal record | Automated: unit + HTTP integration (supertest) | Partial | v014 10:38 — 6-row error matrix + ragged columns + rivalsync; 100% x4 (run 1038) | CODE + CONTRACT + LIVE-HUBSPOT | CODE satisfied. MISSING: CONTRACT, LIVE-HUBSPOT — no live portal, provider or external assessment exists yet.
ST-050 | F5 | Deal/line-item sync | As a user, I get notifications (in-app + email) for key Deal/line-item sync events with per-type mute | 3 | P2 | S8 | SCR-3 + HubSpot deal record | Automated: unit + HTTP integration (supertest) | Partial | v014 10:38 — sync_failed + sync_completed incl. plural wording; 100% x4 (run 1038) | CODE + CONTRACT + LIVE-HUBSPOT | CODE satisfied. MISSING: CONTRACT, LIVE-HUBSPOT — no live portal, provider or external assessment exists yet.
ST-051 | E1 | Install & lifecycle | Marketplace OAuth install completes and lands on welcome state in <2 min | 5 | P0 | S1 | SCR-1 Onboarding / first-run | Automated: unit + HTTP integration (supertest) | Partial | v007 22:03 — oauth.ts + GET /install,/oauth/callback + tokenStore/config; suites services/app/units; 100% x4 (run 2203) | CODE + CONTRACT + LIVE-HUBSPOT + COMMERCIAL | CODE satisfied. MISSING: CONTRACT, LIVE-HUBSPOT, COMMERCIAL — no live portal, provider or external assessment exists yet.
ST-052 | E1 | Install & lifecycle | Uninstall webhook removes tokens, schedules data deletion per policy | 3 | P0 | S1 | SCR-1 Onboarding / first-run | Automated: unit + HTTP integration (supertest) | Partial | v007 22:03 — webhooks/signature.ts (v3 HMAC + replay guard) + uninstall.ts + deletionQueue; 7 webhook HTTP cases; 100% x4 (run 2203) | CODE + CONTRACT + LIVE-HUBSPOT | CODE satisfied. MISSING: CONTRACT, LIVE-HUBSPOT — no live portal, provider or external assessment exists yet.
ST-053 | E1 | Install & lifecycle | Re-install restores account within retention window | 3 | P1 | S2 | SCR-1 Onboarding / first-run | Automated: unit + HTTP integration (supertest) | Partial | v008 22:19 — restore-on-reinstall + DeletionExecutor retention purge; webhook->reinstall->restored-note E2E; 100% x4 (run 2219) | CODE + CONTRACT + LIVE-HUBSPOT + SECURITY | CODE satisfied. MISSING: CONTRACT, LIVE-HUBSPOT, SECURITY — no live portal, provider or external assessment exists yet.
ST-054 | E1 | Install & lifecycle | Multi-user roles: owner/admin/member permission matrix enforced | 5 | P0 | S2 | SCR-1 Onboarding / first-run | Automated: unit + HTTP integration (supertest) | Partial | v008 22:19 — rbac matrix + identity middleware + first-user-owner bootstrap + /api/users; enforcement across endpoints; 100% x4 (run 2219) | CODE + CONTRACT + LIVE-HUBSPOT | CODE satisfied. MISSING: CONTRACT, LIVE-HUBSPOT — no live portal, provider or external assessment exists yet.
ST-055 | E1 | Install & lifecycle | Session/token refresh survives platform token rotation | 3 | P0 | S1 | SCR-1 Onboarding / first-run | Automated: unit + HTTP integration (supertest) | Partial | v007 22:03 — tokenManager.ts rotation-safe refresh (60s skew, 5xx retry, 401 path); 9 unit cases; 100% x4 (run 2203) | CODE + CONTRACT + LIVE-HUBSPOT | CODE satisfied. MISSING: CONTRACT, LIVE-HUBSPOT — no live portal, provider or external assessment exists yet.
ST-056 | E1 | Install & lifecycle | Install telemetry: source attribution (listing/search/referral) captured | 2 | P1 | S1 | SCR-1 Onboarding / first-run | Automated: unit + HTTP integration (supertest) | Partial | v007 22:03 — telemetry.ts + normaliseSource + OAuth state attribution; hostile-source bucketing tests; 100% x4 (run 2203) | CODE + CONTRACT + LIVE-HUBSPOT + COMMERCIAL + OPS | CODE satisfied. MISSING: CONTRACT, LIVE-HUBSPOT, COMMERCIAL, OPS — no live portal, provider or external assessment exists yet.
ST-057 | E5 | Billing & plans | 14-day trial without card; banner shows days remaining | 5 | P0 | S6 | SCR-7 Billing | Automated: unit + HTTP integration (supertest) | Partial | v012 12:47 — countdown 14->1, expired flip, first-touch seeding; 100% x4 (run 1247) | CODE + COMMERCIAL | CODE satisfied. MISSING: COMMERCIAL — no live portal, provider or external assessment exists yet.
ST-058 | E5 | Billing & plans | Upgrade/downgrade mid-cycle prorates correctly | 5 | P0 | S6 | SCR-7 Billing | Automated: unit + HTTP integration (supertest) | Partial | v012 12:47 — exact cents 3267/13267/10000; -7500 no-call; clamp 0/0/0; 100% x4 (run 1247) | CODE + COMMERCIAL | CODE satisfied. MISSING: COMMERCIAL — no live portal, provider or external assessment exists yet.
ST-059 | E5 | Billing & plans | Marketplace billing API used where mandated; external Stripe fallback elsewhere | 8 | P0 | S6 | SCR-7 Billing | Automated: unit + HTTP integration (supertest) | Partial | v012 12:47 — routed calls + URLs asserted + failure persists nothing; R-Q10 open; 100% x4 (run 1247) | CODE + COMMERCIAL | CODE satisfied. MISSING: COMMERCIAL — no live portal, provider or external assessment exists yet.
ST-060 | E5 | Billing & plans | Failed payment: 7-day grace, 3 dunning emails, then read-only mode | 3 | P1 | S7 | SCR-7 Billing | Automated: unit + HTTP integration (supertest) | Partial | v013 10:26 — grace/notice cadence/lapse/recovery + writes 402 while reads 200; 100% x4 (run 1026) | CODE + COMMERCIAL | CODE satisfied. MISSING: COMMERCIAL — no live portal, provider or external assessment exists yet.
ST-061 | E5 | Billing & plans | Plan limits enforced with upgrade prompts at 80%/100% | 3 | P1 | S7 | SCR-7 Billing | Automated: unit + HTTP integration (supertest) | Partial | v013 10:26 — 80% once per crossing, 100% blocks all quote paths, upgrade lifts ceiling; 100% x4 (run 1026) | CODE + COMMERCIAL | CODE satisfied. MISSING: COMMERCIAL — no live portal, provider or external assessment exists yet.
ST-062 | E5 | Billing & plans | Invoices/receipts downloadable; GST/VAT fields supported | 3 | P2 | S7 | SCR-7 Billing | Automated: unit + HTTP integration (supertest) | Partial | v013 10:26 — GST 18% / VAT 20% to the cent, receipt parity, no invoice on net<=0; 100% x4 (run 1026) | CODE + COMMERCIAL + OPS | CODE satisfied. MISSING: COMMERCIAL, OPS — no live portal, provider or external assessment exists yet.
ST-063 | E5 | Billing & plans | Cancellation flow with save-offer and exit survey | 3 | P1 | S7 | SCR-7 Billing | Automated: unit + HTTP integration (supertest) | Partial | v013 10:26 — offer guard, survey validation, cancelled portal reads + exports; 100% x4 (run 1026) | CODE + COMMERCIAL | CODE satisfied. MISSING: COMMERCIAL — no live portal, provider or external assessment exists yet.
ST-064 | E6 | Compliance & security | Scopes requested map 1:1 to shipped features (least privilege doc) | 3 | P0 | S7 | SCR-6 Settings & team | Automated: unit + HTTP integration (supertest) | Partial | v013 10:26 — leastPrivilege vs real config; over/under-asking flagged; 100% x4 (run 1026) | CODE + CONTRACT + LIVE-HUBSPOT + SECURITY | CODE satisfied. MISSING: CONTRACT, LIVE-HUBSPOT, SECURITY — no live portal, provider or external assessment exists yet.
ST-065 | E6 | Compliance & security | Data-flow diagram + retention policy published | 3 | P0 | S8 | SCR-6 Settings & team | Automated: unit + HTTP integration (supertest) | Partial | v014 10:38 — 7 stores asserted complete incl. 7-year billing retention; 100% x4 (run 1038) | CODE + SECURITY | CODE satisfied. MISSING: SECURITY — no live portal, provider or external assessment exists yet.
ST-066 | E6 | Compliance & security | Encryption at rest + in transit verified; secrets in vault | 5 | P0 | S8 | SCR-6 Settings & team | Automated: unit + HTTP integration (supertest) | Partial | v014 10:38 — PARTIAL on SEC-03/SEC-04 with owner (R-Q11); redaction proven; 100% x4 (run 1038) | CODE + SECURITY | CODE satisfied. MISSING: SECURITY — no live portal, provider or external assessment exists yet.
ST-067 | E6 | Compliance & security | Audit log for admin-sensitive actions | 5 | P1 | S8 | SCR-6 Settings & team | Automated: unit + HTTP integration (supertest) | Partial | v014 10:38 — admin view includes pause/subscribe/sync.settings, excludes sync.push; 100% x4 (run 1038) | CODE + SECURITY | CODE satisfied. MISSING: SECURITY — no live portal, provider or external assessment exists yet.
ST-068 | E6 | Compliance & security | Pen-test (or platform-required evidence) completed and archived | 8 | P0 | S9 | SCR-6 Settings & team | Automated: unit + HTTP integration (supertest) | Partial | v015 10:56 — 10 abuse cases, statement disclaims uncommissioned pen test; R-Q12; 100% x4 (run 1056) | CODE + SECURITY | CODE satisfied. MISSING: SECURITY — no live portal, provider or external assessment exists yet.
ST-069 | E6 | Compliance & security | Data export + delete-my-data self-serve | 5 | P0 | S9 | SCR-6 Settings & team | Automated: unit + HTTP integration (supertest) | Partial | v015 10:56 — export + manifest + two-step deletion w/ receipt and expiry; 100% x4 (run 1056) | CODE + SECURITY | CODE satisfied. MISSING: SECURITY — no live portal, provider or external assessment exists yet.
ST-070 | E6 | Compliance & security | Rate-limit backoff + circuit breaker on platform APIs | 5 | P0 | S8 | SCR-6 Settings & team | Automated: unit + HTTP integration (supertest) | Partial | v014 10:38 — open/fail-fast/half-open/close + failed-trial re-open; 100% x4 (run 1038) | CODE + SECURITY | CODE satisfied. MISSING: SECURITY — no live portal, provider or external assessment exists yet.
ST-071 | E7 | Telemetry & analytics | Activation funnel events (install->setup->aha->habit) in one dashboard | 5 | P0 | S4 | SCR-8 Analytics | Automated: unit + HTTP integration (supertest) | Partial | v010 08:17 — activation ladder unit + setup->aha->habit over 10 HTTP quotes; markers on oauth/defaults/quotes; 100% x4 (run 0817) | CODE + CONTRACT + LIVE-HUBSPOT + OPS | CODE satisfied. MISSING: CONTRACT, LIVE-HUBSPOT, OPS — no live portal, provider or external assessment exists yet.
ST-072 | E7 | Telemetry & analytics | Error tracking with release tagging; alert on error-rate spike | 3 | P0 | S4 | SCR-8 Analytics | Automated: unit + HTTP integration (supertest) | Partial | v010 08:17 — errorTracker episode semantics unit + 5x502 HTTP spike notifying admins once; release v0.4.0 tag; 100% x4 (run 0817) | CODE + OPS | CODE satisfied. MISSING: OPS — no live portal, provider or external assessment exists yet.
ST-073 | E7 | Telemetry & analytics | Feature-usage heatmap for roadmap decisions | 3 | P2 | S8 | SCR-8 Analytics | Automated: unit + HTTP integration (supertest) | Partial | v014 10:38 — ranked heatmap + unused features; 100% x4 (run 1038) | CODE + OPS | CODE satisfied. MISSING: OPS — no live portal, provider or external assessment exists yet.
ST-074 | E7 | Telemetry & analytics | Weekly automated metrics email to team | 2 | P2 | S8 | SCR-8 Analytics | Automated: unit + HTTP integration (supertest) | Partial | v014 10:38 — digest asserted; scheduler deployment-side; 100% x4 (run 1038) | CODE + OPS | CODE satisfied. MISSING: OPS — no live portal, provider or external assessment exists yet.
ST-075 | E7 | Telemetry & analytics | Health score computed per account (usage+billing+support) | 5 | P1 | S8 | SCR-8 Analytics | Automated: unit + HTTP integration (supertest) | Partial | v014 10:38 — score bands + funnel-milestone activity chain; 100% x4 (run 1038) | CODE + COMMERCIAL + OPS | CODE satisfied. MISSING: COMMERCIAL, OPS — no live portal, provider or external assessment exists yet.
ST-076 | E7 | Telemetry & analytics | Metrics export to CSV/warehouse for founder analysis | 3 | P2 | S8 | SCR-8 Analytics | Automated: unit + HTTP integration (supertest) | Partial | v014 10:38 — CSV header + rows; 100% x4 (run 1038) | CODE + SECURITY + OPS | CODE satisfied. MISSING: SECURITY, OPS — no live portal, provider or external assessment exists yet.
ST-077 | E7 | Telemetry & analytics | Alert thresholds configurable (activation drop, error spike, churn signal) | 3 | P2 | S8 | SCR-8 Analytics | Automated: unit + HTTP integration (supertest) | Partial | v014 10:38 — three alert types, severity escalation, validation; 100% x4 (run 1038) | CODE + OPS | CODE satisfied. MISSING: OPS — no live portal, provider or external assessment exists yet.
ST-078 | E8 | Onboarding, docs & support | First-run checklist reaches aha-moment in <1 day | 5 | P0 | S5 | SCR-9 Help & support | Automated: unit + HTTP integration (supertest) | Partial | v011 08:52 — checklist 14%->100% + ahaReached over HTTP; 100% x4 (run 0852) | CODE + OPS | CODE satisfied. MISSING: OPS — no live portal, provider or external assessment exists yet.
ST-079 | E8 | Onboarding, docs & support | Empty states teach next action on every screen | 3 | P1 | S5 | SCR-9 Help & support | Automated: unit + HTTP integration (supertest) | Partial | v011 08:52 — five lists emptyState present-then-absent; 100% x4 (run 0852) | CODE + OPS | CODE satisfied. MISSING: OPS — no live portal, provider or external assessment exists yet.
ST-080 | E8 | Onboarding, docs & support | Help center with 15 launch articles + search | 5 | P1 | S10 | SCR-9 Help & support | Automated: unit + HTTP integration (supertest) | Partial | v016 11:11 — 15 articles, ranked search, public access, feature-coverage test; 100% x4 (run 1111) | CODE + OPS | CODE satisfied. MISSING: OPS — no live portal, provider or external assessment exists yet.
ST-081 | E8 | Onboarding, docs & support | In-app chat with <4 business-hr first response | 3 | P0 | S10 | SCR-9 Help & support | Automated: unit + HTTP integration (supertest) | Partial | v016 11:11 — business-hours maths both directions, weekend case, breach + overdue reporting; 100% x4 (run 1111) | CODE + OPS | CODE satisfied. MISSING: OPS — no live portal, provider or external assessment exists yet.
ST-082 | E8 | Onboarding, docs & support | In-app review ask after aha-moment (marketplace rating engine) | 3 | P1 | S11 | SCR-9 Help & support | Automated: unit + HTTP integration (supertest) | Partial | v017 11:25 — all suppression signals, 90-day floor, lifetime cap, permanent decline; no review-gating; 100% x4 (run 1125) | CODE + COMMERCIAL + OPS | CODE satisfied. MISSING: COMMERCIAL, OPS — no live portal, provider or external assessment exists yet.
ST-083 | E8 | Onboarding, docs & support | Demo video (2 min) + interactive sandbox/demo data mode | 5 | P1 | S10 | SCR-9 Help & support | Automated: unit + HTTP integration (supertest) | Partial | v016 11:11 — sandbox dashboards populated (75% win rate, large deals, alerts); double-seed 409; 100% x4 (run 1111) | CODE + OPS | CODE satisfied. MISSING: OPS — no live portal, provider or external assessment exists yet.
ST-084 | E8 | Onboarding, docs & support | Status page + incident comms template | 2 | P2 | S10 | SCR-9 Help & support | Automated: unit + HTTP integration (supertest) | Partial | v016 11:11 — component roll-up from live signals; 4 incident templates render clean; 100% x4 (run 1111) | CODE + OPS | CODE satisfied. MISSING: OPS — no live portal, provider or external assessment exists yet.
ST-085 | EQ | Quality engineering | Unit+integration test coverage gate 100% on ALL code (D13, 10 Sep 2026 — supersedes the earlier >=70% gate) | 5 | P0 | S3 | — (cross-cutting) | Automated: unit + HTTP integration (supertest) | Done | v009 22:52 — jest.config.js coverageThreshold 100x4 (since S1); run 20260910_2252: 150 tests / 7 suites, All files 100¦100¦100¦100, EXIT=0 | CODE | CODE satisfied — the only class this story requires. Stays Done.
ST-086 | EQ | Quality engineering | E2E smoke suite runs on every deploy | 5 | P0 | S4 | — (cross-cutting) | Automated: E2E smoke journey (supertest) | Partial | v010 08:17 — tests/smoke.test.ts install->uninstall journey; npm run test:smoke; CI smoke-on-deploy on main; green in run 0817 | CODE + OPS | CODE satisfied. MISSING: OPS — no live portal, provider or external assessment exists yet.
ST-087 | EQ | Quality engineering | p95 latency budgets defined and monitored per surface | 3 | P0 | S8 | — (cross-cutting) | Automated: unit + HTTP integration (supertest) | Partial | v014 10:38 — p95 nearest-rank, bounded window, middleware samples; 100% x4 (run 1038) | CODE + OPS | CODE satisfied. MISSING: OPS — no live portal, provider or external assessment exists yet.
ST-088 | EQ | Quality engineering | Load test at 5x expected launch traffic | 5 | P1 | S8 | — (cross-cutting) | Automated: unit + HTTP integration (supertest) | Done | v014 10:38 — 250 requests, budgets held, 50 deals synced once each; 100% x4 (run 1038) | CODE | CODE satisfied — the only class this story requires. Stays Done.
ST-089 | EQ | Quality engineering | Accessibility WCAG AA pass on primary flows | 3 | P1 | S9 | — (cross-cutting) | Automated: unit + HTTP integration (supertest) | Done | v015 10:56 — 5 shells pass; checker tested per rule; served HTML asserted; 100% x4 (run 1056) | CODE | CODE satisfied — the only class this story requires. Stays Done.
ST-090 | EQ | Quality engineering | Backup + restore drill executed | 3 | P1 | S9 | — (cross-cutting) | Automated: unit + HTTP integration (supertest) | Partial | v015 10:56 — round-trip verified; skipped surfaced; drill no longer destroys non-restorable data; 100% x4 (run 1056) | CODE + OPS | CODE satisfied. MISSING: OPS — no live portal, provider or external assessment exists yet.
ST-091 | EQ | Quality engineering | Chaos test: platform API outage degrades gracefully with user comms | 3 | P2 | S9 | — (cross-cutting) | Automated: unit + HTTP integration (supertest) | Done | v015 10:56 — six degradation properties under outage; 100% x4 (run 1056) | CODE | CODE satisfied — the only class this story requires. Stays Done.
ST-092 | EQ | Quality engineering | Zero-downtime deploy verified (blue/green or rolling) | 3 | P2 | S8 | — (cross-cutting) | Automated: unit + HTTP integration (supertest) | Partial | v014 10:38 — drain flips readiness, liveness green, in-flight completes; 100% x4 (run 1038) | CODE + OPS | CODE satisfied. MISSING: OPS — no live portal, provider or external assessment exists yet.
ST-093 | EL | Launch & listing | Marketplace listing copy A + B variants drafted and reviewed | 3 | P0 | S9 | — (marketplace listing) | Automated: unit + HTTP integration (supertest) | Partial | v015 10:56 — variants A/B, limits asserted by test; 100% x4 (run 1056) | CODE + COMMERCIAL | CODE satisfied. MISSING: COMMERCIAL — no live portal, provider or external assessment exists yet.
ST-094 | EL | Launch & listing | 5 screenshots + 2-min demo video meet platform asset specs | 5 | P0 | S9 | — (marketplace listing) | Automated: unit + HTTP integration (supertest) | Partial | v015 10:56 — brief complete; capture blocked on R-Q5; 100% x4 (run 1056) | CODE + COMMERCIAL | CODE satisfied. MISSING: COMMERCIAL — no live portal, provider or external assessment exists yet.
ST-095 | EL | Launch & listing | Pricing page/plan matrix published with FAQ | 3 | P0 | S10 | — (marketplace listing) | Automated: unit + HTTP integration (supertest) | Partial | v016 11:11 — published prices asserted equal to PLANS (DQ19); FAQ covers dunning and cancellation; 100% x4 (run 1111) | CODE + COMMERCIAL | CODE satisfied. MISSING: COMMERCIAL — no live portal, provider or external assessment exists yet.
ST-096 | EL | Launch & listing | Security/trust page (data handling, subprocessors) live | 3 | P0 | S10 | — (marketplace listing) | Automated: unit + HTTP integration (supertest) | Partial | v016 11:11 — retention, subprocessors, scopes and unmet controls with owners; 100% x4 (run 1111) | CODE + COMMERCIAL + SECURITY | CODE satisfied. MISSING: COMMERCIAL, SECURITY — no live portal, provider or external assessment exists yet.
ST-097 | EL | Launch & listing | Submission dry-run against platform checklist by second reviewer | 3 | P0 | S10 | — (marketplace listing) | Automated: unit + HTTP integration (supertest) | Partial | v016 11:11 — 12 pass / 0 fail / 2 manual from live state; failure paths asserted; 100% x4 (run 1111) | CODE + COMMERCIAL | CODE satisfied. MISSING: COMMERCIAL — no live portal, provider or external assessment exists yet.
ST-098 | EL | Launch & listing | Launch-day runbook: monitoring, rollback, comms tree | 3 | P1 | S11 | — (marketplace listing) | Automated: unit + HTTP integration (supertest) | Partial | v017 11:25 — go/no-go from live state incl. real drill; verified rollback ordering; comms tree; 100% x4 (run 1125) | CODE + COMMERCIAL + OPS | CODE satisfied. MISSING: COMMERCIAL, OPS — no live portal, provider or external assessment exists yet.
ST-099 | EL | Launch & listing | Post-launch listing SEO iteration 1 from search-term data | 2 | P2 | S12 | — (marketplace listing) | Automated: unit + HTTP integration (supertest) | Partial | v018 11:34 — five verdicts + threshold boundaries; unsupported demand excluded (DQ25); erp-in-enterprise and sign-in-design locked; baseline fallback on over-long copy; 100% x4 (run 1134) | CODE + COMMERCIAL | CODE satisfied. MISSING: COMMERCIAL — no live portal, provider or external assessment exists yet.
ST-100 | EL | Launch & listing | First 10 design-partner reviews scheduled | 2 | P1 | S11 | — (marketplace listing) | Automated: unit + HTTP integration (supertest) | Partial | v017 11:25 — identified/contacted count as 0 scheduled; target flips onTrack at 10; 100% x4 (run 1125) | CODE + COMMERCIAL + SECURITY | CODE satisfied. MISSING: COMMERCIAL, SECURITY — no live portal, provider or external assessment exists yet.
ST-101 | F6 | Platform surface | Projects app + React app card on the 2026.03 developer platform, replacing the legacy CRM card | 8 | P0 | PS14/PS15 | SCR-1 Deal app card | Automated: dealCard unit + HTTP integration; route-removal assertion | Partial | hubspot-project/ + src/services/dealCard.ts + GET /api/cards/deal/:dealId | CODE + LIVE-HUBSPOT | CODE satisfied. MISSING: LIVE — nothing installed (R-Q15).
ST-102 | F6 | Identity | Session mint from a HubSpot-signed extension context; header identity deleted | 5 | P0 | PS16 | SCR-1 Deal app card | Automated: mint happy path, forged/stale/malformed refusals, TTL expiry, header path gone | Done | POST /session/mint; src/services/identity.ts; tests/s3api.test.ts | CODE + SECURITY | CODE + SECURITY satisfied.
ST-103 | F7 | Tenancy | Row-level security on every tenant table, enforced by the database | 8 | P0 | PS21 | — (infrastructure) | Automated: PGlite migration run, policy inventory, cross-tenant read returns zero rows, superuser refusal | Done | migrations 007/009/011/014/017; tenantContext.ts; tests/tenantRls.test.ts | CODE + SECURITY | CODE + SECURITY satisfied on a real Postgres engine.
ST-104 | F7 | Durability | Envelope-encrypted tokens and a durable outbox with retry, dead-letter and replay | 8 | P0 | PS19/PS20 | — (infrastructure) | Automated: seal/open/rewrap, key rotation, claim/lease/backoff/DLQ/replay | Done | src/store/pg/envelope.ts; src/store/jobs.ts; tests/outbox.test.ts | CODE + SECURITY | CODE + SECURITY satisfied.
ST-105 | F7 | Observability | Structured logs with correlation ids, Prometheus metrics, SLO burn-rate, error reporting | 5 | P1 | PS22 | SCR-9 Ops | Automated: span propagation, exposition format, quantiles, burn-rate evaluation | Partial | src/services/observability.ts; tests/observability.test.ts | CODE + OPS | CODE satisfied. MISSING: OPS — no backend receives it yet.
ST-106 | F1 | Configuration engine | Product model with attributes, option groups, compatibility rules and conditional visibility | 13 | P0 | PS23 | SCR-3 Price book workspace | Automated: five unsupported-by-native scenarios, determinism, tie-break, guided selection | Done | src/services/configurationEngine.ts; tests/configuration.test.ts; tests/cpqApi.test.ts | CODE | CODE satisfied — the class this story can reach without design partners.
ST-107 | F1 | Configuration engine | Explainability trace: every included or excluded component names the rule that decided it | 8 | P0 | PS23 | SCR-3 Price book workspace | Automated: trace assertions on every decision kind; prose rendering | Done | explain() + TraceEntry; tests/configuration.test.ts | CODE | CODE satisfied.
ST-108 | F1 | Configuration engine | Authoring validation rejects contradictory or circular rule sets at save time | 5 | P0 | PS23 | SCR-3 Price book workspace | Automated: nine problem classes, plus refusal at the store boundary and the route | Done | validateModel/assertAuthorable; PUT /api/config/models/:id | CODE | CODE satisfied.
ST-109 | F1 | Pricing depth | Nested bundles, entity price-book inheritance and override | 8 | P0 | PS24 | SCR-3 Price book workspace | Automated: compounding discounts, cycle/depth refusal, inheritance attribution | Done | src/services/pricingEngine.ts; tests/pricingDepth.test.ts | CODE | CODE satisfied.
ST-110 | F1 | Pricing depth | Multi-currency with pinned FX, per-currency exponent and rounding mode | 8 | P0 | PS24 | SCR-3 Price book workspace | Automated: three currencies exact to the minor unit; JPY exponent shift; half-up vs half-even | Done | CURRENCIES/roundMicros/fxRate; tests/pricingDepth.test.ts | CODE | CODE satisfied.
ST-111 | F1 | Pricing depth | Ramps, usage commit and overage, cost-plus and margin floors, channel matrices | 8 | P0 | PS24 | SCR-3 Price book workspace | Automated: graduated tiers, marginal overage rate, hard floor block, class-specific channel caps | Done | priceQuoteDeep; tests/pricingDepth.test.ts | CODE | CODE satisfied.
ST-112 | F1 | Pricing depth | Full price waterfall per line: list -> book -> bundle -> rule -> discount -> channel -> floor -> fx | 5 | P0 | PS24 | SCR-3 Price book workspace | Automated: every step present with a zero delta when it did nothing; text rendering for a CFO | Done | renderWaterfall; tests/pricingDepth.test.ts | CODE | CODE satisfied.
ST-113 | F2 | Deal desk | Conditional approval DAG with parallel branches and quorum | 13 | P0 | PS25 | SCR-5 Approvals | Automated: three approvers across two branches, quorum 2-of-3, DAG validation and cycle detection | Done | src/services/dealDesk.ts; tests/dealDesk.test.ts; tests/cpqApi.test.ts | CODE | CODE satisfied.
ST-114 | F2 | Deal desk | Delegation with an explicit audit; SLA timers and escalation ladders in business hours | 8 | P0 | PS25 | SCR-5 Approvals | Automated: delegate decides in their own name; weekend does not breach; ladder catches up in one sweep | Done | activeDelegation + sweep(); tests/dealDesk.test.ts | CODE | CODE satisfied.
ST-115 | F2 | Deal desk | Recall, resubmit and version-aware approval invalidation | 5 | P0 | PS25 | SCR-5 Approvals | Automated: content-hash change invalidates prior decisions, visibly, without erasing them | Done | recall/resubmit; tests/dealDesk.test.ts | CODE | CODE satisfied.
ST-116 | F2 | Deal desk | Immutable approval audit with no bypass path, verified by attempting every bypass | 8 | P0 | PS25 | SCR-5 Approvals | Automated: eight bypass attempts, each denied AND recorded; store returns deep copies | Done | decide() refuse path; tests/dealDesk.test.ts bypass block | CODE + SECURITY | CODE + SECURITY satisfied.
ST-117 | F2 | Deal desk | Deal-desk queue with ageing in business hours and workload view | 5 | P1 | PS25 | SCR-5 Approvals | Automated: oldest first, breach counts, per-approver load | Done | queue()/workload(); GET /api/desk/queue | CODE | CODE satisfied.
ST-118 | F4 | Billing correctness | Authenticated, correctly encoded provider calls and inbound webhooks with replay and ordering | 8 | P0 | PS29 | SCR-7 Billing | Automated: form-encoding, idempotency key, every signature failure mode, duplicate and out-of-order events | Partial | src/services/billingProviders.ts; tests/billingCorrectness.test.ts | CODE + CONTRACT | CODE satisfied. MISSING: CONTRACT — no provider credentials (R-Q10).
ST-119 | F4 | Billing correctness | Entitlements gate by plan, and proration runs on real calendar billing periods | 5 | P0 | PS29 | SCR-7 Billing | Automated: plan/status matrix, read-only keeps reads, February vs March prorate differently | Done | entitlementFor/prorate; tests/billingCorrectness.test.ts | CODE | CODE satisfied.
ST-120 | F5 | Operations | Migrations roll back, or declare that they cannot, and refuse before dropping anything | 5 | P0 | PS30 | — (infrastructure) | Automated: apply 017 -> roll back to 013 -> apply forward, on a real engine; refusal across an irreversible step | Done | rollbackPlan/rollbackMigrations; tests/operations.test.ts | CODE + OPS | CODE + OPS satisfied for rollback specifically.
ST-121 | F5 | Operations | Chaos: Postgres, HubSpot and the mail provider each killed, with graceful degradation asserted | 5 | P0 | PS30 | — (infrastructure) | Automated: retryable 503s, a failed sync run recorded rather than thrown away, mail dead-lettered not dropped | Done | tests/operations.test.ts chaos block | CODE + OPS | CODE + OPS satisfied for induced failures.
ST-122 | F5 | Operations | Data-residency option and subprocessor list, declared and validated | 3 | P1 | PS30 | SCR-10 Trust | Automated: posture self-consistency; only provisioned regions and in-use subprocessors are publishable | Done | src/services/residency.ts; tests/operations.test.ts | CODE | CODE satisfied. No region is provisioned and the sheet says so.
ST-123 | F5 | Operations | Multi-instance load test to p95 <500ms at a stated concurrency | 8 | P0 | PS30 | — (infrastructure) | Harness written; NOT RUN | Blocked | scripts/loadtest.js | PERF | MISSING: PERF — needs a hosted target (R-Q17). Claim CL-10 blocked.
ST-124 | F5 | Operations | Backup and restore drill with a measured RPO and RTO | 8 | P0 | PS30 | — (infrastructure) | Harness written; NOT RUN | Blocked | scripts/restore-drill.sh | OPS | MISSING: OPS — needs managed Postgres with PITR (R-Q18). Claim CL-11 blocked.
ST-125 | F5 | Quality system | Evidence-class tagging, CI per-class counts, claims register and a release manifest that carries the matrix | 8 | P0 | PS31 | — (process) | Automated: every test file tagged, invalid tags caught, register audited, manifest block asserted | Done | src/services/evidence.ts; tests/evidence.test.ts; scripts/release-manifest.js; .github/workflows/ci.yml | CODE + OPS | CODE + OPS satisfied.

## Sprint_Status_Rollup
SPRINT STATUS ROLLUP — live formulas over Traceability_Matrix
Do not edit computed cells. 'Done' now counts only stories whose evidence classes are ALL satisfied (CB-01/QF-011, tracker v027) — not merely Done-in-code under D13. The count fell from 98 to 25 as a direct result; the missing classes are LIVE-HUBSPOT, CONTRACT, SECURITY, OPS and COMMERCIAL, none of which can be produced without a dev portal, a mail provider, billing credentials and an external assessment. RAG is manual.
Sprint | Focus | Stories | Points | Done | Done points | % points done | RAG (manual) | Exit criteria
S1 | Foundation (2 wks) | [5 empty] | AMBER under V001 evidence classes — 4/4 done-in-code; live install pending (R-Q5) | App installs cleanly in dev store/org; telemetry firing
S2 | Core feature Price book + bundles - part 1 | [5 empty] | AMBER under V001 evidence classes — 6/6 done-in-code; happy path E2E-proven | Price book + bundles happy path demoable
S3 | Core feature Price book + bundles - part 2 + Approval chains start | [5 empty] | AMBER under V001 evidence classes — 11/11 done-in-code; live CRM card fetch pending (R-Q6) | Price book + bundles complete with tests; Approval chains skeleton
S4 | Core feature Approval chains | [5 empty] | AMBER under V001 evidence classes — 9/9 done-in-code; smoke suite = MVP loop; Postgres carried (R-Q4) | MVP loop usable end-to-end internally
S5 | Feature E-signature + alpha hardening | [5 empty] | AMBER under V001 evidence classes — 12/12 done-in-code; e-sign loop smoke-verified; live dogfood needs deployment (R-Q5) | Internal alpha: team dogfoods daily
S6 | Billing + Quote analytics | [5 empty] | AMBER under V001 evidence classes — 13/13 done-in-code; smoke charges + upgrades a test portal; live charging needs R-Q10 credentials | Can charge a test customer; upgrade/downgrade paths work
S7 | Private beta (design partners) | [5 empty] | AMBER under V001 evidence classes — 5/5 done-in-code; full paying-customer billing lifecycle + scope disclosure exercised; partner recruitment external (R-Q5) | 3+ partners active weekly; NPS pulse >30
S8 | Beta iteration + Deal/line-item sync | [5 empty] | AMBER under V001 evidence classes — 22/22 done-in-code; sync loop smoke-verified with idempotency; ST-066 encryption posture partial pending vault/at-rest provisioning (R-Q11) | Retention of beta cohort week-over-week >60%
S9 | Marketplace review prep | [5 empty] | AMBER under V001 evidence classes — AMBER — 5/7 Done; ST-068 needs a commissioned external pen test (R-Q12) and ST-094 needs a live install to capture assets (R-Q5). All code-side work complete and tested. | Review submission accepted into queue
S10 | Review remediation + docs | [5 empty] | AMBER under V001 evidence classes — 7/7 done-in-code; submission dry-run reports 12 pass / 0 fail / 2 manual against live state | Marketplace approval obtained (or final remediation cycle)
S11 | Launch | [5 empty] | AMBER under V001 evidence classes — GREEN (code) — 3/3 done-in-code. Launch itself is BLOCKED: preflight returns no_go on PRE-07 because billing runs against stubs (R-Q10). Supply live credentials and the preflight goes green. | First 10 installs; first 3 reviews; activation >40%
S12 | Iterate & scale decision | [5 empty] | AMBER under V001 evidence classes — 1/1 done-in-code. Engine and guards shipped; iteration against real search-term data needs the listing live (R-Q5/R-Q10). | Growth model doc with CAC/LTV first estimates
TOTAL

## RAID_Carryover
RAID — seeded from v006/v009 Risk_Register + build findings
ID | Type | Raised | Item | Status | Notes / Mitigation
R-Q1 | Risk | v006 | HubSpot ships native CPQ upgrades to close the gap (High/Medium) | Open | Depth on approvals + e-sign; certified-app trust moat (Launch_Checklist #5) ¦ V001 QF-013 escalates this: HubSpot Revenue Hub now bundles AI CPQ with approvals, e-sign and payments. Raised at v006, never mitigated.
R-Q2 | Risk | v006 | Portal API rate limits throttle bulk quote ops (Medium/Medium) | Open | PlatformClient backoff shipped S2 (ST-004); queue + batch architecture from S4+; load test at ST-088
R-Q3 | Risk | v006 | SMB price sensitivity caps ARPU (Medium/High) | Open | Per-quote-sender pricing; annual plan push; pricing test at S12
R-Q4 | Constraint | 22:19 | Sandbox has no Postgres — persistence is in-memory behind store interfaces | Open | DQ4/L-018: adapter deferred; L-024 (11 Sep): live apt install attempted — mirror 404s + timeout, PG_ABSENT verified. Needs working mirror or container DB; carried to S5. Interfaces unchanged. UPDATE 13 Sep 16:36: schema delivered in review pass 2 and adapters for audit/analytics/sync delivered now, proved against a real Postgres engine in tests. Outstanding: a live instance, the remaining six stores, and R-Q13.
R-Q5 | Dependency | 22:03 | LIVE dev-portal install verification (S1 exit criterion) needs Senthil | Open | HubSpot dev portal app + client ID/secret; code-verified via integration tests meanwhile (E004)
R-Q6 | Dependency | 22:52 | LIVE CRM card fetch from a real HubSpot portal (ST-005 surface) needs Senthil | Open | Same dev-portal setup as R-Q5; signed-request handling already proven in automation
R-Q7 | Constraint | 22:52 | Email transport is a no-op default until a provider is wired | Open | DQ5: sent/failed/retry paths fully tested against mutable fake; provider lands with GTM plumbing S5 note: signer outreach (envelope links + reminders) rides the same provider — API returns signerLinks meanwhile (DQ5 update). ¦ V001 QF-010: production now refuses to boot on the no-op sender.
R-Q8 | Risk | 22:19 | /api identity header-based until HubSpot-signed identity extends beyond the card surface | Open | DQ2: signed CRM card shipped S3; UI-extension auth rides S4+; risk is spoofed headers in any pre-launch shared deployment — do not expose /api publicly before then ¦ V001 QF-004: sharpened — signSession has NO production caller at all, so there is no viable session mint, not merely a weak one.
A-Q1 | Assumption | 22:03 | D13 (interviews parked, 100% coverage) applies portfolio-wide incl. QuoteFlow | Open | Per Senthil 20:45 instruction; S0 activities (PRD sign-off, prototype tests) remain formally unclosed
A-Q2 | Assumption | 08:17 | CI smoke-on-deploy job treats pushes to main as the deploy trigger (ST-086) | Open | Wire to the real deploy pipeline hook when hosting lands (S8 zero-downtime work, ST-092)
R-Q10 | Risk | Live billing needs provider credentials: HubSpot marketplace listing approval (app-monetization access) for the marketplace channel and Stripe API keys for the direct channel. Until then charging is verified against provider stubs + asserted API URLs only. | Open | Senthil | Opened S6 close (12:47). Code paths fully tested; swap stubs for live keys and re-run smoke. S7 note: dunning, recovery and invoice issue paths are all provider-stubbed too — the same credential swap covers them. ¦ V001 QF-007: also found the providers send no Authorization header and the Stripe call is JSON — the call shape is wrong as well as uncredentialed.
R-Q11 | Risk | SEC-03 (managed secret vault + rotation) and SEC-04 (encryption at rest) are published as PARTIAL on the trust page. Both are deployment-side: a vault must be provisioned and Postgres stood up before the page can claim full compliance. Marketplace security review will ask. | Open | Senthil | Opened S8 close (10:38). Code declares the posture honestly; a test fails the build if the outstanding list is emptied without the work being done.
R-Q12 | Risk | No external penetration test has been commissioned. The evidence pack covers 8 of 10 abuse cases with automated tests and says so plainly, but infrastructure-level assessment needs an external tester. Marketplace security review may require it before listing. | Open | Senthil | Opened S9 close (10:56). Budget and vendor selection needed; the abuse-case list can serve as the scope document.
R-Q13 | Issue | Store interfaces are synchronous, so the Postgres adapters use a write-through cache and support a single writer only. Multi-instance deployment requires migrating the interfaces to async across roughly 40 call sites. | Open | Senthil / next code phase | UPDATE 13 Sep 17:30: the dangerous half is closed - a writer lease now refuses a second instance at startup instead of allowing silent divergence. The async interface migration itself (~40 call sites) remains open and should be a dedicated phase, not a review fix.
R-Q14 | Issue | Approval chains and requests are still in-memory. The tables exist (migration 002) but no adapter writes them, so approval requests do not survive a restart even on the Postgres backend. | Closed | Next code phase | Closed 13 Sep 17:23: PgApprovalStore written and wired; an approval decision is proved to survive a restart through the real HTTP flow.
R-Q15 | Issue | 23:02 (V001) | No HubSpot Projects app or UI extension exists (QF-001): zero hsmeta/TSX/JSX/hubspot.extend() in the package. The product's native HubSpot surface is legacy CRM cards, which stop rendering 31 Oct 2026. | Open | Highest-consequence open item in the product. Needs a HubSpot dev portal account before code is worth writing — scaffolding blind would repeat exactly the defect class this review found. Blocks QF-004 (session mint) behind it.
R-Q16 | Issue | 23:02 (V001) | Release artifact was not reproducible (QF-008): no package-lock.json shipped while both workflows run npm ci, so the delivered package could not pass its own CI. | Closed | Closed 13 Sep 23:30: lockfile committed and the exact tree verified in a clean room (npm ci → tsc → jest, 488 green). Open question for Senthil: was the lockfile missing from the REPO or only from the zip? If the latter, the packaging step needs the fix too.
R-Q17 | Dependency | 2026-09-20 (V002) | PERF evidence needs a hosted environment: two instances behind a load balancer to measure p95 at a stated concurrency. | Open | scripts/loadtest.js is written and has never been run. Claim CL-10 blocked. Running it against localhost proves localhost is fast, which is not the claim.
R-Q18 | Dependency | 2026-09-20 (V002) | OPS evidence needs a managed Postgres with point-in-time recovery, to produce a measured RPO and RTO. | Open | scripts/restore-drill.sh restores, then proves the restored database serves tenant-scoped reads, then prints the two numbers. Claim CL-11 blocked until it has run.
R-Q19 | Risk | 2026-09-20 (V002) | The PS23 configuration scenarios are drawn from published native limitations, not from prospects. The engine may be deep in the wrong direction. | Open | Mitigation is PS13/PS32, not more code. Marked COMMERCIAL-absent in the claims register so no listing copy can imply customer validation.
R-Q20 | Issue | 2026-09-20 (V002) | Invoice tax is still a single flat rate per portal, while quoting is now fully multi-currency (PXR-010 half-closed). | Open | Stated rather than counted as done. Needs a jurisdiction table and per-line tax codes; sized for the next sprint, not faked in this one.

## Gate_Checklist
COMPLETION GATE (D7) — QuoteFlow is DONE only when every row passes
R2: code complete counts for nothing. Gate decision = Senthil.
ID | Gate item | Source | Status
G-01 | App LISTED on HubSpot App Marketplace (approved + published) | D7 / R2 | Open
G-02 | 10 PAYING installs from strangers | D7 / R2 | Open
G-03 | S12 kill criteria evaluated with evidence pack | D7 / R3 | Open
G-04 | Kill/continue decision recorded by Senthil | R5 / D10 | Open
G-05 | On CONTINUE: next-rank build authorised; QuoteFlow enters run mode | N4 / R1 | Open
External review V001 findings closed or explicitly owned | FAIL — 4 of 14 closed, 10 open | Claude / Senthil | QF-001 (no UI extension) and QF-004 (no session mint) are the blockers; both need a HubSpot dev portal before code.
Every Done story satisfies its evidence classes (CB-01) | FAIL — most stories carry CODE only | Claude | Applied this release. Stories needing LIVE-HUBSPOT cannot pass until R-Q5/R-Q15 are moved by Senthil.

## ExtReview_V002_Board
EXTERNAL REVIEW V002 — fix board (Perplexity, 16 Sep 2026)
Score 4.1/10, NOT ENTERPRISE GRADE, 16 findings, sprint plan PS13–PS32. Senthil instructed full scope: "enterprise grade product do all dont shrink the scope." Status below is what the TREE does, not what the plan intended. Where a finding is closed only in code, it says so and names the blocker for the higher evidence class.
Ref | Severity | Finding | Status | What closure means, precisely
PXR-001 | BLOCKER | No HubSpot Projects app or UI extension; the only card surface was a legacy CRM card that cannot be listed | CODE-closed; LIVE blocked | hubspot-project/ at platformVersion 2026.03 with a React app card (hubspot.extend) and a serverless proxy. crmCard.ts and GET /crm-card DELETED (DQ41); a test asserts the route 404s. Evidence class CODE — nothing has been installed. Blocked on R-Q15.
PXR-002 | BLOCKER | OAuth tokens and the deletion queue had no durable, encrypted home | Closed | Envelope encryption (AES-256-GCM, per-record DEK wrapped by a KEK, rotation by re-wrap) on the Postgres token store; durable outbox on the jobs table replaces the in-memory queue. Production refuses to boot on in-memory stores (DQ39).
PXR-003 | BLOCKER | Tenant isolation lived only in application code | Closed | RLS on every tenant table, transaction-local GUCs via set_config, FORCE ROW LEVEL SECURITY, non-BYPASSRLS quoteflow_app role, boot refuses to serve as superuser. Proved on PGlite: a query omitting portal_id returns zero rows. tests/tenantRls.test.ts.
PXR-004 | BLOCKER | replaceLineItems deleted line items QuoteFlow did not create | Closed | Provenance property qf_managed on every created item; batch/read partitions owned from unowned; replace REFUSES with 409 LINE_ITEMS_NOT_OWNED unless an admin opts in, and archives rather than deletes. tests/extreview2.test.ts (CODE+CONTRACT).
PXR-005 | HIGH | The blue/green deploy workflow could not work: a writer lease refused a second instance | Closed | The async cascade retired the lease (migration 012 drops the table; writerLease.ts deleted). Blue/green is the default again with a tripwire that fails the build if acquireWriterLease reappears in server.ts. OPS evidence still absent — no deploy has run (CL-12).
PXR-006 | HIGH | The trust page claimed encryption at rest the code did not provide | Closed | DATA_FLOW declares atRest per store as application / platform / none, and a test fails the build if a store claims more than the code does. Subprocessor and residency posture added in PS30-07.
PXR-007 | HIGH | The homegrown signer produced no admissible evidence | Closed | Deterministic document rendering with a content seal (SHA-256 of the exact bytes at send), certificate of completion (identity, timestamps, IP, user agent, consent record, document hash), offline verification endpoint, HMAC access codes, and a provider adapter seam. tests/signatureEvidence.test.ts (CODE+SECURITY).
PXR-008 | HIGH | There was no quote object: quotes existed only as events | Closed | Persisted quote entity with immutable versions, content hashes, lifecycle draft->approved->sent->accepted/expired/superseded, an ownership table encoding which system owns which field, and drift detection against the deal.
PXR-009 | HIGH | Configuration and approvals were too shallow to survive Revenue Hub | Closed (CODE) | PS23 configuration engine and PS25 deal-desk DAG, both persisted, routed, RBAC-gated, audited and purge-clean, with contract tests on BOTH store backends. Differentiation is CODE evidence; that customers want it is COMMERCIAL and is not claimed (CL-14).
PXR-010 | MEDIUM | Single currency, flat tax | Closed for quoting; open for invoicing | PS24 gives multi-currency with per-currency exponent and rounding, pinned FX, multi-entity books with inheritance, ramps, usage tiers and channel matrices. Invoice tax remains a single flat rate per portal and is stated as such rather than counted done.
PXR-011 | HIGH | 100% coverage was presented as proof of enterprise readiness | Closed | PS31: @evidence tags on every test file, a claims register with required vs held classes, a CI gate on untagged files and empty classes, and the matrix carried in release-manifest.json. The gate is relabelled a REGRESSION FLOOR in code, CI and README (DQ43).
PXR-012 | HIGH | Billing never heard back from a provider | CODE-closed; CONTRACT blocked | Stripe form-encoded authenticated charges with an idempotency key; inbound webhooks verified, deduplicated by event id and ordered by the event timestamp so a late payment_failed cannot undo a later success; plan-based entitlements; proration on real calendar months. Blocked on R-Q10 for CONTRACT evidence.
PXR-013 | MEDIUM | No production session mint path | Closed | POST /session/mint takes a HubSpot-SIGNED body carrying the extension context, verifies it, and returns a 30-minute HMAC session. Header identity deleted entirely (DQ42). tests/s3api.test.ts PS16 block.
PXR-014 | MEDIUM | OAuth used sunset v1 endpoints | Closed | OAuth v3 throughout (/oauth/v3/token, /oauth/v3/access-tokens/{token}); hub id resolved from the token info response; DELETE /appinstalls/v3/external-install for app-initiated uninstall.
PXR-015 | MEDIUM | No data-residency option or subprocessor list | Posture declared; none provisioned | src/services/residency.ts declares three regions (available: yes, provisioned: NO) and a subprocessor list that distinguishes in-use from chosen — HubSpot is the only one in use. Validated by test; the trust page may list only what exists (DQ50).
PXR-016 | MEDIUM | Notification fan-out was synchronous | Closed | Mail goes through the durable outbox with backoff and dead-lettering. An unresolvable recipient raises EMAIL_RECIPIENT_UNKNOWN and dead-letters visibly instead of retrying forever or being dropped. The remaining half of R-Q7 is that the UI does not yet collect addresses.

## Gates_G11_G15
COMPLETION GATES G11–G15 — added by external review V002
G1–G10 (V001) are unchanged and still govern. These five are the gates V002 implied but did not number. A gate that passes only in one evidence class says which.
ID | Gate | What passing means | Status | Evidence / why
G11 | Platform surface is the one HubSpot will accept in 2027 | The tree contains a 2026.03 Projects app and a React app card; no legacy CRM card route exists anywhere. | PASS (CODE) / FAIL (LIVE) | Code: PASS — crmCard.ts deleted, route 404s under test, hsproject.json at 2026.03. Live: FAIL — nothing installed. R-Q15.
G12 | Tenant isolation is enforced by the database | A query that omits portal_id returns zero rows on a real Postgres engine, and the app cannot connect as a role that bypasses RLS. | PASS (SECURITY) | tests/tenantRls.test.ts on PGlite; assertRlsEnforceable refuses superuser/BYPASSRLS; 26 tenant tables carry the policy.
G13 | Nothing is lost when a process dies | Tokens are encrypted and durable, side effects go through an outbox with retry and dead-letter, and two instances share one database with no lease. | PASS (CODE) | Envelope encryption + PgJobStore + the retired writer lease. OPS evidence (a real restart under load) is absent — CL-11/CL-12.
G14 | Depth that native quoting cannot match, and can explain itself | Configuration, pricing and approvals are each persisted, routed, RBAC-gated, audited, purge-clean and contract-tested on both backends, and every output names the rule behind it. | PASS (CODE) | PS23/24/25 with migration 016/017 and tests/cpqApi.test.ts across memory and Postgres. COMMERCIAL evidence that anyone wants it: absent (CL-14).
G15 | No claim outruns its evidence | Every test file declares its evidence class; every published claim has required and held classes; CI fails on an untagged file or an empty class a shipped feature claims. | PASS | 8 of 15 claims supported, 7 blocked with named owners. Classes: CODE 45, CONTRACT 2, LIVE 0, SECURITY 8, PERF 0, OPS 4, COMMERCIAL 0.

## Evidence_Matrix
EVIDENCE MATRIX (PS31-05) — generated, never typed
Counted from the test tree at release time and carried inside release-manifest.json. Tree 43de1cac3aa5 · 793 tests / 45 suites. The 100% coverage gate is a REGRESSION FLOOR, not a quality claim.
Evidence class | Test files | What it does and does not prove
CODE | 45 | The cheapest class, and the only one a coverage gate speaks to.
CONTRACT | 2 | Recorded-fixture tests against real third-party payload and error shapes.
LIVE | 0 | EMPTY — nothing has run against a real HubSpot account. R-Q15.
SECURITY | 8 | Adversarial tests: forged sessions, cross-tenant reads, every approval bypass, tampered signature packages.
PERF | 0 | EMPTY — scripts/loadtest.js exists and has never been run against a deployed target. PS30-01.
OPS | 4 | Migration rollback on a real engine, chaos degradation, boot/observability. A restore drill and a real deploy are still absent.
COMMERCIAL | 0 | EMPTY — no listing, no design partners, no revenue. PS32.
BLOCKED CLAIMS — may not be published anywhere until the gap closes
Claim | Missing class | Owner / what unblocks it
CL-01 | LIVE | R-Q15 — needs a HubSpot developer account before any app card can be installed
CL-09 | CONTRACT | R-Q10 — needs Stripe test-mode keys and HubSpot monetisation access
CL-10 | PERF | PS30-01 — needs a hosted environment to load-test against
CL-11 | OPS | PS30-03 — needs a managed Postgres with point-in-time recovery
CL-12 | OPS | PS30-02 — the lease is gone and the workflow is blue/green, but no deploy has been run
CL-13 | SECURITY | PS30-06 — a pen test is a purchase, not a sprint
CL-14 | COMMERCIAL | PS32 — no listing, no design partners, no revenue