## Version_Control
SESSION HANDOVER v003 — supersedes v002 (13/09 21:56). 20 September 2026.
Version | Date/Time | Author | Change Description | Status
v003 | 2026-09-20 11:40 | Claude for Senthil/KP | Covers one pass: external review V001 (Perplexity, 16/09) absorbed in full. Five defects closed in code, seven artifact corrections applied (two of them lowering a status we had published), eleven of the fourteen recommended sprints executed as far as code can take them, and a new standing gate for the defect class that no existing gate could see. The three sprints that are not done need a live Jira site, a Marketplace purchase and ten conversations — they are Open in the tracker with everything prepared for them, not quietly dropped. Release position is unchanged: NOT RELEASE READY until LC-1 and D18. | Released

## Current_Files
CURRENT FILES — everything else is superseded
Artifact | What it is | Version / time
Sprint tracker + traceability | TestPulse delivery record — 12 sheets, 112 log entries, the 14-sprint plan at TASK level (95 rows), 120 stories, RAID, gate checklist, code inventory | v028 @ 20/09 11:40
Product workbook | Product record — 25 sheets incl. the PRX findings, the corrected financial model, the re-scored enterprise gates, the scorecard with movement, the AEC gap and the market evidence | v035 @ 20/09 11:40
TestPulse codebase | 55 suites / 530 tests / 100% x4, seven gates, clean-room verified from the lockfile, 0 production dependencies | zip @ 20/09 11:40
External review V001 | The source document for this pass — Perplexity Computer, 16/09 19:37, five findings and a 14-sprint plan | as supplied
Evidence logs | CI run, clean-room run and the re-baselined performance envelope — inside the codebase zip under evidence/ | @ 20/09 12:04
Review gates kit | Seven gates + init scaffolder + review-bundle script, with the porting guide in tools/review-gates/README.md and the per-repo procedure in docs/portfolio-gate-rollout.md — now including G-5 | v5 @ 20/09
Marketplace build standard | Portfolio: defect classes, lessons (now incl. L-P8), phase gates, rollout plan | v004 @ 13/09 — L-P8 to be added

## What_Changed
WHAT CHANGED IN THIS PASS — grouped by what it cost and what it bought
Read this if you read nothing else.
Area | Before | After | Why it mattered
Concurrent use | Two people using TestPulse at once silently lost each other's work, including audit entries and webhook replay ids | Versioned values with compare-and-set, commutative ledgers, one key per entity, conflicts surfaced as "reload and try again" | The reviewer called this disqualifying for any paid install, and it was. It is also the reason G-5 exists: no gate that reads one invocation can see it.
Case identity | Pressing "Generate more cases" twice produced the same three ids, so run boards merged different cases | Unique ids on every creation path, asserted at write | Reporting was quietly wrong and demo teardown deleted real cases.
Project isolation | Scope was written into the audit log and never used in the decision; any licensed member saw every project | Enforced against Jira BROWSE_PROJECTS as the calling user, failing closed | LC-6 had been published as done. It is now Open and will only flip with live evidence.
Flaky detection | One FIFO ledger was both the storage cap and the analysis window, so a noisy suite erased the signal | Per-run storage, per-test and per-branch windows, clusters, owned quarantines | The headline analytic degraded to noise at exactly the volume that made it valuable.
Per-invocation cost | Every panel open loaded the whole tenant | Each call declares what it reads; whoami loads two keys | Closes OBS-TP1, which had been open since the first review pass.
Readiness (the wedge) | Coverage and open P0s — 60% of the score — were typed into Settings by the owner | Derived from Jira, CI results and recorded executions; every factor names its source; overrides are attributed and labelled | "A spreadsheet with a dial." The positioning in Decision 4 is now earned by the code rather than asserted by the listing.
Automation ingest | A hand-rolled payload shape only | JUnit XML, Playwright JSON and Cucumber JSON against committed real-shape fixtures | EG-06 was MISSING. A team can now point its existing pipeline at TestPulse without writing an adapter.
Traceability | Nothing | Requirement -> test -> run -> defect, plus coverage per release and both gap reports | EG-05 was MISSING and the reviewer called it the single biggest capability gap against Xray.
AI | A wired provider on a shared key, story text inside the instruction string | BYO key in Secret Storage, injection-hardened prompt, per-source cost attribution, monthly ceiling, multi-model fallback | Stops the vendor funding every tenant and closes a real injection path.
Enterprise programme | A gap assessment against a programme that had closed | Atlassian Enterprise Certified, row by row, with two rows marked as procurement | The old document concluded "no structural gaps" about a bar that no longer existed.
Economics | 17% marketplace fee assumed | 0% until $1M lifetime Forge revenue; per-user anchor 40-50% under Xray, sub-10 seats conceded | Net MRR was understated ~20%. At 10 seats the old intent was 12x Xray.
The gate that was missing | Six gates, none of which could see a two-invocation defect | Seven. G-5 is static plus dynamic, and it went red on its own first run for 8 of 13 keys | L-P8. Every portfolio product that stores a collection in one value has PRX-02 today.

## Decisions
THE DECISIONS — what is still yours
Three of the six from the review are effectively settled by what shipped. What remains is what only you can do.
# | Decision | Why it matters / what it unblocks | Cost of deciding | State
1 | LC-1: run the live install (PR-04) | Still the highest return per minute in the pack, and it now answers more: extension.project.key for the project page, the restricted-project denial that flips LC-6, a real CI post, and the two wall-time figures that decide whether to enable Forge SQL (D19). Every scale and latency number in the package is still verified against documentation. | ~45 min | OPEN — yours
6 | D18 per-user pricing and the test purchase (PR-13) | Blocks the partner console, the test purchase and every published price. The anchor table is written against the corrected 0% fee; what is missing is your decision on the numbers and the console work. | ~1 hour + console | OPEN — yours
D19 | Forge SQL: enable it, or stay on per-entity KVS | The adapter, its migrations and its tests are built. Enabling it is a manifest change and a MAJOR version. It buys a real atomic compare-and-set and turns a 102-round-trip board query into one indexed query. It needs real KVS latency to justify, which is LC-1. | Decision after PR-04 | OPEN — after LC-1
D-TP-WB | Jira write-back as a funded feature | PR-08 links requirements to tests inside TestPulse. Writing links back INTO Jira needs write:jira-work, which TPR-003 removed because nothing used it. The review was explicit: re-add it as a feature with a named call path, never as a silent permission. | Decision only | OPEN — yours
5 | Portfolio rollout of G-5 | PRX-02 is not a TestPulse defect; it is a design pattern defect. Every product that stores a collection in one value has it today, and none of them has a gate that can see it. The kit is ready to port. | Decision + a pass per repo | OPEN — highest leverage
2 | Runs on Atlassian vs AI | Settled: Option B, keep AI. The badge no longer carries a revenue delta and the enterprise bar is now AEC, which wants egress transparency rather than zero egress. No second major version was built. | — | Settled
3 | AI on or off at launch | Settled: off by default, with BYO key and a monthly ceiling on the shared key, so the "weaker demo" problem is an activation-design problem rather than a cost problem. | — | Settled
4 | Positioning: Release Quality Intelligence | Settled in the code (PR-05) and in the scope document. The remaining edit is the listing copy, which still describes a test-case manager. | Listing copy | Mostly settled

## Where_It_Stands
STATE OF THE PRODUCT — honest summary
Dimension | Status | Note
Code quality | Strong | 55 suites / 530 tests / 100% x4, zero pragmas, clean-room reproducible from the lockfile, 0 production dependencies.
Standing gates | Seven, all green | Reachability, claims (42), platform entrypoints, entrypoint wiring, scope/egress, secret-PII, and concurrent write safety (new).
External review V001 | Fully absorbed | 5/5 findings closed in code, 7/7 corrections applied, 11 of 14 sprints executed. The three that remain need a site, a purchase and people.
Enterprise gates | 4 PASS, 10 PARTIAL, 1 UNPROVEN | Counted from the 20/09 column of the workbook's V002_Enterprise_Gates. Two MISSING became PARTIAL (EG-05 traceability, EG-06 automation ingest) and four PARTIALs moved within PARTIAL. NOTHING moved to PASS: EG-10 (scale) stays PARTIAL and EG-15 (PMF evidence) stays UNPROVEN, because both need evidence no code can produce.
Market readiness | Not market-ready | 7/10 on demand: proven category, credible wedge now earned by the code, stale differentiation corrected, and still ZERO primary validation.
Enterprise grade | ~5.6/10 by our own arithmetic on the reviewer's basis, from 4.5 | The code moved a long way; the evidence did not move at all. A reviewer would be entitled to hold the old number until something runs on a real site.
Operational evidence | 1/10 — unchanged | Nothing has ever run on a real Jira site. No production p95, no cold start, no KVS latency, no forge eligibility output.
Release readiness | NOT RELEASE READY | Gated on LC-1 (PR-04) and D18 (PR-13). No amount of further code changes this, and this pass did not pretend otherwise.
Defects this pass | 5 external + 2 found while absorbing them | F-TP46 (conn:/ai: namespaces outside the data-rights registry) and F-TP47 (a repeat install event could re-stamp installedAt — the F-TP45 class, reintroduced by this pass's own rewrite and caught by the pinned regression that existed for it).

## If_You_Send_A_Repo
WHAT I CAN DO NEXT WITHOUT ANY DECISION FROM YOU
Input | What happens
Any other product repo as a zip | Port the seven gates including G-5, triage the first red run, and fix what is real. Expect PRX-02 to be present: every product that stores a collection in one value has it. RevRescue first on the evidence — WIN rank 1 and never cold-reviewed.
forge logs + lc1-verify output after the install | Triage whatever reality disagrees with, close the pending-live stories with evidence, and answer D19 (Forge SQL) with the real latency figures.
An external review of another product | Same absorption as V001/V002: accept or reject each finding explicitly, fix, pin regressions, correct the rollups downwards where they were overstated.
Three real Xray/Zephyr export files | Close LC-5 in an afternoon — the importer is format-faithful and the CI adapters are fixture-backed, so this is acceptance evidence rather than development.
Nothing | I would not start another TestPulse code sprint. What is left is a live install, a purchase, ten conversations, and a decision about Forge SQL that needs the install first. The next genuinely high-leverage build work is porting G-5 across the portfolio.