## Version_Control
VERSION CONTROL — VoiceBridge CTI
Version | Date | Author | Change | Status
v001-v004 | 2026-09-05 | Claude for Senthil/KP | Lineage: marketplace master (868 entries) -> portfolio plan (12 products) -> wave-1 (RetainKit/ShiftDesk/EngageOS, v005) -> this product selected for wave-2 | Released
v006 | 2026-09-05 19:46 | Claude for Senthil/KP | Full product workbook for VoiceBridge CTI on Salesforce AppExchange: spec, screen inventory, 100+ story backlog, live sprint board, 18-month financial model (editable assumptions), GTM execution tasks, platform launch checklist, metric targets, risk register | Released
v007 |  |  | PLANNED: post-S0 re-baseline after discovery interviews; verified platform terms; wireframe links added to Screens sheet | Planned

## ReadMe_Scope
VoiceBridge CTI — Omnichannel CTI: click-to-dial, call logging, WhatsApp/SMS threads native in Salesforce
PLATFORM: Salesforce AppExchange ¦ CATEGORY: Sales Engagement / Telephony
PROBLEM: Mid-market telephony connectors are either enterprise-priced (NICE/Genesys) or shallow loggers
DIFFERENTIATION: Deep Flow/Einstein integration, transparent per-seat pricing, India+global carrier coverage
ICP: B2B sales orgs 50-500 seats on Sales/Service Cloud, existing telephony spend, RevOps function present
HOW TO USE: Full_Backlog is the single source of truth (edit Status column during execution). Sprint_Board recalculates points per sprint automatically. Financial_Model assumptions (yellow) are editable — the 18-month build recalculates. Launch_Checklist is the platform-specific gate before submission. All costs/timelines are market-standard estimates; verify platform terms (fees/review rules) during S0.
STACK ASSUMPTION (market standard): TypeScript/Node or platform-mandated runtime, React frontends, Postgres, hosted on AWS/GCP/platform FaaS as required, GitHub Actions CI, PostHog + Sentry telemetry, Intercom-class support.

## Product_Spec
PRODUCT SPEC
Module (feature) | Scope in MVP | Out of scope (v1) | Non-functional requirements
Click-to-dial + softphone | Click-to-dial + softphone: end-to-end happy path + edge cases + permissions | Advanced automation, AI beyond listed, multi-language beyond launch set | p95 <500ms API / <2s UI loads
Auto call/WhatsApp logging | Auto call/WhatsApp logging: end-to-end happy path + edge cases + permissions | Advanced automation, AI beyond listed, multi-language beyond launch set | 99.5% monthly uptime
Cadence/sequence lite | Cadence/sequence lite: end-to-end happy path + edge cases + permissions | Advanced automation, AI beyond listed, multi-language beyond launch set | WCAG AA
Coaching analytics | Coaching analytics: end-to-end happy path + edge cases + permissions | Advanced automation, AI beyond listed, multi-language beyond launch set | SOC2-track controls
Flow actions pack | Flow actions pack: end-to-end happy path + edge cases + permissions | Advanced automation, AI beyond listed, multi-language beyond launch set | Rate-limit safe (backoff+queue)
Persona | Jobs-to-be-done
RevOps lead | Evaluates on admin effort, Flow compatibility, reporting
Sales leader (VP) | Buys on rep productivity metrics; needs dashboards
Salesforce admin | Gatekeeper; security review status and permission sets decide the deal

## Screens_Wireframes
SCREEN INVENTORY (attach Figma links in col E during S0)
# | Screen | Purpose | Key elements | Wireframe link
1 | Onboarding / first-run | Reach aha in <1 day | Checklist, sample data toggle, connect steps
2 | Home dashboard | Daily habit surface | KPI cards, activity feed, alerts
3 | Click-to-dial + softphone workspace | Core value surface | List+detail, bulk actions, status chips
4 | Auto call/WhatsApp logging builder | Configure second pillar | Rule builder, preview, test mode
5 | Cadence/sequence lite view | Differentiator surface | Timeline/visual, export
6 | Settings & team | Roles, notifications, data | Role matrix, API keys, danger zone
7 | Billing | Plan/trial/invoices | Plan cards, usage meter, invoices
8 | Analytics | Prove ROI | Funnel, cohort, export
9 | Help & support | Deflect + assist | Search, chat, status

## Full_Backlog
FULL BACKLOG
ID | Epic | Story | Points | Priority | Sprint | Status
ST-001 | F1 | As a RevOps lead, I can set up Click-to-dial + softphone with sensible defaults in one screen | 5 | P0 | S2 | Backlog
ST-002 | F1 | As a RevOps lead, the Click-to-dial + softphone happy path completes without documentation | 8 | P0 | S2 | Backlog
ST-003 | F1 | As a Sales leader, I can customise Click-to-dial + softphone rules/conditions for my workflow | 5 | P1 | S2 | Backlog
ST-004 | F1 | As a user, Click-to-dial + softphone shows clear errors and retry paths on platform API failures | 3 | P0 | S2 | Backlog
ST-005 | F1 | As a Salesforce admin, Click-to-dial + softphone works on the Lightning utility-bar softphone + LWC surface end-to-end | 5 | P0 | S3 | Backlog
ST-006 | F1 | As a Sales leader, I can see Click-to-dial + softphone performance metrics and trends | 3 | P1 | S3 | Backlog
ST-007 | F1 | As a user, Click-to-dial + softphone respects role permissions and audit logging | 3 | P1 | S3 | Backlog
ST-008 | F1 | As a RevOps lead, I can pause/disable Click-to-dial + softphone without data loss | 2 | P2 | S3 | Backlog
ST-009 | F1 | As a Sales leader, I can import/migrate existing data into Click-to-dial + softphone (CSV + competitor importer) | 5 | P1 | S3 | Backlog
ST-010 | F1 | As a user, I get notifications (in-app + email) for key Click-to-dial + softphone events with per-type mute | 3 | P2 | S3 | Backlog
ST-011 | F2 | As a RevOps lead, I can set up Auto call/WhatsApp logging with sensible defaults in one screen | 5 | P0 | S3 | Backlog
ST-012 | F2 | As a RevOps lead, the Auto call/WhatsApp logging happy path completes without documentation | 8 | P0 | S3 | Backlog
ST-013 | F2 | As a Sales leader, I can customise Auto call/WhatsApp logging rules/conditions for my workflow | 5 | P1 | S3 | Backlog
ST-014 | F2 | As a user, Auto call/WhatsApp logging shows clear errors and retry paths on platform API failures | 3 | P0 | S3 | Backlog
ST-015 | F2 | As a Salesforce admin, Auto call/WhatsApp logging works on the Lightning utility-bar softphone + LWC surface end-to-end | 5 | P0 | S4 | Backlog
ST-016 | F2 | As a Sales leader, I can see Auto call/WhatsApp logging performance metrics and trends | 3 | P1 | S4 | Backlog
ST-017 | F2 | As a user, Auto call/WhatsApp logging respects role permissions and audit logging | 3 | P1 | S4 | Backlog
ST-018 | F2 | As a RevOps lead, I can pause/disable Auto call/WhatsApp logging without data loss | 2 | P2 | S4 | Backlog
ST-019 | F2 | As a Sales leader, I can import/migrate existing data into Auto call/WhatsApp logging (CSV + competitor importer) | 5 | P1 | S4 | Backlog
ST-020 | F2 | As a user, I get notifications (in-app + email) for key Auto call/WhatsApp logging events with per-type mute | 3 | P2 | S4 | Backlog
ST-021 | F3 | As a RevOps lead, I can set up Cadence/sequence lite with sensible defaults in one screen | 5 | P0 | S5 | Backlog
ST-022 | F3 | As a RevOps lead, the Cadence/sequence lite happy path completes without documentation | 8 | P0 | S5 | Backlog
ST-023 | F3 | As a Sales leader, I can customise Cadence/sequence lite rules/conditions for my workflow | 5 | P1 | S5 | Backlog
ST-024 | F3 | As a user, Cadence/sequence lite shows clear errors and retry paths on platform API failures | 3 | P0 | S5 | Backlog
ST-025 | F3 | As a Salesforce admin, Cadence/sequence lite works on the Lightning utility-bar softphone + LWC surface end-to-end | 5 | P0 | S5 | Backlog
ST-026 | F3 | As a Sales leader, I can see Cadence/sequence lite performance metrics and trends | 3 | P1 | S5 | Backlog
ST-027 | F3 | As a user, Cadence/sequence lite respects role permissions and audit logging | 3 | P1 | S5 | Backlog
ST-028 | F3 | As a RevOps lead, I can pause/disable Cadence/sequence lite without data loss | 2 | P2 | S5 | Backlog
ST-029 | F3 | As a Sales leader, I can import/migrate existing data into Cadence/sequence lite (CSV + competitor importer) | 5 | P1 | S5 | Backlog
ST-030 | F3 | As a user, I get notifications (in-app + email) for key Cadence/sequence lite events with per-type mute | 3 | P2 | S5 | Backlog
ST-031 | F4 | As a RevOps lead, I can set up Coaching analytics with sensible defaults in one screen | 5 | P0 | S6 | Backlog
ST-032 | F4 | As a RevOps lead, the Coaching analytics happy path completes without documentation | 8 | P0 | S6 | Backlog
ST-033 | F4 | As a Sales leader, I can customise Coaching analytics rules/conditions for my workflow | 5 | P1 | S6 | Backlog
ST-034 | F4 | As a user, Coaching analytics shows clear errors and retry paths on platform API failures | 3 | P0 | S6 | Backlog
ST-035 | F4 | As a Salesforce admin, Coaching analytics works on the Lightning utility-bar softphone + LWC surface end-to-end | 5 | P0 | S6 | Backlog
ST-036 | F4 | As a Sales leader, I can see Coaching analytics performance metrics and trends | 3 | P1 | S6 | Backlog
ST-037 | F4 | As a user, Coaching analytics respects role permissions and audit logging | 3 | P1 | S6 | Backlog
ST-038 | F4 | As a RevOps lead, I can pause/disable Coaching analytics without data loss | 2 | P2 | S6 | Backlog
ST-039 | F4 | As a Sales leader, I can import/migrate existing data into Coaching analytics (CSV + competitor importer) | 5 | P1 | S6 | Backlog
ST-040 | F4 | As a user, I get notifications (in-app + email) for key Coaching analytics events with per-type mute | 3 | P2 | S6 | Backlog
ST-041 | F5 | As a RevOps lead, I can set up Flow actions pack with sensible defaults in one screen | 5 | P0 | S8 | Backlog
ST-042 | F5 | As a RevOps lead, the Flow actions pack happy path completes without documentation | 8 | P0 | S8 | Backlog
ST-043 | F5 | As a Sales leader, I can customise Flow actions pack rules/conditions for my workflow | 5 | P1 | S8 | Backlog
ST-044 | F5 | As a user, Flow actions pack shows clear errors and retry paths on platform API failures | 3 | P0 | S8 | Backlog
ST-045 | F5 | As a Salesforce admin, Flow actions pack works on the Lightning utility-bar softphone + LWC surface end-to-end | 5 | P0 | S8 | Backlog
ST-046 | F5 | As a Sales leader, I can see Flow actions pack performance metrics and trends | 3 | P1 | S8 | Backlog
ST-047 | F5 | As a user, Flow actions pack respects role permissions and audit logging | 3 | P1 | S8 | Backlog
ST-048 | F5 | As a RevOps lead, I can pause/disable Flow actions pack without data loss | 2 | P2 | S8 | Backlog
ST-049 | F5 | As a Sales leader, I can import/migrate existing data into Flow actions pack (CSV + competitor importer) | 5 | P1 | S8 | Backlog
ST-050 | F5 | As a user, I get notifications (in-app + email) for key Flow actions pack events with per-type mute | 3 | P2 | S8 | Backlog
ST-051 | E1 | Marketplace OAuth install completes and lands on welcome state in <2 min | 5 | P0 | S1 | Backlog
ST-052 | E1 | Uninstall webhook removes tokens, schedules data deletion per policy | 3 | P0 | S1 | Backlog
ST-053 | E1 | Re-install restores account within retention window | 3 | P1 | S2 | Backlog
ST-054 | E1 | Multi-user roles: owner/admin/member permission matrix enforced | 5 | P0 | S2 | Backlog
ST-055 | E1 | Session/token refresh survives platform token rotation | 3 | P0 | S1 | Backlog
ST-056 | E1 | Install telemetry: source attribution (listing/search/referral) captured | 2 | P1 | S1 | Backlog
ST-057 | E5 | 14-day trial without card; banner shows days remaining | 5 | P0 | S6 | Backlog
ST-058 | E5 | Upgrade/downgrade mid-cycle prorates correctly | 5 | P0 | S6 | Backlog
ST-059 | E5 | Marketplace billing API used where mandated; external Stripe fallback elsewhere | 8 | P0 | S6 | Backlog
ST-060 | E5 | Failed payment: 7-day grace, 3 dunning emails, then read-only mode | 3 | P1 | S7 | Backlog
ST-061 | E5 | Plan limits enforced with upgrade prompts at 80%/100% | 3 | P1 | S7 | Backlog
ST-062 | E5 | Invoices/receipts downloadable; GST/VAT fields supported | 3 | P2 | S7 | Backlog
ST-063 | E5 | Cancellation flow with save-offer and exit survey | 3 | P1 | S7 | Backlog
ST-064 | E6 | Scopes requested map 1:1 to shipped features (least privilege doc) | 3 | P0 | S7 | Backlog
ST-065 | E6 | Data-flow diagram + retention policy published | 3 | P0 | S8 | Backlog
ST-066 | E6 | Encryption at rest + in transit verified; secrets in vault | 5 | P0 | S8 | Backlog
ST-067 | E6 | Audit log for admin-sensitive actions | 5 | P1 | S8 | Backlog
ST-068 | E6 | Pen-test (or platform-required evidence) completed and archived | 8 | P0 | S9 | Backlog
ST-069 | E6 | Data export + delete-my-data self-serve | 5 | P0 | S9 | Backlog
ST-070 | E6 | Rate-limit backoff + circuit breaker on platform APIs | 5 | P0 | S8 | Backlog
ST-071 | E7 | Activation funnel events (install->setup->aha->habit) in one dashboard | 5 | P0 | S4 | Backlog
ST-072 | E7 | Error tracking with release tagging; alert on error-rate spike | 3 | P0 | S4 | Backlog
ST-073 | E7 | Feature-usage heatmap for roadmap decisions | 3 | P2 | S8 | Backlog
ST-074 | E7 | Weekly automated metrics email to team | 2 | P2 | S8 | Backlog
ST-075 | E7 | Health score computed per account (usage+billing+support) | 5 | P1 | S8 | Backlog
ST-076 | E7 | Metrics export to CSV/warehouse for founder analysis | 3 | P2 | S8 | Backlog
ST-077 | E7 | Alert thresholds configurable (activation drop, error spike, churn signal) | 3 | P2 | S8 | Backlog
ST-078 | E8 | First-run checklist reaches aha-moment in <1 day | 5 | P0 | S5 | Backlog
ST-079 | E8 | Empty states teach next action on every screen | 3 | P1 | S5 | Backlog
ST-080 | E8 | Help center with 15 launch articles + search | 5 | P1 | S10 | Backlog
ST-081 | E8 | In-app chat with <4 business-hr first response | 3 | P0 | S10 | Backlog
ST-082 | E8 | In-app review ask after aha-moment (marketplace rating engine) | 3 | P1 | S11 | Backlog
ST-083 | E8 | Demo video (2 min) + interactive sandbox/demo data mode | 5 | P1 | S10 | Backlog
ST-084 | E8 | Status page + incident comms template | 2 | P2 | S10 | Backlog
ST-085 | EQ | Unit+integration test coverage gate ≥70% on core modules | 5 | P0 | S3 | Backlog
ST-086 | EQ | E2E smoke suite runs on every deploy | 5 | P0 | S4 | Backlog
ST-087 | EQ | p95 latency budgets defined and monitored per surface | 3 | P0 | S8 | Backlog
ST-088 | EQ | Load test at 5x expected launch traffic | 5 | P1 | S8 | Backlog
ST-089 | EQ | Accessibility WCAG AA pass on primary flows | 3 | P1 | S9 | Backlog
ST-090 | EQ | Backup + restore drill executed | 3 | P1 | S9 | Backlog
ST-091 | EQ | Chaos test: platform API outage degrades gracefully with user comms | 3 | P2 | S9 | Backlog
ST-092 | EQ | Zero-downtime deploy verified (blue/green or rolling) | 3 | P2 | S8 | Backlog
ST-093 | EL | Marketplace listing copy A + B variants drafted and reviewed | 3 | P0 | S9 | Backlog
ST-094 | EL | 5 screenshots + 2-min demo video meet platform asset specs | 5 | P0 | S9 | Backlog
ST-095 | EL | Pricing page/plan matrix published with FAQ | 3 | P0 | S10 | Backlog
ST-096 | EL | Security/trust page (data handling, subprocessors) live | 3 | P0 | S10 | Backlog
ST-097 | EL | Submission dry-run against platform checklist by second reviewer | 3 | P0 | S10 | Backlog
ST-098 | EL | Launch-day runbook: monitoring, rollback, comms tree | 3 | P1 | S11 | Backlog
ST-099 | EL | Post-launch listing SEO iteration 1 from search-term data | 2 | P2 | S12 | Backlog
ST-100 | EL | First 10 design-partner reviews scheduled | 2 | P1 | S11 | Backlog
Total stories: 100. Epics: F1-F5 = product features; E1 install, E5 billing, E6 compliance, E7 telemetry, E8 onboarding/docs/support, EQ quality. Edit Status (Backlog/In progress/Done) during execution.

## Sprint_Board
SPRINT BOARD — live counts from Full_Backlog
Sprint | Focus | Stories | Points | Done | Exit criteria
S0 | Discovery & Design (2 wks) | 0 | 0 | 0 | PRD signed off; prototype tested with 5 target users
S1 | Foundation (2 wks) | 4 | 13 | 0 | App installs cleanly in dev store/org; telemetry firing
S2 | Core feature Click-to-dial + softphone - part 1 | 6 | 29 | 0 | Click-to-dial + softphone happy path demoable
S3 | Core feature Click-to-dial + softphone - part 2 + Auto call/WhatsApp logging start | 11 | 47 | 0 | Click-to-dial + softphone complete with tests; Auto call/WhatsApp logging skeleton
S4 | Core feature Auto call/WhatsApp logging | 9 | 34 | 0 | MVP loop usable end-to-end internally
S5 | Feature Cadence/sequence lite + alpha hardening | 12 | 50 | 0 | Internal alpha: team dogfoods daily
S6 | Billing + Coaching analytics | 13 | 60 | 0 | Can charge a test customer; upgrade/downgrade paths work
S7 | Private beta (design partners) | 5 | 15 | 0 | 3+ partners active weekly; NPS pulse >30
S8 | Beta iteration + Flow actions pack | 22 | 87 | 0 | Retention of beta cohort week-over-week >60%
S9 | Marketplace review prep | 7 | 30 | 0 | Review submission accepted into queue
S10 | Review remediation + docs | 7 | 24 | 0 | Marketplace approval obtained (or final remediation cycle)
S11 | Launch | 3 | 8 | 0 | First 10 installs; first 3 reviews; activation >40%
S12 | Iterate & scale decision | 1 | 2 | 0 | Growth model doc with CAC/LTV first estimates
| TOTAL | 100 | 399
Velocity check: points/sprint S2-S8 should sit within 30-45 for a 4-6 person team; rebalance Sprint column in backlog if a sprint exceeds capacity.

## Financial_Model
18-MONTH FINANCIAL MODEL — Salesforce: enterprise pilot-led (edit yellow assumptions)
Assumption | Value
Qualified pilots/mo (month 1) | 4
Monthly growth of that | 0.1
Pilot->paid % | 0.3
ARPU $/mo | 600
Monthly churn | 0.012
Marketplace fee | 0.15
Team cost month 1 (India-lean $) | 40000
Cost growth/mo | 0.03
Fee note: 15% PNR to Salesforce on net revenue
Line | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18
Leads/installs | 4 | 4.4 | 4.84 | 5.324 | 5.8564 | 6.442 | 7.0862 | 7.7949 | 8.5744 | 9.4318 | 10.375 | 11.4125 | 12.5537 | 13.8091 | 15.19 | 16.709 | 18.3799 | 20.2179
New paying | 1.2 | 1.3 | 1.5 | 1.6 | 1.8 | 1.9 | 2.1 | 2.3 | 2.6 | 2.8 | 3.1 | 3.4 | 3.8 | 4.1 | 4.6 | 5 | 5.5 | 6.1
Paying accounts | 1.2 | 2.5 | 4 | 5.6 | 7.3 | 9.1 | 11.1 | 13.3 | 15.7 | 18.3 | 21.2 | 24.3 | 27.8 | 31.6 | 35.8 | 40.4 | 45.4 | 51
MRR (net of fee) | 612 | 1275 | 2040 | 2856 | 3723 | 4641 | 5661 | 6783 | 8007 | 9333 | 10812 | 12393 | 14178 | 16116 | 18258 | 20604 | 23154 | 26010
Team cost | 40000 | 41200 | 42436 | 43709 | 45020 | 46371 | 47762 | 49195 | 50671 | 52191 | 53757 | 55370 | 57031 | 58742 | 60504 | 62319 | 64189 | 66115
Net cash/mo | -39388 | -39925 | -40396 | -40853 | -41297 | -41730 | -42101 | -42412 | -42664 | -42858 | -42945 | -42977 | -42853 | -42626 | -42246 | -41715 | -41035 | -40105
Cumulative | -39388 | -79313 | -119709 | -160562 | -201859 | -243589 | -285690 | -328102 | -370766 | -413624 | -456569 | -499546 | -542399 | -585025 | -627271 | -668986 | -710021 | -750126
Reading: churn applies before adds; MRR nets the marketplace fee; costs use India-lean base from Team_Roles_Budget (v004). Breakeven = first month Net cash ≥ 0. This is a planning model, not a forecast — replace assumptions with S7-S8 beta actuals.

## GTM_Execution
GTM EXECUTION TASKS
Phase | Task | Owner (role) | Target sprint
Pre-launch | Positioning doc + message house (problem/promise/proof) | Founder | S7
Pre-launch | Listing SEO: keyword study in marketplace search + title/intro drafts | Growth | S8
Pre-launch | 10 design-partner mini case snippets with metric proof | Founder | S8
Pre-launch | 5 comparison/alternative pages drafted | Growth | S9
Pre-launch | Screenshots (5) + 2-min demo video produced | Design | S9
Launch | Listing live + launch post + video published | Growth | S11
Launch | Founder outreach: 100 named ICP accounts, 3-touch sequence | Founder | S11
Launch | Community value-posts (3 relevant communities) | Founder | S11
Launch | Review-generation program on (in-app ask post-aha) | Eng | S11
Post-launch | Weekly SEO/how-to content cadence starts | Growth | S12
Post-launch | Marketplace paid placement pilot (where offered) | Growth | S12
Post-launch | 2 integration co-marketing swaps | Founder | S12+
Post-launch | G2/Capterra profiles + first 10 reviews | Growth | S12+

## Launch_Checklist
PLATFORM LAUNCH CHECKLIST — Salesforce AppExchange
# | Item | Status
1 | ISV Partner Program application + agreement executed | Open
2 | Developer/scratch orgs + managed package namespace registered | Open
3 | AppExchange Security Review: pen-test evidence, code scan clean, Trust questionnaire | Open
4 | Open CTI / Service Cloud Voice compatibility decision documented | Open
5 | Permission sets + profiles install experience tested in 3 org shapes | Open
6 | Data residency: Hyperforce region support statement | Open
7 | Managed package upgrade path tested (push upgrades) | Open
8 | AppExchange listing: demo org, video, security tab complete | Open
9 | Pricing: per-seat tiers + annual; PNR reporting process set up | Open
10 | 2 lighthouse customers referenced (logo permission) before listing | Open

## Metrics_Targets
METRIC TARGETS (first 12 months post-launch)
Metric | M1 | M3 | M6 | M12 | Notes
Installs/signups cumulative | varies | 3x M1 | 8x M1 | 20x M1 | Drive via listing SEO + outbound
Activation % (24h) | 30% | 40% | 45% | 50% | Onboarding iterations S12+
Trial→paid % | baseline | +2pts | +4pts | +6pts | Pricing test at S12
Rating | 4.5+ | 4.6+ | 4.7+ | 4.7+ | Review program + support speed
MRR | first $ | 3x | 8x | 20x | Model sheet has the math
Logo churn/mo | <5% | <4% | <3% | <3% | Health-score saves

## Risk_Register
PRODUCT RISK REGISTER
Risk | Impact | Likelihood | Mitigation
Security review cycles exceed 2 iterations (3+ months delay) | High | High | Specialist review consultant pre-submission; scopes austerity
Service Cloud Voice bundling squeezes third-party CTI | High | Medium | Mid-market focus + WhatsApp/SMS omnichannel angle SCV lacks
Enterprise sales cycle vs cash runway | High | Medium | Paid pilots; annual prepay; partner-sourced deals