## ReadMe
PORTFOLIO DEFECT PATTERN REGISTER — v001, 13 Sep 2026
Source: the cold reviews, verification sweeps and artifact-gap audits run across TeleField, VoiceBridge, FlowCast, ShiftDesk, EngageOS, MeetSync, TestPulse, OnCall Copilot, DocMerge Pro and RetainKit between 10 and 13 September 2026.
Why this file exists. Roughly a hundred defects have now been found across ten products built the same way by the same process. They are not a hundred different mistakes. They are about sixteen patterns, each recurring in four to seven products, each found late and separately every time.
Two things follow. First, several of these need ONE decision from Senthil rather than one per product — the Portfolio_Decisions sheet lists those. Second, most of them are findable by a checklist run BEFORE a product is declared code-phase complete, rather than by an adversarial review afterwards — that is the Pre_Completion_Audit sheet.
What this file is NOT. It is built from the recorded findings, not from re-reading each codebase. Product coverage in Evidence_By_Product is therefore "known to have hit this", not "confirmed absent elsewhere". A blank is an unknown, not a clean bill of health.
Suggested use: run Pre_Completion_Audit against each product that has not had a full cold review plus verification sweep plus artifact-gap audit. On current records that is DocMerge Pro (no cold review yet, mid-S7) and any product where only pass 1 was done.

## Pattern_Register
DEFECT PATTERN REGISTER — sixteen patterns behind roughly a hundred findings
Products column counts products KNOWN to have hit the pattern. A product absent from a row was not checked for it, not cleared of it.
ID | Pattern | What it looks like | Where it has been found | Why it matters | The rule that prevents it | # products
P01 | Status computed, never enforced | A field correctly records that something should be blocked — trial expired, dunning read-only, subscription cancelled, account paused — and no code path reads it. | VoiceBridge F-V03/F-V07/F-V09; EngageOS F-011/F-013; MeetSync M-F01/M-F02; OnCall F-006; RetainKit F-RK02/F-RK03 | Merchants keep full write access after they stop paying. Invisible to coverage because the field is set and read by its own tests. | RULE: every status field must have at least one reader that changes behaviour, and a test that proves the block. When adding a status, grep for its readers before declaring it done. | 7
P02 | Published policy never implemented | A retention or deletion promise exists in docs, a gate row or a privacy page, and the code deletes a subset or nothing. | TestPulse F-TP01/F-TP02; VoiceBridge F-V01/F-V08; EngageOS F-014; OnCall F-009; MeetSync M-F03; RetainKit F-RK07/F-RK10 | Direct breach of a published policy and of platform privacy requirements. Two products had deletion working on one route and broken on another. | RULE: deletion sweeps a single registry that fails closed when a domain has no adapter. A published promise needs a test that fails if the promise becomes untrue. | 6
P03 | Unbounded in-memory ledgers | Dedupe ledgers, error logs, notification queues and alert stores grow without a cap. | FlowCast F-001; OnCall F-007/F-010; EngageOS F-016; ShiftDesk; MeetSync M-F14 (eight of them); TestPulse F-TP06 (five of them) | Memory exhaustion under sustained load; found only by reading, never by tests. | RULE: one shared capped Ledger with FIFO eviction and drop telemetry. No module keeps its own unbounded collection. | 6
P04 | Naive CSV parsing | Importers split on commas, so any quoted field containing a comma corrupts the row. | ShiftDesk F-010; OnCall F-013; EngageOS F-015; MeetSync M-F10/M-F20 | Silent data corruption on exactly the files importers exist to read — competitor exports. | RULE: one shared RFC-4180 csv.ts per product. Never hand-roll a split. | 4
P05 | Backoff that does not back off | Retry-After parsed in the wrong unit, or a production sleep that is a no-op because every test injects its own. | VoiceBridge F-V06; TestPulse F-TP08 (ms vs seconds); MeetSync M-F05; RetainKit F-RK06 | Retries hammer an already rate-limited endpoint. VoiceBridge F-V06 is the clearest case of 100% coverage proving nothing: the tests never executed the real sleep. | RULE: header-to-ms conversion lives in one tested function; the production sleep path is exercised by at least one test; add jitter and a maximum wait. | 4
P06 | Circuit breaker: unlimited half-open probes | After cooldown the breaker admits every caller as a trial, not one. | FlowCast OBS-002; VoiceBridge OBS-V2; MeetSync OBS-M1; TestPulse OBS-TP2; RetainKit OBS-RK1 | A recovering dependency is hit by the full load the instant cooldown expires. Logged as an observation in five products and decided in none. | ONE PORTFOLIO DECISION — see Portfolio_Decisions D-P1. Five separate dispositions is five times the thinking for one answer. | 5
P07 | No payment-recovery path | Dunning emails and read-only mode ship without ever re-attempting the charge. | OnCall F-005; VoiceBridge F-V02; EngageOS F-012; RetainKit F-RK04 | Most failed card payments succeed on retry. The app emails merchants about a problem it could have fixed, then penalises them for it. | RULE: dunning attempts recovery before its first email. Recovery success clears dunning and sends nothing. | 4
P08 | Config claims what code does not provide | Manifests, setup guides, CI workflows and load harnesses reference routes, resources, schemas or packages that do not exist. | OnCall GAP-OC1/GAP-OC2 (no HTTP app, no schema); EngageOS GAP-E1..E6; TestPulse (manifest static resource); VoiceBridge (2GP shim package); RetainKit GAP-RK1..GAP-RK6 | The most expensive class found so far: install fails on the day. Three products had full test suites at 100% and nothing that could receive a request. | RULE: an artifact-gap audit is mandatory before code-phase complete. When you write config, write its drift gate in the same pass. | 5
P09 | Live docs contradict the implementation | Verified behaviour differs from what the code assumes, in ways no test can see. | FlowCast VER-001 (Xero rejects any body on a 200); OnCall VER-OC1 (3-second slash-command ack, else duplicate channels); VoiceBridge VER-V01/V02 (dead softphone); TestPulse (no listKeys API, Node 20 EOL, wrong asset spec); RetainKit VER-RK01/03/04/07 | Every one of these was live-blocking and invisible to a green suite. Several would have failed on submission day rather than in testing. | RULE: an external verification sweep against live platform docs is mandatory before submission, and is separate from code review. | 5
P10 | Compliance module built but never called | Opt-in checks, session-window checks and consent gates exist as fully tested modules that no send path invokes. | EngageOS F-009/F-010 (marketing to non-consented contacts; sends outside the 24h window); RetainKit F-RK01/F-RK05 (imports reset opt-outs; consent checked only at scheduling time) | Platform violations. Invisible at 100% coverage precisely because each module is fully exercised by its own tests — the integration is what is missing. | RULE: a guard module must be a required collaborator of the thing it guards, not an optional one. Coverage measures execution, not integration. | 2
P11 | Tenancy and identity taken on trust | One service instance serves every tenant, or identity comes from caller-supplied headers. | MeetSync M-F04/M-F11/M-F12; OnCall F-014/F-015 | Cross-tenant reads and privilege escalation. M-F11 allowed anyone to claim owner on any workspace. | RULE: tenant resolution and identity verification are the first two things a request touches, and both are signed or looked up, never asserted by the caller. | 2
P12 | OAuth callback without CSRF state | The callback accepts any code with no server-side state to match. | MeetSync M-F15; OnCall F-015; RetainKit (prevented — state stored server-side and single-use) | Standard OAuth CSRF. Cheap to prevent, awkward to explain after a listing review finds it. | RULE: state is generated server-side, stored, single-use, and time-limited in the same statement that consumes it. | 2
P13 | Demo mode touching live data | Demo or sandbox seeding writes into a real tenant. | MeetSync M-F16 (overwrote a live workspace token with the string "demo"); RetainKit (prevented by namespace refusal) | Destroys a real merchant install. Trivially preventable, catastrophic if missed. | RULE: demo mode refuses any tenant outside a reserved namespace, by construction. | 1
P14 | Async handler rejection swallowed | A rejected promise from an async route handler leaves the request hanging with no status. | MeetSync M-F21 (Express 4); RetainKit (prevented — router awaits inside try/catch) | The test times out rather than failing, so the suite still looks green. Worth grepping for across every product with an HTTP layer. | RULE: every handler is awaited inside a try/catch that returns a 500 with no leaked detail. | 1
P15 | A passing test defends the defect | Tests assert the buggy behaviour, so fixing the code breaks the suite and the fix looks wrong. | VoiceBridge L-V2 (a mock with no state field rubber-stamped F-V12); OnCall L-OC2 (two paging tests defended the bug); RetainKit (four tests changed during the cold review) | Actively slows the fix and can reverse it. The instinct to "make the test pass again" is exactly wrong here. | RULE: when a fix breaks a test, read the test before touching the code. A test that encodes a defect is a defect. | 3
P16 | Coverage read as correctness | 100% on all four metrics taken as evidence the product works. | Logged as F-V14, L-E1, L-OC3, L-RK1, L-RK4 — the same lesson learned independently five times | Every product on this list was at 100% throughout the period in which these defects existed. | RULE: state the limit out loud in each product README and review pack. Coverage proves execution, not correctness, not integration, and not that a product exists. | 5

## Portfolio_Decisions
DECISIONS THAT SHOULD BE MADE ONCE, NOT ONCE PER PRODUCT
Each row currently exists as several separate open items across products. Deciding once closes all of them.
ID | Decision | Where it is currently open | The substance | Why it is one decision
D-P1 | Circuit breaker half-open policy | FlowCast, VoiceBridge, MeetSync, TestPulse, RetainKit all log this as an open observation. | Allow ONE trial call per cooldown, queue or fail the rest fast. The alternative — admitting everyone — recreates the burst that opened the breaker. | ONE decision, applied to all five. Currently five separate open dispositions for one question.
D-P2 | In-memory persistence across the portfolio | MeetSync OBS-M3, RetainKit OBS-RK2/R-K10, and by implication every product still on InMemoryStore. | Decide the bar: single-process pilot is acceptable for a dev store and first paying installs; anything past that needs real adapters. RetainKit now has Postgres adapters and a schema drift gate that can serve as the pattern. | One policy, not one argument per product.
D-P3 | Chat vendor | FlowCast D-F6, ShiftDesk D-SD4, EngageOS D-E4, VoiceBridge D-V1, RetainKit DR-7 — five products have built an in-house chat SLA engine making the vendor optional. | Either adopt a vendor once across the portfolio, or ratify the built-in engine once and stop re-raising it. | Five open ratifications for the same call.
D-P4 | Consent handling on imports | RetainKit DR-3 established: never infer marketing consent; require a column or a recorded attestation. | If ratified, apply to every product with a customer importer — EngageOS and MeetSync both import contact data. | Applies beyond the product that raised it.
D-P5 | Shared modules vs per-product copies | csv.ts, ledger.ts, backoff and breaker have now been written separately in five to seven products, each with its own defects. | Decide whether a shared internal package is worth the coupling, or whether the per-product copy stays and the Pre_Completion_Audit catches the defects instead. | Currently the worst of both: duplicated code AND duplicated defects.
D-P6 | D15 — sequencing | Still open since 10 Sep. Ten products now hold code-phase-complete or near-complete state, all blocked on live inputs. | Parallel builds have produced ten products waiting on the same person. The constraint is no longer build capacity. | This register is evidence for the decision: the bottleneck is live access and dispositions, not code.

## Pre_Completion_Audit
PRE-COMPLETION AUDIT — run BEFORE declaring a product code-phase complete
Seventeen checks derived from the sixteen patterns. On the record so far, this would have caught the large majority of findings before an adversarial review, and the CRITICAL rows are the ones that were live-blocking.
ID | Check | Detail | Pattern | Severity if missed
A-01 | Does an application exist that can receive a request? | Every route named in a manifest, setup guide, CI workflow or load harness resolves to code. | P08 | CRITICAL
A-02 | Does a schema exist behind every persistence claim? | Backup drills, retention sweeps and data registries name real tables. | P08 | CRITICAL
A-03 | Does every published promise have a test that fails when it becomes untrue? | Retention policy, pricing page, trust page, SLA, plan limits. | P02, P16 | CRITICAL
A-04 | Does every status field have a reader that changes behaviour? | Grep each status enum for consumers. Trial expiry, dunning mode, cancellation, pause. | P01 | CRITICAL
A-05 | Is every guard module a required collaborator of what it guards? | Consent, opt-in, session windows, entitlement. A guard nothing calls is decoration. | P10 | CRITICAL
A-06 | Does deletion sweep one registry that fails closed? | Both the platform webhook path and any self-serve path use the same sweep. | P02 | HIGH
A-07 | Has an external verification sweep run against live platform docs? | API versions, response-body rules, ack deadlines, auth schemes, asset specs, scope approvals. | P09 | CRITICAL
A-08 | Is identity verified rather than asserted, and is tenancy resolved per request? | No caller-supplied role or user header is trusted. | P11 | CRITICAL
A-09 | Does the OAuth callback match server-side, single-use, time-limited state? |  | P12 | HIGH
A-10 | Is every async handler awaited inside a try/catch? | A rejected handler must produce a 500, not a hung socket that times out the test. | P14 | HIGH
A-11 | Is every retained collection capped? | Dedupe ledgers, error logs, notification queues, alert stores. | P03 | HIGH
A-12 | Is CSV parsing RFC-4180 compliant and shared? | No hand-rolled split on commas anywhere. | P04 | MEDIUM
A-13 | Is the production backoff path executed by at least one test? | And is any Retry-After header converted in exactly one tested place? | P05 | HIGH
A-14 | Does dunning attempt recovery before its first email? |  | P07 | MEDIUM
A-15 | Does demo or sandbox mode refuse any tenant outside a reserved namespace? |  | P13 | HIGH
A-16 | Have any tests changed during the review, and was each change read as a finding? | A test that had to change was defending something. | P15 | MEDIUM
A-17 | Does the README or review pack state what coverage does not prove? |  | P16 | LOW

## Evidence_By_Product
WHAT HAS BEEN RUN, PER PRODUCT
Blank or unknown means not checked, not clean. Products with no recorded verification sweep or artifact-gap audit are where the next live-blocking defect is most likely to be sitting.
Product | Reviews run | Patterns known to have hit it | Note / what is missing
TeleField | Cold review + completion wave | P01 | Code phase complete. No standalone verification sweep or artifact-gap audit recorded — A-01, A-02 and A-07 worth running.
VoiceBridge | Cold review passes 1+2, verification sweep | P01, P02, P05, P06, P07, P15 | Most thoroughly reviewed. Artifact gap found and closed (sfpackage).
FlowCast | Cold review passes 1+2, verification sweep, artifact-gap audit | P03, P06, P09 | VER-001 was live-blocking and invisible to two clean cold reviews.
ShiftDesk | Cold review passes 1+2, completion wave | P03, P04 | No verification sweep or artifact-gap audit recorded — A-01, A-02, A-07.
EngageOS | Cold review passes 1+2, artifact-gap audit | P02, P03, P04, P07, P08, P10 | GAP-E1: 30 modules at 100% and nothing that could receive a message.
MeetSync | Cold review passes 1+2, workbook re-baseline | P01, P02, P03, P04, P05, P11, P12, P13, P14 | Richest single source of new patterns. No verification sweep against live Zoom docs recorded — A-07.
TestPulse | Cold review pass 1, verification sweep | P02, P03, P05, P06 | Cold review pass 2 outstanding.
OnCall Copilot | Cold review passes 1-3, verification sweep, artifact-gap audit | P02, P03, P04, P06, P07, P08, P09, P11, P12 | Only product with a third review pass, which found two CRITICALs in the layer the second pass had just built (L-OC4).
DocMerge Pro | NONE — mid-S7, no cold review | unknown | HIGHEST PRIORITY for this checklist. Ten sprints of code with no adversarial review at all.
RetainKit | Cold review pass 1, verification sweep, artifact-gap audit, Postgres adapters | P01, P02, P05, P08, P09, P10 | Code phase complete. P12, P13, P14 prevented by construction because the sibling findings were read first.