## Version_Control
VERSION CONTROL — Marketplace Build Standard & Review Protocol
File naming: claude_v<NNN>_<proper file name>_YYYYMMDD_HHMI.xlsx. Portfolio-level: applies to all 12 products, not one.
Version | Date/Time | Author | Change Description | Status
v001 | 2026-09-13 11:35 | Claude for Senthil/KP | THIS FILE — the build standard, defect taxonomy, walkthrough protocol and gate rollout plan, derived from the actual defect record of 11 products (10-13 Sep 2026: cold reviews, verification sweeps, artifact-gap audits). Every class in Defect_Classes was found AFTER a product reached 100% coverage, in more than one product. Answers 'do all properly': (1) rollout plan per product with expected classes, (2) the walkthrough protocol as 12 named probes each tied to a real defect, (3) the standard folded into a revised definition of done. Executing (1) and (2) needs the repos in hand — this file is the instrument, not the execution. | Released
v002 | 2026-09-13 11:51 | Claude for Senthil/KP | MARKETPLACE BASELINE SHIPPED — the other half of the standard. The gates catch 7 of the 13 classes; the remaining six are not gateable, they are things code either does or does not do, and each had already been retrofitted into several products AFTER they reached 100% coverage. The baseline package does that retrofit once: tenantData (DC-01, 8 products), ledger (DC-02, 7), writeGate incl. the payment-recovery path whose absence was the defect in six (DC-03/DC-10), csv (DC-04, 5), backoff with a real default sleep and Retry-After in seconds (DC-06, 5), identity derived server-side (DC-07, 4), tenancy with per-tenant ids from day one (DC-11, 2), asyncRouter (DC-13, open portfolio-wide). 30 tests, 100% x4, zero pragmas, no runtime dependencies; every test written as the defect it prevents, in the shape that defect actually took. New Baseline_Modules sheet maps class to module to adoption status per product. | Released
v003 | 2026-09-13 11:57 | Claude for Senthil/KP | CONFORMANCE SUITE — the baseline made adoptable without a rewrite, and then MEASURED. Adopting eight modules is a rewrite, which is how adoption stalls; what matters is the invariant, not the code. conformance.ts exports one check per class, each taking a small harness describing what the product ALREADY has (your purge, your dedupe set, your role resolution, your route table). Each check is tested twice — against an implementation that holds the invariant and one shaped like the defect — because a check that cannot go red is decoration. Run against TestPulse's own code, five checks passed and the tenancy check FAILED, with the defect in the baseline itself: nextId scoped the sequence per tenant but returned BOARD-1 for every tenant, and the baseline's own test asserted that as correct — lesson L-6 (a passing test can pin the defect) occurring inside the code written to prevent L-6. Fixed with tenant-qualified ids; a second bug surfaced on the fix (similar tenant ids produced the same hash prefix), fixed by taking the low-order end. TestPulse now carries the conformance run as a permanent test: 38 suites / 338 tests / 100% x4, six CI gates green. Baseline: 42 tests, 100% x4, zero pragmas. | Released
v004 |  |  | PLANNED: conformance results per product as the rollout proceeds. | Planned

## ReadMe_Scope
WHAT THIS IS — the standard the next product should be built against, derived from what the last eleven actually got wrong.
EVIDENCE BASE — TeleField, TestPulse, VoiceBridge, FlowCast, OnCall Copilot, EngageOS, ShiftDesk, MeetSync, RetainKit, DocMerge Pro, RevRescue.
Roughly 150 defects found between 10 and 13 Sep 2026, every one in code that was already at 100% test coverage with zero pragmas.
THE CENTRAL FACT — no story count moved in any review pass on any product. None of this was new scope. All of it was shipped scope that did not work.
HOW TO USE IT — Defect_Classes is the checklist to build against; Phase_Gates is the revised definition of done; Walkthrough_Protocol is the
45-minute manual pass that the gates cannot replace; Rollout_Plan is the order to run the gates across the portfolio, with the classes each
product is most likely to have. Gate_Register says what each gate costs and catches.
HONEST LIMIT — the gates cover about two thirds of the record. The rest needs someone using the product (L-7). Budget the walkthrough; do not
let a green CI run stand in for it.

## Defect_Classes
RECURRING DEFECT CLASSES — each found after 100% coverage was reached, in more than one product
"Products" counts products where this class was actually found. Detection names what would have caught it earliest.
ID | Class | Products | Where it was found (examples) | Prevention (build against this) | Detection (earliest catch) | Gate that catches it
DC-01 | Published deletion/retention not implemented | 8 | TestPulse F-TP01/02; FlowCast F-007; OnCall F-009; EngageOS F-014; VoiceBridge F-V01/V08; MeetSync M-F03; TeleField delete-my-data left user records | One tenant-data registry that export, delete AND the retention sweep all read; deletion proof rows kept | Drift test: any namespace written by an end-to-end flow that the registry does not claim fails the build | reachability + claims
DC-02 | Unbounded ledgers | 7 | FlowCast F-001; OnCall F-010; ShiftDesk; EngageOS F-016; VoiceBridge F-V05; MeetSync M-F14; TestPulse F-TP06 | Shared FIFO ledger helper with a drop counter; never append raw arrays to storage | Grep for array-append-to-store at review; platform value-size limits make this a hard failure, not a leak | none
DC-03 | Billing state declared, never enforced | 6 | OnCall; ShiftDesk; VoiceBridge F-V02/V03; EngageOS F-012/013; MeetSync M-F01/02; TestPulse OBS-TP4 | One write gate at the mutating ENTRY POINTS, not inside billing | Test from the entry point: an expired trial must fail a real write | reachability
DC-04 | Naive CSV handling | 5 | OnCall F-013; EngageOS F-015; ShiftDesk F-010; MeetSync M-F10/20; TestPulse F-TP11 | Shared RFC-4180 parser for input AND quoting for output | One CRLF fixture per importer — every platform export is CRLF | none
DC-05 | Platform contract wrong (LIVE-BLOCKING) | 5 | FlowCast VER-001 body on webhook ack; OnCall VER-OC1 3s ack; VoiceBridge VER-V01/V06; TeleField VER-T1 header/timestamp; TestPulse VER-P01/02/03 | Verify every platform contract against live docs BEFORE declaring a code phase complete, and again at deploy | Live-doc sweep; no test can see it | platform entrypoints
DC-06 | Retry/backoff that does not run | 5 | VoiceBridge F-V06 no-op sleep; ShiftDesk backoff never applied; FlowCast OBS-002; MeetSync M-F05; TestPulse F-TP08 ms-vs-seconds | Exercise the PRODUCTION path; injected sleeps in every test hide a dead one | A test that asserts the real delay, plus one that fails if the sleep is removed | none
DC-07 | Caller-declared identity | 4 | TeleField spoofable x-user-id; MeetSync M-F11; TestPulse F-TP14; VoiceBridge F-V21 (open by direction) | Identity derived server-side from the platform context that is documented as trustworthy | For every authorization input, write down where it comes from and who can set it | none
DC-08 | Module with no caller (unwired seam) | 4 | EngageOS F-009/010 optIn+sessionWindow never called; TestPulse F-TP16 AI provider never called; VoiceBridge F-V10 /log route absent | Report a seam closed only when a test drives the real path end to end | Reachability gate: orphan modules and orphan methods from the real entrypoints | reachability
DC-09 | Missing artifact behind a documented path | 4 | OnCall GAP-OC1/2 no HTTP app, no schema; EngageOS GAP-E1/E2 same; TeleField no listen()/npm start; TestPulse VER-P01 entrypoint commented out | Run the setup guide's own commands as part of the build | Artifact-gap audit; platform-entrypoint gate for the manifest half | platform entrypoints
DC-10 | Read-only / suspended state not enforced | 4 | EngageOS F-011; VoiceBridge F-V07; ShiftDesk; MeetSync M-F02 | Same write gate as DC-03; reads pinned open so data is never held hostage | Entry-point test per mutating surface | reachability
DC-11 | No multi-tenancy | 2 | OnCall F-014 one instance + id counter for every workspace; MeetSync M-F04 process-wide engine | Tenant registry from the day a store is introduced; ids scoped per tenant | Two-tenant test on any stateful surface | none
DC-12 | OAuth flow without state (CSRF) | 2 | OnCall F-015; MeetSync M-F15 | state + PKCE where the platform supports it | Security checklist at the first OAuth commit | claims
DC-13 | Async handler errors swallowed | 1 | MeetSync M-F21 (Express 4 ignores rejected promises — request hangs, test times out instead of failing) | Async-safe router wrapper | Grep portfolio-wide: this one is still open elsewhere | none
TOTAL | Product-incidences across all classes | 57
| Classes a standing gate catches | 7 | of | 13 | Remaining classes need a build habit or the walkthrough, not a gate

## Lessons
LESSONS — each one paid for by a product
ID | Lesson | Where it was paid for | What it changes | Gate / practice
L-1 | A 100%-covered codebase can be undeployable — nothing in a test run loads the file the platform loads | TestPulse VER-P01 (entrypoint commented out); VoiceBridge VER-V01 (bridge script never loaded) | The deploy entrypoint is part of the build, not a deployment detail | Entrypoint type-check against real vendor packages, in CI
L-2 | Reachable is not invoked — a handler with a door still needs the manifest to open it | TestPulse F-TP42: install path passed five review passes AND the reachability gate | Every platform-owned hook must be declared, not merely implemented | Platform-entrypoint gate
L-3 | A module with no caller is not a feature, and a test suite cannot tell the difference | TestPulse pass 3 (9 findings); EngageOS F-009/010 | Capability lists need a "reached by" column | Reachability gate
L-4 | A document is an assertion about the code and should be tested like one | TestPulse pass 4: 4 false customer-facing statements, all true when written | Mechanical claims get a five-line test; the rest get an owner and a date | Published-claims gate
L-5 | A seam is not a feature | TestPulse F-TP16 (R-P6 reported closed on an unreachable class) | A risk closes when a test drives the real path, not when the adapter exists | Review discipline
L-6 | A passing test can pin the defect | VoiceBridge L-V2 (mock encoded the bug); OnCall L-OC2 (two tests defended double-paging); VoiceBridge F-V06 (injected sleeps hid a dead one) | Ask what a test would fail to notice if the behaviour were removed | Review discipline
L-7 | Walk the primary loop as the user, once, before launch | TestPulse pass 6/7: generate-on-mount, no navigation, member could not complete the loop, install never fired | 45 minutes per product, before launch, by someone willing to be bored | Walkthrough_Protocol
L-8 | Review before declaring a code phase complete | TeleField L-T1: declared FINAL at 627 tests/100%, then its first review found 18 defects + 4 gaps | "Code phase complete" now requires one cold review already done | Phase_Gates
L-9 | Coverage over modules proves the modules work, not that a product exists | OnCall L-OC3 / EngageOS L-E2: 30 modules at 100% and nothing that could receive a message | The setup guide's commands must run end to end | Artifact-gap audit
L-10 | New surfaces inherit old blind spots | OnCall L-OC4: the new HTTP layer repeated multi-tenancy and CSRF defects already known elsewhere | Re-run the class checklist against any new surface | Defect_Classes

## Gate_Register
STANDING GATES — what each costs and what it catches
ID | Gate | What it checks | Classes caught | Port effort | CI command
G-1 | Reachability | Orphan modules and orphan methods measured from the REAL entrypoints (never the tests); exceptions need written reasons; stale exceptions reported | DC-01, DC-03, DC-08, DC-10 | ~10 lines of config | npm run gates
G-2 | Published claims | Each published promise tied to the code evidence that must hold; retired promises must not creep back | DC-01, DC-12, doc drift | 15 claims ≈ 1 hour | npm run gates
G-3 | Platform entrypoints | Manifest and deploy entrypoint read together: unexported handlers, unpointed exports, orphan functions, required module declarations | DC-05, DC-09 | ~15 lines of config | npm run gates
G-4 | Entrypoint type-check | The deploy entrypoint compiles against the REAL vendor packages | DC-05, DC-09 | one tsconfig | npm run typecheck:<platform>
G-5 | Posture check | The config assertion the trust page claims CI makes actually runs | doc drift | ~20 lines | npm run check:posture
G-6 | Automated a11y | axe-core over every screen on every build | accessibility | one test file | in the suite
| Gates shipped and tested | 6

## Phase_Gates
REVISED DEFINITION OF DONE — each addition was paid for by a product that skipped it
Phase | Previously | Now also requires | Paid for by
Foundation | Modules at 100% coverage | A store with tenant scoping; the capped-ledger helper; the RFC-4180 parser — all three retrofitted into 7+ products later | DC-02, DC-04, DC-11
Feature complete | Stories done-in-code | Every module has a named caller (reachability gate green) | DC-08 (EngageOS, TestPulse)
Code phase complete | Backlog zero at 100% coverage | Entrypoint compiles against real vendor packages; every platform hook declared in the manifest; the setup guide's own commands run end to end; ONE COLD REVIEW ALREADY DONE | L-8 (TeleField declared FINAL, then 18 defects), DC-09
Review prep | Evidence pack written | Every published claim pinned to code by a test; the encryption/posture assertion actually runs in CI | L-4, DC-01
Launch ready | Review pack + assets | The customer-path walkthrough completed and its findings dispositioned | L-7
Listed | Marketplace approval | Live verification script run against the deployed app, with evidence distinguishing verified from assumed | DC-05

## Walkthrough_Protocol
CUSTOMER-PATH WALKTHROUGH — 45 minutes, on a real install, as the lowest-privilege role
Rules: no knowledge of the code; take the boring step twice; write your expectation before each step; never fix while walking — note and continue.
# | Probe | Defect it actually caught | Class
1 | Install it and watch for ten minutes | TestPulse F-TP42: the install trigger was never declared, so nothing bootstrapped — no trial, no owner, no secret | DC-05/DC-09
2 | Open the main screen twice and compare | TestPulse F-TP39: mounting the panel called a write — duplicate data per view and a billed AI call | —
3 | Reach every screen the listing advertises using only what is on screen | TestPulse F-TP43: five screens, no navigation, four unreachable | —
4 | Complete the primary loop as a member, not an admin | TestPulse F-TP40: recording a run needed a board id only an admin could create | DC-07
5 | Do the first step with no data present | Empty states that teach nothing (ST-079 class across products) | —
6 | Look for every control the help centre mentions | TestPulse F-TP19: a Settings screen that did not exist and a run status the product never had | DC-09
7 | Use self-serve export, then delete | TestPulse F-TP21 + DC-01 everywhere: the rights existed as code with no door and covered a fraction of the data | DC-01
8 | Change a setting, reload, confirm it stuck | TestPulse F-TP07: threshold stored on an instance, silently discarded each invocation | DC-08
9 | Send malformed input to every public surface | TestPulse F-TP12: 500 with a stack to an unauthenticated caller | —
10 | Disconnect the dependency mid-flow | VoiceBridge F-V11: "will sync when the connection recovers" with nothing queuing | DC-06
11 | Do something twice the platform may deliver twice | TestPulse F-TP45: repeat install event reset the installation and wiped tokens | DC-05
12 | Read the trust page aloud with the code open | TestPulse F-TP33: an email subprocessor the app could not even reach | DC-01/L-4

## Rollout_Plan
GATE ROLLOUT — order, per-product entry hints, and the classes each is most likely to have
Status columns: NOT STARTED / GREEN / RED (n findings). Fill as each product is run. Yellow = needs Senthil input.
Product | Platform | Code state (13 Sep) | Likely entrypoints | Classes most likely present (not yet reviewed there) | G-1 | G-2 | G-3 | G-4 | Notes
RevRescue | Stripe Apps | S1 foundation code-complete | app entry + Stripe webhook handler | DC-01, DC-02, DC-03, DC-05, DC-09 | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | WIN rank 1; least reviewed of all — highest expected yield
TeleField | Zoho | Code phase complete + passes 1-3 | server entry (listen()), Zoho webhook | DC-07 open, DC-11, DC-13 | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | R-T4 adapter + OBS-T1/T2/T4/T5 open
TestPulse | Atlassian Forge | 8 passes; gates already running | forge/index.ts, static/entry.ts | — | GREEN | GREEN | GREEN | GREEN | Reference implementation; LC-1 pending
VoiceBridge | Salesforce | Code phase complete + 2 passes + 2 sweeps | sfpackage static resource, Apex-free | DC-13; DC-07 open by direction (F-V21) | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | D-V2/D-V3 open; ECA migration done
FlowCast | Xero | Code phase complete + 2 passes + sweep | server entry, Xero webhook | DC-09, DC-11, DC-13 | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | ci.yml/deploy.yml built in v017
OnCall Copilot | Slack | Passes 1-3 + gap audit + HTTP layer | router/app, Slack events + slash | DC-13, DC-04 done, DC-12 done | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | Needs Postgres + OPERATOR_TOKEN to deploy
EngageOS | WhatsApp / Meta | Code phase complete + pass 2 + gap audit | app router, /webhook, /healthz | DC-11, DC-13 | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | Migrations + signature verify built in v012
ShiftDesk | Teams / AppSource | Code phase complete + 2 passes | bot entry, Teams manifest | DC-09, DC-11, DC-13 | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | Teams manifest is the G-3 target
MeetSync | Zoom | Passes 1-2 + web UI layer | src entry + web/ app, Zoom SDK boundary | DC-09 (InMemoryStore is the only Store) | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | OBS-M3: every cap/purge is process-local
RetainKit | Shopify | S8 done-in-code; no cold review yet | server entry, Shopify webhooks + GDPR hooks | DC-01, DC-03, DC-05, DC-08, DC-09 | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | No review yet — expect the full class list
DocMerge Pro | Google Workspace | S7 done-in-code; no cold review yet | add-on entry, OAuth callback | DC-01, DC-03, DC-05, DC-09, DC-12 | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | LC-1 GCP project blocked 7 sprints (R-D8)
(12th product) | — | reconcile against the WIN order | — | — | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | Not named in the portfolio record I hold — confirm from the action board
ROLLUP |  |  |  |  | 1 | 1 | 1 | 1 | Products green per gate
| Products not yet gated at all |  | 11 | of | 12

## Findings_Log
ROLLOUT FINDINGS LOG — one row per finding, across products
Disposition: FIX / ALLOW (needs a written reason) / CUT. Cutting unfunded scope is a legitimate and usually honest outcome.
ID | Product | Class | Finding | Gate that found it | Disposition | Closed
(example) | RetainKit | DC-01 | Retention sweep removes only the account row | G-1 reachability | FIX | No
ROLLUP | Findings logged | 1 | Fixed | 1 | Allowed | 0

## Baseline_Modules
MARKETPLACE BASELINE — one module per non-gateable class; adoption status per product goes in the rollout log
30 tests, 100% branches/functions/lines/statements, zero pragmas, no runtime dependencies. Store is the only assumed interface (4 methods).
Class | Module | Products | What it prevents | Why it could not be a gate | Adoption
DC-01 | tenantData.ts | 8 | Export, delete and the retention sweep read ONE namespace registry; exact-segment tenant matching; drift guard reporting any unregistered namespace | The reachability gate finds the unreachable call; it cannot tell you the sweep covers the wrong keys | TestPulse: adopted
DC-02 | ledger.ts | 7 | FIFO-capped ledgers with a visible drop counter; seenBefore() for webhook dedupe | No static signal — an append to storage looks identical whether or not it is bounded | TestPulse: adopted
DC-03/10 | writeGate.ts | 6 / 4 | One gate at the mutating entry points, reads always open, plus the payment-recovery path whose absence was the defect in six products | Enforcement is a runtime property of every call site, not a declaration | Not yet adopted anywhere
DC-04 | csv.ts | 5 | RFC-4180 in and out; validate-then-apply so a bad row leaves nothing written | A naive split parses fine until a CRLF file arrives | TestPulse: adopted
DC-06 | backoff.ts | 5 | Real default sleep (not a no-op), Retry-After in SECONDS and capped, breaker shared across operations, run(label, op) for SDK calls | The dead version passes every test that injects its own sleep | TestPulse: partial (client only)
DC-07 | identity.ts | 4 | Role derived server-side from trustworthy platform context; ownership claimed once; requireRole for consistent guards | A header read looks like any other read | TestPulse: adopted
DC-11 | tenancy.ts | 2 | Per-tenant instances and per-tenant monotonic ids, from day one | Single-tenant code is correct until the second tenant arrives | Not yet adopted anywhere
DC-13 | asyncRouter.ts | 1 open | A rejected async handler becomes a response, not a hung request; assertAllWrapped fails the build on a bare route | The failing test TIMES OUT rather than failing, so the suite stays green | Not yet adopted anywhere
TOTAL | Classes covered by the baseline | 8 | Product-incidences addressed | 31 | (DC-03/10 and DC-13 counted as text — see class rows)

## Conformance
CONFORMANCE CHECKS — prove the invariant with the code a product already has
Result column: PASS / FAIL / N-A (with reason). A check recorded as N-A must say why; never leave one blank.
Class | Check | Harness the product supplies | TestPulse result | Notes
DC-01 | conformsDeletion | seed a real end-to-end flow; purge; list what remains | PASS | Covers a flow that writes cases, boards, audit, notifications, webhook ledger, account and subscription
DC-02 | conformsLedgerCap | append 2x the cap through your own path; report size | PASS | Webhook dedupe ledger bounded at 10k
DC-07 | conformsIdentity | resolve a role from a payload that claims a privileged one | PASS | deriveRole ignores the claim entirely
DC-03/10 | conformsWriteGate | blocked state; attempt a write; attempt a read | PASS | Enforcement point is the licensing gate, not billing.ts (Paid via Atlassian)
DC-06 | conformsBackoff | call your client WITHOUT injecting a sleep | N-A | TestPulse has no live HTTP call in-process to time; covered by the unit test asserting Retry-After seconds
DC-13 | conformsAsyncRoutes | your route table with a wrapped flag per route | PASS | Parsed from app.ts; every route wrapped
DC-11 | conformsTenancy | create the same record for two tenants; report what each sees | PASS (after fix) | FOUND A DEFECT IN THE BASELINE: nextId returned BOARD-1 for every tenant and the baseline test asserted it — L-6 inside the L-6 prevention
ROLLUP | Checks passing | 6 | of | 7