## Daily Tracker
Sl: No: | Date | Time | Day | Category | Task Details | Priority | Actual Start Date | Actual Start Time | Actual End Date | Actual End Time | Status | Remarks / Notes | Next Action | Follow-up Date
1 | 2026-07-10 | 14:00 | Friday | Hiring | Menaga and Jaya Sudha whatsapp msg preparation | High | 2026-07-10 | 14:20 | 2026-07-10 | 14:40 | Completed partially | Msg Shared in group | After the approval need to share directly | 2026-07-11
2 | 2026-07-10 | 14:00 | Friday | Documentation | Create a master sheet and Put together all the links | High
3 | 2026-07-10 | 11:00 | Friday | Company Registration | Talk to Renu Chennai | High | 2026-07-10 | 16:00 |  |  |  | She is Refering her Auditor cum Auditor friend as she handles only GST |  | 2026-07-11
4 | 2026-07-11 |  | Saturday | Web Site Design | Cute Pay Website Design, Need to check the UI and Speak to them
5 | 2026-07-11 |  | Saturday | Web Site Design | Jacob for branding ans suggestion for UI from Cute Pay
6 | 2026-07-11 | 11:00 | Saturday | Company Registration | Renu Akka ask friend number and speak to auditor |  | 2026-07-11 | 11:00
7 | 2026-07-11 | 11:00 | Saturday | Company Registration | Auditir Bala Murugan previously Registered Auditort |  | 2026-07-11 | 11:15 | 2026-07-11 | 11:30 | COmpleted | Actual to Move to Jageedeswari akka, as we wan to support womens | NIl
8 | 2026-07-12 | 14:00 | Sunday | Interview | jayashree Interview for Customer Support | High | 2026-07-10 | 14:20 | 2026-07-12 | 14:45 | COmpleted | Suitable for Customer Support Executive
9 | 2026-07-12 | 11:00 | Sunday | Learnings | Public Speaking class Completde | Medium | 2026-07-12 | 11:00 | 2026-07-12 | 14:00
10 | 2026-07-12 | 11:00 | Sunday | Interview | Recuritments Preparations |  | 2026-07-12 | 14:00 | 2026-07-12 | 14:25 | Completed
11 | 2026-07-12 | 11:00 | Sunday | Interview | Swetha |  | 2026-07-12 | 16:30
12 | 2026-07-12 | 11:00 | Sunday | Interview | Subu lakshmi
13 | 2026-07-12 | 11:00 | Sunday |  | Google
14 | 2026-07-13 | 11:00 | Monday | Interview | Swetha |  | 2026-07-13 | 11:30
15 | 2026-07-13 | 11:00 | Monday | Learning | BPO training |  | 2026-07-13 | 12:00
16 | 2026-07-13 | 10:30 | Monday | Documentation | Informed Princy to document the Call recording software absorvation and Hostel in tambaram
17 | 2026-07-13 | 10:30 | Monday | Website | Cute Pay check the status of teh website, logo and company profile
18 | 2026-07-13 | 14:30 | Monday | Training Session | Jaya Shree, Swetha, Subu lakshmi, Princy shedule not confirmed, Muthulakshmi will check the recording |  | 2026-07-13 | 19:00
19 | 2026-07-14 | 10:00 | Tuesday | training Session | Training Record check
20 | 2026-07-15 | 10:30 | Wednesday | Website | Need to share abous Us, Service and other details
21 | 2026-07-15 | 10:30 | Wednesday | Training Session
22 | 2026-07-15 | 10:30 | Wednesday | website | Create Instagram Page, face book page, linkedin page and twitter
23 | 2026-07-16 | 12:20 | Thursday |  | Today send another set of datas
24 | 2026-07-17 |  | Friday | chithirai Event | Chennai travel
25 | 2026-07-18 |  | Saturday | chithirai Event | chithirai Event
26 | 2026-07-19 |  | Sunday | chithirai Event | Return to Tirunelveli from Chennai
27 | 2026-07-20 | 10:00 | Monday | Asset purchase | laptop Collect | High | 15/07/2026 |  | 2026-07-20 | 10:5
28 | 2026-07-20 | 10:00 | Monday | Client Followup | Send a reminder whatsapp msg to i met at chithirai event |  | 18/07/2026 |  |  |  |  | whatsapp msg
29 | 2026-07-20 | 10:00 | Monday | Asset purchase | Laptop Setup |  | 20/07/2026 | 11:30 | 2026-07-20 | 12:50 | completed
30 | 2026-07-20 | 10:00 | Monday | Software Analysis | TeleCMI Purchase |  | 20/07/2026
31 | 2026-07-20 | 10:00 | Monday | Software Analysis | Other call recording Software need to check |  | 20/07/2026
32 | 2026-07-20 | 10:00 | Monday | Software Analysis | CRM Software need to check |  | 20/07/2026
33 | 2026-07-20 | 10:00 | Monday | Software Analysis | Vsanth Ticket management, Chennai Event demo need to check |  | 20/07/2026
34 | 2026-07-20 | 10:00 | Monday | Hiring | Selvi 9years experience candidate need to interview |  | 20/07/2026
35 | 2026-07-20 | 10:00 | Monday | Hiring | Employees Schedule Confirmation |  | 20/07/2026 | 13:10 | 2026-07-20 | 13:26 | completed | Whatsa app
36 | 2026-07-20 | 10:00 | Monday | Training (Incoming Call) | Rajiv Taljeras team |  | 20/07/2026 | 11:10 | 2026-07-20 | 11:20 | Completed
36 | 2026-07-20 |  | Monday | friendly call (Incoming call) | Falmora Ragi chennai event participants |  | 20/07/2026 | 13:45 | 2026-07-20 | 13:55 | Completed
36 | 2026-07-20 | 14:10 | Monday |  | Call center pricing analysis |  | 20/07/2026 | 14:24
37 | 2026-07-20 | 15:15 | Monday | Mentoring Session | Senthil Anna call regarding client pricing and general discussion |  | 20/07/2026 | 15:15 | 2026-07-20 | 19:55 | Completed
| 2026-07-20 | 21:00 | Monday | Chithirai Chennai Event: Transcript | Initially tried Perplexity but stopped in Mid half do started to download and convert Mpeg to MP3 and upload in sarvai Ai and got the transcipt |  | 2026-07-20 | 21:00 | 2026-07-20 | 22:40 | Completed
| 2026-07-20 | 22:50 | Monday | Planner | Planning and Dailyy planner =sheet updated |  | 2026-07-20 | 10:50 | 2026-07-20 | 22:30
| 2026-07-21 | 10:10 | Tuesday | Planner | Palnner Sheet Updated |  | 2026-07-21 | 10:10 | 2026-07-21 | 10:25
| 2026-07-21 | 10:26 | Tuesday | Personal Incoming call | Parvathy regading Bairava school Issue, they send outside of the class room because he made lot of noise in class room |  | 2026-07-21 | 10:26 | 2026-07-21 | 10:38 | Completed
| 2026-07-21 | 10:40 | Tuesday | Personal Incoming call | Arefa Trainer regarding Bairava School Issue |  | 2026-07-21 | 10:46 | 2026-07-21 | 11:05 | Completed
| 2026-07-21 | 11:20 | Tuesday | Recording Software Purchase | TeleCMI Ravindar for 2 agents purchase called
| 2026-07-21 | 11:25 | Tuesday | BPO training | BPO training class ned to attend, Tried Pradeep call not picked
| 2026-07-21 | 0:00 | Tuesday | Hiring - Preparation | Selvi 9years experience candidate need to interview |  | 2026-07-21 | 0:00 | 2026-07-21 | 0:25
| 2026-07-21 | 0:25 | Tuesday | Hiring - Google Meet link | Googel Meet Link Created |  | 2026-07-21 | 0:40 | 2026-07-21 | 0:30
| 2026-07-21 | 0:30 | Tuesday | Hiring - Interview | Interview |  | 2026-07-21 | 0:30 | 2026-07-21 | 13:00
| 2026-07-21 | 13:30 | Tuesday | Hiring - Preparation | Jothi Prakash Diabetic Patient, Viestage, Parvathy Reference, Amutha akka product eduthu pannura company |  | 2026-07-21 | 13:30 | 2026-07-21 | 13:30
| 2026-07-21 | 1:55 | Tuesday | Hiring - Google Meet link | Googel Meet Link Created |  | 2026-07-21 | 13:50 | 2026-07-21 | 13:50
| 2026-07-21 | 1:55 | Tuesday | Hiring - Interview | Interview |  | 2026-07-21 | 14:00 | 2026-07-21 | 14:20
| 2026-07-21 | 14:20 | Tuesday | Lunch | Lunch |  | 2026-07-21 | 14:20 | 2026-07-21 | 15:00
| 2026-07-21 | 15:00 | Tuesday | Incoming call | Senthil Anna call |  | 2026-07-21 | 15:00 | 2026-07-21 | 15:30
| 2026-07-21 | 15:30 | Tuesday | Incoming call | Tata tele Service |  | 2026-07-21 | 15:30 | 2026-07-21 | 15:45
| 2026-07-21 | 15:50 | Tuesday | Incoming call | Bajaj Finance, 24000 pay pannuna NDC issue pannuren sollranga |  | 2026-07-21 | 15:50 | 2026-07-21 | 16:00
| 2026-07-21 | 4:00 | Tuesday | Documentation | Move all the Palm Era group to Archieve | Medium | 2026-07-21 | 16:00 | 2026-07-21 | 16:20
| 2026-07-21 | 4:00 | Tuesday | Employee | Subu Lakshmi call asked sim for call training purpose |  | 2026-07-21 | 16:20 | 2026-07-21 | 16:25
| 2026-07-21 | 16:30 | Tuesday | Mentoring Session | Senthil Anna call |  | 2026-07-21 | 16:30 | 2026-07-21 | 6.30 Pm
| 2026-07-21 | 21:30 | Tuesday | Mentoring Session | Bhuvana Annie call |  | 2026-07-21 | 21:30 | 2026-07-21 | 22:30
| 2026-07-21 | 22:30 | Tuesday | Scheduling | Planner and Daily tracker updation |  | 2026-07-21 | 22:30 | 2026-07-21 | 23:15
| 2026-07-22 | 10:20 | Wednesday | Accounts | At Team main accounts need to be updated |  | 2026-07-22 | 10:30 | 2026-07-21 | 11:40
| 2026-07-22 | 11:40 | Wednesday | Software | Asked for queartely but they mentioned not possible |  | 2026-07-22 | 11:40 | 2026-07-22 | 11:50
| 2026-07-22 | 11:50 | Wednesday | Team Lead | Selvi Team Lead informed to check the call recording software |  | 2026-07-22 | 11:50 | 2026-07-22 | 12:00
| 2026-07-22 | 12:00 | Wednesday | Pricing Calculation Analysis | https://www.magellan-solutions.com/blog/calculate-cost-per-call/ |  | 2026-07-22 | 12:00 | 2026-07-22 | 12:45
| 2026-07-22 | 12:45 | Wednesday | Personal Incoming call | Jenolin about her twin kids and chennai event details |  | 2026-07-22 | 12:45 | 2026-07-22 | 13:10
| 2026-07-22 | 13:10 | Wednesday | Training | BPO Training Class |  | 2026-07-22 | 13:25 | 2026-07-22 | 13:45
| 2026-07-22 | 13:45 | Wednesday | Incoming call | Rem Lead : Selvi regarding the My operator and zoho book pricing |  | 2026-07-22 | 13:45 | 2026-07-22 | 13:55
| 2026-07-22 | 14:00 | wednesday | Break | Lunch |  | 2026-07-22 | 14:00 | 2026-07-22 | 14:30
| 2026-07-22 | 14:30 | Wednesday | Analysis | https://www.magellan-solutions.com/blog/calculate-cost-per-call/ |  | 2026-07-22 | 14:30 | 2026-07-22 | 15:00
| 2026-07-22 | 15:00 | Wednesday |  | Creating sales proposal |  | 2026-07-22 | 15:00 | 2026-07-22 | 16:15
| 2026-07-22 | 16:15 | Wednesday | Break | tea Break |  | 2026-07-22 | 16:15 | 2026-07-22 | 16:30
| 2026-07-22 | 16:30 | Wednesday |  | Sales Proposal |  | 2026-07-22 | 16:30 | 2026-07-22 | 17:50
| 2026-07-22 | 17:50 | Wednesday |  | Senthil Anna Call |  | 2026-07-22 | 17:50 | 2026-07-22 | 19:10
| 2026-07-22 | 20:45 | Wednesday | Research | Check all the previous Chithirai Follow up calls | High | 2026-07-22 | 20:45 | 2026-07-22 | 21:00
| 2026-07-22 | 21:00 | Wednesday | Research | Prepare subha previous work experience | High | 2026-07-22 | 21:00 | 2026-07-22 | 21:30
| 2026-07-22 | 21:30 | Wednesday | Research | Services Subha worked on her experience | High | 2026-07-22 | 21:30 | 2026-07-22 | 21:40
| 2026-07-22 | 21:40 | Wednesday | Research | Industries where BPO can give service | High | 2026-07-22 | 21:40 | 2026-07-22 | 22:00
| 2026-07-22 | 22:00 | Wednesday | Pricing | Cost calculation for Starter, standard, premium | High | 2026-07-22 | 22:00 | 2026-07-22 | 23:05
| 2026-07-23 | 9:15 | Thursday | Tracker | Updated the Pending time sheet, daily tracker, planner | High | 2026-07-23 | 9:15 | 2026-07-23 | 9:45
| 2026-07-23 | 9:45 | Thursday | Technical Issue | Particularly in Time sheet The bottom sheet name is not visible when the column hides only the bottom sheet name is displaying |  | 2026-07-23 | 9:45 | 2026-07-23 | 10:15 | Holding | Taking so much time so holding moved to New sheet
| 2026-07-23 | 10:15 | Thursday | QUestion Preparation | Auditor Question preparation regarding name change issue and what are all the things we consider for a company |  | 2026-07-23 | 10:15 | 2026-07-23 | 11:00 | Compled | https://docs.google.com/spreadsheets/d/1BX1arbiV9XQvbCuUtAJIHWUkeA-NH-pXHAf1W1kwv68/edit?usp=sharing
| 2026-07-23 | 11:00 | Thursday | Break | tea Break |  | 2026-07-23 | 11:00 | 2026-07-23 | 11:15
| 2026-07-23 | 11:15 | Thursday | Software Analysis | My operator for call recording |  | 2026-07-23 | 11:15 | 2026-07-23 | 11:30 |  | Create a New Audio and Audio Shared in Software Analysis group
| 2026-07-23 | 11:30 | Thursday | Team Lead | Confirmed through Whatsapp that she is available to join the demo |  | 2026-07-23 | 11:30 | 2026-07-23 | 11:40
| 2026-07-23 | 11:40 | Thursday | Break |  |  | 2026-07-23 | 11:40 | 2026-07-23 | 0:00
| 2026-07-23 | 12:00 | Thursday | Demo | My Operator Call Recording software demo |  | 2026-07-23 | 12:00 | 2026-07-23 | 12:20 | Completed
| 2026-07-23 | 12:20 | Thursday | Incomig Call | Team Lead Selvi call regarding the My Operator |  | 2026-07-23 | 12:20 | 2026-07-23 | 12:30
| 2026-07-23 | 12:30 | Thursday | Break
| 2026-07-23 | 13:05 | Thursday | Incoming call | Senthil Anna Call |  | 2026-07-23 | 13:05 | 2026-07-23 | 14:00
| 2026-07-23 | 14:00 | Thursday | Break
| 2026-07-23 | 14:15 | Thursday | Finance | Karthiga HDFC Bank Credit card and cibil score |  | 2026-07-23 | 14:15 | 2026-07-23 | 14:30
| 2026-07-23 | 14:30 | Thursday |  | Break |  | 2026-07-23 | 14:30 | 2026-07-23 | 18:00
| 2026-07-23 | 18:00 | Thursday | Mentoring | Bhuvana Annie call preparation |  | 2026-07-23 | 18:00 | 2026-07-23 | 19:00
| 2026-07-23 | 19:00 | Thursday | Mentoring | Google Meet |  | 2026-07-23 | 19:00 | 2026-07-23 | 19:35
| 2026-07-23 | 19:35 | Thursday |  | Break |  | 2026-07-23 | 19:35 | 2026-07-23 | 22:30
| 2026-07-23 | 22:30 | Thursday | Planner | Update the planner and daily planner |  | 2026-07-23 | 22:30 | 2026-07-23 | 22:50
| 2026-07-24 | 9.30 Am | Friday | Bank Work | HDFC Bank Karthiga Mathan Anna Friend: Regarding Credit card, credit card applied with 25000 fixed deposit, we can use 20,000 after that it will increase based on our performance, Current account and salary account details check, While checking refered a KTC Nagar Auditor Vignesh for Cancellation the old MSME and applying New MSME and GST, he will check with the MSME for the drawback for the cancellation and what source to apply for Startup funds, Shared Adhar and Pan card for checking |  | 2026-07-24 | 9.30 Am | 2026-07-24 | 11:20
| 2026-07-24 | 11:20 | Friday | Srilanka Event | Eswari Call regarding Srilanka Event for Visa and team Discount |  | 2026-07-24 | 11:20 | 2026-07-24 | 11:30
| 2026-07-24 | 11:30 | Friday | Auditor | Auditor for OTP |  | 2026-07-24 | 11:30 | 2026-07-24 | 11:35
| 2026-07-24 | 11:35 | Friday | Marketing | Website content check |  | 2026-07-24 | 11:35 | 2026-07-24 | 2:00
| 2026-07-24 | 2:00 | Friday | Break | Lunch |  | 2026-07-24 | 2:00 | 2026-07-24 | 2.30 PM
| 2026-07-24 | 2.30 PM | Friday | Banking | HDFC OTP for Credit card |  | 2026-07-24 | 2.30 PM | 2026-07-24 | 2.43 PM
| 2026-07-24 | 2.43 PM | Friday | Banking | HDFC OTP for Credit card |  | 2026-07-24 | 2.50 PM | 2026-07-24 | 15:00
| 2026-07-24 | 15:00 | Friday | Mentoring | Subha BPO Training |  | 2026-07-24 | 15:00 | 2026-07-24 | 16:00
| 2026-07-24 | 16:00 | Friday | Mentoring | Live call Practice |  | 2026-07-24 | 16:00 | 2026-07-24 | 16:30
| 2026-07-24 | 16:30 | Friday | Mentoring | Bhuvana Annie call preparation |  | 2026-07-24 | 16:30 | 2026-07-24 | 17:30
| 2026-07-24 | 18:15 | Friday | Documentation | Rental Agreement for Spaco Co work space |  | 2026-07-24 | 18:15 | 2026-07-24 | 18:20 |  | Called pooja not attend so shared the msg
| 2026-07-24 | 18:20 | Friday | Marketing | Website Content check for about page and service page |  | 2026-07-24 | 18:20 | 2026-07-24 | 19:00
| 2026-07-24 | 19:00 | Friday | Mentoring | Bhuvana Annie call |  | 2026-07-24 | 19:00 | 2026-07-24 | 19:25
| 2026-07-24 | 22:00 | Friday | Tracker | Daily Tracker and Planner Update |  | 2026-07-24 | 22:00 | 2026-07-24 | 22:30
| 2026-07-25 | 10:10 | Saturday | Hiring | Team Lead : selvi regarding the confirmation |  | 2026-07-25 | 10:10 | 2026-07-24 | 10:15
| 2026-07-25 | 10:15 | Saturday | Client | Chithirai CLient Pitch and Database enter |  | 2026-07-25 | 10:15 | 2026-07-25 | 14:00
| 2026-07-25 | 14:00 | Saturday | Break | Break |  | 2026-07-25 | 14:00 | 2026-07-25 | 14:40
| 2026-07-25 | 14:50 | Saturday | Hiring | Team Lead : selvi regarding the confirmation |  | 2026-07-25 | 14:50 | 2026-07-25 | 15:05
| 2026-07-25 | 15:05 | SAturday | Marketing | Website content check |  | 2026-07-25 | 15:05 | 2026-07-25 | 17:00
| 2026-07-25 | 18:00 | Saturday | Mentoring | Class Started Skill Arbitrage |  | 2026-07-25 | 18:00 | 2026-07-25 | 21:20
| 2026-07-26 | 9.30 Pm | Sunday | Time Sheet | Yesterday Pending Time sheet |  | 2026-07-26 | 9.30 Pm | 2026-07-26 | 21:50
| 2026-07-26 | 21:50 | Sunday | Documentation | Sharing all the yesterday Skill Atribute Class in a folder and creating group |  | 2026-07-26 | 21:50 | 2026-07-26 | 12:00
| 2026-07-26 | 13:45 | Sunday | Marketing | Website content check |  | 2026-07-26 | 13:45 | 2026-07-26 | 15:00
| 2026-07-26 | 18:00 | Sunday | Mentoring | Class Started Skill Arbitrage |  | 2026-07-26 | 18:00 | 2026-07-26 | 21:30
| 2026-07-26 | 22:00 | Sunday | Marketing | Sales Proposal |  | 2026-07-26 | 22:00 | 2026-07-27 | 14:00
| 2026-07-27 | 22:35 | Monday | Marketing | Sales Call planning
| 2026-07-27 | 13:45 | Monday | Software & Yes Networking | Commercial Communication Rock Sir |  | 2026-07-27 | 13:45 | 2026-07-27 | 13:47 | Ringing
| 2026-07-27 | 13:50 | Monday | Software | Aura Gold Anand |  | 2026-07-27 | 13:50 | 2026-07-27 | 13:52 | Number Busy
| 2026-07-27 | 14:02 | Monday | Data Entry works | ISM Data tenkasi Muthu |  | 2026-07-27 | 14:02 |  | 14:10 | Planning to meet him tomorrow
| 2026-07-27 | 14:10 | Monday | Hiring | Princy Telecaller |  | 2026-07-27 | 14:10 |  | 14:30
| 2026-07-27 |  | Monday | Hiring | Subhu Lakshmi Telecaller
| 2026-07-27 | 15:40 | Monday | Staff Regular activity | Selvi Team Lead Call |  | 2026-07-27 | 15:40 | 2026-07-27 | 16:00
| 2026-07-28 | 10:20 | Tuesday | Travel | From Home to tenkasi ISM Data Technology, |  | 2026-07-28 | 10:20 | 2026-07-28 | 11:30
| 2026-07-28 | 10:20 | Tuesday | Pricing | Started working for Price to give to Ravi International and Sathya priya event management |  | 2026-07-28 | 10:20 | 2026-07-28 | 11:30
| 2026-07-28 | 11:30 | Tuesday | Company Visit | ISM DATA Technology direct visit |  | 2026-07-28 | 11:30 | 2026-07-28 | 12:40
| 2026-07-28 | 12:50 | Tuesday | Pricing | Started working for Price to give to Ravi International and Sathya priya event management |  | 2026-07-28 | 12:50
| 2026-07-28 |  |  |  | Telecaller Subu Lakshmi call not attend, share the msg that you send the resume with details regarding previous experience in Medical billing |  | 2026-07-28 | 13:15 | 2026-07-28 | 13:20
| 2026-07-28 | 17:00 | Tuesday |  | ISM Medical Billing agrrement Check |  | 2026-07-28 | 17:00 | 2026-07-28 | 17:45
| 2026-07-28 | 17:45 | Tuesday | Call Pricing | ISM Data Technology regarding the pricing, he mention initially a user can make rs.10000 per month, we are getting monthly Rs.35000 from a user with 3 months experience |  | 2026-07-28 | 17:45 | 2026-07-28 | 17:55
| 2026-07-28 | 18:00 | Tuesday | Event | women professional connect |  | 2026-07-28 | 18:00 | 2026-07-28 | 18:15 | Inform the team to contact you
| 2026-07-28 | 18:20 | Tuesday | Marketing | Penniyam Academy |  | 2026-07-28 | 18:20 | 2026-07-28 | 6:30 | Tamilarasi contact person, share all the details in whatsapp sir will check and update
| 2026-07-28 | 17:00 | Tuesday | Client pricing | Client pricing broucher prepared |  | 2026-07-28 | 17:00 | 2026-07-28 | 18:45 | Completed
| 2026-07-28 | 19:00 | Tuesday |  | Vignesh Auditor regarding Client Agreement and Employee Agreement |  | 2026-07-28 | 19:00 | 2026-07-28 | 19:15
| 2026-07-28 | 19:15 | Tuesday | Break |  |  | 2026-07-28 | 19:15 | 2026-07-28 | 21:30
| 2026-07-28 | 21:30 | Tuesday | Poster Creation | Poster creation for Meta Ads |  | 2026-07-28 | 21:30 | 2026-07-28 | 0:20
| 2026-07-29 | 10:05 | Wednesday | Time sheet Update | Yesterday Pending Time sheet Updated |  | 2026-07-29 | 10:05 | 2026-07-29 | 10:20
| 2026-07-29 | 10:20 | Wednesday | Employee | Employees Issues regarding Palm era training handled |  | 2026-07-29 | 10:20 | 2026-07-29 | 11:00
| 2026-07-29 | 11:00 | Wednesday | Networking | Exploring Tamilpreneur Community |  | 2026-07-29 | 11:00 | 2026-07-29 | 13:00
| 2026-07-29 | 11:00 | Wednesday | Software | Exploring ZOHO Startup features |  | 2026-07-29 | 11:00 | 2026-07-29 | 13:00
| 2026-07-29 | 13:00 | Wednesday | Website | Cute Web Website correction co ordination |  | 2026-07-29 | 13:00 | 2026-07-29 | 13:35
| 2026-07-29 | 13:35 | Wednesday | Break | Lunch |  | 2026-07-29 | 13:35 | 2026-07-29 | 14:00
| 2026-07-29 | 14:15 | Wednesday | Networking | TamilPreneur Madhan Kumar |  | 2026-07-29 | 14:15 | 2026-07-29 | 14:40
| 2026-07-29 | 14:57 | Wednesday | Networking and general discussion | Chithirai Participant Ragavi |  | 2026-07-29 | 14:57 | 2026-07-29 | 15:20
| 2026-07-29 | 15:20 | Wednesday | Cold calling & Data Collection | Checking Business peoples in Instagram and sending personalised msg |  | 2026-07-29 | 15:20 | 2026-07-29 | 16:30
| 2026-07-29 | 16:30 | Wednesday | Documentation | For rental aggrement witness sign pannurathu avnaga kila vanthnaga poi sign vangittu vanthen |  | 2026-07-29 | 16:30 | 2026-07-29 | 16:45
| 2026-07-29 | 16:45 | Wednesday | Mentoring | Bhuvana Annie call preparation |  | 2026-07-29 | 16:45 | 2026-07-29 | 17:15
| 2026-07-29 | 17:15 | Wednesday | Marketing | Karunya Team Digital Marketing need to check |  | 2026-07-29 | 17:15 | 2026-07-29 | 17:20
| 2026-07-29 | 17:20 | Wednesday | Client Acusation | Call to Ravi International to confirm the pricing and next step |  | 2026-07-29 | 17:20 | 2026-07-29 | 17:25
| 2026-07-29 | 17:25 | Wednesday | Client Acusation | Call to Hepziba to confirm the pricing and next step |  | 2026-07-29 | 17:25 | 2026-07-29 | 17:30
| 2026-07-29 | 17:30 | Wednesday | Client Acusation | Elavarasan Chiti Export Chennai event participant |  | 2026-07-29 | 17:30 | 2026-07-29 | 17:35
| 2026-07-29 | 19:00 | Wednesday | Networking | Tamil Prennuer Membership details check and explore |  | 2026-07-29 | 17:35 | 2026-07-29 | 19:00
| 2026-07-29 | 19:00 | Wednesday | Mentoring | Bhuvana Annie call |  | 2026-07-29 | 19:00 | 2026-07-29 | 19:40
| 2026-07-29 | 21:20 | Wednesday | Searching | Searched crm cum call recording software, what to do next, For Meta 10 creatives concept 3 creatives done , balance need to update |  | 2026-07-29 | 21:20 | 2026-07-29 | 23:50
| 2026-07-30 | 10:00 | Thursday | Client Acusation | Lakshmi Krishna Naturals, Facing issue in labelling and becoming trend in Instagram, so they need custome support, the outlet is in samathanapuram so planning to visit directly and pitch the BPO |  | 2026-07-30 | 10:00 | 2026-07-30 | 11:00
| 2026-07-30 | 12:00 | Thursday | Software Demo | Tele CRM Demo |  | 2026-07-30 | 12:00 | 2026-07-30 | 13:15
| 2026-07-30 | 13:30 | Thursday | Hiring | Mani Megalai for Social Media Marketing |  | 2026-07-30 | 13:30 | 2026-07-30 | 13:45
| 2026-07-30 | 13:45 | Thursday | Data Entry Project | Tesing ISM Data technology in chatgpt how it will be profit, how many entries a individual can made, |  | 2026-07-30 | 13:45 | 2026-07-30 | 16:00
| 2026-07-30 | 16:00 | Thursday | Marketing | Website content checking |  | 2026-07-30 | 16:00 | 2026-07-30 | 17:50
| 2026-07-30 | 17:50 | Thursday | Networking | Searched the networking platform and explore |  | 2026-07-30 | 17:50 | 2026-07-30 | 18:50
| 2026-07-30 | 18:50 | Thursday | Time sheet Update | Update the Pending Sheet |  | 2026-07-30 | 18:50 | 2026-07-30 | 19:10
| 2026-07-31 | 10:00 | Friday | Digital Marketing | Search Digial MArketing Partner |  | 2026-07-31 | 10:00 | 2026-07-31 | 11:30
| 2026-07-31 | 11:30 | Friday |  | Tele CRM Demo Video Check and price comparison and new crm software analysis |  | 2026-07-31 | 11:30 | 2026-07-31 | 15:30
| 2026-07-31 | 15:30 | Friday |  | Lunch |  | 2026-07-31 | 15:30 | 2026-07-31 | 16:00
| 2026-07-31 | 16:00 | Friday |  | Lakshmi Krishna Naturals appointment check |  | 2026-07-31 | 16:00 | 2026-07-31 | 4:05
| 2026-07-31 | 4:05 | Friday |  | Follow Happy Ending and Penniyam Academy |  | 2026-07-31 | 4:05 | 2026-07-31 | 4:10
| 2026-07-31 | 5:30 | Friday |  | Cheked tamiprenuer community check all the post and active members and explore the event activities |  | 2026-07-31 | 4:10 | 2026-07-31 | 5:30
| 2026-07-31 | 5:30 | Friday |  | Digital Marketign related videos checked, How to run Meta ads |  | 2026-07-31 | 5:30 | 2026-07-31 | 6:30

## Over All Planner
Sl. No. | Noted Start Date | Noted Start Time | Noted Time Spend | Noted End Date | Noted End Time | Day | Category | Task / Activity | Priority | PlanStart Date | PlanStart Time | PlanEnd Date | PlanEnd Time | Status | Remarks / Notes | Next Action | Follow-up Date
1 | 2026-07-20 | 10:00 |  |  |  | Monday | Software Analysis | TeleCMI Purchase |  | 2026-07-21 |  | 2026-07-21 |  |  | Need to Purchase 2 agents, and check all the features
2 | 2026-07-20 | 10:00 |  |  |  | Monday | Software Analysis | Other call recording Software need to check
3 | 2026-07-20 | 10:00 |  |  |  | Monday | Software Analysis | CRM Software need to check
4 | 2026-07-20 | 10:00 |  |  |  | Monday | Software Analysis | Vsanth Ticket management, Chennai Event demo need to check
5 | 2026-07-20 | 18:55 |  | 2026-07-20 | 19:00 | Monday | Hiring | Selvi 9years experience candidate need to prepare for Interview, Google sheet, Folder, Timing confirmation |  | 2026-07-21 | 0:00 | 2026-07-21 | 0:25
6 | 2026-07-20 | 10:00 |  |  |  | Monday | Hiring | Selvi 9years experience candidate need to interview |  | 2026-07-21 | 0:30 | 2026-07-21 | 13:00 |  | Need to check the availability time
7 | 2026-07-20 | 10:00 |  |  |  | Monday | Training (Incoming Call) | Rajiv Taljeras team | [5 empty] | Future Planning
8 | 2026-07-20 | 10:00 |  |  |  | Monday | Pricing | Pricing fro Client need to work out
9 | 2026-07-20 | 14:37 |  |  |  | Monday | Documentation | Company mail Id
10 | 2026-07-20 | 15:05 |  |  |  | Monday | Mentoring | Bhuvana Annie call preparation
11 | 2026-07-20 | 18:10 |  |  |  | Monday | Accounts | Chithirai Events Expense need to be corrected details in the pending
12 | 2026-07-20 | 18:35 |  |  |  | Monday | Accounts | Need to check how a gmail is placed in desktop | Low
13 | 2026-07-20 | 18:35 |  |  |  | Monday | Accounts | Main Accounts update form july 10th 2026
14 | 2026-07-20 | 21:30 | 2 MInutes | 2026-07-20 | 21:30 | Monday | Transcript | Sarvam Ai: Chithirai Chennai Event Transcription | Medium | 2026-07-20 | 21:10 | 2026-07-20 | 10:40 | Completed | Initially started with Perplexity, But perplexity record stopped unexpectedly, so again download the file and convert to MP3 file using online free converter and upload the document | Nil | Nil
15 | 2026-07-20 | 22:45 | 2 MInutes | 2026-07-20 | 22:47 | Monday |  | Organise File and Folders in Laptop (Book Mark)
16 | 2026-07-20 | 22:50 | 2 MInutes | 2026-07-20 | 22:52 | Monday |  | Move all the Palm Era group to Archieve
17 | 2026-07-20 | 23:10 | 2 MInutes | 2026-07-20 | 23:13 | Monday | Scheduling | Need to talk to all the telecallers, Pesi romba nal achu, enna pannittu irukanga, avanga current situation ennan kekanum
18 | 2026-07-21 | 10:10 | 2 Minutes | 2026-07-21 | 10:12 | Tuesday | Marketing | Personal Branding | Medium | 2026-07-21 | 10:12
19 | 2026-07-21 | 10:15 | 2 Minutes | 2026-07-21 | 10:20 | Tuesday | Marketing | Social Media Marketing: Instagram, Facebook and Linkedin | Medium | 2026-07-21 | 10:20
20 | 2026-07-21 | 10:20 | 2 Minutes | 2026-07-21 | 10:25 | Tuesday | Technical | Need to Check while sharing the screen the google meet disconnects, yesterday call with bhuvana annies the issue occurs 2 times | High | 2026-07-21 | 10:25
21 | 2026-07-21 | 10:35 | 2 Minutes | 2026-07-21 | 11:04 | Tuesday | Technical | Subha BPO training class need to Plan | Medium | 2026-07-21 | 11:04
22 | 2026-07-21 | 18:45 | 2 Minutes | 2026-07-21 | 18:47 | Tuesday | Documentation | Auditor Kitta pesanum , Before that prepare set of question | High | 2026-07-23 | 10:00 | 2026-07-23 | 10:15 | https://docs.google.com/spreadsheets/d/1BX1arbiV9XQvbCuUtAJIHWUkeA-NH-pXHAf1W1kwv68/edit?usp=sharing
23 | 2026-07-21 | 18:47 | 2 Minutes | 2026-07-21 | 18:49 | Tuesday | Documentation | Chatgptla Whatsapp Notes pottu analyse pannanum | High | 2026-07-21 | 18:49
24 | 2026-07-21 | 18:49 | 2 Minutes | 2026-07-21 | 18:51 | Tuesday | Research | Check Previous sheet for Pricing and resources | High | 2026-07-21 | 18:51
25 | 2026-07-21 | 22:40 | 2 Minutes | 2026-07-21 | 22:42 | Tuesday | Research | Compare BNI, JCI, Rotary, and other association | Medium | 2026-07-21 | 22:42
26 | 2026-07-21 | 22:40 | 2 Minutes | 2026-07-21 | 22:42 | Tuesday | Research | Analyse the website for price calculation https://www.magellan-solutions.com/blog/calculate-cost-per-call/ | High | 2026-07-21 | 22:42
27 | 2026-07-21 | 22:40 | 2 Minutes | 2026-07-21 | 22:42 | Tuesday | Research | Target Audience List | High | 2026-07-21 | 22:42
28 | 2026-07-21 | 22:50 | 1 MInutes | 2026-07-21 | 22:52 | Tuesday | Research | Set of Questions for Client Requirement Checking | Medium | 2026-07-21 | 22:52
29 | 2026-07-22 | 20:45 | 1 MInutes | 2026-07-22 | 20:47 | Wednesday | Research | Check all the previous Chithirai Follow up calls | High | 2026-07-22 | 20:47 | 2026-07-22 | 21:00
30 | 2026-07-22 | 20:47 | 1 MInutes | 2026-07-22 | 20:49 | Wednesday | Research | Prepare subha previous work experience | High | 2026-07-22 | 21:00 | 2026-07-22 | 21:30
31 | 2026-07-22 | 20:49 | 1 MInutes | 2026-07-22 | 20:52 | Wednesday | Research | Services Subha worked on her experience | High | 2026-07-22 | 21:30 | 2026-07-22 | 21:40
32 | 2026-07-22 | 20:52 | 1 MInutes | 2026-07-22 | 20:54 | Wednesday | Research | Industries where BPO can give service | High | 2026-07-22 | 21:40 | 2026-07-22 | 22:00
33 | 2026-07-22 | 22:00 |  | 2026-07-22 | 22:02 | Wednesday | Pricing | Cost calculation for Starter, standard, premium |  | 2026-07-22 | 22:00 | 2026-07-22 | 23:05
34 | 2026-07-23 | 9:45 |  | 2026-07-23 | 9:46 | Thursday | Client | Sales Proposal
35 | 2026-07-23 | 9:46 |  | 2026-07-23 | 9:47 | Thursday | Marketing | Digital Marketing
36 | 2026-07-23 | 9:47 |  | 2026-07-23 | 9:48 | Thursday | Marketing | Website followup and finalise
37 | 2026-07-23 | 22:30 |  | 2026-07-23 | 22:32 | Thursday | Finance | HDFC Bank Direct visit |  | 2026-07-24 | 9:15 | 2026-07-24 | 10:15
38 | 2026-07-23 | 22:32 |  | 2026-07-23 | 22:34 | Thursday | Asset : Post Paid Sim Purchase | Airtel Office -> Post Paid Sim to get fancy number to display in website and marketing activities post
39 | 2026-07-23 | 22:34 |  | 2026-07-23 | 22:36 | Thursday | Hiring : Appointment | Tead lead Selvi Requirt, Monthly Salary will be 18000 initially, after 3 months the salary will be revised
40 | 2026-07-23 | 22:36 |  | 2026-07-23 | 22:38 | Thursday | Software : Purchase | My operator to be finalised tomorrow
41 | 2026-07-23 | 22:38 |  | 2026-07-23 | 22:40 | Thursday | Marketing | Website content to be finalised tomorrow
42 | 2026-07-23 | 22:40 |  | 2026-07-23 | 22:42 | Thursday | Registration | Auditor call about registration and other prepared questions
43 | 2026-07-23 | 22:42 |  | 2026-07-23 | 22:44 | Thursday | Mentoring | Bhuvana Annie Call Preparation Industry and the services,
44 | 2026-07-23 | 22:44 |  | 2026-07-23 | 22:46 | Thursday | Scheduling | Call with Telecallers, take Individual call, and check there available time and challeges if any
45 | 2026-07-23 | 22:46 |  | 2026-07-23 | 22:48 | Thursday | Mentoring | Bhuvana Annie Call Preparation Industry and the services,
46 | 2026-07-23 | 22:48 |  | 2026-07-23 | 22:50 | Thursday | Mentoring | Bhuvana Annie call
47 | 2026-07-24 | 18:00 |  | 2026-07-24 | 18:05 | Friday | Documentation | Rental Agreement for Spaco Co work space
48 | 2026-07-25 | 18:00 |  | 2026-07-25 |  | Saturday | mentoring | HR Skill Attribute 3 days Boot camp 25th to 27th July
49 | 2026-07-26 | 21:45 |  | 2026-07-26 |  | Sunday |  | Skill Attribute Analyse and workout
| 2026-07-26 | 21:45 |  | 2026-07-26 |  | Sunday |  | RA Business school for Content Creation
| 2026-07-26 | 21:48 |  | 2026-07-26 |  | Sunday |  | Create a group and folder and share all the details in the group
| 2026-07-27 | 10:25 |  | 2026-07-27 |  | Monday |  | Commmercial Communication Rock Sir, regarding Yes Membership and IVR Service
| 2026-07-27 | 10:25 |  | 2026-07-27 |  | Monday |  | Muthu kulathur regarding WFH data entry project |  | 2026-07-27 | 10:25 | 2026-07-28 | 12:40
[6 empty] | Tuesday |  | Aura Gold Anand Sir, Reagrding My operator as he is already using this software
[6 empty] | Tuesday |  | Check Subu Lakshmi Telecaller as she allready mentioned that she have experience in medical billing
[6 empty] | Tuesday |  | Telecaller Subu Lakshmi call not attend, share the msg that you send the resume with details regarding previous experience in Medical billing
| 2026-07-30 | 10:00 | Thursday | 2026-07-30 |  | Thursday |  | Lakshmi Krishna Naturals, Facing issue in labelling and becoming trend in Instagram, so they need custome support, the outlet is in samathanapuram so planning to visit directly and pitch the BPO
| 2026-07-30 | 10:00 | Thursday | 2026-07-30 |  | Thursday |  | Tele CRM Demo
| 2026-07-30 | 10:00 | Thursday | 2026-07-30 |  | Thursday |  | Mani Megalai for Social Media Marketing
| 2026-07-30 | 10:00 | Thursday | 2026-07-30 |  | Thursday |  | Tesing ISM Data technology in chatgpt how it will be profit, how many entries a individual can made,
| 2026-07-30 | 10:00 | Thursday | 2026-07-30 |  | Thursday |  | Website content checking

## Daily Planner
Sl: No: | Date | Time | Day | Category | Details | Priority | Planned Start Date | Planned Start Time | Planned End Date | Planned End Time | Status | Remarks / Notes | Next Action | Follow-up Date
1 | 2026-07-21 | 10:00 | Tuesday | Hiring | Selvi 9years experience candidate need to prepare for Interview, Google sheet, Folder, Timing confirmation | High | 2026-07-21 | 10:30 | 2026-07-21 | 11:00
2 | 2026-07-21 | 10:00 | Tuesday | Hiring | Selvi 9years experience candidate need to interview | High | 2026-07-21 | 11:00 | 2026-07-21 | 11:30
3 | 2026-07-21 | 10:00 | Tuesday | Scheduling | Need to talk to all the telecallers, Pesi romba nal achu, enna pannittu irukanga, avanga current situation ennan kekanum | High | 2026-07-21 | 11:30 | 2026-07-21 | 14:00
4 | 2026-07-21 | 10:00 | Tuesday | Documentation | Organise File and Folders in Laptop (Book Mark) | High | 2026-07-21 | 14:00 | 2026-07-21 | 14:30
5 | 2026-07-21 | 10:00 | Tuesday | Documentation | Move all the Palm Era group to Archieve | Medium | 2026-07-21 | 2.30Pm | 2026-07-21 | 15:00
6 | 2026-07-21 | 10:00 | Tuesday | Mentoring | Bhuvana Annie call preparation | High | 2026-07-21 | 15:00 | 2026-07-21 | 16:00
7 | 2026-07-21 | 11:25 | Tuesday | BPO training | BPO training daily class | Medium | 2026-07-21 | 16:00 | 2026-07-21 | 17:00 |  | Pradeep in travel, so call training moved to tomorrow
8 | 2026-07-21 | 10:00 | Tuesday | Pricing | Pricing fro Client need to work out | High | 2026-07-21 | 17:00 | 2026-07-21 | 18:00
9 | 2026-07-22 | 10:00 | Wednesday | Research | Analyse the website for price calculation https://www.magellan-solutions.com/blog/calculate-cost-per-call/ | High | 2026-07-22 | 10:00 | 2026-07-22 | 11:00
10 | 2026-07-22 | 10:00 | Wednesday | Reserach | Prepare Set of Questions for Auditor for Name change, pricing, and what are all the things a company will face | High | 2026-07-22 | 11:00 | 22-Ju;-2026 | 11:30
11 | 2026-07-22 | 10:00 | Wednesday | Research | Talk to Auditor Jagadeswari, Allan Cowork space, Santhi (Chithirai Chennai Participants) | High | 2026-07-22 | 11:30 | 2026-07-22 | 0:15
12 | 2026-07-22 | 10:00 | Wednesday | Hiring | Requirt selvi telecalling tomorrow, Assign Market research for call recording tools | Medium | 2026-07-22 | 12:15 | 2026-07-22 | 13:00
13 | 2026-07-22 | 10:00 | Wednesday | Training | Subha BPO Training class | Medium | 2026-07-22 | 13:00 | 2026-07-22 | 14:00
14 | 2026-07-22 | 10:00 | Wednesday | Schedule | Call with Telecallers, take Individual call, and check there available time and challeges if any | High | 2026-07-22 | 14:00 | 2026-07-22 | 16:00
15 | 2026-07-22 | 10:00 | Wednesday | Documentation | Organise File and Folders in Laptop (Book Mark) | High | 2026-07-22 | 16:00 | 2026-07-22 | 17:00
16 | 2026-07-22 | 10:00 | Wednesday | Mentoring | Bhuvana Annie call preparation | High | 2026-07-22 | 17:00 | 2026-07-22 | 18:00
17 | 2026-07-22 | 10:00 | Wednesday | Documentation | Chithirai participants list update in sheet | Medium | 2026-07-22 | 18:00 | 2026-07-22 | 18:30
18 | 2026-07-22 | 10:15 | Wednesday | Accounts | Main Accounts Sheet Update | High | 2026-07-22 | 10:20 | 2026-07-22 | 11:00 | Completed
19 | 2026-07-23 | 10:00 | Thursday | Reserach | Prepare Set of Questions for Auditor for Name change, pricing, and what are all the things a company will face | High | 2026-07-23 | 9:30 | 2026-07-23 | 10:00
20 | 2026-07-23 | 10:00 | Thursday | Research | Talk to Auditor Jagadeswari, Allan Cowork space, Santhi (Chithirai Chennai Participants) | High | 2026-07-23 | 10:00 | 2026-07-23 | 10:15 | Completed | https://docs.google.com/spreadsheets/d/1BX1arbiV9XQvbCuUtAJIHWUkeA-NH-pXHAf1W1kwv68/edit?usp=sharing
21 | 2026-07-23 | 10:00 | Thursday | Scheduling | Call with Telecallers, take Individual call, and check there available time and challeges if any | High | 2026-07-23 | 10:15 | 2026-07-23 | 0:00
22 | 2026-07-23 | 10:00 | Thursday | Research | Chithirai participants list update in sheet | High | 2026-07-23 | 0:00 | 2026-07-23 | 13:00
23 | 2026-07-23 | 10:00 | Thursday | Research | Call Recording software finalise tomorrow | High | 2026-07-23 | 13:00 | 2026-07-23 | 14:00
24 | 2026-07-23 | 10:00 | Thursday | Cibil Score | Kathika , Mathan Anna Friend Need to check for Bajaj Finance closing and Credit Card | High | 2026-07-23 | 14:00 | 2026-07-23 | 14:15 | Completed
25 | 2026-07-23 | 10:00 | Thursday | Social Media Manager | Manimegai Social Media Manager Need to talk regarding Linkedin, Facebook and Instagram | High | 2026-07-23 | 14:15 | 2026-07-23 | 15:00
26 | 2026-07-23 | 10:00 | Thursday | BPO training | BPO training daily class | Medium | 2026-07-23 | 15:00 | 2026-07-23 | 16:00
27 | 2026-07-24 | 9:15 | Friday | Finance | HDFC Bank Direct visit |  | 2026-07-24 | 9:15 | 2026-07-24 | 10:15 | Completed
28 | 2026-07-24 | 9:15 | Friday | Asset : Post Paid Sim Purchase | Airtel Office -> Post Paid Sim to get fancy number to display in website and marketing activities post |  | 2026-07-24 | 10:15 | 2026-07-24 | 11:00
29 | 2026-07-24 | 9:15 | Friday | Hiring : Appointment | Tead lead Selvi Requirt, Monthly Salary will be 18000 initially, after 3 months the salary will be revised |  | 2026-07-24 | 11:00 | 2026-07-24 | 11:30
30 | 2026-07-24 | 9:15 | Friday | Software : Purchase | My operator to be finalised tomorrow |  | 2026-07-24 | 11:30 | 2026-07-24 | 0:00
31 | 2026-07-24 | 9:15 | Friday | Marketing | Website content to be finalised tomorrow |  | 2026-07-24 | 0:00 | 2026-07-24 | 14:00
32 | 2026-07-24 | 9:15 | Friday | Registration | Auditor call about registration and other prepared questions |  | 2026-07-24 | 14:00 | 2026-07-24 | 14:30 | Completed
33 | 2026-07-24 | 9:15 | Friday | Mentoring | Bhuvana Annie Call Preparation Industry and the services, |  | 2026-07-24 | 14:30 | 2026-07-24 | 16:30
34 | 2026-07-24 | 9:15 | Friday | Scheduling | Call with Telecallers, take Individual call, and check there available time and challeges if any |  | 2026-07-24 | 16:30 | 2026-07-24 | 18:30
35 | 2026-07-24 | 9:15 | Friday | Mentoring | Bhuvana Annie Call Preparation Industry and the services, |  | 2026-07-24 | 18:30 | 2026-07-24 | 19:00
36 | 2026-07-24 | 9:15 | Friday | Mentoring | Bhuvana Annie call |  | 2026-07-24 | 19:00 | 2026-07-24 | 19:30
37 | 2026-07-24 | 9:15 | Friday | Documentation | Rental Agreement for Spaco Co work space |  | 2026-07-24 | 18:15 | 2026-07-24 | 18:20
38 | 2026-07-25 | 9:15 | Saturday | Hiring | Hire Selvi Tomorrow |  | 2026-07-25 | 22:00 | 2026-07-25 | 22:30
39 | 2026-07-25 | 9:15 | Saturday | Training | Check Bounvoice again, and start training with bounvoice tomorrow before that speak to the employees |  | 2026-07-25 | 22:30 | 2026-07-25 | 12:00
40 | 2026-07-25 | 9:15 | Saturday | Documentation | Chithirai participants list update in sheet |  | 2026-07-25 | 12:00 | 2026-07-25 | 13:00
41 | 2026-07-25 | 9:15 | Saturday | Client Auaction | Chithirai participant pulse check and how the market pricing and requirements |  | 2026-07-25 | 13:00 | 2026-07-25 | 15:00
42 | 2026-07-25 | 9:15 | Saturday | Marketing | Complete the Pending website content works |  | 2026-07-25 | 15:00 | 2026-07-25 | 16:00
43 | 2026-07-25 | 9:15 | Saturday | Marketing | Plan for social media pages |  | 2026-07-25 | 16:00 | 2026-07-25 | 17:00
44 | 2026-07-25 | 9:15 | Saturday | Mentoring | BPO training daily class |  | 2026-07-25 | 17:00 | 2026-07-25 | 18:00
45 | 2026-07-25 | 9:15 | Saturday | Mentoring | HR Skill Attribute 3 days Boot camp |  | 2026-07-25 | 18:00 |  | 21:00
46 | 2026-07-27 | 10:30 | Monday | Course | Rd Business School Personal Branding
47 | 2026-07-27 | 10:30 | Monday | IVR Software Analysis | Commmercial Communication Rock Sir, regarding Yes Membership and IVR Service |  | 2026-07-27 | 13:45 | 2026-07-27 | 13:47
48 | 2026-07-27 | 10:30 | Monday | Recuritments | Muthu kulathur regarding WFH data entry project |  | 2026-07-27 | 14:02 | 2026-07-27 | 14:10
49 | 2026-07-27 | 10:30 | Monday | IVR Software Analysis | Aura Gold Anand Sir, Reagrding My operator as he is already using this software |  | 2026-07-27 | 13:50 | 2026-07-27 | 13:52
50 | 2026-07-28 | 11:30 | Tuesday | Company Visit | ISM Data tenkasi Muthu planning to meet tomorrow regarding vendor |  | 2026-07-28 | 11:30 | 2026-07-28 | 12:40
51 | 2026-07-28 | 11:30 | Tuesday | Documentation | Need to speak to auditor regarding Client Agreement and Employee agreement |  | 2026-07-28 | 19:00 | 2026-07-28 | 19:15
52 | 2026-07-29 | 11:07 | Wednesday | Documentation | Co Work space Rental agreement and EB Bill Need to check |  | 2026-07-29 | 10:15
53 | 2026-07-29 | 11:07 | Wednesday | Marketing | Karunya Team Digital Marketing need to check |  | 2026-07-29 | 17:15 | 2026-07-29 | 17:20
54 | 2026-07-29 | 11:07 | Wednesday | Vendor | ISM Data Technology need to check for E book and Voice Process |  | 2026-07-29 | 11:30
55 | 2026-07-29 | 11:07 | Wednesday | Marketing | Mani megalai for Digital MArketing
56 | 2026-07-29 | 11:07 | Wednesday | Marketing | Women Empowerement Madurai Event Need to Check
57 | 2026-07-29 | 11:07 | Wednesday | Client Auaction | Call to Ravi International to confirm the pricing and next step |  | 2026-07-29 | 17:20 | 2026-07-29 | 17:25
58 | 2026-07-29 | 11:07 | Wednesday | Client Auaction | Call to Hepziba to confirm the pricing and next step |  | 2026-07-29 | 17:25 | 2026-07-29 | 17:30
59 | 2026-07-29 | 11:07 | Wednesday | Client Auaction | Call to Elavaran Chitti Export regarding English Telecallers |  | 2026-07-29 | 5:30
60 | 2026-07-29 | 11:07 | Wednesday | Hiring | Check swetha, Ramani for Data entry (Medical billing work) |  | HOLD
61 | 2026-07-30 | 10:00 | Thursday |  | Lakshmi Krishna Naturals, Facing issue in labelling and becoming trend in Instagram, so they need custome support, the outlet is in samathanapuram so planning to visit directly and pitch the BPO |  | 2026-07-29 | 10:00 | 2026-07-29 | 11:00
63 | 2026-07-30 | 12:00 | Thursday |  | Tele CRM Demo |  | 2026-07-30 | 12:00 | 2026-07-30 | 13:15
64 | 2026-07-20 | 13:30 | Thursday |  | Mani Megalai for Social Media Marketing |  | 2026-07-20 | 13:30 | 2026-07-20 | 13:45
65 | 2026-07-20 | 13:45 | Thursday |  | Tesing ISM Data technology in chatgpt how it will be profit, how many entries a individual can made, |  | 2026-07-20 | 13:45 | 2026-07-20 | 16:00
66 | 2026-07-20 | 16:00 | Thursday |  | Website content checking |  | 2026-07-20 | 16:00 | 2026-07-20 | 17:50
67 | 2026-07-20 | 17:50 | Thursday |  | Searched the networking platform and explore |  | 2026-07-20 | 17:50 | 2026-07-20 | 18:50
68 | 2026-07-20 | 18:50 | Thursday |  | Update the Pending Sheet |  | 2026-07-20 | 18:50 | 2026-07-20 | 19:05
69 |  |  |  |  | Search Digial MArketing Partner
70 |  |  |  |  | Tele CRM recording and Doubts clarification
71 |  |  |  |  | Lakshmi Krishna Naturals appointment check
72 |  |  |  |  | Follow Happy Ending and Penniyam Academy
73 |  |  |  |  | Follow Auditor regarding GST, Agreement and Finance Advisor
74 |  |  |  |  | Talk with Princy, Subhu Lakshmi regarding Medical billing work

## Time Sheet
Date | Name | From Home to Office | CO Work Space Check In | CO Work Space Check Out | From Office to Home | Home Work Start time | Home Work End time
2026-07-21 | Thilaga Subha S | 9:46 | 10:06 | 19:22 | 20:00 | 20:45 | 23:15
2026-07-22 | Thilaga Subha S | 9:45 | 10:14 | 19:35 | 19:55 | 20:45 | 23:10
2026-07-23 | Thilaga Subha S | NIL | NIL | NIl | Nil | 9:15 | 22:50
2026-07-24 | Thilaga Subha S | 9:30 | 11:20 | 19:48 | 20:15 | 22:00 | 22:30
2026-07-25 | Thilaga Subha S | 9:10 | 9:40 | 17:00 | 17:40 | 18:00 | 21:20
2026-07-26 | Thilaga Subha S | NIL | NIL | NIL | NIL | 9:30 | 0:00
2026-07-26 | Thilaga Subha S | NIL | NIL | NIL | NIL | 13:45 | 15:00
2026-07-26 | Thilaga Subha S | NIL | NIL | NIL | NIL | 18:00 | 21:30
2026-07-26 | Thilaga Subha S | NIL | NIL | NIL | NIL | 22:45 | 14:15
2026-07-27 | Thilaga Subha S | 22:05 | 22:26 | 17:31 | 17:38 | 18:10 | 22:12
2026-07-28 | Thilaga Subha S | 10:20 Pm (ISM Data Technology Tenkasi) | 11:40 (ISM Data technology) | 12:50 PM(ISM Data Technology) | 2:20:00 PM(Reached Home) | 17:00 | 0:20
2026-07-29 | Thilaga Subha S | 9:45 | 10:04 | 20:00 | 20:45 | 21:20 | 23:50
2026-07-30 | Thilaga Subha S | 9:28 | 11:45 | 19:20 | 19:40
2026-07-31 | Thilaga Subha S | 9:25 | 9:50 | 18:35