## 00_Cover
AT_IPBS Time Sheet — Full Analysis & Discussion Record
Generated: 31/07/2026 19:26 BST ¦ Analysed by: Perplexity AI (research assistant, this workbook)
Source file analysed: AT_IPBS Time Sheet New (1).xlsx
Related file referenced: AT_IPBS_Planning_Discussion_Full_Context.xlsx (earlier summary prepared by ChatGPT, attached by user)
Purpose of This Workbook
This workbook consolidates (1) the data-quality analysis Perplexity performed on the AT_IPBS Time Sheet workbook, and (2) the design/architecture discussion held in this chat about how the Daily Planner, Daily Tracker, Overall Planner and Timesheet should evolve into a proper Workforce Operating System. It is meant to be uploaded into a fresh AI chat session to restore context quickly.
How to Use This Workbook
01_Timesheet_Issues — Concrete data-quality problems found in the actual timesheet file, with fixes applied or recommended.
02_Discussion_Log — Chronological record of the design discussion: what was said, by whom, and what was concluded.
03_Agile_Comparison — Comparison of the user's planning model against Scrum/Kanban concepts, as discussed.
04_Key_Decisions — Decisions reached during the discussion and the reasoning behind each.
05_Architecture_Vision — The target data model / Workforce Operating System architecture discussed.
06_Open_Questions — Unresolved questions flagged for future decision.
07_Recommendations — Perplexity's consolidated recommendation on next steps.
'07_Recommendations'!A1
Prepared by: Perplexity AI ¦ Attached reference file authored by ChatGPT: AT_IPBS_Planning_Discussion_Full_Context.xlsx
Document generated: 31/07/2026 19:26 BST

## 01_Timesheet_Issues
# | Sheet | Problem Found | Solution Applied / Recommended | Status
1 | Over All Planner | Google Sheets URL pasted directly into the Status column (row 23) instead of a real status value — likely cause of the "Google Sheet failing to show" symptom, since a raw link in a status field can render broken depending on viewer | Moved link into Remarks/Notes as a proper clickable hyperlink; cleared the Status cell | Fixed
2 | Daily Tracker | Inconsistent Status spelling: "COmpleted", "completed", "Compled", "Completed partially" | Standardized all variants to "Completed" / "Completed (Partial)" | Fixed
3 | Daily Tracker / Daily Planner | Day-of-week text does not match the actual Date (e.g. 20-Jul-2026 labeled "Thursday" instead of "Monday"; typos "wednesday","SAturday") | Recalculated Day from Date column and overwrote incorrect labels | Fixed
4 | Daily Tracker / Daily Planner | Sl. No. column has duplicate/skipped numbers (e.g. 36,36,37; jump 62→63 repeating) | Renumbered Sl. No. sequentially for all populated rows | Fixed
5 | Daily Tracker (39 rows) / Over All Planner (49 rows) / Daily Planner (73 rows) | Category blank on 3-13 rows and Priority blank on 32-47 rows per sheet — most tasks untagged | Added yellow conditional-formatting highlight on blank Category/Priority cells with a task | Highlighted — needs manual entry
6 | All 3 tracker sheets | Status is free-typed text with no controlled list, causing typos and unreliable reporting | Added dropdown data validation list (Completed, Completed (Partial), In Progress, Pending, Holding, Cancelled) | Fixed
7 | Time Sheet | Time columns mix real times with free text like "NIL","2:20:00 PM(Reached Home)","10:20 Pm (ISM Data Technology Tenkasi)" — breaks any future duration formula | Flagged; recommend splitting free text into a separate Notes column, keep time column purely time-formatted | Flagged — needs manual cleanup
8 | Time Sheet | 31-Jul row missing Check-Out/Home-Work times; 30-Jul missing Home-Work Start/End | No auto-fix possible; flagged for owner to complete | Flagged — needs manual entry
9 | Time Sheet | 26-Jul-2026 appears 4 times as separate rows for different home-work sessions with no session label | Recommend adding a Session # / Work Block column | Flagged — needs manual entry
10 | All sheets | No Excel Tables, frozen header rows, or auto-filter on 200+ row logs — hard to filter/sort | Recommended conversion to formal Excel Tables (not applied to avoid disrupting layout) | Recommended — not applied

## 02_Discussion_Log
Seq | Timestamp | Speaker | Topic | What Was Said / Reasoning | Outcome / Resolution
1 | 31/07/2026 18:16 | User | Initial request | Asked Perplexity to analyse the AT_IPBS Time Sheet workbook, list problems and solutions, specifically flagging that "Google Sheet is failing to show on the screen", and requested fixes be put into Excel too. | Perplexity performed a full structural analysis of all 5 sheets (Daily Tracker, Over All Planner, Daily Planner, Index, Time Sheet).
2 | 31/07/2026 18:16 | Assistant | Workbook analysis result | Found the Google Sheets link issue was a URL typed into a Status cell instead of a real status; also found inconsistent status spelling, mismatched day-of-week labels, broken Sl.No sequences, blank Category/Priority fields, and free-text time entries. | Delivered AT_IPBS_Time_Sheet_Fixed.xlsx with an "Issues Found" tab, corrected data, dropdown validation, and conditional formatting highlights.
3 | 31/07/2026 ~18:20 (reported in user query) | Assistant (a separate/earlier session, per user paste) | Design-level critique | A prior assistant response (pasted by user, attributed contextually to conversation with ChatGPT/other tool) argued the deeper problem is not Excel but the data model: same information duplicated across Daily Planner, Daily Tracker and Overall Planner; recommended a single Master Task table with generated views, unique Task IDs, Owner column, KPI dashboard, and warned Google Sheets would slow down at scale (FILTER/QUERY/IMPORTRANGE, many editors, volatile formulas). | Proposed redesigning around one master table with many views instead of triple data entry.
4 | Follow-up | User | Correction — sheets are not duplicates | User corrected the assumption of duplication: Overall Planner captures every idea/task immediately (may sit for months, get postponed, or never get executed); Daily Planner is only the subset of work selected for that day. The sheets represent different planning stages, not copies of the same data. | Assistant accepted the correction and revised its understanding of the workflow.
5 | Follow-up | Assistant | Agile mapping (first pass) | Proposed a mapping: Overall Planner ≈ Product Backlog, Daily Planner ≈ Sprint/Today's plan, Daily Tracker ≈ Daily execution, Timesheet ≈ Actual effort log — framed as conceptually similar to Scrum artifacts. | Comparison offered as a loose analogy, not an exact match.
6 | Follow-up | User | Correction — sprints also change | User corrected the sprint-stability assumption: sprint backlogs do change in real life too — work moves, gets postponed, reprioritised or scrapped. Daily Stand-up reviews yesterday and today's plan, but today's plan itself can change immediately due to business priorities. | Assistant accepted the correction as an important nuance.
7 | Follow-up | Assistant | Revised understanding | Agreed the model is event-driven and planning is continuous; described the Daily Stand-up as a snapshot in time rather than a fixed commitment, and stressed the importance of preserving a history of re-planning events. | Adopted "planning is dynamic, history must be preserved" as a design principle.
8 | Follow-up | User | Weekly Planner suggestion | User suggested inserting a Weekly Planner layer between the Overall Planner and the Daily Planner to bridge long-term backlog and daily execution. | Accepted as a valuable addition to the workflow hierarchy.
9 | Follow-up | Assistant | State-machine idea | Proposed that, in a future software version, a task should not be copied between sheets/tables at each stage. Instead, one task record should move through a lifecycle of states (Captured, Prioritised, Scheduled, Started, Paused, Resumed, Blocked, Completed, Logged, Reviewed), with planners/trackers acting only as filtered views. | Framed as a future software/database architecture direction, not an immediate spreadsheet change.
10 | Follow-up | Assistant | Product vision statement | Concluded that, given the user's BPO, HR and workforce-scheduling ambitions, this is not merely a timesheet but the foundation of a "Workforce Operating System" — a lightweight ERP-style platform (Employee, Task, Project, Client masters feeding Time Log, Attendance, Leave, Meetings, Expenses, Dashboards, Reports). | Established as the long-term product vision.
11 | Follow-up | Assistant | First attempt at capturing discussion in Excel | Created AT_IPBS_TimeSheet_Analysis.xlsx with an "Analysis & Recommendations" sheet summarising the above as bullet points and a comparison table. | User pointed out this was a summary, not a full capture of the discussion.
12 | Follow-up | User | Explicit correction on task type | User clarified the actual request was: "capture all the discussion in this page in an excel document properly, don't miss any information" — a fundamentally different task than producing a condensed summary. | Assistant acknowledged the two tasks (summary vs full capture) are very different and it had defaulted to summarising.
13 | Follow-up | Assistant | Self-critique of what was lost | Assistant listed what the summary had omitted: the initial duplication theory, the user's correction that sheets are different planning stages, the detailed Agile mapping, the sprint-backlog-changes correction, the DSU-as-snapshot idea, the Scrum/Kanban/user-model comparison, the state-transition vs copying idea, the Workforce OS reasoning, the spreadsheet→software→product evolution narrative, and all supporting examples/diagrams. | Reframed the deliverable as needing to be a "conversation knowledge base," not a one-page summary.
14 | Follow-up | Assistant | Second attempt — structured workbook | Built AT_IPBS_Planning_Discussion_Full_Context.xlsx with sheets: 00_Overview, 01_Detailed_Discussion, 02_Agile_vs_User_Model, 03_Key_Decisions, 04_Open_Questions — capturing the workflow evolution and discussion in more structured, narrative form. | Delivered as an improvement, but assistant flagged it was still only ~8-10 discussion entries versus the full richness of the conversation, and estimated a truly complete capture would need 100-300 rows across 10-20 sheets.
15 | Follow-up | User | Skepticism about portability | User questioned whether uploading this workbook into a brand-new chat would actually let an AI "recreate this context," and decided to leave the deeper capture for now ("leave it"). | Assistant agreed with reservations: structural facts (workflow, decisions, comparisons, vision) would transfer, but tone, rejection reasoning, idea sequencing, and the specific corrections/assumptions that shaped the discussion would not fully transfer via spreadsheet alone.
16 | Follow-up | Assistant | "Portable brain" reframing | Proposed that what the user actually wants is not chat memory but a portable knowledge base — analogous to Architecture Decision Records (ADRs) — organised as a folder of markdown files (Project Overview, Product Vision, Planning Methodology, Decision Log, Workflow, Agile Comparison, Data Model, Wireframes, Feedback/Learnings, Open Questions, Roadmap) alongside supporting Excel/Images/Diagrams/Meeting Notes. | Recommended this markdown-based "portable brain" as a better long-term artifact than an Excel-only chat transcript, but recommended building it deliberately going forward rather than trying to reconstruct the last few weeks retroactively.
17 | 31/07/2026 19:26 | User | Follow-up request (this message) | Asked for a "proper excel from the chat and what u understand from ur research," with the file name including date/time, referencing "perplexity attached prepared by chatgpt" (i.e. noting the earlier workbook was ChatGPT-authored, this one should be Perplexity's). | This workbook (AT_IPBS_Discussion_Analysis, generated 31/07/2026 19:26) is the response — combining the concrete timesheet findings with the full design discussion log.

## 03_Agile_Comparison
Agile / Scrum Concept | User Planning Model Equivalent | Discussion Notes / Nuance
Product Backlog | Overall Planner | All possible work is captured here immediately when an idea occurs; may sit unexecuted for months.
Sprint / Iteration Planning | Weekly Planner (proposed addition) | Bridges the long-term backlog and the daily execution list; not yet in the current workbook.
Today's Sprint Task List | Daily Planner | Only the subset of work selected for a specific day.
Daily Stand-up (DSU) | Daily Tracker | User corrected the assistant: DSU is a snapshot in time, not a fixed commitment — today's plan can change immediately due to business priorities.
Work Log / Time Tracking | Timesheet | Captures actual effort/time spent, separate from planning intent.
Sprint stability assumption | N/A — corrected by user | Assistant initially implied sprints are relatively stable once set; user corrected that sprint backlogs also change constantly in real practice — reprioritisation, postponement and scrapping happen in both models.
Backlog grooming | Continuous re-planning | Both Agile and the user's model treat planning as an ongoing, event-driven activity rather than a one-time exercise.

## 04_Key_Decisions
Decision | Reasoning / Why
Google Sheets link removed from Status column and relocated to Remarks with a real hyperlink | A raw URL in a status field does not behave as a clickable link reliably and breaks status-based filtering/reporting — most likely cause of the reported "Google Sheet failing to show" issue.
Standardize Status values via dropdown (Completed, Completed (Partial), In Progress, Pending, Holding, Cancelled) | Free-typed status text ("COmpleted","Compled" etc.) makes filtering and reporting unreliable.
Overall Planner, Daily Planner and Daily Tracker are NOT duplicate data | User corrected the assistant's initial duplication theory — each sheet represents a different planning stage/timeframe, not a copy of the same task.
Weekly Planner should be added between Overall Planner and Daily Planner | Bridges long-horizon backlog thinking and same-day execution; suggested by the user as a missing layer.
Preserve history of re-planning events | Understanding *why* a task moved or was postponed is as valuable as knowing the current state; corrected assistant's earlier assumption that daily plans are stable once set.
Future software should avoid copying tasks between sheets/tables | A task should carry a single ID through a lifecycle of states (Captured → Prioritised → Scheduled → Started → Paused/Resumed → Blocked → Completed → Logged → Reviewed); planners/trackers become filtered views, not separate copies.
Long-term product direction is a "Workforce Operating System," not a timesheet | Given the user's BPO, HR and workforce-scheduling ambitions, the underlying need is closer to a lightweight ERP (Employee, Task, Project, Client masters feeding Time Log, Attendance, Leave, Meetings, Expenses, Dashboards, Reports).
A full verbatim chat-capture in Excel is the wrong artifact for context restoration | Spreadsheets compress tone, rejected ideas, and reasoning sequence poorly; user acknowledged this and chose to defer a deeper capture effort.
Long-term knowledge should live as a structured markdown "portable brain," not chat memory | Modeled on Architecture Decision Records (ADRs); intended to let any AI tool (ChatGPT, Perplexity, Claude, Codex) continue the project from documented reasoning rather than re-deriving it from scratch each time.

## 05_Architecture_Vision
Layer / Concept | Description
Current flow (as-is) | Daily Planner → Daily Tracker → Overall Planner → Timesheet, with the same task effectively re-entered at each stage.
Proposed flow (to-be, near-term) | Idea → Overall Planner → Weekly Planner → Daily Planner → Daily Tracker → Timesheet, adding a Weekly Planner bridge layer.
Longer-term possibility discussed | Annual → Quarterly → Monthly → Weekly → Daily → Tracker → Timesheet → Review, giving a full planning-horizon hierarchy.
Master Task Table concept | One record per task with a unique Task ID (e.g. TSK-000001); all planners/trackers/dashboards become generated views over this one table rather than separate manually-entered sheets.
State-machine model (future software) | Each task moves through defined states — Captured, Prioritised, Scheduled, Started, Paused, Resumed, Blocked, Completed, Logged, Reviewed — instead of being copy-pasted between sheets at each planning stage.
Structured table set (~12 tables) discussed | Employee Master, Task Master, Project Master, Client Master, Time Log, Attendance, Leave, Follow-up, Meeting, Expense, Dashboard, Reports — all linked by IDs.
Workforce Operating System (long-term vision) | Employee → Task → Time Log → Attendance → Meeting → Expense → Call Log → Client → Project, functioning as a lightweight ERP for a BPO with 20-100+ employees, from which Daily Planner, Daily Tracker, Weekly/Monthly Reviews, Employee Productivity, Client Billing, Payroll Hours and KPI Dashboards can all be generated automatically without duplicate entry.
Why Google Sheets/Excel alone will struggle at scale | Thousands of rows, many dropdowns, FILTER/QUERY formulas, IMPORTRANGE, conditional formatting, multiple simultaneous editors and volatile formulas cause slow scrolling, delayed typing, loading spinners and edit conflicts once the workbook becomes operational rather than a personal log.

## 06_Open_Questions
Open Question | Context
Should the Weekly Planner be a separate physical sheet or a filtered/generated view of the Master Task table? | Raised when the user proposed adding a Weekly Planner layer.
Should a reason/justification be mandatory whenever a task is re-planned or postponed? | Follows from the "preserve history of re-planning" decision.
How should recurring tasks be represented without creating duplicate rows every cycle? | Not resolved during the discussion.
Should timestamps be captured automatically (system-generated) rather than manually typed? | Relevant given the free-text time entries found in the Time Sheet (e.g. "2:20:00 PM(Reached Home)").
Is an approval workflow needed before a task moves to "Completed"? | Raised as a future consideration for the state-machine model.
How should this integrate with attendance and payroll systems? | Connects to the long-term Workforce Operating System vision.
Can uploading a structured Excel/markdown "portable brain" into a new AI chat actually reconstruct design reasoning, or only conclusions? | User explicitly questioned this; assistant's answer was "yes for structure, no for reasoning/tone/sequence" — left as an accepted limitation rather than solved.

## 07_Recommendations
Recommendation | Rationale
Fix the immediate timesheet data-quality issues (already applied in AT_IPBS_Time_Sheet_Fixed.xlsx) | Removes typos, mismatched days, broken numbering and the stray Google Sheets link causing display problems — low effort, immediate benefit.
Do not keep incrementally patching the current 4-sheet Excel/Google Sheets design long-term | As task volume and employee count grow, duplicated manual entry across Daily Planner/Daily Tracker/Overall Planner/Timesheet will not scale and Google Sheets performance will degrade (large ranges, many formulas, multiple editors).
Introduce a Weekly Planner layer next, as the lowest-effort structural improvement | Directly addresses the gap the user identified between long-term backlog (Overall Planner) and daily execution (Daily Planner), without requiring a full rebuild yet.
Plan a migration to a Master Task Table with generated views (medium-term) | Removes triple data entry and inconsistency risk; each planner/tracker/dashboard becomes a filtered view of one underlying table rather than a separately maintained sheet.
Treat the long-term product as a Workforce Operating System (BPO-grade), not a personal timesheet | Matches the user's stated ambitions (TalkProof, hiring, client operations); justifies eventually moving off spreadsheets into a proper database-backed application.
Build the "portable brain" knowledge base deliberately going forward, not retroactively | Backfilling the full nuance of past discussions into documents costs more effort than it recovers; capturing decisions and rationale as an ADR-style log from this point forward is more sustainable.
Start the portable brain with a Product Vision document, then add a Decision Log incrementally | Every other document's reasoning traces back to the product vision; the decision log should grow naturally as real decisions are made rather than be reconstructed after the fact.