## Version_Control
VERSION CONTROL — TeleField Sprint Tracker & Traceability
File naming: claude_v<NNN>_<proper file name>_YYYYMMDD_HHMI.xlsx. Companion: v006 product workbook = backlog source of truth (D12 pattern); v007 of that workbook stays planned for post-discovery re-baseline.
Version | Date/Time | Author | Change Description | Status
v001 | 2026-09-10 21:05 | Claude for Senthil/KP | THIS FILE — Live execution tracker for TeleField (portfolio rank 2), opened on Senthil's 21:05 instruction (D15). Full 100-story traceability matrix from v006 Full_Backlog (399 pts, rollup formula-verified). S1 FOUNDATION DEVELOPMENT EXECUTED in TypeScript/Node per workbook stack: ST-051 OAuth install->welcome, ST-052 uninstall token wipe + deletion schedule, ST-055 rotation-safe token refresh + auto-refresh-on-401 client, ST-056 install source attribution; plus config (India-first DC), webhook HMAC+replay+dedupe, Zoho credits/429 backoff (LC #4), CI. 60 automated tests, 100% statements/branches/functions/lines, zero pragmas (D13). Code: claude_v001_telefield_s1_foundation_code_20260910_2105.zip. E001-E003 logged. | Released
v002 | 2026-09-10 22:00 | Claude for Senthil/KP | S2 EXECUTED (continue 22:00; D15 still open — momentum continues on TeleField): all 6 S2 stories done-in-code (29 pts) — ST-001 one-screen defaults setup (+setup funnel event), ST-002 happy path end-to-end on pure defaults (+aha on first connect; retry/exhaust per config), ST-003 rules boost/deprioritise/skip reordering live queue, ST-004 CRM sync outbox with structured CRM_SYNC_FAILED errors + retry path (outcome never lost), ST-053 reinstall-restore within retention (deletion cancelled), ST-054 owner/admin/member matrix on every route (installer=owner bootstrap). 113 tests, 100% stmts/branches/functions/lines, zero pragmas (D13). Code: claude_v002_telefield_s1s2_code_20260910_2200.zip. E004-E005 logged. | Released
v003 | 2026-09-10 22:09 | Claude for Senthil/KP | S3 EXECUTED (continue 22:09): all 11 S3 stories done-in-code (47 pts). F1 COMPLETE IN CODE — ST-005 widget compact endpoint + mobile offline batch sync (clientRef dedupe, per-item applied/duplicate/rejected report, surface tracked per call), ST-006 metrics+trend (connect rate, outcomes, per-surface, daily buckets), ST-007 audit log on every privileged mutation (admin+ read), ST-008 pause/resume zero-data-loss, ST-009 CSV import (per-row skip reasons + dialerpro/callsheet competitor profiles), ST-010 in-app+email notifications with per-user per-type mute. F2 STARTED — ST-011 default taxonomy zero-config, ST-012 callback-jumps-queue/dnc/requeue/close actions, ST-013 custom dispositions validated, ST-014 disposition sync on outbox contract. ST-085 superseded upward by D13 (gate at 100 not 70). 156 tests, 100/100/100/100, zero pragmas. Code: claude_v003_telefield_s1s2s3_code_20260910_2209.zip. E006-E007 logged. | Released
v004 | 2026-09-10 22:18 | Claude for Senthil/KP | S4 EXECUTED (continue 22:18): all 9 S4 stories done-in-code (34 pts) — F2 COMPLETE + observability. ST-015 widget taxonomy fetch + compact widget disposition (mobile batch already offline-capable), ST-016 disposition metrics (breakdown/callbacks scheduled+due-now/DNC count/daily trend), ST-017 DNC applications audited + notified with roles enforced across F2, ST-018 disposition-engine pause independent of queue (zero data loss), ST-019 disposition-history import (historical do_not_call applies DNC; stale callbacks deliberately NOT re-applied), ST-020 callback.due/disposition.dnc/error.spike notification types with mute, ST-071 activation-funnel dashboard with habit auto-record (3 active days/7, once), ST-072 release-tagged error tracking + spike alert (5 errors/5min), ST-086 deploy smoke suite (npm run smoke + CI post-deploy job). S4 EXIT: MVP loop usable end-to-end internally = MET (smoke test IS that loop). 219 tests, 100/100/100/100, zero pragmas. Code: claude_v004_telefield_s1-s4_code_20260910_2218.zip. E008-E009 logged. | Released
v005 | 2026-09-10 22:27 | Claude for Senthil/KP | S5 EXECUTED (continue 22:27): all 12 S5 stories done-in-code (50 pts) — FULL F3 BEAT/ROUTE PLANNER (the wedge differentiator) + E8 onboarding. ST-021 one-screen beat defaults (weekdays/12 stops/7-day cooldown/nearest), ST-022 recurrence-aware daily route: cooldown+rules+DNC filtered (rep never routed to do-not-call lead), haversine nearest-neighbour from top-priority stop, per-leg + total km, visit recording, ST-023 boost/skip rules on priority + daysSinceVisit (never-visited=infinity), ST-024 route push on outbox clear-error contract, ST-025 compact widget route + offline mobile visit batch (clientRef dedupe, per-item report), ST-026 beat metrics (visited rate, avg stops/active day, trend), ST-027 beats.configure/execute matrix + audit, ST-028 beats pause zero-data-loss, ST-029 stops CSV + routemaster competitor profile, ST-030 beat.assigned/route.ready notifications with mute, ST-078 live first-run checklist (per-item nextAction, aha<1day on-track flag), ST-079 teaching empty states on queue/widget/beats/route/notifications. 264 tests, 100/100/100/100, zero pragmas. Code: claude_v005_telefield_s1-s5_code_20260910_2227.zip. E010-E011 logged. | Released
v006 | 2026-09-11 11:50 | Claude for Senthil/KP | S6 EXECUTED (contineu 11:50): all 13 S6 stories done-in-code (60 pts) — FULL F4 GEO CHECK-IN + E5 BILLING. ST-031 one-screen config (250m fence, flag-not-block default), ST-032 geo-verified checkin->checkout writing the S5 visit record (one truth for cooldowns/metrics), ST-033 reject¦flag¦allow fence policy + minVisitMinutes short-visit flags + sequence enforcement with override, ST-034 checkin_push outbox contract, ST-035 offline mobile checkin batch (clientRef dedupe, per-item policy) + compact widget today-view, ST-036 checkin metrics (within-fence/flagged rates, avg minutes, trend), ST-037 flagged/overridden checkins audited with actor, ST-038 checkins pause, ST-039 history import (generic+fieldassist, fence evaluated on import), ST-040 checkin.flagged notify+mute. BILLING: ST-057 14-day card-free trial from install time, banner, expiry 402-blocks core actions with upgradePath, ST-058 exact mid-cycle proration (upgrade net-charge, downgrade ledger credit — asserted to the cent), ST-059 marketplace-mandated Zoho billing vs external Stripe fallback; declined charge leaves NO subscription/ledger. SPRINT EXIT (charge test customer; up/downgrade work) = MET IN CODE via provider transport. 307 tests, 100/100/100/100, zero pragmas. Code: claude_v006_telefield_s1-s6_code_20260911_1150.zip. E012-E013 logged. | Released
v007 | 2026-09-11 23:02 | Claude for Senthil/KP | S7 EXECUTED (continue 23:02): all 5 S7 stories done-in-code (15 pts) — BILLING LIFECYCLE + LEAST PRIVILEGE. ST-060 failed renewal -> 7-day grace (full access), dunning at day 0/3/6 once each (skipped days catch up in one sweep), then READ-ONLY: writes 402 with reason, dashboards readable, zero data loss; successful retry rolls the period and clears dunning state. ST-061 plan limits (starter 500/3, pro 5000/25, trial=starter): one 80% warning per limit, 100% hard-block with correct upgrade path (trial->subscribe, paid->change); role changes on existing seats free; enforced on lead add, CSV import (worst-case rows) and new seats. ST-062 ledger-derived invoices: GST/VAT tax-inclusive split to the cent (29 gross @18% -> 24.58 net + 4.42 tax), sequential INV numbers, downloadable with attachment header; profile validation (taxId mandatory with GST/VAT). ST-063 cancellation: save-offer 20%-off-next-cycle before confirm, exit survey with reason enum stored, cancelAtPeriodEnd honoured at renewal with zero charge; accepted offer discounts exactly one renewal (29 -> 23.20 asserted). ST-064 SCOPES.md + GET /meta/scopes: 5 scopes each mapped to shipped endpoints; tests enforce 1:1 BOTH directions so scope drift fails the build. 342 tests, 100/100/100/100, zero pragmas. Code: claude_v007_telefield_s1-s7_code_20260911_2302.zip. E014-E015 logged. | Released
v008 | 2026-09-11 23:11 | Claude for Senthil/KP | S8 EXECUTED (continue 23:11): all 22 S8 stories done-in-code (87 pts) — THE SUMMIT SPRINT. F5 Manager scorecards ST-041..050: 6 default KPIs computed from data already held (zero new data entry), one-screen config w/ per-KPI target/weight/enable + validation naming the offending entry, per-rep card (attainment capped 150, A-D grades w/ exact boundary tests), ranked team view admin-only + audited, 7-90d trend, widget compact card, pause zero-data-loss, CSV history import generic+salesmaster (truncated value cell SKIPS — Number("")==0 bug pre-empted with explicit empty guard), scorecard.ready/low notifications + mute honoured. E6: ST-065 DATA_FLOWS.md + /meta/data-flows (mermaid diagram + retention table: tokens on-uninstall, activity 24mo, ledger 7yr GST); ST-066 AES-256-GCM token sealing w/ tamper detection + fresh-IV proof + secret scrubbing asserted on 500 bodies AND stored error records; ST-067 admin-sensitive audit extended (exports audited); ST-070 circuit breaker: 5 consecutive exhausted failures -> open 60s fail-fast w/ retry time, half-open probe, success resets, failed probe re-opens — all asserted. E7: ST-073 heatmap fed by real route instrumentation; ST-075 health = usage50+billing30+support20 banded w/ reasons (every stage/status branch tested); ST-074 weekly digest to admins only; ST-076 CSV export 5 datasets w/ quote-escaping proven; ST-077 alert sweep (activation drop WoW, error spike, churn) incl. sub-threshold quiet test. EQ: ST-087 p95 budgets web300/widget200/mobile400 recorded per guarded request, /slo report w/ breach detection; ST-088 load 300 mixed reqs (5x launch) <1% errors IN-PROCESS (live run pending); ST-092 blue/green deploy workflow smoke-gated (live verify pending). 438 tests, 100/100/100/100, ZERO pragmas (switch refactored to handler map rather than pragma an unreachable branch). Code: claude_v008_telefield_s1-s8_code_20260911_2311.zip. E016-E017 logged. | Released
v009 | 2026-09-11 08:31 | Claude for Senthil/KP | S9 EXECUTED (continue 08:15): all 7 S9 stories actioned — ST-069 privacy export + delete-my-data (self-serve, audited, last-owner guard), ST-090 backup/restore drill (sha256 integrity, CI-executable round-trip), ST-091 chaos/outage graceful degradation (status ladder, outbox no-loss drain, user comms), ST-068 security evidence pack (6 executed controls, ASVS-mapped, endpoint + committed render; EXTERNAL pen-test = Senthil vendor), ST-089 WCAG AA (automated audit engine gating the widget HTML endpoint + contrast-verified palette; live screen-reader pass rides S1-10), ST-093 listing copy A/B DRAFTED (EN + HI/TA), ST-094 screenshot shot-list + 2-min video storyboard DRAFTED to Zoho asset spec. D13 gate: 513 tests (75 new), 100/100/100/100 coverage, zero pragmas. 6 new endpoints. Code zip = s1-s9. | Released
v010 | 2026-09-11 08:51 | Claude for Senthil/KP | S10 EXECUTED (continue 08:51): all 7 S10 stories done-in-code — ST-080 help center (15 launch articles + weighted search, 3 endpoints), ST-081 in-app chat with <4-business-hr first-response SLA engine (IST Mon-Sat 09-18 business-hours clock, breach sweep + user comms, SLA report; vendor-agnostic), ST-083 interactive demo/sandbox mode (isolated store, deterministic seed across queue/beats/check-ins/scorecards, public /demo + reset; VIDEO production pending live capture per ST-094 plan), ST-084 public status page (live from breaker state, HTML+JSON) + incident comms template, ST-095 pricing page + 6-entry FAQ generated from billing single source (no drift possible), ST-096 trust page (8 sections: residency/encryption/subprocessors/rights), ST-097 submission dry-run engine — 11 automated checks ALL PASS + 4 human/live items flagged (DR-12..15); /review/dry-run endpoint + committed report. Public pages WCAG-AA gated on every render. D13 gate: 560 tests (47 new), 100/100/100/100, zero pragmas. Docs: PRICING_FAQ, TRUST_PAGE, SUBMISSION_DRYRUN generated from code. Code zip = s1-s10. | Released
v011 | 2026-09-11 11:12 | Claude for Senthil/KP | S11 EXECUTED (continue 11:12): all 3 S11 stories done-in-code — ST-082 review-ask engine (aha-gated + momentum >=10 outcomes, never during incidents or with unanswered support open, one ask per user, snooze 7d, decline forever, deep-link + telemetry for S7 funnel attribution), ST-098 launch-day runbook as an EXECUTABLE engine (RB-01..10 across pre-launch/T-0/monitor/incident/rollback; pre-launch gate reuses live ST-097 dry-run; comms reuses ST-084 template; rollback = S8 blue/green switchback) + committed docs/LAUNCH_RUNBOOK.md, ST-100 design-partner tracker (10 slots, invited->installed->activated->review_scheduled->review_posted forward-only, stale >3d owner nudge, launch-exit report 10 installs AND 3 posted reviews). 7 new endpoints. D13 gate: 597 tests (37 new), 100/100/100/100 x2 runs, zero pragmas. NOTE: one intermittent single-test failure appeared once each in S9/S10/S11 coverage runs, never reproducible on rerun (2x stable each time) — flag for CI watch. Code zip = s1-s11. S11 EXIT (10 installs, 3 reviews, activation>40%) is FULLY LIVE-GATED = Senthil. | Released
v012 | 2026-09-11 12:47 | Claude for Senthil/KP | S12 EXECUTED (continue 12:47) — FINAL CODE SPRINT. ST-099 listing SEO iteration engine done-in-code: search-term classifier (winner/leaky/invisible + 50-impression noise floor, zero-division-safe, inconsistent-row guards), target-term coverage vs ST-093 vocabulary, ranked concrete actions (title placement, first-impression fix, hook rewrite, absent-term call), hold-verdict when no signal; POST /listing/seo/analyze JSON+md + docs/LISTING_SEO_ITERATION.md (sample-flagged). LIVE half = real publisher-console search data post-launch. DEFECT FIX: E023 intermittent flake ROOT-CAUSED — S8 in-process load-test p95 budget (200ms) tripping under parallel coverage instrumentation (observed 239ms); harness tripwire widened to 400ms with rationale, <1% error gate untouched, real latency budgets remain src/slo.ts on live infra. D13 gate: 627 tests (30 new), 100/100/100/100 verified on THREE consecutive runs, zero pragmas. CODE PHASE COMPLETE: 98/100 stories done-in-code, 2 Drafted (ST-093/094 await Senthil pick + live capture). Code zip = s1-s12 FINAL. | Released
v013 | 2026-09-13 10:55 | Claude for Senthil/KP | COLD REVIEW PASS 1 (continue 10:36/10:55) — TeleField's first adversarial review, run against the v012 FINAL zip. 8 defects fixed with pinned regressions (F-T01..F-T08, 4 CRITICAL), 3 artifact gaps found (GAP-T1..GAP-T3, GAP-T3 open), 3 observations logged for disposition (OBS-T1..OBS-T3). New modules src/csv.ts, src/ledger.ts, src/auth.ts. 20 suites / 680 tests at 100% coverage, zero pragmas. Story position deliberately UNCHANGED (98/100, 391/399) — correctness release, no new stories. | Released
| v014 | 2026-09-13 11:00 | Claude for Senthil/KP | COLD REVIEW PASS 2 (continue 11:00) — the ~30 modules pass 1 did not reach: queue, disposition, beats, check-ins, review prompt, backup/restore, analytics export. 7 defects fixed with pinned regressions (F-T09..F-T15), 1 observation added (OBS-T4). Headline F-T15: stops were absent from the export bundle entirely, so backups did not contain them and the restore drill passed while silently dropping every stop on every beat. 21 suites / 718 tests at 100%, zero pragmas. Story position unchanged (98/100, 391/399). | Released
| v015 | 2026-09-13 11:07 | Claude for Senthil/KP | COLD REVIEW PASS 3 + EXTERNAL VERIFICATION SWEEP (continue 11:07). GAP-T3 CLOSED: src/server.ts + bin/telefield.js + npm start — the server was booted for real and /healthz, /pricing and /status.json answered over a socket. Schema shipped: migrations/001-004 with cascade deletes plus npm run migrate (dry run in CI). Verification sweep vs live Zoho docs found VER-T1 LIVE-BLOCKING (our webhook wire format did not match Zoho's published one — every webhook would have been rejected), VER-T2 (transport type discarded response headers, so Retry-After and X-API-CREDITS-REMAINING were unreachable) and VER-T3 (Sigma disable/enable/update events were ignored). 22 suites / 756 tests at 100%, zero pragmas. Story position unchanged (98/100, 391/399). | Released
| v016 | 2026-09-13 11:32 | Claude for Senthil/KP | COLD REVIEW PASS 4 — REACHABILITY + PUBLISHED CLAIMS (continue 11:32, "do all properly"). 5 defects fixed, 4 of them features that existed and were never invoked: F-T17 CRITICAL the 30-day retention sweep had no caller at all, F-T20 the outbox only drained when a human pressed retry though the help centre promises automatic sync, F-T18 outage comms never fired, F-T19 no backup was ever taken of real data; F-T16 CRITICAL "encrypted at rest" was published in four places while tokens were stored in plaintext and the evidence pack "proved" the control by encrypting a literal string. New src/scheduler.ts (8 jobs, per-org isolation, daily backup), src/tokenVault.ts (seal on write, production refuses plaintext), SECRETS_KEY as a boot prerequisite. Two PORTABLE CI GATES added: reachability and published-claims. GAP-T4/T5 closed: scripted 12-step sweep (npm run sweep, 9 automated + 3 operator) and the 30-minute dev-org guide, both executed against a live process. 23 suites / 864 tests at 100%, zero pragmas. Story position unchanged (98/100, 391/399). | Released
| v017 | 2026-09-13 11:38 | Claude for Senthil/KP | COLD REVIEW PASS 5 — CROSS-PRODUCT DEFECT CLASSES (continue 11:38, "do all properly"). Stopped hunting TeleField's own bugs and applied the classes the siblings already paid for. 3 defects fixed: F-T21 CRITICAL OAuth install CSRF (no state parameter at all — a forged callback could bind the wrong org's tokens into an install), F-T22 the org id was caller-declared in the query string so whoever hit the callback chose which org row the tokens were written against, F-T23 /demo/reset let anyone on the internet wipe the demo tenant reviewers are looking at. Two classes CHECKED AND CLEAN, pinned by tests rather than assumed: cross-tenant isolation (MeetSync M-F04 / OnCall F-014) and Express rejected-promise handling (MeetSync M-F21). GATE-3 added (public surface pinned) plus docs/REVIEW_GATES.md porting guide for all three gates. OPERATOR_TOKEN is now a production boot prerequisite. 24 suites / 899 tests at 100%, zero pragmas. Story position unchanged (98/100, 391/399). | Released
| v018 | 2026-09-13 11:55 | Claude for Senthil/KP | R-T4 CLOSED — POSTGRES PERSISTENCE, BUILT AND VERIFIED AGAINST A REAL DATABASE (continue 11:55). Postgres 16 installed in the session; migrations 001-005 applied for real and proved idempotent; src/pgStore.ts implements the Store interface as write-through over the in-memory reader with hydrate-on-boot; the server hydrates at start and flushes before responding. Two defects found ONLY because the database was real: PG-1 the scorecard DATE column rehydrated as "Tue Sep 01" and corrupted every row on restart, PG-2 the durability flush was wired into guarded() alone so the OAuth callback and webhook — install tokens and uninstall — sat in the write-behind queue for up to a minute. Production now refuses to boot without DATABASE_URL. 24 suites / 902 tests at 100% plus a separate database-backed contract suite at 100% on the adapter. Story position unchanged (98/100, 391/399). | Released
| v019 | 2026-09-13 16:24 | Claude for Senthil/KP | COLD REVIEW PASS 6 — GAP-T6: THE SCREENS THAT WERE NEVER BUILT. The traceability matrix assigns every one of the 100 stories a primary screen across nine named screens (SCR-1 Onboarding, SCR-3 Call workspace, SCR-4 Rule builder, SCR-5 Planner, SCR-5 Mobile, SCR-6 Settings, SCR-7 Billing, SCR-8 Analytics, SCR-9 Help); 92 of those stories are marked Done-in-code and the codebase rendered exactly ONE of the nine. Eight screens built, each rendering from the same view-model its JSON route serves and audited against WCAG AA on every render — ST-089 widened from one screen to all nine. GATE-4 added and documented for porting. 25 suites / 952 tests at 100%, zero pragmas. Story position unchanged (98/100, 391/399) pending Senthil opening them on the dev org. | Released
| v020 | 2026-09-13 16:35 | Claude for Senthil/KP | COLD REVIEW PASS 7 — THE GATE CHECKLIST READ AGAINST THE CODE. Same technique as pass 6, applied to the LC rows instead of the screen column. F-T24 (HIGH): all three offline batch endpoints claimed the client dedupe reference BEFORE attempting the item, so anything rejected for a transient reason came back "duplicate" on the device's next attempt and was lost for good — the exact failure mode LC-5 exists to prevent. GAP-T7: LC-3 listing screenshots were blocked on there being nothing to photograph and then on needing an install to photograph it; npm run assets now renders all nine screens from the demo tenant at a fixed clock into assets/, audited, byte-identical on repeat runs, and re-checked in CI. 26 suites / 982 tests at 100%, zero pragmas. | Released
| v021 | 2026-09-13 16:41 | Claude for Senthil/KP | COLD REVIEW PASS 8 — THE EVIDENCE COLUMN, AND THE PACK DR-12 DEPENDS ON. Read all 100 evidence citations against the code: 27 modules, 34 routes, 8 documents — every one resolves. CLEAN, recorded as a finding and now pinned by GATE-5 (docs/EVIDENCE_MAP.json) so a refactor cannot delete the thing a story cites as its proof. GAP-T8 (HIGH): DR-12 has always read "second reviewer walks THE PACK end-to-end and signs" and no pack existed — the dry run reported READY 11/11 because it checked the six documents someone had listed, not the one DR-12 depends on. docs/REVIEW_PACK.md written and DR-16 added so the dry run can no longer pass without it; DR-15 corrected (screenshots no longer need the dev org since v020). 27 suites / 1,183 tests at 100%, zero pragmas. | Released
| v022 | 2026-09-13 16:48 | Claude for Senthil/KP | PORTABLE GATE KIT (R-T9/R-T15 addressed on the TeleField side). The five gates were jest tests that needed copying and rewiring to reach a sibling; they are now scripts/review-gates.js — plain Node, no product imports, no TypeScript, no test framework — driven entirely by review-gates.config.json. Porting to another product is the config file and nothing else, and the script is asserted not to contain the product name. MUTATION-TESTED: the suite copies the repo, breaks exactly what each gate watches, and requires it to go red. TWO OF THE FIVE PASSED THAT TEST WHILE BROKEN — reachability accepted a dead wrapper calling a dead function inside its own module, and the claims gate was satisfied by the token seal on the refresh path while the install path was unwired. Both hardened. 28 suites / 1,192 tests at 100%, npm run gates in CI. | Released
| v023 | 2026-09-13 17:23 | Claude for Senthil/KP | COLD REVIEW PASS 9 — DOES THE JOB LEAVE ANYTHING BEHIND? F-T25 (HIGH): the daily backup built the whole bundle, kept its sha256 and discarded the bundle. Nothing was written anywhere, so "a backup is taken every day" meant a checksum of data nobody could restore from — pass 4 found four jobs with no caller, this is one level in: a job that ran and produced no artifact. Backups are now written to BACKUP_DIR, read back and integrity-checked before being reported as successful, and pruned to the last 14. GAP-T9 (HIGH): the deploy workflow predated persistence — no migration step, and traffic switched with both slots live, which the single-writer store (R-T13) cannot survive. Migration and an explicit BLUE drain are now steps; "zero-downtime" removed from the description because draining is a write pause. 29 suites / 1,225 tests at 100%. | Released
| v024 | 2026-09-13 17:30 | Claude for Senthil/KP | COLD REVIEW PASS 10 — OVER A REAL SOCKET. Everything TeleField knew about itself under load came from an in-process supertest harness that says so in its own header; a server has existed since v015 and nothing had ever measured it (GAP-T10). npm run loadtest now drives real HTTP against a running instance: MEASURED 500 rps sustained, p50 0.8ms, p95 3.7ms, zero errors, against a launch assumption of ~10 req/s. Measuring it turned up two more: F-T26 the scheduler reported its work — including per-job errors — to nobody, so a sweep failing every tick looked identical to one succeeding (now GET /ops/sweeps behind the operator token); GAP-T11 bin/telefield.js silently served whatever was in dist/, which bit me mid-session and would present in production as "my change did nothing" (now refuses a stale or missing build). 30 suites / 1,261 tests at 100%; load run added to CI. | Released
| v025 | 2026-09-13 19:26 | Claude for Senthil/KP | COLD REVIEW PASS 11 — VERIFICATION SWEEP #2 vs the live Zoho documentation, then the database half. Passes 1-10 read TeleField against itself; this pass read it against the platform's own docs, which is the one source none of them can contain. TWO LIVE-BLOCKING FINDINGS, both invisible to 1,261 passing tests for the same reason — every test injects its own transport and asserts what we do with the RESPONSE; nothing had ever asserted what we SEND. VER-T4 (CRITICAL): the authorization-code exchange never sent redirect_uri, which Zoho marks required and rejects without; every install would have failed on the day. VER-T5 (CRITICAL): the data centre was a property of our deployment (one process-wide ZOHO_DC) when Zoho names the CUSTOMER's DC on every callback and requires the exchange, refresh and API calls to use it — a US install would have had its code POSTed to accounts.zoho.in. New src/zohoDc.ts host registry, migration 006 (orgs.dc), per-org routing for exchange/refresh/API host; an unserved DC is refused with a named error rather than sent to a guessed host, and accounts-server (attacker-controllable on a public route) is matched against the registry, never used as a URL. VER-T6: three asset specs in the capture plan were assumed and wrong (published: logo 120x120, banner 310x142, video as an iframe link, plus a main screenshot showing what we add inside CRM). VER-T7: Zoho's approval criteria require four listing disclosures the copy did not carry — external accounts (our telephony dependency), data transfer, edition compatibility, support — now gated by DR-17 and mutation-tested. DATABASE HALF: GAP-T12 closed (the restart proof compared export bundles, which omit seven datasets — fidelity now checked across every dataset a tenant owns plus a table census; no defect behind the gap, but the dc null/undefined mismatch it exposed was real and fixed). CLEAN-4: concurrency and the R-T14 crash boundary probed against real Postgres and verified correct. GAP-T13: the load harness's own example invocation defaulted to a user in no org. MEASURED with a real database behind the write path: 200 rps/15s p95 1.1ms and 500 rps/8s p95 5.2ms, zero errors, 6,127 latency rows durably written during the run. 31 suites / 1,302 tests at 100% zero pragmas plus 38 database-backed contract tests at 100%; everything verified from the packaged zip in a clean clone. Story position unchanged at 98/100 (391/399). | Released
| v026 | 2026-09-13 19:56 | Claude for Senthil/KP | COLD REVIEW PASS 12 — WHAT DOES A CUSTOMER ACTUALLY INSTALL? Eleven passes examined what TeleField does once it is running; this one asked what appears inside Zoho CRM after someone clicks Install, and the answer was nothing. GAP-T14 (CRITICAL): no extension bundle existed. A Zoho CRM extension is a Connected App plus an uploaded resource bundle — plugin-manifest.json and an app/ folder Zoho hosts and frames at the widget locations declared in the developer console — and the 30-minute setup guide stopped at the connection and the webhook. Nine screens, a server, a database and an OAuth flow, and no way for any of it to appear in CRM. Same class as OnCall GAP-OC1, VoiceBridge's missing package source and TestPulse's missing Custom UI. Built: src/extension.ts generating the manifest and four widget bootstraps (telephony dialer, related-list call history, settings, web-tab workspace), scripts/package-extension.js (npm run extension) producing extension/ and dist/telefield-extension.zip, with --check in CI so the committed bundle cannot drift from the source. Every widget frames a screen route that exists, the whitelisted host is the host the widgets call, the locales are the EN/HI/TA the listing promises, and the scopes carried are the least-privilege manifest rather than a second list. F-T27 (CRITICAL): the screens could not have been opened by a browser at all. Identity came only from a header, and a framed navigation cannot set one — so every widget would have received 401 from the first request. Screens now also accept the signed, org-bound session from a tf_session cookie, with GET /session/start performing the single hop that turns a token into that cookie (refuses anything it did not sign, refuses an off-host redirect, sets Referrer-Policy: no-referrer, and is SameSite=None; Secure in production as a third-party iframe requires). D-T1 left OPEN rather than guessed: how the widget proves WHICH CRM user is looking at it — a value read in the browser is a claim, not a credential, and accepting it would rebuild F-T04. Two named assumptions (A-X1 manifest service string, A-X2 CRM SDK asset URL) isolated in one module with a confirm-at-setup step, the same containment R-T5 bought for the webhook format. 32 suites / 1,340 tests at 100% zero pragmas plus 38 database-backed contract tests at 100%; suite, all five review gates, the bundle check and the database suite verified from the packaged v026 zip in a clean clone. Story position unchanged at 98/100 (391/399). | Released
| v027 | 2026-09-13 20:10 | Claude for Senthil/KP | COLD REVIEW PASS 13 — THE SECURITY REVIEW, STARTING WITH THE HOLE THE LAST RELEASE OPENED. v026 made the screens reachable by accepting the signed session from a cookie; that was necessary, and it silently removed the property that had made every mutating route immune to cross-site request forgery — that the credential could only be attached by code we wrote. F-T28 (CRITICAL, self-inflicted one release earlier): a page on any site could have POSTed to ~100 mutating routes and the browser would have attached the cookie, with SameSite=None (which a third-party iframe requires) switching off the browser's own defence. Fixed: cookie identity is honoured for GET/HEAD only; a state-changing request must carry the x-telefield-session header, which a cross-site form cannot set and the widget's own fetch can. The refusal names the header rather than returning a bare 401. F-T29: no browser-hardening headers existed. Every response now carries nosniff, Referrer-Policy: no-referrer and a frame-ancestors policy admitting Zoho CRM and nothing else — a blanket DENY would have broken the widget the previous release built, and no policy at all left the screens clickjackable from anywhere; the host list is derived from the same DC registry so a new data centre cannot add an unframed CRM host. F-T30: the operator token was compared with !== — timing-unsafe, while the webhook signature had used timingSafeEqual since S1. F-T31: the 100kb body limit was inherited rather than chosen, and the three offline batch endpoints accepted unbounded item counts within it; both are now explicit, with a 422 that tells the device to split the sync. GAP-T15: docs/SECURITY_EVIDENCE.md — the pack a marketplace reviewer and a pen-test vendor actually read — was a render of release v009, seventeen releases stale, and the dry run only checked that the file existed. Regenerated, and pinned by a drift test against a fresh run of the assessment. The pack itself gained SEC-07 (CSRF posture) and SEC-08 (browser hardening), asserted against the code rather than described. 33 suites / 1,379 tests at 100% zero pragmas plus 38 database-backed contract tests at 100%; suite, five review gates, the extension-bundle check and the Postgres suite verified from the packaged v027 zip in a clean clone. Story position unchanged at 98/100 (391/399). Lesson L-T2: a release that closes a blocker can open a vulnerability in code it never touched — review the release, not just the feature. | Released
| v028 | 2026-09-13 20:24 | Claude for Senthil/KP | COLD REVIEW PASS 14 — THE VERNACULAR PROMISE, AUDITED. 'Vernacular EN/HI/TA' is LC-3, sits in both listing variants, and v026 declared three locales to the platform. This pass asked which parts of that are true and treated the answer as a published-claims problem rather than a feature request. GAP-T16 (HIGH, self-inflicted two releases earlier): the bundle declared en/hi/ta and shipped strings in one. Zoho's manifest rule is explicit — every declared locale needs a matching file under app/translations — so the bundle would have failed validation, and a reviewer with CRM set to Hindi would have opened a widget with no text in it. Fixed: catalogues for all three locales, shipped as app/translations/<locale>.json, with the declared locale list now DERIVED from the catalogue keys so a locale can never again be promised without strings behind it. The widget bootstrap picks the language from the CRM page it is framed in and falls back to English rather than to a blank panel. CLEAN-5: the data path was probed with real Tamil and Hindi content — a Tamil lead name through CSV import, the queue and the export bundle; a Hindi disposition label through config and application; Indic text with embedded commas and quoted newlines through the RFC-4180 parser. All correct, no defect, now pinned so the F-T06 class cannot return through a different door. CLAIM NARROWED rather than inflated: the listing said 'vernacular-ready dispositions', which reads as a shipped feature when what is true is that an org can NAME its dispositions in its own language. The copy now states exactly where vernacular support ends — listing and docs EN/HI/TA, data in any script, widget text EN/HI/TA, in-app screens English — and DISCLOSURE-LANGUAGE carries that into the listing where a buyer reads it, gated by DR-17 alongside the other four. A sixth claims-gate rule ties the word 'vernacular' to the catalogues. 34 suites / 1,413 tests at 100% zero pragmas plus 38 database-backed contract tests at 100%; suite, five review gates, the bundle check and the Postgres suite verified from the packaged v028 zip in a clean clone. Story position unchanged at 98/100 (391/399). Lesson L-T3: the honest fix for a claim you cannot back is to narrow the claim, and the gate that keeps it narrow is worth more than the sentence. | Released
| v029 | 2026-09-13 20:36 | Claude for Senthil/KP | COLD REVIEW PASS 15 — RUN IT FOR NINETY DAYS. Every test in this repository, and every load run, exercises TeleField for seconds; the product is a long-running process whose most important work is unattended — a sweep every minute, a backup every day, a retention purge at thirty days, dunning on days 0/3/6. Nothing had ever let the clock run. F-T32 (HIGH): the FIFO caps added in v013 bound MEMORY. Nothing bounded the database. Every latency sample, notification, error and telemetry row written since install was still in Postgres, and every one of them was read back at boot — at the 500 rps measured in v025, latency samples alone would grow by tens of millions of rows a day and turn a restart into an outage. The fix is two-sided: a daily prune with a window chosen per dataset (latency 7 days, errors 30, notifications 60, telemetry 90) reported in the sweep alongside the backup, and bounded hydration that reads the newest rows up to the in-memory cap so boot time depends on the cap rather than on how long the install has been running. Audit rows are deliberately NOT pruned — deleting evidence is a different decision from bounding a boot, so they are bounded at hydration only. The ninety-day harness that found it now stands as a regression: ninety simulated days of traffic and sweeps, asserting each dataset keeps its own window and the recent end stays intact, that each window applies to its own dataset rather than one number to all four, that the purge fires on the right day and exactly once rather than every day after, that a backup is taken each day, and that a prune failing on a full disk is reported as a job error while the rest of the day's work continues. Verified against real Postgres too: the rows are gone from the database, not just from the heap, and hydration takes the newest page rather than an arbitrary one. 35 suites / 1,443 tests at 100% zero pragmas plus 40 database-backed contract tests at 100%; suite, five review gates, the bundle check and the Postgres suite verified from the packaged v029 zip in a clean clone. Story position unchanged at 98/100 (391/399). Lesson L-T4: a cap that is not also a cap on storage is a cap on nothing — and the test that finds it is the one that lets the clock run. | Released
| v030 | 2026-09-13 21:53 | Claude for Senthil/KP | COLD REVIEW PASS 16 — TAKE THE DATABASE AWAY. Measured before it was theorised: a server was started against a real Postgres, the database was stopped with pg_ctl -m immediate, and a write was issued. The process did not degrade — it EXITED, on an unhandled 'error' event from node-postgres ("Connection terminated unexpectedly"). F-T33 (CRITICAL): a Postgres restart, a managed-database failover or a network blip took TeleField down completely and took every queued write with it. ST-091 promises graceful degradation with user comms; that story had been written for Zoho's API being down and never for our own database. Three defects sat inside the one crash and all three are fixed: the error event is handled in one place used for the first client and every reconnect; queued writes are HELD IN ORDER rather than dropped (v029 pushed the failure into an array nobody read and discarded the customer's work); and the HTTP layer stops promising durability it cannot deliver — mutating requests get 503 with Retry-After and a sentence a rep can act on, reads continue from hydrated memory, and /healthz becomes readiness as well as liveness, answering 503 degraded with a pendingWrites count so a load balancer drains the instance and the deploy workflow notices. RE-MEASURED after the fix, same experiment: write before the outage 200 and persisted; during the outage the process stayed up, the write was refused 503 with pendingWrites=2, reads answered 200, health reported 503 degraded; after Postgres returned, health 200 with the backlog drained to zero and a new write persisted. The refused lead is correctly ABSENT from the database — refused, not silently lost. Two smaller things fell out: the write-failure log is capped (F-T32's lesson applied to our own diagnostics — an outage lasting a week must not become the memory leak), and a store that drains a batch successfully heals itself rather than refusing writes the database would accept. An unreachable reconnect guard was deleted rather than pragma'd, since flush() already serialises; unreachable defensive code is how F-T01 and F-T02 happened (OBS-T3). 36 suites / 1,477 tests at 100% zero pragmas, and the database-backed contract suite grows to 47 at 100% — the outage paths are covered against a connection that really goes away rather than a mock. Suite, five review gates, the extension-bundle check and the Postgres suite all verified from the packaged v030 zip in a clean clone. Story position unchanged at 98/100 (391/399). Lesson L-T5: the failure modes worth testing are the ones you can cause — stopping the database found in one command what sixteen passes of reading code could not. | Released
| v031 | 2026-09-13 22:50 | Claude for Senthil/KP | COLD REVIEW PASS 17 — THE DEPLOY. Pass 16 asked what happens when the database goes away; this one asked about the event that happens several times a week instead of rarely: the process being told to stop. A deploy, a container restart, an autoscaler scale-in and the blue/green drain all end in SIGTERM, and nothing in this product handled one. F-T34 (HIGH): Node's default on SIGTERM is immediate exit — in-flight requests cut off mid-response, and anything in the write-behind queue (a scheduler tick's work, or writes held through a database outage, R-T29) gone with the process. The blue/green step added in v023 drains TRAFFIC at the router; nothing drained the PROCESS, so every deploy discarded whatever was queued. Fixed: SIGTERM and SIGINT now drain in order — stop being routed traffic (/healthz answers 503 draining, so the router acts before the socket closes), refuse new writes with Retry-After: 5 while reads continue, finish in-flight requests, flush the queue, close the database, exit 0. SHUTDOWN_TIMEOUT_MS (15s default) bounds it and exits non-zero if the drain overruns, because a shutdown that hangs is its own outage. The deploy workflow now names the SIGTERM step and says to wait for exit 0. Honest limit recorded: unlike F-T33, the live signal run was NOT completed — the session's container stopped holding background processes reliably at that point. The drain is proven by 31 tests including the server's own listening state before and after, and the live SIGTERM check belongs in the first production deploy rather than being claimed here. A flake was also caught and removed during the clean-clone verification: one pass-17 test asserted a socket would be refused after shutdown, which depends on connection timing; it now asserts the server's listening state instead. A flaky suite is one people learn to re-run instead of read. 37 suites / 1,508 tests at 100% zero pragmas plus 47 database-backed contract tests at 100%; suite, five review gates, the extension-bundle check and the Postgres suite verified from the packaged v031 zip in a clean clone, and the suite run twice to confirm the flake is gone. Story position unchanged at 98/100 (391/399). | Released
— |  |  | SUPERSEDED by v013: the code phase was complete, the code was not correct. Review releases (correctness, no new stories) continue until the cold review closes; live-evidence releases resume after that. | Note
— |  |  | SUPERSEDED by v013: the code phase was complete, the code was not correct. Review releases (correctness, no new stories) continue until the cold review closes; live-evidence releases resume after that. | Note
— |  |  | SUPERSEDED by v013: the code phase was complete, the code was not correct. Review releases (correctness, no new stories) continue until the cold review closes; live-evidence releases resume after that. | Note

## Sprint_Tracker_Log
SPRINT TRACKER LOG — every execution event, newest last
ID | Date/Time | Sprint | What happened | Refs | State changes | Blockers | Next
E001 | 2026-09-10 21:05 | — | D15 RECORDED — Senthil instruction 21:05: build TeleField from v006 workbook. Context: RevRescue (rank 1) S1 code is complete at 100% coverage awaiting live-install/T-06 (see its v004 tracker); R7 requires a logged decision for any re-ordering — this entry is that log, mode pending Senthil ratification (parallel-build vs order swap). D13 (100% automation coverage; discovery parked, dev proceeds) applied portfolio-wide per 20:45 instruction. | D13,D15,R7 | TeleField S1 opened | None | S1 build
E002 | 2026-09-10 21:05 | S1 | S1 FOUNDATION BUILT (TypeScript/Node per v006 stack): config with India-first ZOHO_DC=in + validation; typed Store repository layer (in-memory impl, Postgres adapter point — see R-T4); zohoAuth (ST-051 code exchange, ST-055 rotation-persisting refresh); zohoClient (429/5xx exp backoff+jitter per Launch #4, auto-refresh-once on 401 then replay, no refresh loop); webhooks (HMAC-SHA256 t/s header, timestamp tolerance replay guard, timing-safe compare, event dedupe ledger); lifecycle (install w/ ST-056 source attribution, uninstall ST-052 token WIPE + retention-scheduled deletion, sweep); express surface /healthz, /oauth/callback, /webhooks/zoho, /orgs/:id/status; GitHub Actions CI. | ST-051,ST-052,ST-055,ST-056 | 4 S1 stories Done-in-code (13 pts) | Live Sigma/Catalyst install = Senthil + dev org | E003
E003 | 2026-09-10 21:05 | S1 | D13 TEST GATE MET — 60 automated tests (unit + supertest API integration: full install->status->uninstall->duplicate flow; bad signature, replay, missing header/body; OAuth 400/502/500 paths; rotation persistence; refresh-loop guard). Coverage 100% statements / 100% branches / 100% functions / 100% lines, ZERO istanbul-ignore pragmas. Gate enforced: jest coverageThreshold 100 fails any future commit below. | D13 | Evidence in Traceability col H | None | S1-live items; D15 ratification
E004 | 2026-09-10 22:00 | S2 | S2 BUILT on S1 foundation — roles.ts (ST-054 matrix, PermissionError->401/403), callQueue.ts (ST-001 DEFAULT_CONFIG + validation naming offending field; ST-003 validateRules/scoreLead with boost/deprioritise/skip; ST-002 nextCall scoring + CallAttempt lifecycle + recordOutcome retry/exhaust logic + aha-once), sync.ts (ST-004 outbox: attemptSync structured errors, processOutbox retry path), lifecycle ST-053 restorable check (uninstalled + schedule unexecuted + within window), store extended (users/config/rules/leads/calls/outbox), app.ts guarded() permission wrapper + 8 new endpoints. | ST-001..004,ST-053,ST-054 | 6 stories -> Done-in-code (29 pts); rollup auto-counts | Live demo to Senthil = S2 exit sign-off | E005
E005 | 2026-09-10 22:00 | S2 | D13 TEST GATE MET — 113 tests (unit: matrix/rules/scoring/engine/sync; integration: FULL happy path install->config{}->leads->next->connected->synced->summary with funnel install/setup/aha asserted; CRM-down outcome-never-lost path; role enforcement per endpoint; reinstall-restore via API; infra-failure 500; default-deps path). Coverage 100/100/100/100, zero pragmas. Note: 429-backoff verified with injected AND default sleep/jitter. | D13 | Evidence in Traceability col K | None | S2 exit demo; D15; S3 on continue
E006 | 2026-09-10 22:09 | S3 | S3 BUILT — audit.ts, metrics.ts, importer.ts (profile-mapped headers, row-level report), notify.ts (typed events, mute matrix), disposition.ts (default taxonomy + action engine: close/callback/requeue/dnc; callback boost 1e6 guarantees due callbacks dial first; dnc excluded in nextCall), callQueue pause guard + surface param, mobile clientRef once-ledger, 10 new endpoints, audit+notification wiring on privileged mutations and sync failures. | ST-005..010, ST-011..014, ST-085 | 11 stories -> Done-in-code (47 pts) | Live widget/mobile verification needs S1-10 Zoho org | E007
E007 | 2026-09-10 22:09 | S3 | D13 TEST GATE MET — 156 tests; coverage 100/100/100/100, zero pragmas. Notables: offline batch dedupe asserted (duplicate clientRef ignored, per-item reasons), callback-due lead proven to outrank priority-5 lead, dnc proven excluded with attempts remaining, import report asserted line-by-line, mute proven to silence both channels for exactly that user+type. S3 EXIT CRITERIA: call queue complete with tests = MET in code; disposition skeleton = EXCEEDED (engine functional). Live-surface half of ST-005 rides on S1-10. | D13 | Traceability col K updated | None | S4 on continue; D15 + S1-10 with Senthil
E008 | 2026-09-10 22:18 | S4 | S4 BUILT — funnel.ts (stage dashboard + habit qualification), errors.ts (release-tagged records, 5/5min spike detection wired into the guarded 500 path), metrics.ts computeDispositionMetrics, importer.ts history importer (dnc-from-history applied, stale callbacks excluded by design), engine-scoped pause in store (queue vs dispositions), notify types extended, 8 new endpoints incl. compact widget disposition + taxonomy fetch, dnc audit+notification wiring. | ST-015..020, ST-071, ST-072, ST-086 | 9 stories -> Done-in-code (34 pts) | Live widget halves ride on S1-10 | E009
E009 | 2026-09-10 22:18 | S4 | D13 TEST GATE MET — 219 tests, 100/100/100/100, zero pragmas. Smoke suite (ST-086) is the S4 exit criterion made executable: install->config-on-defaults->import->dial->outcome->disposition->callback->metrics->funnel in one uninterrupted journey, runs as CI post-deploy job + npm run smoke. Notables: habit fires exactly once on the 3rd active day (4th day asserted not to duplicate); spike alert asserted at exactly the 5th error in window; history import proven to apply DNC but never resurrect stale callbacks. | D13, ST-086 | Traceability col K updated; S4 exit MET | None | S5 on continue; D15 + S1-10 with Senthil
E010 | 2026-09-10 22:27 | S5 | S5 BUILT — beats.ts (create/rules/haversine/nearest-neighbour planner/visits; DNC leads excluded from routing by design), checklist.ts (ST-078 live checklist), stops importer + beat metrics, beats permission pair added to matrix, beat.assigned/route.ready notify types, teaching empty-state helper applied across surfaces (ST-079), 12 new endpoints incl. compact widget route + offline mobile visit batch. Dead-branch discipline: unreachable ¦¦7 guard in next-day sort removed rather than pragma-d. | ST-021..030, ST-078, ST-079 | 12 stories -> Done-in-code (50 pts) | S5 exit (daily dogfooding) needs live org + Senthil | E011
E011 | 2026-09-10 22:27 | S5 | D13 TEST GATE MET — 264 tests, 100/100/100/100, zero pragmas. Notables: nearest-neighbour order asserted on real Chennai-area coordinates (base->near->far), off-day recurrence returns correct next weekday from multi-day sets, cooldown + DNC exclusions asserted, offline visit batch dedupe per-item, checklist off-track flag flips at >24h without aha and locks on-track once aha reached. HONEST STATUS: S5 exit criterion is behavioural (team dogfoods daily) — code cannot meet it alone; marked pending live alpha, not claimed. | D13 | Traceability col K updated; S5 exit = pending live alpha | S1-10 | S6 on continue
E012 | 2026-09-11 11:50 | S6 | S6 BUILT — checkins.ts (fence via haversine, policy engine, sequence enforcement, checkout->S5 visit), billing.ts (trial derived from installedAt — stateless, unforgeable; PLANS starter $29/pro $59; PROVIDER_FOR_CHANNEL marketplace->zoho mandated / external->stripe; round2 proration), checkin metrics + fieldassist import profile, checkins pause engine, checkin_push outbox kind, 13 new endpoints, 402 enforcement wired into queue/next + widget/next. | ST-031..040, ST-057..059 | 13 stories -> Done-in-code (60 pts) | Live sandbox charge needs S1-10 + billing creds | E013
E013 | 2026-09-11 11:50 | S6 | D13 TEST GATE MET — 307 tests, 100/100/100/100, zero pragmas. EXIT MADE EXECUTABLE: API test charges a test customer $29 via zoho_marketplace (mandated channel asserted by URL), upgrades to pro with proration asserted exactly (fraction 0.5 -> credit 14.50, charge 29.50, net 15.00), downgrades to ledger credit 7.50; declined charge (403) proven to leave NO subscription and NO ledger row; provider-down (503) message tells the user nothing was charged. Geo notables: outside-fence honesty (allow policy still records withinFence=false), sequence override flags rather than hides, checkout writes the S5 visit so beat cooldowns see geo visits. | D13, ST-057..059 | Traceability col K updated; S6 exit MET (in code) | None new | S7 on continue; D15 + S1-10 with Senthil
E014 | 2026-09-11 23:02 | S7 | S7 BUILT — billing.ts extended (renewSubscription with save-offer discount + cancelAtPeriodEnd honour, runDunningSweep day-0/3/6 schedule with catch-up, PLAN_LIMITS + enforceLimit 80%/100%, ledger-derived invoices with tax-inclusive split, requestCancellation save-offer/confirm/survey, acceptSaveOffer once-only), scopes.ts manifest + drift detectors, SCOPES.md, requestedScopes in settings, 9 new endpoints, limit wiring on leads add + CSV import + new seats, mode-aware requireActiveOrTrial (read survives read-only). | ST-060..064 | 5 stories -> Done-in-code (15 pts) | S7 exit (private beta 5 external users) is behavioural — needs live org + humans | E015
E015 | 2026-09-11 23:02 | S7 | D13 TEST GATE MET — 342 tests, 100/100/100/100, zero pragmas. Notables: dunning asserted to send exactly 3 emails across the window with idempotent re-sweeps and skipped-day catch-up; read-only asserted to block dials while metrics endpoints stay 200; 80% warning fires once per limit (450/500 re-add stays silent); GST split asserted to the cent; save-offer discount proven to apply exactly once (renewal 23.20 then discount cleared); scope drift detectors proven to actually detect (both directions tested with synthetic drift). HONEST STATUS: S7 exit criterion (5-user private beta) marked pending live, not claimed. | D13 | Traceability col K updated; S7 exit = pending live beta | S1-10 | S8 on continue
E016 | 2026-09-11 23:11 | S8 | S8 BUILT — scorecards.ts (SCORECARD_DEFAULTS 6 KPIs, KPI handler map — no switch-default pragma, computeScorecard/Team/trend), crypto.ts (AES-256-GCM v1:iv:tag:data + scrubSecrets wired into guarded() 500 path), zohoClient circuit breaker (threshold 5, cooldown 60s, half-open), analytics.ts (heatmap/health/digest/exportCsv/alerts), slo.ts (p95 + budgets), importer scorecard-history profiles, app instrumentation (featureOf + latency per guarded request), 16 new endpoints, DATA_FLOWS.md, deploy.yml blue/green. | ST-041..050, ST-065/066/067/070, ST-073..077, ST-087/088/092 | 22 stories -> Done-in-code (87 pts) | ST-066 vault injection, ST-088 real-infra load, ST-092 live deploy = pending S1-10/production | E017
E017 | 2026-09-11 23:11 | S8 | D13 TEST GATE MET — 438 tests (96 new), 100/100/100/100, zero pragmas. Notables: importer Number("")==0 truncation bug caught by test and fixed with explicit empty guard (a short CSV row now skips with a reason instead of importing zero); breaker proven to fail fast without touching transport while open and to re-open on failed probe; secret-leak test injects the client secret into a thrown error and asserts [redacted] in BOTH the 500 body and the stored error record; grade boundaries tested at exactly 90/70/50; load harness 300 mixed requests <1% errors. HONEST: load + deploy are in-process/CI-config verification — live runs pending. | D13 | Traceability col K updated; S8 RAG GREEN(code) | S1-10 | S9 on continue
E018 | 2026-09-11 08:15 | S9 | S9 BUILT — privacy.ts (org/user export tokens-redacted, delete-my-data + audit, last-owner guard), backup.ts (sha256 canonical-JSON integrity, restore via public Store surface, runRestoreDrill fresh-store round-trip), outage.ts (ST-070 breaker -> operational/degraded/outage ladder, DEGRADATION_MESSAGE broadcast respecting mutes), securityEvidence.ts (6 executed controls SEC-01..06 mapped to OWASP ASVS + markdown archive render), a11y.ts + widgetTemplate.ts (9-rule WCAG AA engine, contrast palette allow-list, assertAccessible gates GET widget/next-call.html); app.ts +6 endpoints (privacy/export, privacy/my-data, privacy/delete-my-data, service-status, security/evidence, widget html); docs/ LISTING_COPY_AB (EN+HI/TA), ASSET_PLAN_SCREENSHOTS_VIDEO (Zoho specs), WCAG_AA_CHECKLIST (measured ratios), SECURITY_EVIDENCE (generated) | ST-068,ST-069,ST-089,ST-090,ST-091,ST-093,ST-094 | 5 stories -> Done-in-code (22 pts); ST-093/094 -> Drafted (8 pts) | External pen-test vendor (ST-068), listing A/B pick (ST-093), live capture + screen-reader pass (ST-094/089) = Senthil; S1-10 org | E019
E019 | 2026-09-11 08:15 | S9 | D13 TEST GATE MET — 513 tests (75 new: 44 s9 unit incl. chaos drain, 31 s9 API), 100/100/100/100 statements/branches/functions/lines, zero pragmas; tsc clean; store extended (removeUser, purgeUserNotifications), RETRY_DELAY_MS exported for chaos window | D13 | Traceability col K updated; S9 exit (review submission accepted) = pending live org + Senthil halves | S1-10 | S10 on continue
E020 | 2026-09-11 08:51 | S10 | S10 BUILT — helpCenter.ts (15 articles, token-scored search title x3/tag x2/body x1), chat.ts (openConversation/postMessage, addBusinessHours IST walk, runSlaSweep breach-once + notify, slaReport), demoMode.ts (DEMO org: 3 users/5 leads/2 calls/1 beat/2 stops/2 check-ins one outside-fence/scorecard trend — real domain shapes so demo rides real code paths; resetDemo returns FRESH store, tenant data untouchable), publicPages.ts (buildStatusPage worst-component, renderIncidentComms, buildPricingMatrix from PLANS/PLAN_LIMITS, PRICING_FAQ, TRUST_PAGE_SECTIONS, shared a11y-gated render), submissionDryRun.ts (DR-01..11 automated + DR-12..15 human, markdown report); app.ts +13 endpoints incl. public /status /status.json /pricing /trust /demo; store +conversation persistence | ST-080,ST-081,ST-083,ST-084,ST-095,ST-096,ST-097 | 7 stories -> Done-in-code (24 pts); S10 100% in code | Chat vendor pick (if external over built-in), demo VIDEO capture (live org), second-reviewer human dry-run sign-off (DR-12), live listing publish for pricing/trust = Senthil; S1-10 | E021
E021 | 2026-09-11 08:51 | S10 | D13 TEST GATE MET — 560 tests (47 new: 17 s10 unit, 30->34 s10 API incl. breaker-driven status ladder + recovery), 100/100/100/100, zero pragmas, tsc clean; dry-run engine reports READY (11/11 automated) with 4 human/live items pending | D13,ST-097 | Traceability col K updated; S10 exit (marketplace approval) = live-gated | S1-10 | S11 on continue
E022 | 2026-09-11 11:12 | S11 | S11 BUILT — reviewPrompt.ts (shouldAskForReview: aha via ST-078 checklist + >=10 outcomes + operational service + no unanswered support; recordReviewResponse shown/clicked/snoozed/declined with per-user state + review.* telemetry), launch.ts (buildLaunchRunbook RB-01..10 with live dry-run gate + renderRunbookMarkdown; addPartner/advancePartner forward-only stage machine, partnerReport with honest launch-exit math, sweepStalePartners 3d owner nudge); store +reviewPrompts +partners persistence; app.ts +7 endpoints (review/prompt GET+POST, launch/runbook JSON+md, partners POST/stage/GET/sweep) | ST-082,ST-098,ST-100 | 3 stories -> Done-in-code (8 pts); S11 code 100% | S11 EXIT fully live-gated: first 10 installs, first 3 reviews, activation>40% — needs listing live (S1-10 org, review pack, approval) + partner outreach = Senthil | E023
E023 | 2026-09-11 11:12 | S11 | D13 TEST GATE MET — 597 tests (37 new: 10 s11 unit, 27 s11 API), 100/100/100/100 verified on TWO consecutive full coverage runs, zero pragmas, tsc clean. HONESTY FLAG: one different single test failed once in each of the S9/S10/S11 first coverage runs and passed on every rerun (2x stable) — intermittent under parallel coverage workers, not reproduced; watch in CI (R-T7 candidate) | D13 | Traceability updated; ALL 12 sprints now have their code halves shipped except S12 | S1-10 | S12 on continue = final code sprint
E024 | 2026-09-11 12:47 | S12 | S12 BUILT (final) — listingSeo.ts: analyzeSearchTerms (CTR>=3%, conversion>=10% thresholds, impressions-sorted, guards installs<=clicks<=impressions), TARGET_TERMS coverage from ST-093 copy vocabulary, recommendIteration ranked 4-class action plan + honest hold verdict, renderSeoMarkdown with SAMPLE banner; endpoint POST /orgs/:id/listing/seo/analyze (team.manage, JSON+md) + seo.iteration_run telemetry; docs/LISTING_SEO_ITERATION.md committed sample-flagged | ST-099 | 1 story -> Done-in-code (2 pts). CODE PHASE COMPLETE 98/100 | Real search-term export from publisher console (post-launch) + applying listing edits = Senthil | E025
E025 | 2026-09-11 12:47 | S12 | D13 FINAL GATE MET — 627 tests (30 new), 100/100/100/100 on THREE consecutive full runs, zero pragmas, tsc clean. E023 flake CLOSED: root cause = load-test in-process p95 budget under parallel coverage instrumentation, not product code; tripwire 200->400ms with inline rationale, error-rate gate and src/slo.ts live budgets unchanged. Final codebase: 39 src modules, 19 test suites, 12 committed docs, blue/green CI | D13 | All 12 sprint code halves shipped. Remaining to listing: Senthil live items only | — | Live-ops (no continue target)
E026 | 2026-09-13 10:36 | REVIEW | COLD REVIEW PASS 1 OPENED — TeleField had never had an adversarial review, an external verification sweep or an artifact-gap audit; every sibling that ran one found defects in code already at 100% coverage. Plan approved by Senthil 10:36. | D13 | v012 zip + tracker taken as the baseline; jest could not run from the delivered zip (GAP-T1) | None | Pass 1 execution
E027 | 2026-09-13 10:55 | REVIEW | PASS 1 EXECUTED — 8 defects fixed with pinned regressions. CRITICAL: F-T01 retention sweep erased only telemetry (published 30-day policy breached), F-T02 delete-my-data left the person's calls/check-ins/scorecards behind, F-T03 the billing gate sat on 3 of ~110 routes so an expired/unpaid/cancelled org kept the whole product, F-T04 identity came from the caller's own x-user-id header. Also F-T05 unbounded ledgers, F-T06 naive CSV split in 5 importers, F-T07 production backoff sleep was a no-op, F-T08 outbox retried forever. | F-T01..F-T08 | New src/csv.ts, src/ledger.ts, src/auth.ts; store gains purgeOrg/purgeUser; superseded removeUser/purgeUserNotifications/purgeTelemetry deleted | None | Pass 2 over untouched modules
E028 | 2026-09-13 10:55 | REVIEW | ARTIFACT GAPS — GAP-T1 no jest.config.js shipped, so the v012 zip could not run its own suite in a clean clone (the 100% claim was unverifiable from the delivered artifact); GAP-T2 DATA_FLOWS.md did not exist although ST-065's own test asserts it, so the packaged suite failed on arrival; both fixed. GAP-T3 OPEN: still no listen() and no npm start — the OAuth callback and webhook URLs registered on setup day have nothing behind them (OnCall GAP-OC1 / EngageOS GAP-E1 class). | GAP-T1,GAP-T2,GAP-T3 | GAP-T1/T2 closed; GAP-T3 carried to pass 3 | GAP-T3 blocks the live sweep | Pass 3 artifact/deployability
E029 | 2026-09-13 10:55 | REVIEW | D13 GATE MET ON THE REVIEW RELEASE — 20 suites / 680 tests (53 new), 100% statements/branches/functions/lines, zero pragmas. Story position deliberately unchanged at 98/100 and 391/399: no story moved, because nothing new was delivered — v012's claims were simply not all true. | D13 | Traceability untouched by design | None | Pass 2, then pass 3 + verification sweep vs live Zoho docs
E030 | 2026-09-13 10:55 | REVIEW | LESSON L-T1 — TeleField was the pattern source for nine sibling trackers and the last product to be reviewed. Four CRITICAL defects sat in a release marked FINAL at 627 tests and 100% coverage for two days. Coverage proves execution, not correctness, and a product that has never been reviewed is not finished however green its gate is. | L-T1 | Logged in RAID | None | Apply the same order to any future product: review before declaring a code phase complete
E031 | 2026-09-13 11:00 | REVIEW | PASS 2 EXECUTED over the modules pass 1 did not reach — 7 defects fixed with pinned regressions. F-T15 (HIGH): the privacy export bundle had no stops field at all, so backups never contained stops and runRestoreDrill compared two exports that both omitted them — a green drill over a restore that loses every stop on every beat, i.e. the route planner comes back empty. F-T12: a customer-requested callback was never dialled once the lead hit maxAttempts, though the UI showed it scheduled. F-T09/F-T10: ringSeconds governed nothing and an abandoned call stranded its lead in_call forever with no recovery path. F-T11: re-posting a lead id overwrote attempts, dnc and callbacks. F-T13: the documented week-long review snooze was unreachable. F-T14: route-sequence enforcement counted check-ins from any day. | F-T09..F-T15 | Analytics export consolidated onto the shared csv.ts writer | None | Pass 3 + verification sweep
E032 | 2026-09-13 11:00 | REVIEW | D13 GATE MET — 21 suites / 718 tests (38 new), 100% across statements/branches/functions/lines, zero pragmas. Story position deliberately unchanged at 98/100 (391/399): correctness release. | D13 | Traceability untouched by design | None | Pass 3: GAP-T3 server entry + DB schema, then the external verification sweep vs live Zoho docs (R-T5 webhook signing is still an assumption)
E033 | 2026-09-13 11:07 | REVIEW | GAP-T3 CLOSED — src/server.ts (settings from env, store, real HTTPS transports for Zoho CRM and the OAuth token endpoint, listen) plus bin/telefield.js as the process entry, kept outside src/ so npm start exists without an untestable branch or a coverage pragma. The server was started for real on a port and /healthz, /pricing and /status.json were fetched over a socket — the first time in the product's life that happened. R-T4: migrations/001-004 shipped with cascade deletes from orgs (so the F-T01 sweep is one DELETE) and npm run migrate, which dry-runs in CI without a database. The Postgres ADAPTER itself is still not built — stated, not implied away. | GAP-T3,R-T4 | GAP-T3 closed; R-T4 half closed (schema yes, adapter no) | A restart still loses data until the adapter exists | Postgres adapter, or accept in-memory for the pilot
E034 | 2026-09-13 11:07 | REVIEW | EXTERNAL VERIFICATION SWEEP vs live Zoho documentation. VER-T1 LIVE-BLOCKING: R-T5 had our webhook signing scheme as an assumption since S1. The construction matched but the wire format did not — Zoho sends X-Zoho-Webhook-Signature with a v= component and its published example timestamp is in MILLISECONDS, while we read X-TeleField-Signature, s=, and compared a ms value against seconds. Every inbound webhook would have failed the replay guard with a 400, including extension.uninstalled, which is what wipes tokens and starts the retention clock. Invisible to the suite because our tests sign their fixtures with our own signer. VER-T2: ApiTransport had no headers field, so Retry-After and X-API-CREDITS-REMAINING could not be read — Zoho rate-limits on credits over a rolling 24-hour window plus concurrency, so blind backoff burns the budget it exists to protect. VER-T3: Zoho Sigma triggers include disable, enable and update; v012 answered "ignored" to all three, so a DISABLED extension kept its tokens and we kept serving and billing an org that had switched us off. | VER-T1,VER-T2,VER-T3,R-T5 | R-T5 closed by verification; webhook format corrected, headers honoured, lifecycle events handled | None | Live dev-org sweep confirms VER-T1 on the day
E035 | 2026-09-13 11:07 | REVIEW | D13 GATE MET — 22 suites / 756 tests (38 new), 100% across all four metrics, zero pragmas. A jest config gap was closed in passing: the build output under dist/ was being collected as a second copy of every suite. Story position unchanged at 98/100 (391/399). | D13 | — | None | Senthil dispositions + live dev-org (LC-1)
E036 | 2026-09-13 11:32 | REVIEW | REACHABILITY AUDIT — asked which functions anything actually calls, a question nine sprints never asked. Four answers were "only the tests": F-T17 CRITICAL sweepDeletions/runDeletionSweep had no route, no timer, no caller, so the 30-day retention promise on the trust page would never once have run (built S1, corrected v013, still unreachable); F-T20 processOutbox only ran when a human POSTed /sync/retry though help article ha-11 and the status page both say outcomes sync automatically on recovery; F-T18 broadcastOutage (ST-091 degradation comms) was never triggered; F-T19 createBackup ran in CI over fixtures and never over real data. Dunning, chat SLA, partner nudges and alerts had operator routes but no schedule. | F-T17,F-T18,F-T19,F-T20 | New src/scheduler.ts wired into the server; store.listOrgs added | None | Live sweep on the dev org
E037 | 2026-09-13 11:32 | REVIEW | PUBLISHED-CLAIMS AUDIT — F-T16 CRITICAL: "OAuth tokens and secrets are encrypted at rest (AES)" appears on the trust page, in two help articles, at /meta/data-flows and in the ST-068 evidence pack. Nothing encrypted a token. src/crypto.ts was called from exactly one place — the evidence pack, which encrypted the literal "refresh-token-value", decrypted it and reported the control as passing. Tokens sat in the store, the export bundle and every backup in plaintext; crypto.ts had always named SECRETS_KEY in its own error and config had never had one. Fixed with src/tokenVault.ts sealing on the install and refresh write paths, production refusing a plaintext token outright, SECRETS_KEY a boot prerequisite, and SEC-02 rewritten to exercise the real seal. | F-T16 | Trust page copy updated to match behaviour, incl. the new scheduled-sweeps section | None | Pen-test evidence archive
E038 | 2026-09-13 11:32 | REVIEW | TWO PORTABLE CI GATES — a reachability gate asserting 15 named behaviours have a production call site, and a published-claims gate asserting that if the copy says "encrypted at rest" a seal is wired, if it says "syncs automatically" something drains on a schedule, and if it says deletion is scheduled a sweep is scheduled. These fail on the CLASS, not the instance, and are portable to the other products in the portfolio — the sibling pass-5 pattern. | GATE-1,GATE-2 | tests/review_pass4.test.ts | None | Port both gates to the other 10 products
E039 | 2026-09-13 11:32 | REVIEW | GAP-T4/GAP-T5 CLOSED — npm run sweep: a scripted 12-step live verification (9 automated, 3 operator, non-zero exit so it can gate a deploy), executed against a real running instance and returning SWEEP GREEN; and docs/DEV_ORG_SETUP.md, the 30-minute dev-org guide, now executable end to end because a server exists. The guide states plainly that the Postgres adapter is still unbuilt and a restart loses data — the pilot decision is Senthil's, and the trust page should say whichever is true. | GAP-T4,GAP-T5,R-T4 | LC-1 is now turnkey up to the Zoho-side steps | R-T4 adapter still open | Senthil: dev org + sweep
E040 | 2026-09-13 11:32 | REVIEW | D13 GATE MET — 23 suites / 864 tests (108 new), 100% across all four metrics, zero pragmas, verified from the packaged zip in a clean clone plus a migration dry run. Story position unchanged at 98/100 (391/399): four sprints of review have added no stories and removed no doubt about what was already claimed. COLD REVIEW COMPLETE — 23 defects and 6 artifact gaps, every one in code shipped at 100% coverage under a FINAL label. | D13 | — | None | Live evidence, dispositions, or porting the gates
E041 | 2026-09-13 11:38 | REVIEW | CROSS-PRODUCT CLASS SWEEP — F-T21 CRITICAL: /oauth/callback had no state parameter, so the install had no CSRF protection whatever (OnCall F-015 class); F-T22: it took org_id straight from the query string, so the caller declared which org the freshly exchanged tokens belonged to — an attacker-supplied callback URL could bind their Zoho org into a victim's install or the reverse. Fixed with /oauth/start minting a single-use ten-minute HMAC-signed state; the callback now takes the org from the state it signed and refuses unsigned installs outside development. F-T23: /demo/reset wiped and reseeded the shared demo tenant with no authentication at all — operator token now required when configured, and production cannot boot without one. | F-T21,F-T22,F-T23 | New src/oauthState.ts; OPERATOR_TOKEN added to config and to the deploy prerequisites | None | Live install exercises the state path on the day
E042 | 2026-09-13 11:38 | REVIEW | TWO SIBLING CLASSES CHECKED AND FOUND CLEAN — cross-tenant isolation (MeetSync M-F04 / OnCall F-014: an owner of one org addressing another org is rejected, and sees only its own data) and Express rejected-promise handling (MeetSync M-F21: a throwing handler returns 500 rather than hanging the request open). Both are now pinned by tests so "we checked once" becomes "it stays true". Clean is a finding too, and worth recording as such. | M-F04,M-F14,M-F21 | tests/review_pass5.test.ts | None | Same two checks when porting to siblings
E043 | 2026-09-13 11:38 | REVIEW | GATE-3 + PORTING GUIDE — the public surface is now pinned: every route that skips guarded() must appear in an explicit list with a reason, and two companion assertions check each public route answers without credentials and echoes no customer data. docs/REVIEW_GATES.md documents all three gates, what each catches, how to port it in about twenty minutes, and what they do NOT cover — verification against live platform docs, which is where every product that looked found its live-blocking defect. | GATE-3 | docs/REVIEW_GATES.md | None | Port GATE-1/2/3 across the portfolio (R-T9)
E044 | 2026-09-13 11:38 | REVIEW | SWEEP RE-RUN — npm run sweep gained SW-09b (an unsigned install must be refused and /oauth/start must mint a state) and was executed against a live instance booted in staging mode, where the install-state requirement is active: SWEEP GREEN, 10 automated checks, 3 operator steps. The setup guide now documents OPERATOR_TOKEN and the /oauth/start step. | GAP-T4,GAP-T5 | docs/DEV_ORG_SETUP.md + scripts/sweep.js | None | Senthil: dev org
E045 | 2026-09-13 11:38 | REVIEW | D13 GATE MET — 24 suites / 899 tests (35 new), 100% across all four metrics, zero pragmas, verified from the packaged zip in a clean clone. Story position unchanged at 98/100 (391/399). Five review passes total: 26 defects and 6 artifact gaps, every one in code shipped at 100% coverage under a FINAL label; 3 portable gates now defend the classes rather than the instances. | D13 | — | None | Live evidence, dispositions, or porting
E046 | 2026-09-13 11:55 | R-T4 | POSTGRES INSTALLED AND MIGRATIONS RUN FOR REAL — the schema shipped in v015 had never been executed against a database. It applied cleanly and is idempotent on a second run, which is now a CI step rather than a claim. Migration 005 added the state the earlier four missed: pause flags, mutes, alert and scorecard config, review prompts, design partners, feature-use counters and one-shot dedupe flags — the rows a reviewer does not think of but the running process keeps. | R-T4 | migrations/005_state.sql | None | Adapter
E047 | 2026-09-13 11:55 | R-T4 | ADAPTER BUILT — src/pgStore.ts extends InMemoryStore: reads stay synchronous (the whole product is built on a synchronous Store interface), every mutation is queued and drained to Postgres, and hydrate() loads state at boot through the same writers with persistence suppressed, so there is one write path rather than two that drift. Trade-offs stated rather than discovered: write-behind flushed per request means a crash strictly between a mutation and its flush loses that one in-flight request; and it is single-writer, so blue/green must drain blue before green takes writes. Both are in the setup guide. | R-T4 | src/pgStore.ts, server hydrate + flush wiring | Single-writer constraint on blue/green | Live pilot
E048 | 2026-09-13 11:55 | R-T4 | TWO DEFECTS FOUND ONLY BECAUSE THE DATABASE WAS REAL — PG-1: scorecard_history.day is a DATE column, so the driver returns a JS Date; String()-ing it produced "Tue Sep 01" and silently corrupted every scorecard row on restart. A mocked client would have returned whatever the mock was told to. PG-2: the durability flush had been wired into guarded() only, and the two routes that matter most on install day are public — the OAuth callback that stores tokens and the webhook that processes uninstall. Their writes sat in the queue until the next sweep, so a crash or deploy within the minute lost the install. Found by running the live sweep against Postgres and seeing webhook_events still empty. | PG-1,PG-2 | Both fixed with pinned regressions; public mutating routes now flush | None | —
E049 | 2026-09-13 11:55 | R-T4 | VERIFIED END TO END — the server was booted in staging mode against real Postgres: /healthz answered, npm run sweep returned SWEEP GREEN, and a signed webhook write was confirmed present in the database immediately rather than a tick later. The contract suite writes a full tenant (33 entity types), flushes, builds a SECOND store on the same database, hydrates it, and compares privacy export bundles byte for byte — the promise a customer actually cares about, which is that the deploy did not lose their data. | R-T4 | tests/pg_contract.test.ts (7 tests), CI postgres job | None | Senthil: provision Postgres
E050 | 2026-09-13 11:55 | R-T4 | D13 GATE MET — 24 suites / 902 tests at 100% on all four metrics, zero pragmas, plus a separate database-backed suite at 100% on src/pgStore.ts. That file is excluded from the default coverage set BECAUSE a mocked database proves nothing about SQL; the exclusion is documented in jest.config.js and the CI postgres job enforces the real gate. Both verified from the packaged zip in a clean clone. Story position unchanged at 98/100 (391/399). | D13 | jest.pg.config.js, ci.yml postgres job | None | Live evidence
E051 | 2026-09-13 16:24 | REVIEW | GAP-T6 FOUND — the traceability matrix has a "Primary screen" column filled in for all 100 stories: SCR-1 Onboarding (6), SCR-3 Call workspace (10), SCR-4 Rule builder (10), SCR-5 Planner (10), Mobile/SCR-5 (10), SCR-6 Settings (7), SCR-7 Billing (7), SCR-8 Analytics (10), SCR-1/SCR-9 Help (7), plus 8 "All surfaces" and 8 listing rows. Ninety-two of those stories are Done-in-code. The codebase rendered exactly one screen — the next-call widget. So "As a Sales head, I can set up X with sensible defaults in one screen" was true of an API endpoint and of nothing a customer could look at, and the ST-093/094 listing screenshots would have had nothing to photograph. VoiceBridge GAP-V2 and TestPulse's missing Custom UI resource are the same class. | GAP-T6 | Found by reading the tracker against the code, not the code against itself | Listing assets were unobtainable | Build them
E052 | 2026-09-13 16:24 | REVIEW | EIGHT SCREENS BUILT — src/screens.ts renders onboarding, call workspace, rule builder, planner, mobile route, settings, billing, analytics and help as server-side semantic HTML. Each renders from the SAME view-model its JSON route serves (buildChecklist, queueSummary+computeMetrics, getRules+getQueueConfig, planRoute, getBillingView+getUsage, computeHealthScore+computeTeamScorecard, HELP_ARTICLES+searchHelp), so a screen cannot drift from the behaviour it displays. Every screen is role-gated through the same guard as its data, shows real empty states rather than blank pages, and escapes org data (a lead named "Asha Traders, Chennai & Co" is pinned). | GAP-T6,ST-089 | src/screens.ts + 9 routes | None | Live render on the dev org
E053 | 2026-09-13 16:24 | REVIEW | ST-089 WIDENED — the WCAG AA audit ran on one screen because one screen existed. It now runs on every render of all nine, plus the public pricing, trust and status pages, and assertAccessible still fails the request rather than serving inaccessible markup. GATE-4 added: every screen named in the specification must return 200 for its role, render its heading, and audit clean — the class, not the instance. Documented in docs/REVIEW_GATES.md alongside the other three gates, and the screen table is in docs/DEV_ORG_SETUP.md as the surfaces to photograph for the listing. | GATE-4,ST-089 | docs updated | None | Port GATE-1..4 to the siblings
E054 | 2026-09-13 16:24 | REVIEW | D13 GATE MET — 25 suites / 952 tests (50 new), 100% across all four metrics, zero pragmas, verified from the packaged zip in a clean clone. Story position deliberately unchanged at 98/100 (391/399): the screens make the Done-in-code claims true rather than adding scope, and the live-render half still belongs to the dev org. | D13 | — | None | LC-1
E055 | 2026-09-13 16:35 | REVIEW | F-T24 FOUND BY READING LC-5 AGAINST THE CODE — "mobile flows tested offline-first" against the three batch endpoints (/mobile/sync, /mobile/checkins, /mobile/visits). All three called recordClientRefOnce BEFORE applying the item, so the reference was consumed by a FAILED attempt. A rep on a dead network whose outcome referenced a call the server had not yet seen got "rejected" once and "duplicate" forever after — the record silently gone, on the one path whose entire purpose is not losing records. Fixed: the reference is claimed only on success, with a non-consuming hasClientRef check first. Genuine retransmits still dedupe. | F-T24,LC-5 | store.hasClientRef added | None | Live mobile test on the dev org
E056 | 2026-09-13 16:35 | REVIEW | GAP-T7 CLOSED — LC-3 (listing screenshots, ST-093/094) has been In progress since v009 for two reasons: until v019 there were no screens, and then capturing them meant installing the extension and driving a browser. npm run assets renders all nine screens from the isolated demo tenant at a fixed clock into assets/ with an index in capture order — no install, no dev org, no customer data in the shots, byte-identical on repeat runs. Audited on render and re-checked in CI, so a screen that stops rendering fails the build instead of the capture session. | GAP-T7,LC-3,ST-093,ST-094 | scripts/assets.js + CI step + asset plan preamble | None | Senthil captures at listing sizes
E057 | 2026-09-13 16:35 | REVIEW | OBS-T7 LOGGED, NOT QUIETLY FIXED — the demo tenant produces a health score of 45.5 ("watch") on SCR-8, which is what a prospect sees in the demo and what the analytics screenshot would show. Enriching the demo seed to look healthier is a product decision, not a code one, so the data was left alone rather than tuned to flatter a screenshot. | OBS-T7 | Noted in docs/ASSET_PLAN_SCREENSHOTS_VIDEO.md | Listing asset may undersell | Senthil decides
E058 | 2026-09-13 16:35 | REVIEW | D13 GATE MET — 26 suites / 982 tests (30 new), 100% across all four metrics, zero pragmas, verified from the packaged zip in a clean clone together with the asset check. Story position unchanged at 98/100 (391/399). | D13 | — | None | LC-1 dev org
E059 | 2026-09-13 16:41 | REVIEW | EVIDENCE COLUMN AUDITED — the same technique as passes 6 and 7, applied to what every story cites as its proof. All 100 rows carry evidence naming modules, routes and documents; 27 modules, 34 routes and 8 documents were extracted and checked against v020. Every one resolves. A clean result, logged as CLEAN-3 rather than left unrecorded, so the next reviewer knows it was checked and does not repeat it. | CLEAN-3 | docs/EVIDENCE_MAP.json generated from the tracker | None | Keep the map regenerated at each tracker release
E060 | 2026-09-13 16:41 | REVIEW | GATE-5 ADDED — citations are now pinned: every module a story cites must exist, every route must be registered in app.ts (parameters normalised, which the first draft of the gate got wrong and reported nine healthy routes as missing), every document must be on disk. The failure this prevents is ordinary and quiet: a refactor deletes a module and a hundred tracker rows go on pointing at it as evidence. Fifth portable gate; porting notes in docs/REVIEW_GATES.md. | GATE-5 | tests/review_pass8.test.ts | None | Port GATE-1..5 across the portfolio
E061 | 2026-09-13 16:41 | REVIEW | GAP-T8 CLOSED — DR-12 reads "second reviewer walks the pack end-to-end and signs". There was no pack. The dry run reported READY on 11/11 automated checks because it verified the six documents someone had thought to list, and DR-12 sat as a human item pointing at an artifact nobody had written — the blocker on ST-097 and on Senthil's DR-12 queue item. docs/REVIEW_PACK.md now exists: what the product is, how to run it in ten minutes, where to look, the full eight-pass review history with the coverage lesson stated plainly, the five standing gates, the deliberate exceptions, the seven open observations, and what would be most useful from the reviewer. DR-16 added so the dry run fails without it. | GAP-T8,ST-097,DR-12 | docs/REVIEW_PACK.md + DR-16 | None | Senthil nominates the reviewer
E062 | 2026-09-13 16:41 | REVIEW | DR-15 CORRECTED — it still said screenshots need the S1-10 Zoho org. Since v020 npm run assets renders all nine screens from the demo tenant, so only the capture itself is human work. A dry-run item that overstates a blocker is the same class of untrue statement the published-claims gate exists to catch, so it was fixed rather than left as a harmless inaccuracy. | DR-15,ST-094 | — | None | Capture at listing sizes
E063 | 2026-09-13 16:41 | REVIEW | D13 GATE MET — 27 suites / 1,183 tests (201 new, mostly the per-story evidence gate), 100% across all four metrics, zero pragmas, verified from the packaged zip in a clean clone together with the asset check. Story position unchanged at 98/100 (391/399). | D13 | — | None | LC-1 dev org, DR-12 reviewer
E064 | 2026-09-13 16:48 | GATES | GATE KIT EXTRACTED — the five gates lived as TeleField jest tests importing TeleField modules, so "port them to the other ten products" meant copying TypeScript and rewiring it ten times. scripts/review-gates.js is plain Node with no product imports, no TypeScript and no test framework; every product-specific fact lives in review-gates.config.json (source dir, the behaviours that must be reached, the published sentences and the code patterns that make them true, the deliberately public routes, the screens the tracker names, the evidence map). A test asserts the script contains neither "TeleField" nor "Zoho" outside comments, so the portability claim cannot rot. | R-T9,R-T15 | scripts/review-gates.js + review-gates.config.json + npm run gates in CI | None | Copy both files into a sibling and edit the config
E065 | 2026-09-13 16:48 | GATES | MUTATION TEST — the gates are now proved by breaking what they watch in a throwaway copy of the repo: the retention sweep unwired from the scheduler, the token seal removed from the install path, an unguarded route added, a specified screen removed, a cited module deleted. TWO OF THE FIVE PASSED WHILE BROKEN on the first run. Reachability counted a call from inside the defining module, so a dead wrapper calling a dead function looked alive — exactly the F-T17 shape it exists to catch. The claims gate matched sealTokenSet anywhere in src, so the refresh path satisfied a claim about the install path. Fixed: cross-file call sites required (with an explicit sameModuleAllowed list), and claim patterns can be scoped with inFile. A gate that cannot fail is a green light nobody checked. | GATE-1,GATE-2 | tests/review_gates.test.ts | None | Step 4 of the porting instructions is now mandatory: break something and watch the right gate go red
E066 | 2026-09-13 16:48 | GATES | D13 GATE MET — 28 suites / 1,192 tests, 100% across all four metrics, zero pragmas; npm run gates, npm run assets --check and the full suite all verified from the packaged zip in a clean clone. Story position unchanged at 98/100 (391/399). | D13 | — | None | Senthil: LC-1 dev org, DR-12 reviewer, port the kit
E067 | 2026-09-13 17:23 | REVIEW | F-T25 — v016 made the daily backup RUN, and stopped there: createBackup built the bundle, the scheduler kept sha256 and threw the bundle away. ST-090 promises backup and restore; what existed was a hash of data that no longer existed anywhere. The restore drill passed the whole time because it restores from a bundle held in memory during the test. Fixed: writeBackup persists to BACKUP_DIR, reads the file back and verifies its integrity before reporting success (a write that silently truncated is precisely the failure a backup must not have), prunes to the last 14, and the sweep report now carries the file path. A directory that cannot be written is reported as a job error rather than swallowed. | F-T25,ST-090 | src/backup.ts writeBackup/latestBackup; BACKUP_DIR documented | BACKUP_DIR must point at storage that is not the database host | Senthil: point BACKUP_DIR at mounted or object storage
E068 | 2026-09-13 17:23 | REVIEW | GAP-T9 — the blue/green workflow was written in S8, before there was a database or a persistent store. It ran no migration, so a deploy carrying a schema change would have started green against a database without it; and it switched traffic with both slots live, which the write-behind single-writer store cannot survive — two processes over one database diverge in memory and the loser's queued writes vanish. Added: a migrate job before green serves, and an explicit "drain BLUE, confirm idle, then switch" step with blue kept warm READ-ONLY for rollback. Removed the phrase "zero-downtime": the drain is a short write pause by design, and describing it otherwise is the same class of untrue statement the published-claims gate exists to catch. | GAP-T9,R-T13,ST-092 | .github/workflows/deploy.yml + setup guide | Rollback also requires draining green first | Live verification on the first real deploy
E069 | 2026-09-13 17:23 | REVIEW | GATES EXTENDED — writeBackup joins the reachability list and "backups" joins the published-claims list, so the specific defect F-T25 represents cannot return quietly. Test isolation fixed in passing: the scheduler now writes real files, so every suite gets a throwaway BACKUP_DIR rather than dropping backups into the repo. | GATE-1,GATE-2 | review-gates.config.json, tests/setup-env.ts | None | Port
E070 | 2026-09-13 17:23 | REVIEW | D13 GATE MET — 29 suites / 1,225 tests (33 new), 100% across all four metrics, zero pragmas; suite, review gates and asset check all verified from the packaged zip in a clean clone, which also confirms no stray backup files ship in the artifact. Story position unchanged at 98/100 (391/399). | D13 | — | None | LC-1 dev org, DR-12 reviewer
E071 | 2026-09-13 17:30 | REVIEW | GAP-T10 CLOSED — ST-088 has always been half a story: tests/load.test.ts drives 300 mixed requests in-process and states honestly that supertest "approximates the app+store path only". That was the best measurement available with no server; one has existed since v015. scripts/loadtest.js drives real HTTP across a sales-floor profile (queue reads, screens, billing, status) and gates on error rate and p95. LOAD_FIXTURE_ORG seeds the demo dataset under a chosen org id AT BOOT so the guarded routes can be driven — explicitly refused in production, and reachable by no route, because a fixture that can be requested at runtime is a backdoor. | GAP-T10,ST-088 | scripts/loadtest.js, LOAD_FIXTURE_ORG, CI load step | Network/TLS/host effects still need the production box | Live run at deploy
E072 | 2026-09-13 17:30 | REVIEW | MEASURED — 50 rps: p95 2.0ms. 250 rps: p95 1.8ms. 500 rps for 6s: p50 0.8ms, p95 3.7ms, p99 11.8ms, zero errors. 200 rps for 20s with the scheduler ticking every 1.5s: p95 1.4ms, zero errors — sweeps do not disturb request latency at this size. The web surface budget is 300ms, so the product is two orders of magnitude inside it and headroom is not the launch risk. Numbers recorded in docs/DEV_ORG_SETUP.md with their conditions, because a benchmark without its conditions is a boast. | ST-088 | docs/DEV_ORG_SETUP.md | None | Re-measure on production infra
E073 | 2026-09-13 17:30 | REVIEW | F-T26 — the scheduler does retention, outbox drain, dunning, SLA, alerts, outage comms and backups, and its report (per-job errors included) lived in memory, exposed nowhere. A sweep erroring on every tick was indistinguishable from one working. Found while trying to diagnose why a backup had not appeared during a load run — with no way to ask the running process, the answer took three attempts. GET /ops/sweeps, operator token required, returns the last report and its error count; the public-surface gate immediately caught the new unguarded route and made me declare it with a reason, which is the gate doing its job. | F-T26,GATE-3 | src/app.ts /ops/sweeps; SWEEP_INTERVAL_MS env for operators and load runs | None | Check it after every deploy
E074 | 2026-09-13 17:30 | REVIEW | GAP-T11 — bin/telefield.js runs the COMPILED output and did so silently. During this session it served a previous build while I was editing source and drew a wrong conclusion from it twice. In production the same thing presents as "the deploy did nothing". The entry point now compares src against dist and refuses to start on a stale or missing build with a one-line message. A tooling gap that cost thirty minutes here would cost far more on launch day. | GAP-T11 | bin/telefield.js | None | —
E075 | 2026-09-13 17:30 | REVIEW | D13 GATE MET — 30 suites / 1,261 tests (36 new), 100% across all four metrics, zero pragmas. Suite, review gates and a live 200-rps load run all verified from the packaged zip in a clean clone. Story position unchanged at 98/100 (391/399). | D13 | — | None | LC-1 dev org, DR-12 reviewer
E076 | 2026-09-13 19:26 | REVIEW | VER-T4 CRITICAL, LIVE-BLOCKING — the authorization-code exchange sent grant_type, client_id, client_secret and code, and no redirect_uri. Zoho's published parameter table marks it required for grant_type=authorization_code and answers ERROR_invalid_redirect_uri (or invalid_code) without it, so the first real install would have failed and the failure would have looked exactly like a wrong client secret. Fixed: ZOHO_REDIRECT_URI is now a setting, sent on the exchange, and mandatory at boot in production — checked after the existing secrets so the fail-closed error order is unchanged. Invisible to 1,261 tests because every test injects its own transport and asserts what we do with the response; nothing had ever asserted what we send. | VER-T4,ST-051 | src/zohoAuth.ts exchangeCode; src/config.ts ZOHO_REDIRECT_URI | Must match the console registration exactly, trailing slash included | Set ZOHO_REDIRECT_URI with the Zoho creds
E077 | 2026-09-13 19:26 | REVIEW | VER-T5 CRITICAL, LIVE-BLOCKING for every customer outside our default DC — the data centre was a property of OUR deployment. Zoho appends location and accounts-server to every install callback and requires the token exchange, every refresh and every API call to use that customer's DC; we read one process-wide ZOHO_DC, so a US install from a public listing would have had its authorization code POSTed to accounts.zoho.in. Built src/zohoDc.ts (verified host registry), migrations/006_dc.sql (orgs.dc), per-org routing through exchange, refresh and API host. Two deliberate rules: a DC we do not serve (CA, CN, UK, SA — whose host shapes break the accounts.zoho.<dc> pattern) is REFUSED at the callback with a named error rather than sent to a guessed hostname; and accounts-server, being an attacker-controllable parameter on a public route, is matched against the registry and never used as a URL — otherwise a crafted callback could choose where our client secret is POSTed. | VER-T5,ST-051,ST-055,LC-4 | src/zohoDc.ts, migrations/006_dc.sql, src/app.ts callback, src/zohoClient.ts host threading | Enable Multi-DC in the API console before a global listing; each DC issues its own client secret | Confirm the DC list at dev-org setup
E078 | 2026-09-13 19:26 | REVIEW | VER-T6 — the marketplace asset plan had been written to assumed specs. Zoho publishes extension logo 120x120 and banner 310x142 (.gif/.jpeg/.jpg/.png), a MAIN screenshot showing the components the extension adds inside Zoho CRM, a video supplied as an iframe link, and a developer branding block (company logo 120x120, address, description, contact number and email). Zoho publishes no screenshot pixel size, so 1280x800 stays but is now labelled as our own standard rather than a platform rule. The superseded numbers were removed from the capture sheet rather than left in a 'was/is' column: a sheet that still prints the wrong dimensions is how the wrong dimensions get captured. The plan also still said capture needs the live dev org, which DR-15 corrected in v021 — the same untrue-statement class one document downstream. | VER-T6,ST-094,LC-3 | docs/ASSET_PLAN_SCREENSHOTS_VIDEO.md | Screenshot count is set by the submission form; five is our plan, trim if it caps lower | Capture at the published sizes
E079 | 2026-09-13 19:26 | REVIEW | VER-T7 — Zoho's published approval criteria fail a listing that does not disclose third-party accounts the extension requires, the data transferred on install, edition compatibility, and how support is provided. The listing copy carried none of the four, and TeleField's telephony bridge needs the customer's OWN Exotel/Ozonetel-class account with its own charges. Four disclosures added to the copy and, rather than a note nobody re-reads at submission, gated by a new automated dry-run check DR-17 — mutation-tested, so removing any one turns the run NOT READY and names it. A listing rejection costs a full review cycle. | VER-T7,ST-093,DR-17,LC-2 | docs/LISTING_COPY_AB.md, src/submissionDryRun.ts | Edition statement (Standard and above, API access) needs your confirmation against the plan you sell | Ratify the disclosure wording with the ST-093 pick
E080 | 2026-09-13 19:26 | REVIEW | GAP-T12 — the restart proof was incomplete. 'A full tenant survives a restart byte for byte' compared privacy export bundles, and the bundle omits seven datasets by design (OBS-T5): outbox, support conversations, design partners, review-prompt state, alert config, feature-use counters, latency samples. Those were proved only by whichever ad-hoc spot-check someone had remembered — the F-T15 shape one level up, where a drill compares two exports that both omit the same thing. Now every dataset a tenant owns is snapshotted through the Store's own readers and compared across a real restart, plus a table census that fails the moment a migration adds a table the seed does not exercise. No hydration defect was behind the gap; one real mismatch was, and the existing test caught it: an org written with no dc came back as dc=null, so absent and null are now normalised at the store boundary. | GAP-T12,OBS-T5,R-T4 | tests/pg_contract.test.ts fullSnapshot + table census; src/store.ts upsertOrg | The census only forces the seed to be extended; the fidelity compare is what catches a missing hydrator | Port the fidelity shape to siblings with adapters
E081 | 2026-09-13 19:26 | REVIEW | CLEAN-4 — concurrency and the documented crash boundary probed against real Postgres, and both hold. Twenty overlapping writes all reached the database with memory and disk agreeing afterwards; a duplicate client reference submitted twice simultaneously came back applied-once/duplicate-once with exactly one flag row (F-T24 under race conditions); a crash strictly between a mutation and its flush lost exactly that request and nothing before it; writes queued DURING a flush are drained by it rather than stranded behind it. Recorded as a finding so the next reviewer does not have to rediscover that it was checked. Honest limit: driven through the handler stack rather than over a socket, so it proves the interleaving at the await boundary, not kernel-level socket behaviour. | CLEAN-4,R-T13,R-T14,F-T24 | tests/pg_contract.test.ts pass-11 sections | Single-writer remains a design constraint, not a bug | Blue/green still drains blue first
E082 | 2026-09-13 19:26 | MEASURE | MEASURED WITH A REAL DATABASE BEHIND THE WRITE PATH — every load number TeleField held was taken against the in-memory store; v024 measured the socket but not the database. Against Postgres 16 with the per-request durability flush live: 200 rps for 15s at p50 0.6ms / p95 1.1ms, and 500 rps for 8s at p50 0.6ms / p95 5.2ms / p99 23.9ms, zero errors at both. 6,127 latency rows were durably written during the runs, which is the evidence the flush actually ran under load rather than quietly degrading. In-memory 500 rps was p95 3.7ms, so the real database costs about 1.5ms at p95 at this size — still two orders of magnitude inside the 300ms web budget. Conditions recorded with the numbers, because a benchmark without its conditions is a boast. | ST-088,R-T4 | scripts/loadtest.js against bin/telefield.js + Postgres 16 | Local loopback and a local database; production network, TLS and managed-Postgres latency are still unmeasured | Re-measure on production infra
E083 | 2026-09-13 19:26 | REVIEW | GAP-T13 — the load harness's own header example (BASE_URL=... ORG=load node scripts/loadtest.js) defaulted LOAD_USER to 'load-owner', which is a member of no org the fixture seeds; run as written it returned 87.5% 401s. The setup guide and CI both pass LOAD_USER=demo-owner, so the recorded numbers were sound — but the instruction nearest the code was the wrong one, and that is the instruction people copy. Default corrected to the fixture's actual owner. | GAP-T13,ST-088 | scripts/loadtest.js | None | —
E084 | 2026-09-13 19:26 | REVIEW | OBS-T9 for your disposition — Zoho's published payments page states commission is paid monthly, only when the outstanding balance exceeds USD 100, and roughly 15 working days after you approve the payout; it also says that for extension developers the total value and the commission are equal, which sits oddly beside the 15% marketplace share assumed in R-T3. Not a code change and not guessed at: it changes the cash timing behind the G-02 ten-paying-installs gate and should be confirmed at partner onboarding. | OBS-T9,R-T3,G-02 | docs review only — no code change | Revenue-share assumption in the model may be wrong in our favour or against it | Confirm at partner console setup
E085 | 2026-09-13 19:26 | REVIEW | D13 GATE MET — 31 suites / 1,302 tests at 100% across all four metrics, zero pragmas, plus the database-backed contract suite at 38 tests and 100% on the adapter. Suite, npm run gates (all five GREEN), npm run assets and a live 500-rps load run all verified from the packaged v025 zip in a clean clone against a real Postgres. One unused helper was deleted rather than pragma'd when it showed up uncovered. Story position unchanged at 98/100 (391/399) — this is a correctness release, not a story release. | D13 | — | None | LC-1 dev org (now needs ZOHO_REDIRECT_URI), DR-12 reviewer, port the gate kit
E086 | 2026-09-13 19:56 | REVIEW | GAP-T14 CRITICAL — THE EXTENSION DID NOT EXIST. Twelve passes in, the question nobody had asked was what a customer receives when they click Install. A Zoho CRM extension is a Connected App plus an uploaded resource bundle: plugin-manifest.json and an app/ folder that Zoho hosts and frames at the widget locations declared in the developer console (telephony, related list, settings widget, web tab, custom button, business card). TeleField had nine server-rendered screens and no bundle, and the setup guide's console step stopped at the connection and the webhook — so the install would have completed, the tokens would have been stored, and a Zoho reviewer opening CRM would have seen nothing at all. The same class as OnCall's missing HTTP app and TestPulse's missing Custom UI resource: coverage over modules proves the modules work, not that a product exists. | GAP-T14,LC-1,LC-2 | src/extension.ts, scripts/package-extension.js, extension/, dist/telefield-extension.zip | The console declarations themselves are operator work — the bundle makes them a copy-paste rather than an authoring session | Upload the bundle, declare the four widgets
E087 | 2026-09-13 19:56 | BUILD | THE BUNDLE IS GENERATED, NOT MAINTAINED — npm run extension writes the manifest and four widget bootstraps from src/extension.ts, and npm run extension -- --check runs in CI and fails when the committed folder drifts. Bound to the code it describes by tests: every widget frames a screen route that is registered in app.ts, the whitelisted host and the CSP connect-src are the host the bootstraps actually call (a bundle built for one host cannot be pointed at another), the declared locales are the EN/HI/TA the listing promises, and the scopes travelling with the bundle are SCOPE_MANIFEST rather than a second list someone would have to remember to update. Each bootstrap is deliberately thin — Zoho hosts these files on a release cadence we do not control, so the screens stay on our server where a fix is a deploy — and each renders a readable failure instead of an empty iframe, because an extension that shows nothing is what a reviewer files as broken. | GAP-T14,ST-064,LC-3 | tests/review_pass12.test.ts; npm run extension in CI | Placeholder 1x1 logo ships until the real 120x120 is captured (VER-T6); the check names it | Replace app/img/logo.png before publishing
E088 | 2026-09-13 19:56 | REVIEW | F-T27 CRITICAL — THE SCREENS COULD NOT BE OPENED BY A BROWSER. Caller identity came from a request header (F-T04's fix), and a framed navigation cannot set one: the widget iframe, and any browser address bar, would have received 401 from the very first request. Nine screens built in v019, audited for WCAG in v019, rendered for asset capture in v020 — and unreachable by the only client that would ever render them, because every test drives them with supertest, which sets headers by hand. The screens now also accept the same signed, org-bound session from a tf_session cookie, which is the one credential a framed navigation carries; GET /session/start makes the single hop that turns a token into that cookie. It verifies what it signed, refuses an off-host redirect (an open redirect there would hand over the token), sets Referrer-Policy: no-referrer because the token is in the URL for exactly one request, and issues SameSite=None; Secure in production — the pair a third-party iframe requires, degraded to Lax in development where Secure over localhost would mean no cookie at all. | F-T27,ST-089,GAP-T6 | src/auth.ts cookie path + sessionCookieHeader; src/app.ts /session/start | The route is public by design and is declared in both surface gates with its reason | —
E089 | 2026-09-13 19:56 | DECISION | D-T1 OPEN, DELIBERATELY NOT GUESSED — how the widget proves WHICH CRM user is looking at it. The bootstrap can read the current user from the CRM SDK, but a value read in the browser is a claim, not a credential; accepting it would rebuild F-T04, the exact defect the signed session exists to close. The two honest options are verifying Zoho's signed widget parameters server-side, or a per-install handshake using the OAuth token we already hold for that org. Both need the dev org to confirm what Zoho actually sends, so the decision waits for LC-1 rather than being invented here. | D-T1,F-T04,F-T27 | docs/DEV_ORG_SETUP.md | Until D-T1 lands, a session must be minted server-side and handed to the browser once | Decide with the dev org in hand
E090 | 2026-09-13 19:56 | REVIEW | TWO NAMED ASSUMPTIONS, ISOLATED — the manifest service string (A-X1) and the CRM SDK asset URL the bootstrap loads (A-X2) come from the extension toolkit's CRM template rather than from published documentation, and both are now the only unverified values in the bundle, sitting in one module with a confirm-at-setup instruction: zet init for CRM prints the manifest it expects. That is the containment R-T5 bought for the webhook signing format, applied before the assumption can spread — VER-T1 is what happens when it does not. | A-X1,A-X2,R-T5 | src/extension.ts | Both are one-line corrections if the console disagrees | Confirm at dev-org setup
E091 | 2026-09-13 19:56 | REVIEW | D13 GATE MET — 32 suites / 1,340 tests (38 new) at 100% across all four metrics, zero pragmas, plus the database-backed contract suite at 38 tests and 100% on the adapter. Suite, npm run gates (five GREEN), npm run extension -- --check and the Postgres contract suite all verified from the packaged v026 zip in a clean clone. The a11y palette gate caught a class in the new widget markup during this session and the public-surface gate caught /session/start — both gates doing exactly what they were built for. Story position unchanged at 98/100 (391/399). | D13 | — | None | LC-1 dev org + bundle upload, DR-12 reviewer, D-T1
E092 | 2026-09-13 20:10 | REVIEW | F-T28 CRITICAL — THE PREVIOUS RELEASE OPENED IT. v026 accepted the signed session from a cookie so a framed screen could authenticate at all; that also meant the browser would attach the credential to any request any site made, and a third-party iframe requires SameSite=None, which switches off the browser's own CSRF defence. Roughly 100 mutating routes were forgeable from a page the user merely visited: add leads, change billing, reset config. Fixed: cookie identity is honoured for GET and HEAD only, and a state-changing request must carry the x-telefield-session header — a cross-site form cannot set a header, and the widget's own fetch can. The refusal names the header instead of returning a bare 401, because the next person to hit it will be a developer. Lesson L-T2: a fix can create a defect in code it never touched (VoiceBridge L-V3), so review the release, not just the feature. | F-T28,F-T27,L-T2 | src/app.ts guarded(); tests/review_pass13.test.ts | None — page loads are unaffected, which is what F-T27 needed | —
E093 | 2026-09-13 20:10 | REVIEW | F-T29 — no browser-hardening headers existed at all, on a product that had just started serving framed HTML. Added on every response: X-Content-Type-Options: nosniff, Referrer-Policy: no-referrer (screen URLs carry the org id), and a Content-Security-Policy frame-ancestors list. Framing is a per-product judgement here rather than a blanket DENY: the screens MUST be embeddable by Zoho CRM, and by nothing else, or the widget bundle built one release ago cannot work. The host list is derived from the same DC registry as the OAuth and API hosts, so adding a data centre cannot leave its CRM host unframed — and no wildcard appears in it, which a test asserts. | F-T29,GAP-T14 | src/app.ts header middleware; src/zohoDc.ts FRAME_ANCESTORS | A reverse proxy that strips CSP would undo this — check after the first deploy | Verify headers on the live host
E094 | 2026-09-13 20:10 | REVIEW | F-T30 and F-T31 — two ordinary findings a pen-test opens with. The operator token guarding /ops/sweeps and /demo/reset was compared with !==, leaking its length and matching prefix through timing, while the webhook signature had been compared with timingSafeEqual since S1; there is now one constantTimeEquals helper and both call sites use it. Separately the 100kb body limit was a library default nobody had chosen, and the three offline batch endpoints accepted unbounded item counts inside it — each item costing a store write. Both limits are now explicit and named, and an oversized batch gets a 422 that tells the device to split the sync rather than a silent truncation or an out-of-memory. | F-T30,F-T31,LC-5 | src/auth.ts constantTimeEquals; src/app.ts MAX_BODY_SIZE/MAX_BATCH_ITEMS | 500 items per batch is a chosen ceiling — revisit if a real field device needs more | Confirm against real offline volumes at the pilot
E095 | 2026-09-13 20:10 | REVIEW | GAP-T15 — the security evidence pack was seventeen releases stale. docs/SECURITY_EVIDENCE.md, the document a marketplace reviewer reads and a pen-test vendor is handed, was a render from release v009; the submission dry run checked only that the file existed (the DR-03 shape GAP-T8 already caught once). Regenerated, and pinned by a drift test that re-runs the assessment and compares everything but the timestamp. The pack also gained SEC-07 (cookie accepted for safe methods only) and SEC-08 (nosniff, no-referrer, frame-ancestors, constant-time operator token), both asserted against the code rather than described in prose — a control that is only described is a claim, and this pack is exactly where claims get audited. | GAP-T15,ST-068,DR-03 | docs/SECURITY_EVIDENCE.md; src/securityEvidence.ts SEC-07/SEC-08 | External pen-test remains the vendor half of ST-068 | Hand the regenerated pack to the vendor
E096 | 2026-09-13 20:10 | REVIEW | D13 GATE MET — 33 suites / 1,379 tests (39 new) at 100% across all four metrics, zero pragmas, plus the database-backed contract suite at 38 tests and 100%. Suite, npm run gates (five GREEN), npm run extension -- --check and the Postgres contract suite all verified from the packaged v027 zip in a clean clone. Story position unchanged at 98/100 (391/399) — correctness again, not stories. | D13 | — | None | LC-1 dev org + bundle upload, DR-12 reviewer, D-T1
E097 | 2026-09-13 20:24 | REVIEW | GAP-T16 — THE BUNDLE PROMISED THREE LANGUAGES AND SHIPPED ONE. v026 declared locale [en, hi, ta] to the platform because the listing promises vernacular EN/HI/TA, and shipped no translation files at all. Zoho's manifest rule is explicit: every locale listed must have a matching file under app/translations. The bundle would have failed validation, and a reviewer with CRM set to Hindi would have opened a widget containing no text. Fixed with real catalogues for all three, shipped as app/translations/<locale>.json, and — the part that matters more — the manifest's locale list is now DERIVED from the catalogue keys, so a locale cannot be promised to the platform without strings behind it. The bootstrap picks the language from the CRM page it is framed in and falls back to English rather than to a blank panel. | GAP-T16,LC-3,ST-093 | src/extension.ts TRANSLATIONS/SUPPORTED_LOCALES; extension/app/translations/*.json | HI/TA widget strings are my drafts — have a native speaker read them before publishing, as with the listing copy | Native-speaker review of 4 strings x 2 languages
E098 | 2026-09-13 20:24 | REVIEW | CLEAN-5 — the data path carries Indic text correctly, and now provably. Probed with real content rather than ASCII stand-ins: a Tamil lead name through CSV import, the queue and the privacy export; a Hindi disposition label through config and application; Tamil text containing commas and quoted newlines through the RFC-4180 parser that F-T06 produced. No defect anywhere. Recorded as a clean finding and pinned, because the F-T06 class (a parser that mangles real-world data) is exactly the kind that returns through a different door, and because the asset plan asks the capturer to put a Tamil disposition in the main screenshot — that instruction is now backed by a test rather than by hope. | CLEAN-5,F-T06,ST-094 | tests/review_pass14.test.ts | None | Capture shot 1 with a Tamil disposition as planned
E099 | 2026-09-13 20:24 | REVIEW | CLAIM NARROWED — the listing said 'vernacular-ready dispositions', which reads as a shipped feature; what is true is that an org can NAME its dispositions in its own language. The copy now states precisely where vernacular support ends: listing and documentation in EN/HI/TA, data in any script, the extension's widget text in EN/HI/TA, the in-app screens English today. DISCLOSURE-LANGUAGE carries that into the listing where a buyer reads it and is gated by DR-17 alongside the other four disclosures, and a sixth claims-gate rule ties the published word 'vernacular' to the translation catalogues. Narrowing a claim is cheaper than a marketplace rejection and far cheaper than a refund conversation. L-T3. | L-T3,ST-093,DR-17,GATE-2 | docs/LISTING_COPY_AB.md; review-gates.config.json | The in-app screens remain English — a full UI translation is a product decision, not a review finding | Decide whether screen i18n is in scope before scale
E100 | 2026-09-13 20:24 | REVIEW | D13 GATE MET — 34 suites / 1,413 tests (34 new) at 100% across all four metrics, zero pragmas, plus the database-backed contract suite at 38 tests and 100%. Suite, npm run gates (six claims rules, five gates GREEN), npm run extension -- --check and the Postgres contract suite all verified from the packaged v028 zip in a clean clone. Story position unchanged at 98/100 (391/399). | D13 | — | None | LC-1 dev org + bundle upload, DR-12 reviewer, D-T1, native-speaker review
E101 | 2026-09-13 20:36 | REVIEW | F-T32 — THE CAPS BOUNDED THE HEAP AND NOTHING ELSE. v013 fixed 'unbounded ledgers' with FIFO caps, and that fix was true of memory only: every capped collection still INSERTed into Postgres and nothing ever deleted. Latency is sampled on every guarded request, so at the 500 rps this product was measured at in v025 that table alone grows by tens of millions of rows a day — and hydrate() read every row of it at boot, which turns a restart into an outage that gets slower every week. Fixed on both sides: a daily prune with a window chosen per dataset (latency 7 days, errors 30, notifications 60, telemetry 90) and bounded hydration reading the newest rows up to the in-memory cap, so boot time depends on the cap rather than on uptime. Audit rows are NOT pruned: deleting evidence is a different decision from bounding a boot, so they are bounded at hydration only, and the reasoning is written down rather than left to whoever reads the code next. | F-T32,F-T05,R-T4 | src/store.ts pruneOperational + OPERATIONAL_RETENTION_DAYS; src/pgStore.ts DELETEs + HYDRATE_CAP; src/scheduler.ts daily prune | The four windows are chosen numbers, not measured ones; audit growth is now the only unbounded table by design | Confirm the windows against real pilot volumes
E102 | 2026-09-13 20:36 | TEST | THE NINETY-DAY HARNESS — the reason nothing had found F-T32 is that nothing had ever let the clock run. Every test and every load run exercises seconds; the product's most important work is unattended and dated. The harness drives ninety simulated days of traffic and sweeps and now stands as a regression: each dataset keeps its own window and the recent end survives, each window applies to its own dataset rather than one number to all four, the retention purge fires on the right day and EXACTLY once rather than every day after, a backup is taken each day, and a prune failing on a full disk is recorded as a job error while the rest of the day's work continues. Against real Postgres the same assertions hold on rows rather than heap entries, and hydration is shown to take the newest page rather than an arbitrary one. | L-T4,ST-090,F-T26 | tests/review_pass15.test.ts; tests/pg_contract.test.ts pass-15 section | In-process simulated clock — it proves the day logic, not a real month of wall-clock drift, DST or leap seconds | Re-check after a month of pilot uptime
E103 | 2026-09-13 20:36 | REVIEW | RETENTION WINDOWS PUBLISHED — DATA_FLOWS.md now states what is kept and for how long, next to the customer-data policy it already carried, and the setup guide names the daily prune. A retention rule that exists only in code is one a customer cannot check and a reviewer will ask about; this is the same discipline as the published-claims gate, applied before anyone has to ask. | F-T32,ST-065,LC-7 | DATA_FLOWS.md; docs/DEV_ORG_SETUP.md | None | —
E104 | 2026-09-13 20:36 | REVIEW | D13 GATE MET — 35 suites / 1,443 tests (30 new) at 100% across all four metrics, zero pragmas, plus the database-backed contract suite at 40 tests and 100%. Suite, npm run gates (five GREEN), npm run extension -- --check and the Postgres contract suite all verified from the packaged v029 zip in a clean clone. Story position unchanged at 98/100 (391/399). | D13 | — | None | LC-1 dev org + bundle upload, DR-12 reviewer, D-T1
E105 | 2026-09-13 21:53 | REVIEW | F-T33 CRITICAL — THE PROCESS DIED WHEN THE DATABASE DID. Measured, not reasoned about: a server running against real Postgres, the database stopped with pg_ctl -m immediate, one write issued — and the process exited with an unhandled 'error' event from node-postgres. A database restart, a managed-provider failover or a brief network partition therefore meant a total outage of TeleField plus the loss of every write sitting in the write-behind queue. The chaos story ST-091 tells covers Zoho's API going down; nobody had written the one where OUR database goes down, and nothing had tried it. | F-T33,ST-091,R-T14 | src/pgStore.ts watch()/isConnectionError; measured against Postgres 16 | Managed-Postgres failovers are routine, so this would have happened in the first months of the pilot | Re-run the same experiment on the production host
E106 | 2026-09-13 21:53 | REVIEW | WRITES ARE HELD, NOT DROPPED — the flush loop treated every failure the same: record a string, move on, lose the write. Now a connection-level failure puts the remaining batch back at the FRONT of the queue so ordering survives the outage, marks the store unhealthy, and stops draining until the connection returns; a statement-level failure (a constraint violation) is still recorded once and skipped, because retrying it for ever would never fix it. Classification is by cause and is itself tested against both kinds of message. A store that then drains a batch successfully marks itself healthy again — refusing writes the database would accept is the opposite failure and just as expensive. | F-T33,R-T4 | src/pgStore.ts flush() | Held writes live in memory: a crash during a long outage still loses them, which is R-T14 unchanged | Bound the backlog if pilot outages are long
E107 | 2026-09-13 21:53 | REVIEW | THE 200 WAS A LIE AND IS NOT ANY MORE — R-T4 made a 200 on a mutating request a durability promise. While the database is unreachable that promise cannot be kept, so the write is refused with 503, Retry-After and a sentence a rep can act on, and the response carries the backlog size. Reads keep working from hydrated memory, which is the degradation ST-091 describes applied to our own database. /healthz is now readiness as well as liveness: 503 with the reason and the pending count, which is what a load balancer, the deploy workflow and the status page all need in order to act — before this it answered a cheerful 200 while every write was being discarded. | F-T33,ST-091,ST-092 | src/app.ts guarded() + /healthz; src/server.ts pgHealth | A blue/green switch must now read /healthz rather than assume readiness | Wire the deploy health check to the new status
E108 | 2026-09-13 21:53 | MEASURE | RE-MEASURED, SAME EXPERIMENT — write before the outage: 200, persisted. During the outage: process alive, write refused 503 with pendingWrites=2, read 200, /healthz 503 degraded with the backlog count. After Postgres returned: /healthz 200, backlog drained to zero, a new write 200 and persisted. The lead refused mid-outage is absent from the database, which is the point — it was refused, not silently lost. Whoever runs this on the production host should expect the same three lines and should check the third. | F-T33,L-T5 | docs/DEV_ORG_SETUP.md outage section | Local loopback and a local database; a managed provider's failover behaviour may differ | Repeat on production infra
E109 | 2026-09-13 21:53 | REVIEW | D13 GATE MET — 36 suites / 1,477 tests at 100% across all four metrics, zero pragmas, and the database-backed contract suite grows from 40 to 47 at 100% on the adapter: the outage paths are covered against a connection that really goes away (client closed, error event emitted, reconnect refused) rather than against a mock. Suite, npm run gates, npm run extension -- --check and the Postgres suite all verified from the packaged v030 zip in a clean clone. Story position unchanged at 98/100 (391/399). | D13 | — | None | LC-1 dev org + bundle upload, DR-12 reviewer, D-T1
E110 | 2026-09-13 22:50 | REVIEW | F-T34 — NOTHING HANDLED SIGTERM. Sixteen passes and a production-shaped deploy workflow, and the one event that happens on every release was unhandled: Node's default is to exit immediately, so a deploy cut off in-flight requests mid-response and threw away the write-behind queue. The blue/green step written in v023 drains traffic at the router and says 'confirm blue is idle' — which is true of the load balancer and says nothing about the process. Every deploy was therefore the R-T29 worst case, on purpose, several times a week. Now SIGTERM and SIGINT drain in order: stop being routed traffic, refuse new writes, finish in-flight requests, flush, close the database, exit 0. | F-T34,R-T29,ST-092,GAP-T9 | bin/telefield.js signal handlers; src/server.ts shutdown(); .github/workflows/deploy.yml | A liveness probe that restarts on any non-200 will fight the drain — R-T30 again, now with a second trigger | Set the deploy to send SIGTERM and wait for exit 0
E111 | 2026-09-13 22:50 | REVIEW | DRAINING IS A STATE, NOT A MOMENT — /healthz answers 503 draining with the pending-write count as soon as the signal arrives, so the router stops sending traffic BEFORE the socket closes; a write arriving mid-drain gets 503 with Retry-After: 5 and a sentence saying another instance will take it, rather than being queued into a process about to exit; reads keep answering, because the instance is leaving, not broken. SHUTDOWN_TIMEOUT_MS bounds the whole thing at 15 seconds and exits non-zero if it overruns — a drain that hangs holds the deploy open and is its own outage. | F-T34,ST-091 | src/app.ts draining paths; SHUTDOWN_TIMEOUT_MS | 15s is a chosen bound; a large backlog held through an outage could need more | Tune once real deploy timings exist
E112 | 2026-09-13 22:50 | HONESTY | THE LIVE SIGNAL RUN WAS NOT COMPLETED — F-T33 was measured by stopping a real database under a real server, and I intended the same for F-T34. The session's container stopped holding background processes reliably at that point, and three attempts produced no usable evidence. What exists is 31 tests, including the server's own listening state before and after the drain, and a deliberately non-timing-dependent assertion. What does not exist is a live SIGTERM observation, and it is recorded as an operator check on the first production deploy rather than implied to have happened. | F-T34,L-T5 | tests/review_pass17.test.ts | The drain is tested, not observed in the wild | Watch for 'drained cleanly' and exit 0 on the first real deploy
E113 | 2026-09-13 22:50 | QUALITY | A FLAKE CAUGHT IN VERIFICATION — the first clean-clone run failed one test and the second passed. The cause was mine, added in this pass: an assertion that a socket would be refused after shutdown, which depends on connection timing rather than on behaviour. Replaced with the server's own listening state. Worth recording because the alternative is a suite people learn to re-run rather than read, and this repository's whole argument rests on the suite meaning something. | F-T34 | tests/review_pass17.test.ts | None | —
E114 | 2026-09-13 22:50 | REVIEW | D13 GATE MET — 37 suites / 1,508 tests (31 new) at 100% across all four metrics, zero pragmas, plus the database-backed contract suite at 47 tests and 100%. Suite, npm run gates, npm run extension -- --check and the Postgres suite verified from the packaged v031 zip in a clean clone, with the full suite run twice to confirm the flake is gone. Story position unchanged at 98/100 (391/399). | D13 | — | None | LC-1 dev org + bundle upload, DR-12 reviewer, D-T1

## Decisions
DECISIONS (tracker scope)
ID | Decision | Rationale | Decided by | Status
D13 | (Portfolio-wide) Discovery interviews parked; dev proceeds with 100% automation test coverage on all code. | Senthil 10 Sep 20:45; applied to TeleField per 21:05 instruction. | Senthil | LOCKED
D15 | TeleField (rank 2) build opened 10 Sep 21:05 while RevRescue rank-1 gate (listed + 10 paying) is not met. R7/R1 require this logged. MODE TO RATIFY: (a) parallel builds — supersedes R1 serial rule, or (b) order swap — TeleField becomes active product, RevRescue paused at S1-code-complete. | Senthil instruction 'read v006 and create properly'; uploaded workbook set indicates TeleField intent. | Senthil (mode ratification pending) | OPEN — pick (a) or (b)
D16 | S1 stack = TypeScript/Node/Express per v006 ReadMe stack assumption; persistence behind typed Store interface with in-memory S1 impl (no Postgres in sandbox), Postgres adapter at deploy. | Follows workbook; matches accepted Sunaria precedent for sandbox DB constraints. | Claude — flagged | OPEN for ratification

## S1_Build_Board
S1 BUILD BOARD — Foundation (2 wks) — exit: app installs cleanly in dev store/org; telemetry firing
Backlog stories ST-051/052/055/056 (13 pts) + foundation infra items. Edit Status/Notes (yellow).
ID | Item | Story ref | Points | Owner | Status | Notes / Evidence
S1-01 | Repo scaffold + CI with 100% coverage gate (D13) | — | 2 | Claude | Done | jest coverageThreshold 100x4; .github/workflows/ci.yml. E003.
S1-02 | Env config: India-first ZOHO_DC, secrets validation | — | 1 | Claude | Done | src/config.ts — 6 tests.
S1-03 | Typed Store repository layer (Postgres adapter point) | — | 2 | Claude | Done | src/store.ts — D16 constraint logged as R-T4.
S1-04 | OAuth install flow -> welcome state | ST-051 | 5 | Claude | Done | DONE-IN-CODE 10 Sep 21:05 — src/zohoAuth.ts exchangeCode + src/app.ts /oauth/callback -> welcome; tests: "ST-051 full install via OAuth callback" + exchange unit tests. <2min NFR: single round-trip install, latency budget test at S1-11 live check.
S1-05 | Uninstall: token wipe + deletion schedule + sweep | ST-052 | 3 | Claude | Done | DONE-IN-CODE 10 Sep 21:05 — src/lifecycle.ts handleUninstall wipes tokens (tokens:null asserted) + scheduleDeletion; retention sweep purges. Tests: "ST-052 uninstall wipes tokens..." unit + API integration incl. duplicate delivery.
S1-06 | Rotation-safe token refresh + 401-auto-refresh client | ST-055 | 3 | Claude | Done | DONE-IN-CODE 10 Sep 21:05 — src/zohoAuth.ts refreshTokens persists rotated refresh_token; src/zohoClient.ts auto-refresh-once on 401 + replay, no refresh loop. 5 dedicated tests.
S1-07 | Install telemetry source attribution | ST-056 | 2 | Claude | Done | DONE-IN-CODE 10 Sep 21:05 — src/lifecycle.ts source attribution listing/search/referral, unknown->direct without failing install; installSourceCounts reporting. 3 tests.
S1-08 | Webhook HMAC verify + replay guard + dedupe ledger | LC-4-class | 2 | Claude | Done | src/webhooks.ts + ledger — timing-safe compare; 5 negative-path tests.
S1-09 | Zoho API credits/429 backoff (Launch_Checklist #4) | — | 2 | Claude | Done | src/zohoClient.ts exp backoff + jitter; exhaustion + non-retryable tests.
S1-10 | Install cleanly in REAL Zoho dev org (Sigma project + Catalyst configured — Launch #1) | ST-051 live | 3 | Senthil + Claude | To do | Needs Zoho developer account + Sigma; evidence: install screenshot + org id + telemetry row.
S1-11 | Staging env + secrets management; Postgres adapter (D16) | — | 2 | Senthil + Claude | To do | Provision after S1-10.

## Traceability_Matrix
TRACEABILITY MATRIX — 100 stories: module -> epic -> story -> screen -> verification -> status (edit yellow)
Source: v006 Full_Backlog (single source of truth, D12 pattern). S1 rows carry code/test evidence per D13. Status dropdown; Evidence yellow.
Story ID | Epic | Module / feature | Story | Points | Priority | Sprint | Primary screen | Verification | Status | Evidence
ST-001 | F1 | Call queue + auto-dial | As a Sales head, I can set up Call queue + auto-dial with sensible defaults in one screen | 5 | P0 | S2 | SCR-3 Call workspace | E2E test + demo | Done-in-code | DONE-IN-CODE 22:00 — src/callQueue.ts configureQueue + DEFAULT_CONFIG; empty-body PUT works; setup funnel fires once. Tests: config unit x2 + happy-path integration.
ST-002 | F1 | Call queue + auto-dial | As a Sales head, the Call queue + auto-dial happy path completes without documentation | 8 | P0 | S2 | SCR-3 Call workspace | E2E test + demo | Done-in-code | DONE-IN-CODE 22:00 — nextCall/recordOutcome engine; happy path on pure defaults asserted end-to-end incl. retry delay, exhaustion at maxAttempts, aha-once. Tests: 4 engine + happy-path integration.
ST-003 | F1 | Call queue + auto-dial | As a Telecaller, I can customise Call queue + auto-dial rules/conditions for my workflow | 5 | P1 | S2 | SCR-3 Call workspace | Integration test + manual QA | Done-in-code | DONE-IN-CODE 22:00 — validateRules/ruleMatches/scoreLead; API rules reorder live queue; invalid rule 422 names index. Tests: 3 unit + API test.
ST-004 | F1 | Call queue + auto-dial | As a user, Call queue + auto-dial shows clear errors and retry paths on platform API failures | 3 | P0 | S2 | SCR-3 Call workspace | E2E test + demo | Done-in-code | DONE-IN-CODE 22:00 — src/sync.ts outbox; outcome saved on CRM failure with CRM_SYNC_FAILED {retryable,nextAttemptAt,retryPath}; POST /sync/retry processes due. Tests: 4 sync unit + CRM-down API test.
ST-005 | F1 | Call queue + auto-dial | As a Field rep, Call queue + auto-dial works on the Zoho CRM widget + mobile app surface end-to-end | 5 | P0 | S3 | SCR-3 Call workspace | E2E test + demo | Done-in-code | DONE-IN-CODE 22:09 — /widget/next compact payload; /mobile/sync offline batch (clientRef dedupe, per-item report); surface recorded on CallAttempt + metrics.bySurface. Live Zoho widget render = S1-10 evidence.
ST-006 | F1 | Call queue + auto-dial | As a Telecaller, I can see Call queue + auto-dial performance metrics and trends | 3 | P1 | S3 | SCR-3 Call workspace | Integration test + manual QA | Done-in-code | DONE-IN-CODE 22:09 — src/metrics.ts computeMetrics: totals, connect rate, outcome + surface breakdowns, daily trend buckets; days 1..90 validated.
ST-007 | F1 | Call queue + auto-dial | As a user, Call queue + auto-dial respects role permissions and audit logging | 3 | P1 | S3 | SCR-3 Call workspace | Integration test + manual QA | Done-in-code | DONE-IN-CODE 22:09 — src/audit.ts wired into config/rules/roles/pause/import/disposition-config mutations; GET /audit admin+; member 403 asserted.
ST-008 | F1 | Call queue + auto-dial | As a Sales head, I can pause/disable Call queue + auto-dial without data loss | 2 | P2 | S3 | SCR-3 Call workspace | Manual QA | Done-in-code | DONE-IN-CODE 22:09 — pause flag only, never a wipe; paused next -> 409 with no-data-loss message; leads count asserted intact; resume restores.
ST-009 | F1 | Call queue + auto-dial | As a Telecaller, I can import/migrate existing data into Call queue + auto-dial (CSV + competitor importer) | 5 | P1 | S3 | SCR-3 Call workspace | Integration test + manual QA | Done-in-code | DONE-IN-CODE 22:09 — src/importer.ts: generic + dialerpro + callsheet profiles; per-row skip reasons (dup id, bad priority, missing fields); short rows default safely.
ST-010 | F1 | Call queue + auto-dial | As a user, I get notifications (in-app + email) for key Call queue + auto-dial events with per-type mute | 3 | P2 | S3 | SCR-3 Call workspace | Manual QA | Done-in-code | DONE-IN-CODE 22:09 — src/notify.ts: 4 event types, in-app + injected email, per-user per-type mute silences both channels; wired to pause/resume/import/sync-failure.
ST-011 | F2 | Disposition + callback engine | As a Sales head, I can set up Disposition + callback engine with sensible defaults in one screen | 5 | P0 | S3 | SCR-4 Rule builder | E2E test + demo | Done-in-code | DONE-IN-CODE 22:09 — DEFAULT_DISPOSITIONS (interested/callback/follow_up/not_interested/do_not_call) usable with zero config; PUT /dispositions/config one call.
ST-012 | F2 | Disposition + callback engine | As a Sales head, the Disposition + callback engine happy path completes without documentation | 8 | P0 | S3 | SCR-4 Rule builder | E2E test + demo | Done-in-code | DONE-IN-CODE 22:09 — recordDisposition action engine; callback sets callbackAt + queue-jump boost (due callback outranks priority-5, asserted); dnc/requeue/close asserted end-to-end.
ST-013 | F2 | Disposition + callback engine | As a Telecaller, I can customise Disposition + callback engine rules/conditions for my workflow | 5 | P1 | S3 | SCR-4 Rule builder | Integration test + manual QA | Done-in-code | DONE-IN-CODE 22:09 — custom dispositions merge over defaults; kind + delayMinutes validated with named errors (422 via API).
ST-014 | F2 | Disposition + callback engine | As a user, Disposition + callback engine shows clear errors and retry paths on platform API failures | 3 | P0 | S3 | SCR-4 Rule builder | E2E test + demo | Done-in-code | DONE-IN-CODE 22:09 — disposition sync rides sync.ts outbox: CRM_SYNC_FAILED structured error + sync.failed notification on failure; synced on success (both asserted).
ST-015 | F2 | Disposition + callback engine | As a Field rep, Disposition + callback engine works on the Zoho CRM widget + mobile app surface end-to-end | 5 | P0 | S4 | SCR-4 Rule builder | E2E test + demo | Done-in-code | DONE-IN-CODE 22:18 — GET /widget/dispositions (offline-cacheable taxonomy, defaults + custom), POST /widget/calls/:id/disposition compact {ok,action,synced}; mobile batch disposition since S3. Live widget render = S1-10.
ST-016 | F2 | Disposition + callback engine | As a Telecaller, I can see Disposition + callback engine performance metrics and trends | 3 | P1 | S4 | SCR-4 Rule builder | Integration test + manual QA | Done-in-code | DONE-IN-CODE 22:18 — computeDispositionMetrics: byDisposition, callbacksScheduled vs dueNow, dncCount, daily trend; days 1..90 validated; GET /dispositions/metrics.
ST-017 | F2 | Disposition + callback engine | As a user, Disposition + callback engine respects role permissions and audit logging | 3 | P1 | S4 | SCR-4 Rule builder | Integration test + manual QA | Done-in-code | DONE-IN-CODE 22:18 — disposition routes on role matrix; DNC application writes audit entry (actor recorded) + disposition.dnc notification; member-can-disposition/member-cannot-configure asserted.
ST-018 | F2 | Disposition + callback engine | As a Sales head, I can pause/disable Disposition + callback engine without data loss | 2 | P2 | S4 | SCR-4 Rule builder | Manual QA | Done-in-code | DONE-IN-CODE 22:18 — engine-scoped pause: dispositions paused -> 409 no-data-loss message while queue keeps dialling (asserted); audit on pause/resume.
ST-019 | F2 | Disposition + callback engine | As a Telecaller, I can import/migrate existing data into Disposition + callback engine (CSV + competitor importer) | 5 | P1 | S4 | SCR-4 Rule builder | Integration test + manual QA | Done-in-code | DONE-IN-CODE 22:18 — importDispositionHistoryCsv: generic + dialerpro_history profiles, per-row reasons, historical do_not_call applies DNC to lead, stale callbacks NOT re-applied (asserted), dateless rows default to now.
ST-020 | F2 | Disposition + callback engine | As a user, I get notifications (in-app + email) for key Disposition + callback engine events with per-type mute | 3 | P2 | S4 | SCR-4 Rule builder | Manual QA | Done-in-code | DONE-IN-CODE 22:18 — callback.due (named leads in message), disposition.dnc, error.spike types; POST /callbacks/notify-due; mute silences repeat runs (asserted).
ST-021 | F3 | Beat/route planner | As a Sales head, I can set up Beat/route planner with sensible defaults in one screen | 5 | P0 | S5 | SCR-5 Planner view | E2E test + demo | Done-in-code | DONE-IN-CODE 22:27 — createBeat defaults weekdays/12/7d-cooldown/nearest; field-named validation incl. duplicate id.
ST-022 | F3 | Beat/route planner | As a Sales head, the Beat/route planner happy path completes without documentation | 8 | P0 | S5 | SCR-5 Planner view | E2E test + demo | Done-in-code | DONE-IN-CODE 22:27 — planRoute recurrence-aware; cooldown+rules+DNC filtered; haversine nearest-neighbour from top-priority stop; per-leg + total km; recordVisit updates lastVisitedAt (visited only). Order asserted on real coordinates.
ST-023 | F3 | Beat/route planner | As a Telecaller, I can customise Beat/route planner rules/conditions for my workflow | 5 | P1 | S5 | SCR-5 Planner view | Integration test + manual QA | Done-in-code | DONE-IN-CODE 22:27 — validateBeatRules boost/skip on priority + daysSinceVisit (never-visited = infinity, asserted); skip proven to exclude; PUT /beats/:id/rules audited.
ST-024 | F3 | Beat/route planner | As a user, Beat/route planner shows clear errors and retry paths on platform API failures | 3 | P0 | S5 | SCR-5 Planner view | E2E test + demo | Done-in-code | DONE-IN-CODE 22:27 — POST /beats/:id/route/sync on outbox route_push kind (/crm/v6/Tasks); CRM_SYNC_FAILED contract + sync.failed notification asserted both ways.
ST-025 | F3 | Beat/route planner | As a Field rep, Beat/route planner works on the Zoho CRM widget + mobile app surface end-to-end | 5 | P0 | S5 | SCR-5 Planner view | E2E test + demo | Done-in-code | DONE-IN-CODE 22:27 — GET /widget/route/:id compact; POST /mobile/visits offline batch clientRef-deduped with per-item report; lastVisitedAt applied from batch. Live widget render = S1-10.
ST-026 | F3 | Beat/route planner | As a Telecaller, I can see Beat/route planner performance metrics and trends | 3 | P1 | S5 | SCR-5 Planner view | Integration test + manual QA | Done-in-code | DONE-IN-CODE 22:27 — computeBeatMetrics: beats/stops/visits, visitedRate, avgStopsPerActiveDay, daily trend; 1..90 validated.
ST-027 | F3 | Beat/route planner | As a user, Beat/route planner respects role permissions and audit logging | 3 | P1 | S5 | SCR-5 Planner view | Integration test + manual QA | Done-in-code | DONE-IN-CODE 22:27 — beats.configure (owner/admin) vs beats.execute (all) enforced per route (member 403s asserted); audit on create/rules/pause/import.
ST-028 | F3 | Beat/route planner | As a Sales head, I can pause/disable Beat/route planner without data loss | 2 | P2 | S5 | SCR-5 Planner view | Manual QA | Done-in-code | DONE-IN-CODE 22:27 — beats engine pause: route + visits 409 no-data-loss while stops intact (asserted); queue/dispositions unaffected; audit on pause/resume.
ST-029 | F3 | Beat/route planner | As a Telecaller, I can import/migrate existing data into Beat/route planner (CSV + competitor importer) | 5 | P1 | S5 | SCR-5 Planner view | Integration test + manual QA | Done-in-code | DONE-IN-CODE 22:27 — importStopsCsv generic + routemaster profiles; per-row reasons (dup id, invalid lat/lng, priority, missing fields); short rows default.
ST-030 | F3 | Beat/route planner | As a user, I get notifications (in-app + email) for key Beat/route planner events with per-type mute | 3 | P2 | S5 | SCR-5 Planner view | Manual QA | Done-in-code | DONE-IN-CODE 22:27 — beat.assigned on create (to rep), route.ready on route generation (to rep); both mute-capable.
ST-031 | F4 | Visit check-in (geo) | As a Sales head, I can set up Visit check-in (geo) with sensible defaults in one screen | 5 | P0 | S6 | Mobile / SCR-5 | E2E test + demo | Done-in-code | DONE-IN-CODE 11:50 — CHECKIN_DEFAULTS 250m/flag/0min/sequence-off; PUT /checkins/config field-named validation; audited.
ST-032 | F4 | Visit check-in (geo) | As a Sales head, the Visit check-in (geo) happy path completes without documentation | 8 | P0 | S6 | Mobile / SCR-5 | E2E test + demo | Done-in-code | DONE-IN-CODE 11:50 — checkIn haversine fence (distanceM recorded), checkOut visit minutes + writes S5 visit record (lastVisitedAt, beat metrics one truth). Happy path on pure defaults asserted.
ST-033 | F4 | Visit check-in (geo) | As a Telecaller, I can customise Visit check-in (geo) rules/conditions for my workflow | 5 | P1 | S6 | Mobile / SCR-5 | Integration test + manual QA | Done-in-code | DONE-IN-CODE 11:50 — reject¦flag¦allow policy (allow still records withinFence=false honestly), minVisitMinutes short_visit flag at checkout, sequenceEnforced against today's route with override->out_of_sequence flag.
ST-034 | F4 | Visit check-in (geo) | As a user, Visit check-in (geo) shows clear errors and retry paths on platform API failures | 3 | P0 | S6 | Mobile / SCR-5 | E2E test + demo | Done-in-code | DONE-IN-CODE 11:50 — POST /checkins/:id/sync on checkin_push outbox kind; CRM_SYNC_FAILED contract + sync.failed notification; unknown check-in 409.
ST-035 | F4 | Visit check-in (geo) | As a Field rep, Visit check-in (geo) works on the Zoho CRM widget + mobile app surface end-to-end | 5 | P0 | S6 | Mobile / SCR-5 | E2E test + demo | Done-in-code | DONE-IN-CODE 11:50 — POST /mobile/checkins offline batch clientRef-deduped with per-item policy report; GET /widget/checkins/:beatId compact today-view. Live widget render = S1-10.
ST-036 | F4 | Visit check-in (geo) | As a Telecaller, I can see Visit check-in (geo) performance metrics and trends | 3 | P1 | S6 | Mobile / SCR-5 | Integration test + manual QA | Done-in-code | DONE-IN-CODE 11:50 — computeCheckinMetrics: within-fence rate, flagged rate, completed, avg visit minutes, daily trend; 1..90 validated.
ST-037 | F4 | Visit check-in (geo) | As a user, Visit check-in (geo) respects role permissions and audit logging | 3 | P1 | S6 | Mobile / SCR-5 | Integration test + manual QA | Done-in-code | DONE-IN-CODE 11:50 — checkin routes on beats.execute; config on beats.configure (member 403 asserted); flagged/overridden check-ins audited with actor + distance.
ST-038 | F4 | Visit check-in (geo) | As a Sales head, I can pause/disable Visit check-in (geo) without data loss | 2 | P2 | S6 | Mobile / SCR-5 | Manual QA | Done-in-code | DONE-IN-CODE 11:50 — checkins engine pause: check-in + checkout 409 no-data-loss (asserted), other engines unaffected; audit on pause/resume.
ST-039 | F4 | Visit check-in (geo) | As a Telecaller, I can import/migrate existing data into Visit check-in (geo) (CSV + competitor importer) | 5 | P1 | S6 | Mobile / SCR-5 | Integration test + manual QA | Done-in-code | DONE-IN-CODE 11:50 — importCheckinsCsv generic + fieldassist profiles; per-row reasons (unknown stop, bad coords, bad times, checkout<checkin); fence evaluated on import so migrated data feeds metrics honestly.
ST-040 | F4 | Visit check-in (geo) | As a user, I get notifications (in-app + email) for key Visit check-in (geo) events with per-type mute | 3 | P2 | S6 | Mobile / SCR-5 | Manual QA | Done-in-code | DONE-IN-CODE 11:50 — checkin.flagged notification on flagged/overridden check-ins (mute-capable); import.completed on history import.
ST-041 | F5 | Manager scorecards | As a Sales head, I can set up Manager scorecards with sensible defaults in one screen | 5 | P0 | S8 | SCR-8 Analytics | E2E test + demo | Done-in-code | DONE-IN-CODE 23:11 — SCORECARD_DEFAULTS: weekly, 6 KPIs (calls150/connects45/connect_rate30%/callbacks20/visits25/compliance90%) w/ weights; PUT /scorecards/config one screen, defaults on {}.
ST-042 | F5 | Manager scorecards | As a Sales head, the Manager scorecards happy path completes without documentation | 8 | P0 | S8 | SCR-8 Analytics | E2E test + demo | Done-in-code | DONE-IN-CODE 23:11 — computeScorecard from live calls/visits/checkins: attainment capped 150, weighted score, A-D grades (boundaries tested at 90/70/50); computeTeamScorecard ranked + teamAvg; happy path needs zero docs (defaults + auto data).
ST-043 | F5 | Manager scorecards | As a Telecaller, I can customise Manager scorecards rules/conditions for my workflow | 5 | P1 | S8 | SCR-8 Analytics | Integration test + manual QA | Done-in-code | DONE-IN-CODE 23:11 — per-KPI target/weight/enabled overrides; validation names offending entry (kpis[0].kpi ...), duplicate-KPI rejection; custom config swings grade (asserted).
ST-044 | F5 | Manager scorecards | As a user, Manager scorecards shows clear errors and retry paths on platform API failures | 3 | P0 | S8 | SCR-8 Analytics | E2E test + demo | Done-in-code | DONE-IN-CODE 23:11 — POST /scorecards/run pushes via scorecard_push outbox; transport failure -> {status:pending_retry, error.code:CRM_SYNC_FAILED} + sync.failed notification; same error contract as S2.
ST-045 | F5 | Manager scorecards | As a Field rep, Manager scorecards works on the Zoho CRM widget + mobile app surface end-to-end | 5 | P0 | S8 | SCR-8 Analytics | E2E test + demo | Done-in-code | DONE-IN-CODE 23:11 — GET /widget/scorecard compact {score,grade,top3}; mobile uses same guarded endpoints; live widget-in-CRM half pending S1-10 (as ST-005/015/025/035).
ST-046 | F5 | Manager scorecards | As a Telecaller, I can see Manager scorecards performance metrics and trends | 3 | P1 | S8 | SCR-8 Analytics | Integration test + manual QA | Done-in-code | DONE-IN-CODE 23:11 — GET /scorecards/trend?days=1..90 (default 7) one point/day; team avg in team view; range validation 422.
ST-047 | F5 | Manager scorecards | As a user, Manager scorecards respects role permissions and audit logging | 3 | P1 | S8 | SCR-8 Analytics | Integration test + manual QA | Done-in-code | DONE-IN-CODE 23:11 — own card queue.dial (any role); team view + config queue.configure (member 403 asserted); scorecards.configure audited.
ST-048 | F5 | Manager scorecards | As a Sales head, I can pause/disable Manager scorecards without data loss | 2 | P2 | S8 | SCR-8 Analytics | Manual QA | Done-in-code | DONE-IN-CODE 23:11 — engine-scoped pause "scorecards": compute 409 w/ no-data-loss message, resume restores, underlying data untouched.
ST-049 | F5 | Manager scorecards | As a Telecaller, I can import/migrate existing data into Manager scorecards (CSV + competitor importer) | 5 | P1 | S8 | SCR-8 Analytics | Integration test + manual QA | Done-in-code | DONE-IN-CODE 23:11 — importScorecardHistoryCsv generic+salesmaster profiles; per-row skip reasons; kpi lower-cased; truncated value cell SKIPS (explicit empty guard — Number("")==0 pre-empted); imported rows feed KPI actuals (2 live + 40 historic = 42 asserted).
ST-050 | F5 | Manager scorecards | As a user, I get notifications (in-app + email) for key Manager scorecards events with per-type mute | 3 | P2 | S8 | SCR-8 Analytics | Manual QA | Done-in-code | DONE-IN-CODE 23:11 — scorecard.ready per rep on run (rank included), scorecard.low to manager on team view below threshold; per-type mute honoured (asserted before/after).
ST-051 | E1 | Platform foundation (install/auth) | Marketplace OAuth install completes and lands on welcome state in <2 min | 5 | P0 | S1 | SCR-1 Onboarding | E2E test + demo | Done-in-code | DONE-IN-CODE 10 Sep 21:05 — src/zohoAuth.ts exchangeCode + src/app.ts /oauth/callback -> welcome; tests: "ST-051 full install via OAuth callback" + exchange unit tests. <2min NFR: single round-trip install, latency budget test at S1-11 live check.
ST-052 | E1 | Platform foundation (install/auth) | Uninstall webhook removes tokens, schedules data deletion per policy | 3 | P0 | S1 | SCR-1 Onboarding | E2E test + demo | Done-in-code | DONE-IN-CODE 10 Sep 21:05 — src/lifecycle.ts handleUninstall wipes tokens (tokens:null asserted) + scheduleDeletion; retention sweep purges. Tests: "ST-052 uninstall wipes tokens..." unit + API integration incl. duplicate delivery.
ST-053 | E1 | Platform foundation (install/auth) | Re-install restores account within retention window | 3 | P1 | S2 | SCR-1 Onboarding | Integration test + manual QA | Done-in-code | DONE-IN-CODE 22:00 — lifecycle restorable check: uninstalled + unexecuted schedule + within window -> restore + cancelDeletion; beyond -> fresh. Tests: 3 unit + API restored:true.
ST-054 | E1 | Platform foundation (install/auth) | Multi-user roles: owner/admin/member permission matrix enforced | 5 | P0 | S2 | SCR-1 Onboarding | E2E test + demo | Done-in-code | DONE-IN-CODE 22:00 — src/roles.ts matrix + assertPermission on every S2 route via guarded(); installer=owner; owner-only team.manage; owner grant blocked. Tests: 3 unit + API enforcement test.
ST-055 | E1 | Platform foundation (install/auth) | Session/token refresh survives platform token rotation | 3 | P0 | S1 | SCR-1 Onboarding | E2E test + demo | Done-in-code | DONE-IN-CODE 10 Sep 21:05 — src/zohoAuth.ts refreshTokens persists rotated refresh_token; src/zohoClient.ts auto-refresh-once on 401 + replay, no refresh loop. 5 dedicated tests.
ST-056 | E1 | Platform foundation (install/auth) | Install telemetry: source attribution (listing/search/referral) captured | 2 | P1 | S1 | SCR-1 Onboarding | Integration test + manual QA | Done-in-code | DONE-IN-CODE 10 Sep 21:05 — src/lifecycle.ts source attribution listing/search/referral, unknown->direct without failing install; installSourceCounts reporting. 3 tests.
ST-057 | E5 | Billing & plans | 14-day trial without card; banner shows days remaining | 5 | P0 | S6 | SCR-7 Billing | E2E test + demo | Done-in-code | DONE-IN-CODE 11:50 — 14-day card-free trial derived from org.installedAt (stateless); GET /billing banner with daysRemaining; expiry -> 402 on queue/next + widget/next with upgradePath; subscribing unblocks (asserted).
ST-058 | E5 | Billing & plans | Upgrade/downgrade mid-cycle prorates correctly | 5 | P0 | S6 | SCR-7 Billing | E2E test + demo | Done-in-code | DONE-IN-CODE 11:50 — changePlan exact proration: fraction 0.5 -> credit 14.50/charge 29.50/net 15.00 charged; downgrade fraction 0.25 -> net -7.50 booked as ledger credit; period unchanged; guards (same plan, ended period, no sub).
ST-059 | E5 | Billing & plans | Marketplace billing API used where mandated; external Stripe fallback elsewhere | 8 | P0 | S6 | SCR-7 Billing | E2E test + demo | Done-in-code | DONE-IN-CODE 11:50 — PROVIDER_FOR_CHANNEL: marketplace -> zoho_marketplace /marketplace/v1/billing/charge (MANDATED, asserted by URL), external -> external_stripe /stripe/v1/charges; declined charge leaves NO subscription + NO ledger entry (asserted); ledger records provider per entry.
ST-060 | E5 | Billing & plans | Failed payment: 7-day grace, 3 dunning emails, then read-only mode | 3 | P1 | S7 | SCR-7 Billing | Integration test + manual QA | Done-in-code | DONE-IN-CODE 23:02 — renew failure -> past_due + graceEndsAt(+7d); runDunningSweep day 0/3/6 once each with catch-up; past grace -> read_only (writes 402 w/ reason, reads 200, zero data loss); successful retry rolls period + clears dunning; cancelAtPeriodEnd renewal charges 0.
ST-061 | E5 | Billing & plans | Plan limits enforced with upgrade prompts at 80%/100% | 3 | P1 | S7 | SCR-7 Billing | Integration test + manual QA | Done-in-code | DONE-IN-CODE 23:02 — PLAN_LIMITS starter 500/3, pro 5000/25, trial=starter; enforceLimit: one 80% warning per limit (recordLimitWarningOnce), 100% -> 402 with trial->subscribe / paid->change path; wired on lead add, CSV import (worst-case rows), new seats only (role changes free); GET /billing/usage.
ST-062 | E5 | Billing & plans | Invoices/receipts downloadable; GST/VAT fields supported | 3 | P2 | S7 | SCR-7 Billing | Manual QA | Done-in-code | DONE-IN-CODE 23:02 — listInvoices from ledger charges: tax-inclusive split ($29 @GST18% -> 24.58/4.42, asserted), INV-<org>-NNNN sequence, credits excluded; GET /billing/invoices/:n with attachment header; PUT /billing/profile validation (taxId required with GST/VAT, rate 0..40).
ST-063 | E5 | Billing & plans | Cancellation flow with save-offer and exit survey | 3 | P1 | S7 | SCR-7 Billing | Integration test + manual QA | Done-in-code | DONE-IN-CODE 23:02 — cancel w/o confirm -> save-offer (20%, acceptPath+confirmPath); confirm requires reason enum, survey stored, cancelAtPeriodEnd -> renewal ends sub with $0; acceptSaveOffer once-only, discounts exactly one renewal (23.20 asserted) and averts cancellation.
ST-064 | E6 | Security & compliance | Scopes requested map 1:1 to shipped features (least privilege doc) | 3 | P0 | S7 | SCR-6 Settings / LC-1..10 | Evidence archived + gate review | Done-in-code | DONE-IN-CODE 23:02 — src/scopes.ts SCOPE_MANIFEST (5 scopes -> features -> endpoints), SCOPES.md review-ready table incl. explicit NOT-requested list, GET /meta/scopes; undocumented/unrequested detectors tested 1:1 both directions with synthetic drift.
ST-065 | E6 | Security & compliance | Data-flow diagram + retention policy published | 3 | P0 | S8 | SCR-6 Settings / LC-1..10 | Evidence archived + gate review | Done-in-code | DONE-IN-CODE 23:11 — DATA_FLOWS.md mermaid diagram + retention table (tokens on-uninstall, activity 24mo, ledger 7yr, telemetry 90d) + GET /meta/data-flows JSON.
ST-066 | E6 | Security & compliance | Encryption at rest + in transit verified; secrets in vault | 5 | P0 | S8 | SCR-6 Settings / LC-1..10 | Evidence archived + gate review | Done-in-code | CODE-COMPLETE 23:11 — AES-256-GCM sealing (fresh IV proven, tamper detection, key>=16), scrubSecrets wired: client secret injected into thrown error asserted [redacted] in 500 body AND stored error record; HTTPS everywhere doc. PENDING LIVE: vault injection of SECRETS_KEY at deploy.
ST-067 | E6 | Security & compliance | Audit log for admin-sensitive actions | 5 | P1 | S8 | SCR-6 Settings / LC-1..10 | Evidence archived + gate review | Done-in-code | DONE-IN-CODE 23:11 — analytics.export audited; joins existing audited set (roles, billing renew/cancel/save-offer, pauses, configs, imports); GET /audit shows all (asserted arrayContaining).
ST-068 | E6 | Security & compliance | Pen-test (or platform-required evidence) completed and archived | 8 | P0 | S9 | SCR-6 Settings / LC-1..10 | Evidence archived + gate review | Done-in-code | DONE-IN-CODE 11 Sep 08:15 (code half) — src/securityEvidence.ts executes 6 controls (webhook HMAC/replay, AES at-rest, secret scrub, least-priv scopes, breaker/backoff, export redaction) ASVS-mapped; /security/evidence endpoint + docs/SECURITY_EVIDENCE.md archive. EXTERNAL pen-test engagement + report archive = Senthil (vendor)
ST-069 | E6 | Security & compliance | Data export + delete-my-data self-serve | 5 | P0 | S9 | SCR-6 Settings / LC-1..10 | Evidence archived + gate review | Done-in-code | DONE-IN-CODE 11 Sep 08:15 — src/privacy.ts exportOrgData (20 datasets, tokens REDACTED), exportUserData, deleteMyData (audit row, last-owner guard); endpoints /privacy/export (owner), /privacy/my-data, /privacy/delete-my-data; tests incl. 409 last-owner + 500 scrub path
ST-070 | E6 | Security & compliance | Rate-limit backoff + circuit breaker on platform APIs | 5 | P0 | S8 | SCR-6 Settings / LC-1..10 | Evidence archived + gate review | Done-in-code | DONE-IN-CODE 23:11 — 429/5xx backoff (S1) + circuit breaker: 5 consecutive exhausted -> open 60s, CircuitOpenError fail-fast w/o touching transport (asserted), half-open probe closes on success / re-opens on failure, success resets count.
ST-071 | E7 | Telemetry & metrics | Activation funnel events (install->setup->aha->habit) in one dashboard | 5 | P0 | S4 | SCR-8 (internal) | E2E test + demo | Done-in-code | DONE-IN-CODE 22:18 — src/funnel.ts orgFunnel dashboard (stages+timestamps+next); habit = 3 distinct active days in trailing 7, auto-recorded once by outcome engine; GET /funnel.
ST-072 | E7 | Telemetry & metrics | Error tracking with release tagging; alert on error-rate spike | 3 | P0 | S4 | SCR-8 (internal) | E2E test + demo | Done-in-code | DONE-IN-CODE 22:18 — src/errors.ts: every guarded 500 recorded {release, route, message}; spike at 5 errors/5min -> error.spike notification; GET /errors admin+; release from RELEASE env.
ST-073 | E7 | Telemetry & metrics | Feature-usage heatmap for roadmap decisions | 3 | P2 | S8 | SCR-8 (internal) | Manual QA | Done-in-code | DONE-IN-CODE 23:11 — store.incrementFeatureUse per guarded request via featureOf(path); GET /analytics/heatmap totals+byDay+topFeature.
ST-074 | E7 | Telemetry & metrics | Weekly automated metrics email to team | 2 | P2 | S8 | SCR-8 (internal) | Manual QA | Done-in-code | DONE-IN-CODE 23:11 — buildWeeklyDigest (calls/connects/visits/funnel/health/errors); POST /analytics/weekly-email/run notifies admins only (member excluded, asserted). Scheduler = hosted cron at deploy.
ST-075 | E7 | Telemetry & metrics | Health score computed per account (usage+billing+support) | 5 | P1 | S8 | SCR-8 (internal) | Integration test + manual QA | Done-in-code | DONE-IN-CODE 23:11 — health = usage(stage+volume,50)+billing(30)+support(errors+flagged,20); bands healthy>=70/watch>=40/at_risk; reasons enumerated (every stage + billing status branch tested).
ST-076 | E7 | Telemetry & metrics | Metrics export to CSV/warehouse for founder analysis | 3 | P2 | S8 | SCR-8 (internal) | Manual QA | Done-in-code | DONE-IN-CODE 23:11 — GET /analytics/export?dataset= calls¦visits¦checkins¦ledger¦scorecard_history; text/csv attachment; quote-escaping proven ("Subscribe ""Starter"""); export audited.
ST-077 | E7 | Telemetry & metrics | Alert thresholds configurable (activation drop, error spike, churn signal) | 3 | P2 | S8 | SCR-8 (internal) | Manual QA | Done-in-code | DONE-IN-CODE 23:11 — PUT /analytics/alerts (drop%/spike/health thresholds validated); sweep: activation_drop WoW (sub-threshold quiet asserted), error_spike, churn_signal; alert.triggered notifications.
ST-078 | E8 | Onboarding, docs & support | First-run checklist reaches aha-moment in <1 day | 5 | P0 | S5 | SCR-1 / SCR-9 Help | E2E test + demo | Done-in-code | DONE-IN-CODE 22:27 — checklist.ts: 7 live-computed items with concrete nextAction each; hoursSinceInstall; on-track flag flips >24h without aha, locks once reached (asserted). GET /checklist.
ST-079 | E8 | Onboarding, docs & support | Empty states teach next action on every screen | 3 | P1 | S5 | SCR-1 / SCR-9 Help | Integration test + manual QA | Done-in-code | DONE-IN-CODE 22:27 — shared teaching empty state {message,nextAction{label,method,path}} on queue/next, widget/next, beats list, route (off-day + zero-stop), notifications (each asserted).
ST-080 | E8 | Onboarding, docs & support | Help center with 15 launch articles + search | 5 | P1 | S10 | SCR-1 / SCR-9 Help | Integration test + manual QA | Done-in-code | DONE-IN-CODE 11 Sep 08:51 — src/helpCenter.ts 15 launch articles (unique ids, feature-traceable) + weighted search; endpoints /help/articles, /help/articles/:id, /help/search with teach-next-action empty state
ST-081 | E8 | Onboarding, docs & support | In-app chat with <4 business-hr first response | 3 | P0 | S10 | SCR-1 / SCR-9 Help | E2E test + demo | Done-in-code | DONE-IN-CODE 11 Sep 08:51 — src/chat.ts conversation store + <4-business-hr SLA (IST Mon-Sat 09-18 clock incl. weekend rollover test), breach sweep notifies opener once, slaReport; 4 endpoints; vendor-agnostic — external vendor (if chosen) plugs behind postMessage = Senthil decision
ST-082 | E8 | Onboarding, docs & support | In-app review ask after aha-moment (marketplace rating engine) | 3 | P1 | S11 | SCR-1 / SCR-9 Help | Integration test + manual QA | Done-in-code | DONE-IN-CODE 11 Sep 11:12 — src/reviewPrompt.ts earned-and-respectful ask: aha (ST-078) + >=10 outcomes + operational + no unanswered support; one ask per user, snooze 7d, decline forever, per-user isolation tested; deep-link REVIEW_URL + review.* telemetry; GET/POST /review/prompt
ST-083 | E8 | Onboarding, docs & support | Demo video (2 min) + interactive sandbox/demo data mode | 5 | P1 | S10 | SCR-1 / SCR-9 Help | Integration test + manual QA | Done-in-code | DONE-IN-CODE 11 Sep 08:51 (sandbox half) — src/demoMode.ts deterministic demo org on REAL domain shapes (flagged check-in, callback disposition, scorecard trend), isolated store, public /demo + /demo/reset; VIDEO (2-min) production = live-org capture per docs/ASSET_PLAN storyboard (Senthil)
ST-084 | E8 | Onboarding, docs & support | Status page + incident comms template | 2 | P2 | S10 | SCR-1 / SCR-9 Help | Manual QA | Done-in-code | DONE-IN-CODE 11 Sep 08:51 — src/publicPages.ts buildStatusPage (worst-component from live ST-070 breaker) + /status HTML (WCAG-gated), /status.json, /status/incident-template; API test walks operational->degraded->outage->recovered from real sync failures
ST-085 | EQ | Quality engineering (cross-cutting) | Unit+integration test coverage gate ≥70% on core modules | 5 | P0 | S3 | All surfaces | Evidence archived + gate review | Done | DONE 22:09 — SUPERSEDED UPWARD by D13: gate enforced at 100/100/100/100 in jest.config.js + CI (>=70 trivially met). Evidence: 156-test run output.
ST-086 | EQ | Quality engineering (cross-cutting) | E2E smoke suite runs on every deploy | 5 | P0 | S4 | All surfaces | Evidence archived + gate review | Done-in-code | DONE-IN-CODE 22:18 — tests/smoke.e2e.test.ts full MVP journey; npm run smoke; CI smoke job (needs: test) documented as post-deploy gate.
ST-087 | EQ | Quality engineering (cross-cutting) | p95 latency budgets defined and monitored per surface | 3 | P0 | S8 | All surfaces | Evidence archived + gate review | Done-in-code | DONE-IN-CODE 23:11 — budgets web300/widget200/mobile400ms; latency recorded per guarded request (surface via path/header); GET /slo p95 vs budget w/ breach list (math tested at 100-sample p95=95).
ST-088 | EQ | Quality engineering (cross-cutting) | Load test at 5x expected launch traffic | 5 | P1 | S8 | All surfaces | Evidence archived + gate review | Done-in-code | CODE-COMPLETE 23:11 — tests/load.test.ts: 300 mixed requests (50rps x 6s = 5x launch), <1% errors, in-process p95 <200ms. PENDING LIVE: real-infra run on production host (S1-10/deploy).
ST-089 | EQ | Quality engineering (cross-cutting) | Accessibility WCAG AA pass on primary flows | 3 | P1 | S9 | All surfaces | Evidence archived + gate review | Done-in-code | DONE-IN-CODE 11 Sep 08:15 (automated half) — src/a11y.ts 9-rule WCAG AA engine (lang/title/h1/alt/button-name/labels/tabindex/aria-live/contrast allow-list) with per-rule failing tests; widgetTemplate.ts primary flow gated by assertAccessible on every render; docs/WCAG_AA_CHECKLIST.md measured ratios. Live screen-reader/zoom pass = S1-10 operator half
ST-090 | EQ | Quality engineering (cross-cutting) | Backup + restore drill executed | 3 | P1 | S9 | All surfaces | Evidence archived + gate review | Done-in-code | DONE-IN-CODE 11 Sep 08:15 — src/backup.ts createBackup (secrets in, sha256 over canonical JSON), verify, restore (refuses tampered), runRestoreDrill fresh-store round-trip byte-identical on fully populated org; LIVE drill re-runs on Postgres adapter at S1-11 (R-T4)
ST-091 | EQ | Quality engineering (cross-cutting) | Chaos test: platform API outage degrades gracefully with user comms | 3 | P2 | S9 | All surfaces | Evidence archived + gate review | Done-in-code | DONE-IN-CODE 11 Sep 08:15 — src/outage.ts serviceStatus ladder off ST-070 breaker + /service-status banner; chaos suite: 5x failures -> circuit open -> CircuitOpenError fail-fast; outbox loses nothing and drains fully on recovery; broadcastOutage alerts all unmuted users with offline-mode comms
ST-092 | EQ | Quality engineering (cross-cutting) | Zero-downtime deploy verified (blue/green or rolling) | 3 | P2 | S8 | All surfaces | Evidence archived + gate review | Done-in-code | CODE-COMPLETE 23:11 — .github/workflows/deploy.yml blue/green: green built + full gate + smoke health-gate BEFORE traffic switch, blue warm for rollback. PENDING LIVE: first production deploy verification.
ST-093 | EL | Launch & listing | Marketplace listing copy A + B variants drafted and reviewed | 3 | P0 | S9 | Listing / LC items | E2E test + demo | Drafted | DRAFTED 11 Sep 08:15 — docs/LISTING_COPY_AB.md: Variant A outcome-led / Variant B persona-led, EN taglines + short/long copy + HI/TA tagline renders, Zoho One line (LC-9) rider. AWAITING Senthil A/B pick + native-speaker vernacular review
ST-094 | EL | Launch & listing | 5 screenshots + 2-min demo video meet platform asset specs | 5 | P0 | S9 | Listing / LC items | E2E test + demo | Drafted | DRAFTED 11 Sep 08:15 — docs/ASSET_PLAN_SCREENSHOTS_VIDEO.md: 5-shot list mapped SCR-2/3/5/7/6 with captions, 10-beat 2-min storyboard, Zoho spec checklist (1280x800, hosted video). CAPTURE pending live dev org (S1-10) = Senthil
ST-095 | EL | Launch & listing | Pricing page/plan matrix published with FAQ | 3 | P0 | S10 | Listing / LC items | E2E test + demo | Done-in-code | DONE-IN-CODE 11 Sep 08:51 — pricing matrix generated from billing PLANS/PLAN_LIMITS single source (drift impossible, test-enforced) + 6-entry FAQ; /pricing WCAG-gated HTML + docs/PRICING_FAQ.md; PUBLISH to listing = live half
ST-096 | EL | Launch & listing | Security/trust page (data handling, subprocessors) live | 3 | P0 | S10 | Listing / LC items | E2E test + demo | Done-in-code | DONE-IN-CODE 11 Sep 08:51 — 8 trust sections (data processed, IN residency ZOHO_DC=in, AES at rest, least-priv scopes, subprocessors incl. telephony, export/delete rights, resilience, security testing); /trust WCAG-gated + docs/TRUST_PAGE.md; LIVE publish = listing half
ST-097 | EL | Launch & listing | Submission dry-run against platform checklist by second reviewer | 3 | P0 | S10 | Listing / LC items | E2E test + demo | Done-in-code | DONE-IN-CODE 11 Sep 08:51 (automated half) — src/submissionDryRun.ts DR-01..11 executed checks ALL PASS (docs present, security pack, 15 articles, pricing source, a11y on public pages, scope manifest) + DR-12..15 human/live flagged; /review/dry-run JSON+md + docs/SUBMISSION_DRYRUN.md; SECOND-REVIEWER human walk + sign = Senthil/external
ST-098 | EL | Launch & listing | Launch-day runbook: monitoring, rollback, comms tree | 3 | P1 | S11 | Listing / LC items | Integration test + manual QA | Done-in-code | DONE-IN-CODE 11 Sep 11:12 — src/launch.ts executable runbook RB-01..10 (pre-launch gate = LIVE ST-097 dry-run, T-0 listing+traffic switch, 10-min/hourly monitor cadence off /status.json+ST-072+SLO, incident comms = ST-084 template, rollback = S8 blue/green <1min); /launch/runbook JSON+md + docs/LAUNCH_RUNBOOK.md committed
ST-099 | EL | Launch & listing | Post-launch listing SEO iteration 1 from search-term data | 2 | P2 | S12 | Listing / LC items | Manual QA | Done-in-code | DONE-IN-CODE 11 Sep 12:47 (engine half) — src/listingSeo.ts classifier + coverage vs ST-093 target vocabulary + ranked iteration plan with hold verdict; /listing/seo/analyze + sample-flagged doc. LIVE half = publisher-console search-term export + listing edits post-launch (Senthil)
ST-100 | EL | Launch & listing | First 10 design-partner reviews scheduled | 2 | P1 | S11 | Listing / LC items | Integration test + manual QA | Done-in-code | DONE-IN-CODE 11 Sep 11:12 (engine half) — src/launch.ts 10-slot tracker, forward-only stages, dupe/empty guards, stale>3d owner nudge, partnerReport launch-exit math (10 installs AND 3 posted); 4 endpoints. OUTREACH + actual scheduling = Senthil (human half); exit live-gated

## Review_Findings
REVIEW FINDINGS — cold review pass 1 (v013, 13 Sep 2026 10:55)
Every FIXED row has a pinned regression in tests/review_pass1.test.ts that fails against v012. OPEN rows need Senthil's disposition — they are not silently fixed.
ID | Severity | Module | What was wrong | Why the 100% suite missed it | Disposition | Fix / regression
F-T01 | CRITICAL | lifecycle.ts / store.ts | The 30-day retention sweep purged install telemetry and set the org status to "purged". Leads, calls, dispositions, beats, stops, visits, check-ins, subscriptions, the invoicing ledger, scorecards, audit, errors, notifications, users and queue config all survived indefinitely — against the deletion policy published in docs/TRUST_PAGE.md. | Every module was fully exercised by its own tests; nothing asserted that anything was actually gone afterwards. | FIXED | store.purgeOrg() across every dataset the privacy export enumerates, returning per-dataset counts as erasure evidence; tombstone org row + executed schedule kept as proof. 3 regressions.
F-T02 | CRITICAL | privacy.ts / store.ts | delete-my-data removed the membership row and that user's notifications only. Their calls, check-ins, scorecard history, review-prompt state, mute settings and every audit row naming them remained. | The test asserted the return shape and that the user role was gone — not that the user's records were. | FIXED | store.purgeUser(); beats released rather than deleted; audit rows retained but actor anonymised so the erasure itself stays provable. 4 regressions.
F-T03 | CRITICAL | app.ts | requireActiveOrTrial was called on 3 of ~110 routes (dial-next and two widget reads). An expired trial, a failed payment past the grace window and a cancelled subscription all left the entire product usable — leads, dispositions, beats, check-ins, imports, scorecards, analytics, mobile sync. An org never had to pay. | Every API test installs its org "now", so every test org was inside its trial. The gate was never exercised on the other 107 routes. | FIXED | Enforcement moved onto the shared guard, keyed on HTTP method for write/read. Billing, privacy, help, chat, service-status and security deliberately exempt so a lapsed org can still pay, export and get support. 4 regressions.
F-T04 | CRITICAL | app.ts / new auth.ts | Caller identity came from a plain x-user-id request header. Anyone who could reach the app could claim to be the owner of any org whose id they knew — read every lead and call, change billing, add users, export the org. The permission matrix was enforced faithfully against an identity the caller chose for themselves. | The matrix was heavily tested; the tests supplied the header, as an attacker would. | FIXED | HMAC-SHA256 org-bound session tokens (src/auth.ts). The dev header is opt-in and loadSettings refuses to boot production without SESSION_SECRET. 6 regressions. MeetSync M-F11 class.
F-T05 | HIGH | store.ts / new ledger.ts | Audit rows, notifications, error records, latency samples, install telemetry, processed webhook ids and mobile client refs all grew without bound. Latency is sampled on every guarded request, so a busy org grew the heap for as long as the process stayed up. | The load test runs for seconds. Unbounded growth is invisible at that timescale. | FIXED | Shared CappedList/CappedSet, FIFO with a dropped counter. 3 regressions. Matches VoiceBridge F-V05, TestPulse F-TP06, OnCall F-010.
F-T06 | HIGH | importer.ts / new csv.ts | Five import paths split lines on bare commas. A company name containing a comma shifted every later column (so the phone number was read out of the wrong cell) and a quoted newline split one record into two. Indian trade names carry commas routinely. | The test fixtures contained no quoted fields. | FIXED | RFC-4180 parser preserving the physical line numbers the skip reports quote. 5 regressions. Matches OnCall F-013, EngageOS F-015, VoiceBridge OBS-V1.
F-T07 | HIGH | app.ts / zohoClient.ts | createApp defaulted the retry sleep to an async no-op, so production backoff never waited: every 429/5xx retried instantly, burning Zoho API credits and defeating Launch_Checklist #4, which is the one thing LC-4 exists to guarantee. | Every test injects its own sleep, so the default was never executed — coverage counted the injected one. | FIXED | realSleep exported and used as the default; the app-level test now measures a real elapsed wait. 2 regressions. Third occurrence in the portfolio after VoiceBridge F-V06 (L-V1).
F-T08 | MEDIUM | sync.ts | A permanently rejected outcome (deleted CRM record, revoked scope) stayed pending and was retried on every sweep for the life of the org, with nothing surfacing it. | Tests attempted one or two syncs, never ten. | FIXED | Dead-letters at MAX_SYNC_ATTEMPTS=10 with an explicit operator message; dead items leave the due queue. 1 regression.
GAP-T1 | HIGH | packaging | The v012 zip shipped no jest.config.js, so npm test failed immediately in a clean clone. The 100%-coverage claim could not be verified from the delivered artifact at all. | Nothing tests the package itself. | FIXED | jest.config.js restored with the 100x4 threshold.
GAP-T2 | HIGH | docs | DATA_FLOWS.md did not exist, although ST-065's own test asserts its presence and content. The packaged suite failed on arrival — 1 of 627. | The failure was real and shipped; it was recorded in v012 as an unrelated load-test flake. | FIXED | DATA_FLOWS.md authored from GET /meta/data-flows so document and code agree.
GAP-T3 | CRITICAL | packaging | There is no listen() anywhere and no npm start. createApp exists and CI exercises it in-process, but nothing serves it: the OAuth callback and webhook URLs registered with Zoho on setup day would have nothing behind them. | Supertest binds the app object directly and never needs a server. | OPEN — pass 3 | Server entry + npm start, with the DB schema question (R-T4) alongside it. OnCall GAP-OC1 / EngageOS GAP-E1 class.
OBS-T1 | — | store.ts | VisitRecord carries no rep attribution, so a per-user erasure cannot reach field visits. Visit notes may contain personal data. | — | OPEN — your call | Schema change (add userId to VisitRecord) vs documenting visits as org-level records. Not guessed at.
OBS-T2 | — | sync.ts | Re-enqueuing an outbox ref for the same entity resets its attempt count and last error, restarting the retry clock. | — | OPEN — your call | Preserve attempts on re-enqueue, or keep the reset as deliberate "user asked again" semantics.
OBS-T3 | — | store.ts | removeUser, purgeUserNotifications and purgeTelemetry became dead once real purging existed. I deleted them rather than leave deletion-shaped code that deletes almost nothing — the exact shape that produced F-T01 and F-T02. | — | FIXED (noted) | Removed from the Store interface and the implementation; nothing referenced them.
F-T09 | MEDIUM | callQueue.ts | ringSeconds and dialMode were validated, stored and shown on the setup screen and governed nothing. Ring time never expired a call; "auto" and "manual" behaved identically. | Config validation was tested thoroughly; nothing asserted the config changed any behaviour. | FIXED (ringSeconds) / OBS-T4 (dialMode) | ringSeconds is now the abandonment window. OnCall F-008 "dead config knobs" class.
F-T10 | HIGH | callQueue.ts | A call opened and never given an outcome left its lead in status in_call permanently. The queue only selects "queued" leads, so that lead was never dialled again and no path existed to recover it — a rep closing the widget lost the lead silently. | Tests always followed nextCall with recordOutcome. | FIXED | reclaimAbandonedCalls() runs on every nextCall: the stale attempt closes as no_answer, counts as an attempt, and the lead requeues under the normal retry delay. 3 regressions.
F-T11 | HIGH | callQueue.ts | addLeads wrote straight over an existing lead with the same id, resetting attempts, lastOutcome, any scheduled callback and — worst — the do-not-call flag. The CSV importer skipped duplicates; the API path did not. | No test posted the same id twice. | FIXED | Duplicate ids rejected with the importer's wording. 1 regression pinning dnc survival.
F-T12 | HIGH | callQueue.ts / disposition.ts | A callback disposition on a lead that had used its attempts requeued the lead and showed it scheduled, but the queue filter excluded it — the callback the customer asked for never rang. | The disposition tests asserted the lead record; the queue tests used fresh leads under the cap. Neither crossed the boundary. | FIXED | A due callback outranks the attempt cap. 2 regressions.
F-T13 | MEDIUM | reviewPrompt.ts | The documented week-long snooze was unreachable: a snooze always follows a shown ask, which sets askedAt, and the already-asked rule fired first — so every snooze was a silent permanent decline and SNOOZE_MS governed nothing. | Snooze was tested on a state where the ask had not been shown, which is not how the flow runs. | FIXED | An expired snooze re-opens the ask; decline and a posted review stay permanent. 2 regressions.
F-T14 | MEDIUM | checkins.ts | Route-sequence enforcement judged completion over every check-in ever recorded, so a stop visited on any earlier day counted as done for today. With a short or zero cooldown the enforcement stopped enforcing anything. | The fixture only ever had one day of check-ins. | FIXED | Completion scoped to the current day. 2 regressions.
F-T15 | HIGH | privacy.ts / backup.ts | The export bundle had no stops field at all. So the data export was incomplete, the backup did not contain stops, restoreBackup could not restore them — and runRestoreDrill compared two exports that both omitted them, reporting ok=true over a restore that loses every stop on every beat. After a real restore, every beat is empty and the route planner returns nothing. | The drill hashes exports against each other. A dataset missing from both sides is invisible to it — the drill can only prove what the export knows about. | FIXED | stops added to the bundle, restore and drill; store.listAllStops added. 3 regressions. Conversations, design partners, review prompts, alert config and the outbox are still outside the bundle — see OBS-T5.
OBS-T4 | — | callQueue.ts | dialMode accepts auto¦manual and nothing anywhere behaves differently. Implementing it means deciding what manual mode should do — most likely propose the next lead without opening the attempt until the rep confirms. | — | OPEN — your call | Implement the semantics you want, or drop the knob from setup rather than ship a setting that does nothing.
OBS-T5 | — | privacy.ts | Support conversations, design partners, review-prompt state, alert config, the CRM outbox, feature-use counters and latency samples are not in the export bundle, so they are outside both the data export and the backup. | — | OPEN — your call | Operational vs customer data: decide which belong in a subject data export and which only in an operational backup. F-T15 fixed the one that is product-critical.
GAP-T3 | CRITICAL | packaging | No listen() and no npm start existed. createApp was only ever bound directly by supertest, so the OAuth callback and webhook URLs registered with Zoho on setup day had nothing behind them, the deploy workflow curled a /healthz that was never served, and the 30-minute dev-org guide was unrunnable. | Supertest binds the app object; a server is exactly the thing an in-process suite never needs. | FIXED (was OPEN in v013) | src/server.ts + bin/telefield.js + npm start/build. Verified by booting it and fetching real routes over a socket. 4 regressions.
VER-T1 | CRITICAL | webhooks.ts / app.ts | LIVE-BLOCKING. R-T5 carried our webhook signing scheme as an assumption from S1. Zoho publishes X-Zoho-Webhook-Signature with t= and v= components, and its own example timestamp is in milliseconds. We read X-TeleField-Signature with s= and compared the timestamp against seconds, so every real webhook would have failed the tolerance check and returned 400 — extension.uninstalled included, which means no token wipe and no retention clock on the day. | The suite signs its fixtures with our own signer, so it proved we are self-consistent, never that we match Zoho. | FIXED | Both header names and both component names accepted; timestamps normalised from seconds or milliseconds. R-T5 closed. 4 regressions. FlowCast VER-001 / OnCall VER-OC1 class.
VER-T2 | HIGH | zohoClient.ts | ApiResponse had no headers field at all, so Retry-After (Zoho tells us exactly how long to wait) and X-API-CREDITS-REMAINING (sent once an org passes 50% of its allowance) were unreachable. Zoho CRM rate-limits on CREDITS over a rolling 24-hour window plus concurrency — an org that exhausts credits is down for hours, and blind exponential backoff keeps spending them. | The transport type was designed around status and body; nothing asked what the server was telling us. | FIXED | Optional headers on ApiResponse; Retry-After honoured over computed backoff; credit balance recorded with a low-balance flag. 3 regressions.
VER-T3 | HIGH | lifecycle.ts / app.ts | Zoho Sigma triggers cover disable, enable and update as well as install and uninstall. All three were answered with {ignored}, so a disabled extension kept its tokens and the app went on serving and billing an org that had switched it off. | Only the two events we had thought of were ever sent to the webhook route in tests. | FIXED | Disable suspends the org (the shared guard already 404s anything not active), enable restores, update is recorded. OrgStatus gains "disabled". 3 regressions.
R-T4 | — | persistence | Schema now exists — migrations/001-004, cascade-deleted from orgs so the retention sweep is one DELETE — with npm run migrate dry-running in CI. The Postgres ADAPTER behind the Store interface is still not built, so a restart still loses everything. | — | PARTIALLY CLOSED — your call | Build the adapter, or accept in-memory for the design-partner pilot and say so on the trust page. Do not let the schema imply persistence that is not there.
F-T16 | CRITICAL | crypto.ts / new tokenVault.ts | "OAuth tokens and secrets are encrypted at rest (AES)" is published on the trust page, in two help articles, at /meta/data-flows and in the ST-068 evidence pack. Nothing encrypted a token: access and refresh tokens went into the store, the export bundle and every backup in plaintext. | crypto.ts was called from one place — the evidence pack, which encrypted the literal string "refresh-token-value", decrypted it, and passed the control. The test proved the algorithm worked, never that anything used it. | FIXED | src/tokenVault.ts seals on the install and refresh write paths; production refuses a plaintext token rather than falling back; SECRETS_KEY (which crypto.ts had always named in its own error) is now a real config value and a production boot prerequisite; SEC-02 exercises the seal. 4 regressions.
F-T17 | CRITICAL | lifecycle.ts / new scheduler.ts | The 30-day retention sweep had no caller anywhere — no route, no timer, nothing. Built in S1, corrected in v013 to erase properly, and it would never have executed once in production. The deletion policy published on the trust page was a function nobody invoked. | Coverage measures whether code runs under test, not whether anything in the product would ever call it. | FIXED | Scheduler runs it first on every tick, before any per-org work. 1 regression + the reachability gate. OnCall F-009 / TestPulse pass-3 class.
F-T18 | HIGH | outage.ts | ST-091 degradation comms existed and were never triggered, so the outage notice users most need was the one that never went out. | Unit-tested in isolation; nothing asked who calls it. | FIXED | Swept per active org against the live circuit-breaker state. 2 regressions.
F-T19 | HIGH | backup.ts | ST-090 backups and the restore drill ran in CI over fixtures. Nothing ever took a backup of real data, so the drill proved a round trip that had no input. | The drill is the test. Nobody asked what it would restore from on the day. | FIXED | Daily backup in the sweep over the same bundle the drill verifies. 1 regression.
F-T20 | HIGH | sync.ts | Help article ha-11 and the status page both promise that outcomes and check-ins "sync automatically on recovery". The outbox drained only when a human POSTed /sync/retry. | processOutbox had a route and a test; neither is a schedule. | FIXED | Drained per active org on every tick. 1 regression + the published-claims gate. VoiceBridge F-V11 class.
GATE-1 | — | tests/review_pass4.test.ts | Reachability gate: 15 named behaviours must have a call site in src outside their own declaration. Heuristic by design — it cannot prove the caller is itself reachable, only that nothing in the product is orphaned, which is the shape this defect class actually takes. | — | ADDED | Fails on the class, not the instance. Portable to the other 10 products.
GATE-2 | — | tests/review_pass4.test.ts | Published-claims gate: if the copy says "encrypted at rest" a seal must be wired into the token write path; if it says "syncs automatically" something must drain on a schedule; if it says deletion is scheduled a sweep must be scheduled; plan prices must come from the billing source. | — | ADDED | The four claims that were false in v012 can no longer become false silently.
GAP-T4 | HIGH | ops | No scripted live verification existed — nothing an operator could run against a deployed instance to know whether it worked. | — | FIXED | npm run sweep: 12 steps, 9 automated and 3 operator, non-zero exit so it gates a deploy. Executed against a real running instance: SWEEP GREEN.
GAP-T5 | HIGH | docs | No dev-org setup guide existed for the product whose siblings all had one — and before v015 it could not have been written truthfully, because there was no server to point Zoho at. | — | FIXED | docs/DEV_ORG_SETUP.md, executable end to end, stating plainly that the Postgres adapter is unbuilt and a restart loses data.
F-T21 | CRITICAL | app.ts / new oauthState.ts | The OAuth install had no state parameter at all — no CSRF protection on the one flow that hands us a customer's CRM credentials. A crafted callback URL delivered to a logged-in admin could complete an install the admin never started. | Every install test drove the callback directly with a code the test had chosen, which is precisely what an attacker does. | FIXED | /oauth/start mints a single-use, ten-minute HMAC-signed state; the callback consumes it once. 4 regressions. OnCall F-015 class.
F-T22 | CRITICAL | app.ts | org_id came from the query string, so whoever called the callback decided which org row the freshly exchanged tokens were written against — an attacker could bind their own Zoho org tokens into a victim's TeleField org, or a victim's into theirs. | Tenancy was correct everywhere it was enforced; nobody asked where the tenant identity came from at install time. | FIXED | The org is read from the signed state and never from the query; an org_id in the URL is ignored. Pinned by a regression where the attacker appends their own org_id and the state still wins. MeetSync M-F11 class on the install path.
F-T23 | HIGH | app.ts | POST /demo/reset wiped and reseeded the shared demo tenant — the one reviewers and prospects are looking at — with no authentication of any kind. A single unauthenticated request during a Zoho review could blank the demo mid-evaluation. | The demo store is isolated from customer data, so the route looked harmless; availability was never considered. | FIXED | Operator token required when configured; OPERATOR_TOKEN is now a production boot prerequisite. 2 regressions. OnCall F-017 class.
CLEAN-1 | — | app.ts / roles.ts | Cross-tenant isolation (MeetSync M-F04 / OnCall F-014) checked: an owner of one org addressing another org is rejected, and sees only its own data. No defect. | — | VERIFIED + PINNED | A clean result recorded as a finding, so the next reviewer does not have to rediscover that it was checked.
CLEAN-2 | — | app.ts | Express rejected-promise handling (MeetSync M-F21) checked: a throwing handler returns 500 with a scrubbed message rather than hanging the request open until the client times out. Express 5 forwards rejections; MeetSync was on Express 4. No defect. | — | VERIFIED + PINNED | Pinned so an Express downgrade cannot silently reintroduce it.
GATE-3 | — | tests/review_pass5.test.ts | Public-surface gate: every route bypassing guarded() must be in an explicit list with a reason, each public route must answer without credentials, and none may echo customer data. | — | ADDED | Portable. docs/REVIEW_GATES.md explains all three gates and how to port them.
PG-1 | HIGH | pgStore.ts | scorecard_history.day is a DATE column. node-postgres returns a JS Date for it, and the hydration path did String(value).slice(0,10) — which yields "Tue Sep 01". Every scorecard row would have been silently corrupted on the first restart. | Nothing had ever run against a real driver. A mocked client returns whatever the mock was told to return, which is why the adapter was written against a live database rather than a fake. | FIXED | Date-only formatting that also handles a driver returning text. Pinned in the contract suite.
PG-2 | CRITICAL | app.ts | The durability flush was wired into guarded() only. The OAuth callback (which stores the customer's tokens) and the webhook (which processes uninstall and wipes them) are public and unguarded, so their writes sat in the write-behind queue until the next scheduler tick — up to a minute. A crash or deploy in that window lost the install, or left tokens live after an uninstall. | The unit suite injects no flush, so the wiring gap was invisible; it surfaced when the live sweep posted a signed webhook and the database row was still absent. | FIXED | Every public mutating route flushes before responding. 1 regression asserting six separate public writes each flush.
R-T4 | — | persistence | Postgres persistence: schema, adapter, hydration, per-request flush, CI job. Production refuses to boot without DATABASE_URL. | — | CLOSED | Boundaries stated in docs/DEV_ORG_SETUP.md: write-behind flushed per request (a crash mid-request loses that request) and single-writer (blue/green must drain blue first).
GAP-T6 | CRITICAL | app.ts / new screens.ts | Nine screens are named across the traceability matrix and 92 stories marked Done-in-code depend on them. One existed. Every "set up X in one screen" story described an API endpoint; the listing screenshots in ST-093/094 had nothing to photograph, and the first thing a Zoho reviewer opens would not have been there. | Coverage, reachability and published-claims gates all pass on a product with no UI. The specification lived in the tracker and the tests never read it — which is why this was found by reading the tracker against the code. | FIXED | Eight screens built in src/screens.ts, each from the view-model its JSON route already serves; role-gated; real empty states; org data escaped. 50 regressions.
GATE-4 | — | tests/review_pass6.test.ts | Specified-screens gate: every screen the matrix names must return 200 for its role, render its heading, and pass the WCAG AA audit on a real render with real data. | — | ADDED | Portable — VoiceBridge GAP-V2 and TestPulse's Custom UI gap are the same class. Porting notes in docs/REVIEW_GATES.md.
ST-089 | — | a11y.ts | The WCAG AA automated audit covered one screen, because one screen existed. It now covers nine screens plus the three public pages, on every render. | — | WIDENED | The live screen-reader pass on the dev org remains the operator half of the story.
F-T24 | HIGH | app.ts / store.ts | All three offline batch endpoints consumed the client dedupe reference before attempting the item. An item rejected for a TRANSIENT reason — an outcome referencing a call the server had not yet seen, a check-in for a beat that had not synced — returned "duplicate" on every later retry and was lost permanently. On the offline path, whose whole purpose is not losing records. | The suite tested duplicates (same ref applied twice) and rejections (bad payload) separately. Nobody tested a rejection FOLLOWED BY a retry, which is what a device on a bad network actually does. | FIXED | hasClientRef checks without consuming; the reference is claimed only after the item applies. 4 regressions across all three endpoints.
GAP-T7 | HIGH | ops / listing | LC-3 and ST-093/094 needed screenshots of screens that did not exist until v019, and then needed a live install to photograph. The asset plan named five shots with no mechanical way to produce any of them. | Not a code defect — a delivery gap that a code-only review does not look for. Found by reading the gate checklist against what a person could actually do. | FIXED | npm run assets: nine screens from the demo tenant at a fixed clock into assets/, with an index in capture order, audited on render and re-checked in CI.
OBS-T7 | — | demoMode.ts | The demo tenant yields a 45.5 "watch" health score on SCR-8 — what a prospect sees in the demo, and what the listing screenshot would show. | — | OPEN — your call | Enrich the demo seed, or leave it honest. Data was not tuned to flatter a screenshot.
OBS-T8 | — | publicPages.ts / billing.ts | The pricing page and FAQ answer "Can I pay in INR?" with an unqualified yes; the INR route is the marketplace channel at Zoho's conversion, while the external Stripe channel is USD. True for the channel most customers will use, imprecise for the other. | — | OPEN — your call | Qualify the FAQ by channel, or drop the external channel for India entirely (it also simplifies LC-8).
GAP-T8 | HIGH | docs / submissionDryRun.ts | DR-12 — the gate item that ends with a second reviewer signing — reads "walks THE PACK end-to-end". No review pack existed, and the dry run reported READY because it checked the six documents that had been listed rather than the one DR-12 depends on. ST-097 and Senthil's DR-12 item were both blocked on an artifact nobody had written. | A dry run can only check the list it was given. Nothing compared that list against what the checklist items actually require. | FIXED | docs/REVIEW_PACK.md written for a real external reviewer, including the eight-pass history and the coverage lesson; DR-16 added so the dry run fails without it. 4 regressions.
CLEAN-3 | — | tracker evidence column | All 100 story evidence citations checked against the code: 27 modules, 34 routes, 8 documents. Every one resolves. No stale citation survived eight passes of refactoring, including the modules that were deleted in v013 as superseded. | — | VERIFIED + PINNED | GATE-5 keeps it true. Clean results are findings too — otherwise the next reviewer re-runs the same check from scratch.
GATE-5 | — | tests/review_pass8.test.ts | Evidence-citation gate over docs/EVIDENCE_MAP.json: cited modules exist, cited routes are registered, cited documents are on disk. | — | ADDED | Portable. Route parameters must be normalised before matching — the first draft flagged nine healthy routes.
DR-15 | — | submissionDryRun.ts | The dry run still told an operator that screenshots need the live Zoho org. Since v020 they do not. | — | FIXED | Corrected to point at npm run assets. An overstated blocker is still an untrue published statement.
GATE-1b | HIGH | scripts/review-gates.js | The reachability gate counted a call site anywhere, including inside the defining module. A dead wrapper calling a dead function therefore looked reached — precisely the F-T17 shape (runDeletionSweep calling sweepDeletions, with nothing calling either). Found by mutation-testing the gate rather than trusting it. | The gate had only ever been run against code that was already correct. | FIXED | Cross-file call site required; sameModuleAllowed lists the deliberate exceptions.
GATE-2b | HIGH | scripts/review-gates.js | The published-claims gate matched its code pattern anywhere in the source tree, so "tokens are sealed" was satisfied by the refresh path while the install path had been unwired — a half-true claim passing as true. | Same reason: a gate written against correct code. | FIXED | Claim patterns accept an inFile scope; the encryption claim now requires the seal on both the install and refresh paths.
R-T9 | — | portfolio | Porting the gates to the other ten products was blocked on them being TeleField-specific jest tests. | — | ADDRESSED (TeleField side) | Kit is config-driven and portable; the copying is now two files and a config edit. Actually running it on each sibling is still open and needs their repos.
F-T25 | HIGH | scheduler.ts / backup.ts | The daily backup built the full bundle, reported its sha256 and discarded the bundle. Nothing was ever written, so ST-090's promise amounted to a checksum of data that existed only for the duration of the function call. The restore drill stayed green throughout because it restores from a bundle held in memory during the test. | Pass 4 asked "does anything call this?" and stopped there. It never asked the next question: when it runs, does anything survive it? | FIXED | writeBackup to BACKUP_DIR with read-back integrity verification and pruning to the last 14; the sweep report carries the file path; a write failure is a reported job error. 6 regressions.
GAP-T9 | HIGH | .github/workflows/deploy.yml | The blue/green workflow predated persistence: no migration ran on deploy, and traffic switched with both slots live. The store is single-writer with write-behind flushing, so two slots over one database diverge in memory and the loser's queued writes are lost — a corrupted deploy, not a slow one. It also called itself zero-downtime. | CI runs the suite; nothing reads the deploy workflow against how the store actually behaves. The workflow was correct for the stateless product it was written for. | FIXED | migrate job before green serves; explicit drain-blue-then-switch with blue warm and read-only; "zero-downtime" removed. 3 regressions reading the workflow.
GAP-T10 | HIGH | ops / ST-088 | No measurement of the running server existed. Every number held about TeleField under load came from an in-process harness with the HTTP layer, socket handling and the per-request durability flush left out — an honest approximation that had quietly become the only evidence. | Nothing was wrong with the in-process test; it was simply never replaced once a server existed. The gap is between "we measured something" and "we measured the thing we ship". | FIXED | scripts/loadtest.js over real HTTP with error-rate and p95 gates; LOAD_FIXTURE_ORG seeds a tenant at boot (refused in production); CI runs a 200-rps pass. Measured 500 rps at p95 3.7ms.
F-T26 | HIGH | app.ts / scheduler.ts | The scheduler performs every piece of unattended work in the product and reported it to nobody. Per-job errors were collected into a report that no route, log line or metric ever surfaced, so a sweep failing on every tick was indistinguishable from one succeeding. | The scheduler tests assert the report object; nothing asked whether a human could ever read it. Found while debugging a missing backup in a running process and having no way to ask it anything. | FIXED | GET /ops/sweeps behind the operator token, plus SWEEP_INTERVAL_MS so an operator can tick faster when diagnosing. 5 regressions.
GAP-T11 | MEDIUM | bin/telefield.js | The entry point runs dist/ and served a stale build silently. It misled me twice in one session; in production the symptom is a deploy that appears to do nothing. | No test runs the compiled artifact — the suite runs TypeScript directly. | FIXED | src/dist mtime comparison; refuses to start on a stale or missing build with a one-line instruction. 2 regressions.
VER-T4 | CRITICAL | zohoAuth.ts / config.ts | LIVE-BLOCKING. The authorization-code exchange sent no redirect_uri. Zoho marks it required for grant_type=authorization_code and rejects the call without it, so every marketplace install would have failed on the day. | Every test injects its own OAuth transport and asserts what we do with the RESPONSE. Nothing in 1,261 tests had ever asserted what we SEND. | FIXED | redirect_uri sent from the new ZOHO_REDIRECT_URI setting, mandatory at boot in production; 3 regressions in tests/review_pass11.test.ts.
VER-T5 | CRITICAL | app.ts / zohoAuth.ts / zohoClient.ts / new zohoDc.ts | LIVE-BLOCKING for any customer outside the configured DC. Zoho names the customer's data centre on every install callback (location + accounts-server) and requires the exchange, refresh and API calls to use it; TeleField used one process-wide ZOHO_DC, so a US install would have been exchanged against accounts.zoho.in. Separately, accounts-server is an attacker-controllable parameter on a public route and would have been a place to send our client secret. | No test had a second data centre in it, and the string interpolation accounts.zoho.${dc} is correct for the five DCs we serve — so the bug was in what the code never considered, not in what it computed. | FIXED | src/zohoDc.ts registry + migrations/006_dc.sql + per-org routing; unserved DC refused with a named error; accounts-server allowlisted, never used as a URL. 9 regressions.
VER-T6 | MEDIUM | docs / listing assets | The asset capture plan stated logo, banner and video specs that came from nowhere. Published: logo 120x120, banner 310x142, video as an iframe link, plus a main screenshot showing what the extension adds inside CRM and a developer branding block. It also still claimed capture needs the live dev org, which DR-15 corrected in v021. | Not a code defect — a delivery document nothing checks. The same class as TestPulse's wrong Marketplace asset spec. | FIXED | Capture sheet rewritten to the published numbers with the superseded ones removed; 3 regressions pin the numbers and the removed claim.
VER-T7 | HIGH | docs / submissionDryRun.ts | Zoho's approval criteria require a listing to disclose third-party accounts the extension needs, the data transferred on install, edition compatibility and support channels. The copy carried none of the four, and TeleField requires the customer's own cloud-telephony account with its own charges. | The dry run checked that documents EXIST, never what they say. | FIXED | Four disclosures added to LISTING_COPY_AB.md and gated by DR-17, mutation-tested: removing any one turns the dry run NOT READY and names it.
GAP-T12 | HIGH | tests/pg_contract.test.ts / store.ts | The restart proof compared privacy export bundles, which omit seven datasets by design (outbox, conversations, design partners, review prompts, alert config, feature use, latency). Durability for those rested on ad-hoc spot-checks — the F-T15 shape one level up. | The test that proves the restart and the bundle that defines 'everything' were the same artefact. | FIXED (proof gap; no defect behind it) | Full-snapshot fidelity across every dataset plus a table census; the one real mismatch it surfaced — org.dc absent vs null — is normalised at the store boundary.
GAP-T13 | LOW | scripts/loadtest.js | The harness header's own example invocation defaulted LOAD_USER to a user that is a member of no seeded org, so run as written it produced 87.5% 401s. CI and the setup guide pass the right user, so no recorded number is affected. | Nothing tests the documentation nearest the code. | FIXED | Default is now the fixture's actual owner.
CLEAN-4 | — | pgStore.ts / app.ts | Concurrency and the R-T14 crash boundary probed against real Postgres: overlapping writes all land, a duplicate client ref raced against itself applies exactly once, a crash between mutation and flush loses exactly that request, and writes queued during a flush are drained by it. No defect. | — | VERIFIED + PINNED | Recorded as a finding so the next reviewer does not repeat it. Limit stated: driven through the handler stack, not over a socket.
OBS-T9 | — | commercial / R-T3 | Zoho's payments page: commission paid monthly, only above a USD 100 outstanding balance, ~15 working days after approval; and 'for extension developers, the total value and commission will be equal', which sits oddly beside the 15% share assumed in R-T3. | — | OPEN — your call | Confirm the share and payout terms at partner-console setup; it changes the cash timing behind G-02.
GAP-T14 | CRITICAL | packaging / in-CRM surface | No Zoho CRM extension bundle existed. A CRM extension is a Connected App plus an uploaded resource bundle (plugin-manifest.json + app/ files Zoho hosts and frames at declared widget locations). The install would have completed and nothing would have appeared inside CRM. | Every test drives the HTTP surface directly. Nothing asked what the platform renders after an install, and the setup guide's console step stopped at the connection and the webhook. | FIXED | Generated bundle (src/extension.ts + npm run extension) with four widget bootstraps; --check gates drift in CI; 8 regressions bind the bundle to the routes, host, locales and scopes it describes.
F-T27 | CRITICAL | auth.ts / app.ts | Caller identity came only from a request header, and a framed navigation cannot set one — so every widget iframe, and every browser address bar, would have received 401 from the first request. The nine screens were unreachable by the only client that renders them. | supertest sets headers by hand, so 1,302 tests drove the screens in a way no browser ever could. | FIXED | Screens accept the signed org-bound session from a tf_session cookie; GET /session/start makes the one hop, refuses off-host redirects, sets Referrer-Policy: no-referrer, and is SameSite=None; Secure in production. 6 regressions.
D-T1 | — | widget identity | How the widget proves which CRM user is viewing it. A user id read from the SDK in the browser is a claim, not a credential; accepting it would rebuild F-T04. | — | OPEN — your call | Verify Zoho's signed widget parameters server-side, or handshake per install using the OAuth token we already hold. Needs the dev org to see what Zoho sends.
A-X1/A-X2 | — | extension.ts | The manifest service string and the CRM SDK asset URL are taken from the toolkit's CRM template rather than published docs — the only unverified values in the bundle. | — | OPEN — confirm at setup | Isolated in one module with a confirm step (zet init prints the expected manifest); one-line correction either way. The R-T5 containment applied before the assumption spreads.
F-T28 | CRITICAL | app.ts / auth.ts | Accepting the session from a cookie (F-T27, one release earlier) made every mutating route cross-site forgeable: the browser attaches the cookie to a request from any site, and SameSite=None — which a third-party iframe requires — removes the browser's own protection. | The vulnerability did not exist when the tests were written. Nothing re-reviews a release for what its own fix changed. | FIXED | Cookie identity for GET/HEAD only; state-changing requests require the x-telefield-session header, which a cross-site form cannot set. 5 regressions, and SEC-07 asserts the posture in the evidence pack.
F-T29 | HIGH | app.ts / zohoDc.ts | No browser-hardening headers: no nosniff, no referrer policy, and nothing restricting who may frame the screens — on a product that had just begun serving HTML designed to be framed. | Header behaviour is invisible to a supertest assertion about a response body. | FIXED | nosniff + no-referrer + frame-ancestors admitting only Zoho CRM hosts, derived from the DC registry so a new DC cannot be left out. 3 regressions, SEC-08.
F-T30 | MEDIUM | app.ts / auth.ts | The operator token was compared with !== — timing-unsafe — while the webhook signature had used timingSafeEqual since S1. | A timing side channel produces identical pass/fail behaviour, so no functional test can see it. | FIXED | One constantTimeEquals helper, both operator call sites. 3 regressions.
F-T31 | MEDIUM | app.ts | The 100kb request-body limit was a library default nobody had chosen, and the three offline batch endpoints accepted unbounded item counts within it, each item costing a store write. | Tests post two or three items. | FIXED | MAX_BODY_SIZE and MAX_BATCH_ITEMS stated explicitly; oversized batch gets a 422 naming the limit and telling the device to split the sync. 3 regressions across all three endpoints.
GAP-T15 | HIGH | docs / securityEvidence.ts | docs/SECURITY_EVIDENCE.md — read by a marketplace reviewer and handed to a pen-test vendor — was a render of release v009, seventeen releases old. The dry run checked only that the file existed. | DR-03 asserts presence, not currency — the same shape as GAP-T8. | FIXED | Regenerated and pinned by a drift test against a fresh assessment run; pack gained SEC-07 and SEC-08.
GAP-T16 | HIGH | extension.ts / bundle | The bundle declared three locales to the platform and shipped strings for one. Zoho requires a matching file under app/translations for every declared locale, so the bundle would have failed validation and a Hindi or Tamil CRM would have rendered a widget with no text. | The bundle was one release old and its only tests asserted the manifest's shape, not that the platform's rules about that shape were met. | FIXED | Catalogues for en/hi/ta shipped as app/translations/*.json; the manifest's locale list is derived from the catalogue keys; the bootstrap selects at runtime and falls back to English. 4 regressions.
CLEAN-5 | — | importer.ts / csv.ts / disposition.ts / privacy.ts | Indic data probed end to end with real Tamil and Hindi content — import, queue, disposition config, export, and quoted fields containing commas and newlines. No defect. | — | VERIFIED + PINNED | Pinned so the F-T06 class cannot return, and so the asset plan's Tamil-disposition screenshot instruction is backed by a test.
L-T3 | — | listing copy | 'Vernacular-ready dispositions' read as a shipped feature; the truth is that an org can name its own dispositions in any language. The claim is narrowed to what the product backs, disclosed to buyers, and gated. | — | NARROWED | DISCLOSURE-LANGUAGE gated by DR-17; a claims-gate rule binds the word 'vernacular' to the catalogues.
F-T32 | HIGH | store.ts / pgStore.ts / scheduler.ts | The FIFO caps from v013 bounded memory only. Every capped collection still INSERTed into Postgres and nothing deleted, so the database grew without limit — latency samples alone by tens of millions of rows a day at the measured 500 rps — and hydrate() read every row at boot, making each restart slower than the last. | Every test runs for seconds. A cap that works in a five-second test looks identical to one that works for a year. | FIXED | Daily prune with per-dataset windows (7/30/60/90 days) reported in the sweep, plus bounded hydration reading the newest rows up to the cap. Audit rows bounded at hydration, never deleted. 30 regressions including a 90-day simulation and a Postgres row-count check.
L-T4 | — | review practice | A cap that is not also a cap on storage is a cap on nothing, and the test that finds it is the one that lets the clock run. Fifteen passes examined behaviour at a point in time; the first to simulate months found a defect none of the others could see. | — | LOGGED | The ninety-day harness is portable to any sibling with a scheduler — the same shape as the review-gate kit.
F-T33 | CRITICAL | pgStore.ts / app.ts / server.ts | node-postgres emits 'error' on a Client whose connection drops and an unhandled 'error' event terminates Node, so a database restart, failover or network blip killed the process outright — and the write-behind queue died with it. Separately, failed writes were dropped and reported into an array nobody read, while the HTTP layer kept answering 200 to writes it could not make durable. | Every test and every load run had a healthy database. Nothing had ever taken it away — which took one command. | FIXED | Error event handled; connection failures hold the batch in order and mark the store unhealthy; mutating requests 503 with Retry-After while reads continue; /healthz is readiness with a pendingWrites count; failure log capped. 33 regressions plus 7 new database-backed tests.
L-T5 | — | review practice | The failure modes worth testing are the ones you can cause. Sixteen passes of reading code did not find F-T33; stopping the database found it in one command, and re-running the same command is what proved the fix. | — | LOGGED | The chaos experiment is three commands and belongs in the pilot runbook, not only in a review.
F-T34 | HIGH | bin/telefield.js / server.ts / app.ts | Nothing handled SIGTERM, so every deploy, container restart, autoscaler event and blue/green drain killed the process outright — cutting off in-flight requests and discarding the write-behind queue. The deploy workflow's drain step drained the router, not the process. | No test starts a process and signals it; the suite starts an app object. The deploy workflow is YAML nobody executes in CI. | FIXED | SIGTERM/SIGINT drain in order (route away, refuse writes, finish in-flight, flush, close DB, exit 0), bounded by SHUTDOWN_TIMEOUT_MS; /healthz reports draining; deploy workflow names the step. 31 regressions.
OBS-T10 | — | F-T34 evidence | The live SIGTERM run was not completed — the container stopped holding background processes. The drain is proven by tests, not observed on a real process. | — | OPEN — operator check | Watch for 'drained cleanly' and exit 0 on the first production deploy; if it does not appear, the handler is not reaching the container's init.

## Sprint_Status_Rollup
SPRINT STATUS ROLLUP — live formulas over Traceability_Matrix
Do not edit computed cells. 'Done' counts Done-in-code + Done. Exit criteria from v006 Sprint_Board.
Sprint | Focus | Stories | Points | Done | Done points | % points done | RAG (manual) | Exit criteria
S1 | Foundation (2 wks) | [5 empty] | GREEN — 4/4 stories done-in-code; live install pending | App installs cleanly in dev store/org; telemetry firing
S2 | Call queue + auto-dial pt 1 | [5 empty] | GREEN — 6/6 done-in-code; exit demo to Senthil pending | Call queue + auto-dial happy path demoable
S3 | Call queue pt 2 + Disposition start | [5 empty] | GREEN — 11/11 done-in-code; exit demo pending | Call queue complete with tests; Disposition skeleton
S4 | Disposition + callback engine | [5 empty] | GREEN — 9/9 done-in-code; MVP loop exit MET (smoke suite) | MVP loop usable end-to-end internally
S5 | Beat/route planner + alpha hardening | [5 empty] | GREEN(code) / AMBER(exit) — 12/12 done-in-code; dogfooding exit needs live alpha | Internal alpha: team dogfoods daily
S6 | Billing + Visit check-in (geo) | [5 empty] | GREEN — 13/13 done-in-code; exit (charge + up/downgrade) MET in code; live sandbox charge rides on S1-10 | Can charge a test customer; up/downgrade paths work
S7 | Private beta (design partners) | [5 empty] | GREEN(code) / AMBER(exit) — 5/5 done-in-code; private-beta exit needs live org + 5 external users | 3+ partners active weekly; NPS pulse >30
S8 | Beta iteration + Manager scorecards | [5 empty] | GREEN(code) — 22/22 done-in-code; ST-066 vault + ST-088 real-infra load + ST-092 live deploy verify pending S1-10/production | Beta cohort WoW retention >60%
S9 | Marketplace review prep | [5 empty] | GREEN(code)/AMBER(exit) — 5/7 done-in-code (22 pts), 2 drafted (ST-093/094, 8 pts) awaiting Senthil pick + live capture; exit (submission accepted) needs S1-10 org + pen-test vendor | Review submission accepted into queue
S10 | Review remediation + docs | [5 empty] | GREEN(code)/AMBER(exit) — 7/7 done-in-code (24 pts); dry-run READY 11/11 automated; exit (marketplace APPROVAL) is live-gated: S1-10 org, review pack upload, second-reviewer sign, pen-test archive | Marketplace approval obtained
S11 | Launch | [5 empty] | GREEN(code)/RED(exit) — 3/3 done-in-code (8 pts); exit metrics (10 installs, 3 reviews, activation>40%) are 100% live-gated on listing approval + partner outreach (Senthil) | First 10 installs; first 3 reviews; activation >40%
S12 | Iterate & scale decision | [5 empty] | GREEN(code)/BLUE(live) — 1/1 done-in-code; iteration 1 executes post-launch on real search data. CODE PHASE COMPLETE ACROSS ALL 12 SPRINTS | Growth model doc with CAC/LTV first estimates
TOTAL | (S1-S12)

## RAID_Carryover
RAID — seeded from v006 Risk_Register + build findings
ID | Type | Raised | Item | Status | Notes / Mitigation
R-T1 | Risk | v006 | Zoho builds native telecalling depth (High/Medium) | Open | Beat-plan + vernacular + telephony-bridge depth; ecosystem partnership.
R-T2 | Risk | v006 | India cloud-telephony provider API instability (Medium/High) | Open | Dual-provider abstraction planned (S3+); health checks + failover.
R-T3 | Risk | v006 | 15% marketplace share + INR pricing squeezes margin (Medium/Medium) | Open | Annual prepay discounts; India-lean costs ($15k/mo base, model M18 cum -$296k pre-scale).
R-T4 | Constraint | 21:05 | Sandbox has no Postgres — S1 persistence is in-memory behind typed Store interface (D16) | CLOSED v018 | Adapter built and verified against real Postgres 16; migrations applied and proved idempotent; CI runs both against a service container.
R-T5 | Risk | 21:05 | Zoho webhook signing scheme assumed (own HMAC t/s header) pending Sigma docs verification — real marketplace notification format may differ | Open | Verify with Launch #1 dev-org setup at S1-10; verification layer isolated in src/webhooks.ts so a format change is one-module.
A-T1 | Assumption | 21:05 | D13 (interviews parked, 100% coverage) applies portfolio-wide, incl. TeleField S0 discovery | Open | Per Senthil 20:45/21:05 instructions; S0 activities (PRD, terms verification, wireframe links for v006 col E) remain owed and are NOT marked done.
A-T2 | Assumption | 21:05 | D15 mode (parallel vs swap) pending — both RevRescue and TeleField S1 code now exist | Open | Senthil to ratify; R1 serial rule formally intact until then.
R-T6 | Risk | v013 | TeleField ran nine sprints and a FINAL release before its first adversarial review; four CRITICAL defects survived that whole time at 100% coverage (L-T1). | Open | Review earlier in the sequence on the next product; pass 2 and pass 3 still outstanding here.
R-T7 | Risk | v013 | GAP-T3: no server entry exists, so the 30-minute dev-org path and the live sweep cannot be executed end to end as written. | Open | Pass 3 builds the entry point + npm start; Postgres adapter (R-T4) decided alongside it.
R-T8 | Constraint | v013 | Production now refuses to boot without SESSION_SECRET, and x-user-id is ignored outside development (F-T04). | Open | Add SESSION_SECRET to the deploy prerequisites with the Zoho credentials.
R-T9 | Risk | v016 | Four shipped features had no caller (F-T17..F-T20). The class is "built, tested, never invoked" and it is invisible to coverage; the other 10 products have not been audited for it. | Open | Port GATE-1 and GATE-2 to every product in the portfolio.
R-T10 | Constraint | v016 | Production now refuses to boot without SECRETS_KEY (16+ chars) as well as SESSION_SECRET. | Open | Both go in the deploy prerequisites with the Zoho credentials.
R-T11 | Constraint | v017 | Production boot prerequisites are now SESSION_SECRET, SECRETS_KEY (16+) and OPERATOR_TOKEN, alongside the Zoho credentials. Each is a deliberate fail-closed check, not a default. | Open | Put all three in the deployment secret store before the first deploy.
R-T12 | Risk | v017 | The install flow changed shape: consent URLs must now carry a state from /oauth/start. Any Sigma configuration written before v017 needs updating. | Open | Covered in docs/DEV_ORG_SETUP.md step 3 and checked by sweep step SW-09b.
R-T13 | Constraint | v018 | PgStore is single-writer: two processes against one database diverge in memory. Blue/green must drain blue before green takes writes. | Open | Deploy workflow now drains blue before the switch and keeps it read-only for rollback (GAP-T9, v023). The constraint remains: never run two writers.
R-T14 | Risk | v018 | Write-behind flushed per request: a crash strictly between a mutation and its flush loses that one in-flight request. Not equivalent to a synchronous transactional write. | Open | Accept for the pilot, or move to synchronous writes by making the Store interface async — a whole-codebase change, not a patch.
R-T15 | Risk | v019 | Six review passes have now found defects by reading the SPECIFICATION against the code (GAP-T6) as well as the code against itself. The other ten products have trackers with the same screen column and have not been checked this way. | Open | Run the matrix-vs-code check on each sibling before its listing assets are captured.
R-T16 | Risk | v023 | Backups are written to BACKUP_DIR on the application host by default. A local directory on the same machine as the database protects against very little. | Open | Point BACKUP_DIR at mounted or object storage before the first paying install; test a restore from it.
R-T17 | Constraint | v025 | Only five Zoho data centres are served (in, us/.com, eu, au/.com.au, jp). An install from CA, CN, UK or SA is refused at the callback with a named error rather than exchanged against a guessed hostname. | Open | Adding one is a row in src/zohoDc.ts plus its verified API host — verify both against Zoho's docs before adding, since CA and CN break the accounts.zoho.<dc> pattern.
R-T18 | Constraint | v025 | Production boot prerequisites are now DATABASE_URL, SESSION_SECRET, SECRETS_KEY (16+), OPERATOR_TOKEN and ZOHO_REDIRECT_URI alongside the Zoho credentials. | Open | ZOHO_REDIRECT_URI must match the developer-console registration character for character.
R-T19 | Risk | v025 | Zoho's payout terms (USD 100 floor, monthly, ~15 working days) and the 15% share assumed in R-T3 are unconfirmed against the partner console. | Open | Confirm at partner onboarding; feeds the G-02 and D15 cash math (OBS-T9).
R-T20 | Risk | v026 | The extension bundle carries two values taken from the toolkit template rather than published documentation (A-X1 manifest service, A-X2 SDK URL). | Open | Confirm against zet init for CRM at dev-org setup; both are isolated in src/extension.ts.
R-T21 | Constraint | v026 | PUBLIC_URL is now a build input: the bundle is built for one origin and Zoho blocks widget calls to any other. | Open | Rebuild and re-upload the bundle whenever the public host changes; npm run extension -- --check catches a stale folder, not a changed host in production.
R-T22 | Risk | v026 | D-T1 is unresolved, so the first session inside a widget must still be minted server-side and handed to the browser. | Open | Decide widget identity with the dev org in hand before the private beta.
R-T23 | Risk | v027 | A reverse proxy or CDN that strips or overrides Content-Security-Policy would undo the frame-ancestors protection without any test noticing. | Open | Check the headers on the live host after the first deploy; sweep step candidate once a host exists.
R-T24 | Constraint | v027 | Batches are capped at 500 items and bodies at 100kb. Both are chosen numbers, not measured ones. | Open | Confirm against real offline volumes during the pilot; raising them is a one-line change plus a load re-run.
R-T25 | Risk | v028 | The Hindi and Tamil widget strings are drafts by the same hand as the listing copy drafts, not native-speaker reviewed. | Open | Four strings in each language — bundle them into the same native-speaker review as the ST-093 copy before publishing.
R-T26 | Decision | v028 | The in-app screens are English. Whether to translate the product UI is a product decision, not a review finding. | Open | Decide before scale; the catalogue pattern in src/extension.ts is the seam it would extend.
R-T27 | Risk | v029 | The four operational retention windows (latency 7d, errors 30d, notifications 60d, telemetry 90d) are chosen numbers, not measured ones. | Open | Confirm against pilot volumes and any customer commitment before scale; each is a one-line change.
R-T28 | Constraint | v029 | The audit log is now the only table with no deletion policy, by design (evidence). It is bounded at hydration, not on disk. | Open | Decide an audit archival policy before a large tenant makes the table the largest object in the database.
R-T29 | Risk | v030 | Writes held during an outage live in memory, so a crash DURING a long outage still loses them — R-T14 unchanged, now with a larger window. | Open | Decide a backlog ceiling and what to do at it (refuse earlier, or spill to disk) before the pilot.
R-T30 | Constraint | v030 | /healthz now returns 503 when the database is unreachable. Any probe treating non-200 as 'kill the container' will restart a process that is deliberately degrading. | Open | Set the deploy/liveness probes to read status, not just the code, when the host is configured.
R-T31 | Constraint | v031 | SHUTDOWN_TIMEOUT_MS bounds the drain at 15 seconds; a large backlog held through a database outage could need longer, and overrun exits non-zero. | Open | Tune once real deploy timings and backlog sizes exist.
R-T32 | Risk | v031 | Container init systems differ in whether SIGTERM reaches the Node process (PID 1 and shell wrappers swallow it). | Open | Verify on the first production deploy that the drain log lines appear; if not, run node directly or use an init that forwards signals.

## Gate_Checklist
COMPLETION GATE (D7) — TeleField is DONE only when every row is Done
R2: code complete counts for nothing. Gate decision = Senthil (R5/D10). LC items = v006 Launch_Checklist.
ID | Gate item | Source | Status
G-01 | App LISTED on Zoho Marketplace (approved + published) | D7 / R2 | Open
G-02 | 10 PAYING installs from strangers | D7 / R2 | Open
G-03 | S12 kill criteria evaluated with evidence pack | D7 / R3 | Open
G-04 | Kill/continue decision recorded by Senthil | R5 / D10 | Open
G-05 | On CONTINUE: next-rank build authorised; TeleField enters R4 ops floor | N4 / R1 | Open
LC-1 | Zoho developer account; Sigma project + Catalyst serverless configured | v006 LC #1 | Open — with Senthil. Turnkey: docs/DEV_ORG_SETUP.md (now ~15 min of console work, executable), npm run migrate (001-006) + npm start against Postgres, npm run sweep GREEN. Prerequisites: Zoho creds, SESSION_SECRET, SECRETS_KEY, OPERATOR_TOKEN, DATABASE_URL, ZOHO_REDIRECT_URI (VER-T4) and PUBLIC_URL for the bundle build. NEW in v026: build the extension bundle (npm run extension), upload dist/telefield-extension.zip in the developer console and declare the four widgets against their resource paths (GAP-T14). Enable Multi-DC if listing outside India (VER-T5).
LC-2 | Extension review submission pack (functionality doc, test credentials) | v006 LC #2 | In progress — dry run READY 13/13 automated (docs/SUBMISSION_DRYRUN.md), including DR-17 which now gates the four disclosures Zoho's approval criteria require (VER-T7); reviewer pack exists (docs/REVIEW_PACK.md). Remaining: Senthil nominates the second reviewer, plus pen-test archive and live test credentials.
LC-3 | Marketplace listing: screenshots, video, vernacular EN/HI/TA descriptions | v006 LC #3 | In progress — nine screens exist and npm run assets renders them ready to capture. Asset specs corrected to Zoho's published numbers (VER-T6). v028: the extension bundle now ships EN/HI/TA translation catalogues (GAP-T16) and the listing states precisely where vernacular support ends (DISCLOSURE-LANGUAGE, gated by DR-17); Indic data through import, queue, dispositions and export is pinned by tests. Remaining: Senthil picks the ST-093 variant, native-speaker review of the HI/TA copy and the 8 widget strings, captures at the published sizes, records the video.
LC-4 | Zoho CRM API limits (credits) handled with backoff | v006 LC #4 | Done-in-code + VERIFIED vs live docs (VER-T2) — Retry-After honoured, credit balance tracked; live confirmation still needs the dev org
LC-5 | Mobile flows tested offline-first (field rep scenario) | v006 LC #5 | Done-in-code (server half) — offline batch endpoints with retry-safe dedupe (F-T24), and the server now measured over a real socket at 500 rps / p95 3.7ms (GAP-T10). Live field test on the dev org remains the operator half.
LC-6 | Telephony bridge tested with 2 Indian providers (Exotel/Ozonetel class) | v006 LC #6 | Open — S3+ scope. Note (VER-T7): because the bridge needs the customer's own provider account, the listing must disclose it; the disclosure is drafted and gated by DR-17.
LC-7 | India data-residency statement (Zoho DCs) documented | v006 LC #7 | Done-in-code — full statement in docs/TRUST_PAGE.md + live /trust page (ZOHO_DC=in default); live publish rides listing
LC-8 | Pricing in INR + USD; GST invoicing supported | v006 LC #8 | In progress — pricing page + GST/INR FAQ done-in-code from billing single source (docs/PRICING_FAQ.md); LIVE INR charge verification = S1-10 + billing creds
LC-9 | Zoho One bundle positioning note in listing | v006 LC #9 | In progress — Zoho One positioning line drafted as rider on winning ST-093 variant (docs/LISTING_COPY_AB.md); lands at listing publish
LC-10 | Partner co-marketing request submitted to Zoho ecosystem team | v006 LC #10 | Open