## Version_Control
VERSION CONTROL — Session handover, 13 Sep 2026
Version | Date/Time | Author | Change Description | Status
v001 | 2026-09-13 12:02 | Claude for Senthil/KP | THIS FILE — index of everything produced on 13 Sep across TestPulse and the portfolio, the consolidated decision queue, the ordered next actions, and what is blocked on inputs I do not have. Written as a closing artifact: the day produced enough files that an index is worth more than another pass. | Released

## Output_Index
OUTPUT INDEX — 13 Sep 2026. Later versions supersede earlier ones; only the latest of each line is current.
Time | File | What it is | Supersedes | Current?
11:03 | claude_v014_testpulse_sprint_tracker... / v021 workbook | TestPulse tracker + product workbook after cold-review pass 7 | v013 / v020 | superseded
11:10 | claude_v015 tracker / v022 workbook | Pass 8 — third review gate + F-TP45 repeat-install defect | v014 / v021 | superseded
11:18 | claude_v016 tracker / v023 workbook | Portfolio rollout kit (init.js bootstrapper + rollout guide) | v015 / v022 | superseded
11:22 | claude_v017 tracker / v024 workbook | LC-1 session pack (verify script, run sheet, asset harness) | v016 / v023 | CURRENT (TestPulse)
11:35 | claude_v001 marketplace build standard | Standard, defect taxonomy, walkthrough protocol, rollout plan | — | superseded
11:51 | claude_v002 marketplace build standard | + Baseline_Modules sheet | v001 | superseded
11:57 | claude_v003 marketplace build standard | + Conformance sheet with TestPulse results | v002 | CURRENT (portfolio)
11:22 | testpulse_codebase_lc1pack_...zip | TestPulse code at 37 suites / 332 tests | earlier code zips | superseded
11:57 | testpulse_codebase_conformance_...zip | TestPulse code at 38 suites / 338 tests, conformance included | 11:22 zip | CURRENT (code)
11:18 | review-gates_rollout-kit_...zip | Gates + init.js + ROLLOUT.md, standalone | earlier gate zips | superseded
11:51 | marketplace_build_standard_kit_v2_...zip | Standard + gates + baseline + docs, one bundle | 11:35 kit | CURRENT (kit)
11:57 | marketplace_baseline_v2_conformance_...zip | Baseline package: 8 modules + conformance, 42 tests 100% | 11:51 baseline zip | CURRENT (baseline)
| Files that are current | 5 | of | 12

## Decision_Queue
DECISION QUEUE — every open decision I am holding, across products. Yellow = blocks other work.
Sourced from the portfolio record. Anything not listed here I am not tracking — add it rather than assume.
ID | Product | Decision | Blocks | Cost of delay | Effort
D15 | Portfolio | Sequencing: strict WIN order vs the parallel builds now running | Everything downstream of the order | Open since 10 Sep; eleven builds are running against a locked serial plan | Decision only
D18 | TestPulse | Per-user price point (Atlassian cloud pricing is per-user tiers; the flat $99/$299 intent cannot be listed) | Partner console, B-17 test purchase, pricing page copy | Blocks the whole billing chain | 1 hour + research
LC-1 | TestPulse | Run the live install session | 15 code-complete stories, asset capture, all live evidence | 8 review passes are verified against docs, not reality | 45 min (pack ready)
ST-075 | TestPulse | Health score needs weekly-active-users that nothing tracks — cut it or fund a usage feed | A metric target that cannot be met | Currently an unfed metric in the listing targets | Decision only
TP-UX | TestPulse | Two customer-visible choices I made for you: default board name "Current release", and habit = 3 distinct days | Activation metric definition | Both ship at LC-1 | Decision only
D-V2 | VoiceBridge | LWC in the package vs rewording 5 stories | Security-review scope | — | Decision only
D-V3 | VoiceBridge | Checkout vs ISVforce+COA (15%/25% share, $999 review, 5-9 month lead) | Listing path and D15 math | Long lead time — decide early | Decision only
F-V21 | VoiceBridge | Caller-declared identity, left unfixed by your direction | Security review will flag it | DC-07 class; every sibling fixed it | ~2 hours to fix
D-E4 | EngageOS | Ratify built-in chat engine (vendor now optional) | ST-081 closure | — | Decision only
D-F6 | FlowCast | Same chat-vendor ratification | ST-081 closure | — | Decision only
DR-12 | TeleField/VoiceBridge | Nominate the external second reviewer | ST-097 on both | Same-AI review is not independent | Nomination only
PEN | Portfolio | Pen-test vendor | ST-068 on every product | External lead time | Procurement
COPY | 5 products | Listing copy A/B picks | Listing submission | — | 1 hour total
R-D8 | DocMerge Pro | GCP project + OAuth consent — blocked 7 consecutive sprints | All live evidence; S7 exit unattemptable | Escalating: the longest-running block in the portfolio | 30-60 min
INFRA | OnCall / EngageOS | Postgres + operator tokens + WABA access | Deploy of both | Both have executable setup paths waiting | 1-2 hours

## Next_Actions
NEXT ACTIONS — ordered by leverage, not by product
# | Action | Who | Effort | Why this order
1 | Run the LC-1 install session on TestPulse | Senthil | 45 min | Converts 8 passes of documentation-based verification into reality, and flips 15 stories. The pack, verify script and asset harness are ready
2 | Unblock the longest-running external items: GCP consent (DocMerge, 7 sprints), Meta/WABA, Salesforce ISV | Senthil | 1-2 hours | Lead times dominate; these block products entirely while code sits finished
3 | Send me RevRescue for a gate + review pass | Senthil → Claude | Upload | WIN rank 1 and the least-reviewed product in the portfolio — the highest expected defect yield anywhere
4 | Settle D15 | Senthil | Decision | Eleven products are being built in parallel against a plan that says strictly serial. Everything downstream inherits the ambiguity
5 | Run conformance on the two never-reviewed products (RetainKit, DocMerge Pro) | Senthil → Claude | Upload | Both reached S7/S8 with no cold review; the class list predicts what they hold
6 | Decide D18 and the TestPulse UX pair | Senthil | 1 hour | Blocks the billing chain and two customer-visible defaults
7 | Grep the portfolio for DC-13 (async handler swallow) | Claude | Needs repos | Found once, open everywhere; a rejected handler hangs the request and times out the test instead of failing it

## Blocked_On_Inputs
WHAT I CANNOT DO FROM HERE
Work | Input it needs
Run the gates on any other product | That repo as a zip — init.js scaffolds the config by scanning it
Customer-path walkthrough on another product | The repo, plus ideally a live install to click through
Adopt the baseline / run conformance elsewhere | The repo; conformance needs no rewrite, only a harness
Validate TestPulse against reality | forge logs + the lc1-verify output after the install
DC-13 portfolio grep | All repos, or one at a time
Confirm the 12th product | The portfolio action board — I can only name eleven from the record I hold