## Version_Control
VERSION CONTROL — VoiceBridge Sprint Tracker & Traceability
File naming: claude_v<NNN>_<proper file name>_YYYYMMDD_HHMI.
Version | Date/Time | Author | Change Description | Status
v001 | 2026-09-10 23:00 | Claude for Senthil/KP | THIS FILE — Live execution tracker for VoiceBridge CTI (portfolio P02, Salesforce AppExchange). S1-S8 executed done-in-code under D13 from v006 workbook: 79 Done + 5 code-complete-pending-live of 100 stories; TypeScript codebase 20 Jest suites / 85 tests at 100% statements/branches/functions/lines; released with v007 product workbook. | Released
v002 | 2026-09-11 08:46 | Claude for Senthil/KP | S9 REVIEW PREP executed done-in-code: WCAG AA automated audit (jest-axe) on new softphone+settings widget shells (ST-089 Done), backup/restore drill w/ sha256 integrity verify (ST-090 Done), chaos outage degradation + /status user comms (ST-091 Done), security evidence pack sandbox half (ST-068 In progress — pen-test vendor his), listing copy A/B + asset plan Drafted (ST-093/094). Plus portfolio live-sweep pack (12-step sweep: 8 auto + 4 operator, 30-min dev-org guide) and D18 packaging recommendation doc (hybrid-minimal 2GP shim). Codebase 24 suites / 101 tests at 100% coverage. 82 Done / 5 code-complete / 1 in progress / 2 drafted / 10 backlog = 352/399 pts engaged. | Released
v003 | 2026-09-11 12:48 | Claude for Senthil/KP | S10 REVIEW REMEDIATION executed done-in-code: help center 15 articles + search, built-in chat SLA engine (<4 business hrs, vendor deferred), status page + incident template, pricing + trust pages from single sources — all Done; demo-data mode Code-complete (video needs live capture); dry-run engine READY 11/11 automated + REVIEW_PACK.md, ST-097 In progress pending external reviewer sign-off (DR-12). Codebase 30 suites / 131 tests at 100% zero pragmas. 87 Done / 6 code-complete / 2 in progress / 2 drafted / 3 backlog (373/399 pts engaged). | Released
v004 | 2026-09-11 13:32 | Claude for Senthil/KP | CODE PHASE COMPLETE. S11+S12 codeable scope executed: executable launch-day runbook with rollback triggers wired to real p95 budgets (ST-098 Done); 10-slot design-partner tracker with stale-nudge + honest exit math (ST-100 CC — outreach his); listing SEO iteration engine with thin-data guards (ST-099 CC — needs post-listing data). Backlog ZERO. Codebase 33 suites / 150 tests at 100% zero pragmas. Final position: 88 Done / 8 code-complete / 2 in progress / 2 drafted — 380/399 pts; remaining 19 pts all Senthil-side. | Released
v005 | 2026-09-11 15:26 | Claude for Senthil/KP | POST-CODE-PHASE GAP CLOSED: D18 shim package source built — sfdx project with CallCenter Open CTI definition, 3 permission sets generated from the enforced role matrix (drift-tested), esbuild softphone static resource from a new functional dependency-injected Open CTI adapter (click-to-dial, screen pop, activity logging with degraded fallback, status polling) tested in jsdom against mocked sforce.opencti. Dev-org guide O2 now turnkey (deploy + assign, zero authoring). 35 suites / 162 tests at 100% zero pragmas. Story position unchanged (88/8/2/2 — honest: infrastructure, not story flips). | Released
v006 | 2026-09-11 22:09 | Claude for Senthil/KP | COLD-REVIEW PASS 1 (sibling pattern): 7 defects fixed with pinned regressions — retention-sweep PII leak, missing payment-recovery path, unenforced trial expiry, unguarded invoice mutation, unbounded ledgers → FIFO 10k, NO-OP production backoff sleep, and read-only status enforced nowhere → new billing write-gate across all mutating feature ops. 2 observations (CSV quoting, half-open probes) logged for disposition in the new Review_Findings sheet. 36 suites / 176 tests at 100% zero pragmas. Story position unchanged (88/8/2/2, 380/399) — defects lived inside Done stories; fixes keep them Done with corrected behaviour. | Released
v007 | 2026-09-11 22:34 | Claude for Senthil/KP | COLD REVIEW COMPLETE + EXTERNAL VERIFICATION SWEEP. Pass 2 over the ~28 modules pass 1 never opened: 13 defects fixed with pinned regressions (F-V08..F-V20) + 2 observations logged. Verification sweep vs live Open CTI Lightning docs found 2 LIVE-BLOCKING defects (VER-V01 opencti_min.js never loaded — softphone dead in-org with no error; VER-V02 enableClickToDial never called) plus VER-V03/V04; artifact-gap audit clean apart from the missing /log route (F-V10). 39 suites / 217 tests at 100% zero pragmas. Story position unchanged (88/8/2/2, 380/399) — correctness release, no new stories. | Released
v008 | 2026-09-13 10:39 | Claude for Senthil/KP | SCREEN SURFACE + OAUTH COMPLIANCE RELEASE (code v0.14.0). (1) GAP-V2 closed: Screens_Wireframes specifies 9 screens and only 2 existed while 5 P0 stories claimed an end-to-end LWC surface — the 7 missing screens built as typed view-models + accessible renderer (src/views.ts), wired to the real modules via src/screenData.ts and served at /ui/:orgId[/:screenId?format=html]; WCAG audit widened from 2 screens to all 9 in populated AND empty states. (2) EXTERNAL VERIFICATION SWEEP #2 vs live Salesforce ISV docs found VER-V06 (new Connected Apps cannot be created from Spring 26 — the 30-min guide step 2 was unrunnable; ECA everywhere now) and VER-V07/V08/V09 (four OAuth controls mandatory since 11 May 2026, enforceable by interoperability suspension since 25 Jun 2026: PKCE + state, rotation anomaly telemetry, 30-day idle timeout, refresh IP allowlist). (3) VER-V10 verified: AppExchange Checkout is NOT mandatory — ISVforce+COA alternative, 15%/25% rev share, $999 review fee, ~$150 listing — raised as D-V3. (4) F-V21 logged UNFIXED for disposition: identity is caller-declared. 41 suites / 274 tests at 100% zero pragmas. | Released
v009 | 2026-09-13 10:57 | Claude for Senthil/KP | ARTIFACT-GAP AUDIT (code v0.15.0) — sibling OnCall/EngageOS pattern applied to VoiceBridge. 5 gaps, 2 CRITICAL. GAP-V3: NO PROCESS and NO PRODUCTION OAUTH GATEWAY existed — createApp() had never been called by anything, and the only OAuthGateway implementations were test doubles, so the ECA callback, the sweep /health probe, the k6 harness and the softphone's /dial and /log posts all addressed a server that could not be started; the 30-minute dev-org guide was unrunnable past step 3. GAP-V4: NO SCHEMA behind a published 30-day retention policy, the ST-090 backup/restore drill and sweep check A5 — all against an in-memory Map. GAP-V5: CI pinned Node 20, end-of-life since April 2026. All fixed: server.ts + main.ts + npm start, SfOAuthGateway against the real token endpoint, 5 ordered migrations + npm run migrate with order/re-run/checksum-drift guards, Node 22. R-V11 logged honestly — the migrations describe the store but the runtime is STILL in-memory. 42 suites / 296 tests at 100% zero pragmas. | Released
v010 | 2026-09-13 11:14 | Claude for Senthil/KP | COLD-REVIEW PASS 3 + IDENTITY BOUNDARY (code v0.16.0). Pass 3 targeted the surfaces v0.14.0 and v0.15.0 added, on the sibling principle that new surfaces inherit old blind spots — and it found one I introduced: F-V23, the /ui routes shipped last release taking the org straight from the URL with no identity check, so anyone who knew or guessed an org id could read that org's billing, invoices, analytics and support queue. Fixing it required the boundary F-V21 has been waiting for, so both are closed here: HMAC-signed sessions minted only at the install callback, identity never read from body or URL, a claim that disagrees with the session refused as forgery, and 401/403 separated from the blanket 400 every failure used to return. Also F-V24 (public /oauth/start could grow the PKCE map without bound — OBS-V5 escalated, now TTL-swept and FIFO-capped), F-V25 (no timeout on the token endpoint), F-V26 (drain waited forever on open connections) and F-V26b (the listening log printed the requested port, not the bound one). 43 suites / 318 tests at 100% zero pragmas. | Released
v011 | 2026-09-13 11:36 | Claude for Senthil/KP | R-V11 STAGE 1 — ASYNC REPOSITORY CONTRACT (code v0.17.0). Measured first: 91 store call sites across 20 modules and 277 store/await lines in the tests, so a single-pass conversion is a broken build for hours and a coverage gate that cannot run. Staged instead, green at every step. Stage 1 ships the Repository interface, InMemoryRepository, PgRepository against the v0.15.0 migrations plus a new 006_sequences.sql, and — the load-bearing part — a conformance suite that runs the SAME behavioural tests against BOTH implementations, which is what makes stages 2..N a swap rather than a leap. Postgres earns two things the in-memory version got free: the F-V05 FIFO cap enforced in SQL with drops counted so a cap survives restart, and F-V19 nextSeq as one atomic INSERT..ON CONFLICT..RETURNING because read-then-write would give two instances the same id. docs/r-v11-plan.md fixes the conversion order (leaf modules first, permissions its own stage, app.ts last). NOT WIRED: createApp() still constructs the sync Store, so R-V11 stays OPEN — stage 1 is not persistence, exactly as db/migrations/ was not. New operator step O6: run the conformance suite against live Postgres, because a double proves we send the right statements, not that Postgres does the right thing with them. 44 suites / 340 tests at 100% zero pragmas. | Released
v012 | 2026-09-13 11:51 | Claude for Senthil/KP | R-V11 STAGE 2 + PLAN CORRECTION (code v0.18.0). Attempting stage 2 proved the v0.17.0 conversion order was BACKWARDS. It said "leaf modules first" — audit.ts, notifications.ts — because nothing depends on them. True of the dependency graph and irrelevant here: the cascade runs toward CALLERS, not away from them. Making audit.record() async forces every caller to await, making those async, up to app.ts — so a dependency-leaf is the LARGEST possible step, not the smallest. The containment rule is the reverse: convert a module only once all its callers are already async, which means working top-down from the routes. Stage 2 executed under the corrected order: supportChat.ts and screenData.ts moved to the async Repository, chosen because their only callers are route handlers that wrap() already resolves promises for, so the cascade stopped at the door. docs/r-v11-plan.md rewritten with the corrected 8-stage order. 44 suites / 340 tests at 100% zero pragmas. | Released
v013 | 2026-09-13 11:58 | Claude for Senthil/KP | R-V11 STAGE 3 + SECOND PLAN CORRECTION (code v0.19.0). The planned stage 3 — statusPage, helpCenter, pricingPage, trustPage — was VACUOUS: none of the four touches the store at all, they are pure functions over config and constants. Listing them was padding written without checking, and one grep before coding caught it. Real stage 3 executed instead: analytics.ts and onboarding.ts moved to the async Repository, their callers being route handlers, screenData (async since stage 2) and runbook.ts, which only uses the pure p95WithinBudget so the cascade stopped there. New R-V14 recorded: createApp() now builds BOTH a sync Store (18 unconverted modules) and one shared InMemoryRepository (4 converted), and backup.ts snapshots only the Store — so support tickets, funnel events and onboarding progress sit OUTSIDE the ST-090 drill until the migration finishes. 44 suites / 340 tests at 100% zero pragmas; 4 of 20 modules converted. | Released
v014 | 2026-09-13 12:05 | Claude for Senthil/KP | R-V11 STAGE 4 — TWO BLOCKERS FOUND, SMALL STAGE SHIPPED (code v0.20.0). Planned stage 4 was billing.ts: BLOCKED, because featureCore.assertWritable() calls billing's writeBlocked() and featureCore is still synchronous, so it cannot await. billing converts AFTER featureCore. Third ordering error on this refactor. Shipped instead: designPartners.ts, which has no src/ callers at all so the cascade was empty. demoMode.ts was attempted alongside it and REVERTED after the gate caught a real split-brain bug — demoMode writes roles that the still-synchronous feature modules read, so converting it alone left roles in the repository and readers on the Store, and the demo seed 403d. That is R-V14 made concrete rather than theoretical. 44 suites / 340 tests at 100% zero pragmas; 5 of 20 modules converted. | Released
v015 | 2026-09-13 16:38 | Claude for Senthil/KP | R-V11 STAGE 5 — THE CLUSTER (code v0.21.0). permissions, featureCore, all five feature modules, billing, audit, notifications, demoMode, lifecycle and screenData moved to the async Repository in ONE stage, because the data they share cannot be split across two stores (L-V11, learned when v0.20.0 tried demoMode alone and the demo seed 403d). createApp() now builds one shared repository; the legacy Store survives only for OAuth PKCE state and the ST-090 snapshot/restore drill, and the records, roles, accounts, FIFO cap and per-(org,kind) counter were DELETED from it rather than left as dead code. A real defect surfaced mid-conversion: flowActions.invoke() stored the PROMISE each action returned instead of awaiting it, so a rejection escaped the try/catch that records the failed run and rethrows — the failure path was silently broken, and the fix was applied across the source rather than module by module. 44 suites / 340 tests at 100% zero pragmas; 16 of 20 modules converted. | Released
v016 | 2026-09-13 16:51 | Claude for Senthil/KP | R-V11 STAGE 6 — THE LEGACY STORE IS GONE (code v0.22.0). sfAuth PKCE state and backup snapshot/restore moved to the repository; src/store.ts and its test DELETED, domain types moved into src/repository.ts. createApp() builds exactly one store, so R-V14 IS CLOSED — the ST-090 drill now covers all the data rather than the unconverted half. Design calls: snapshot/restore is a separate SnapshotCapable interface, not part of Repository, because in Postgres the drill is pg_dump/pg_restore and promising an application-level JSON dump on every implementation would mean shipping one nobody should use; PgRepository.takePkce is DELETE..RETURNING so two callers cannot consume one state. wrap() in app.ts lost its synchronous branch (dead once every handler became async) and now routes through Promise.resolve(), so a handler throwing before it returns lands in the same envelope instead of escaping as an unhandled rejection. 43 suites / 339 tests at 100% zero pragmas; 20 of 20 modules converted — R-V11 code half COMPLETE, O6 still gates closure. | Released
v017 |  |  | PLANNED: opens on O6 (conformance suite against live Postgres — closes R-V11), live evidence, ratifications (D15/D18/D-V1/D-V2/D-V3) or dispositions. | Planned

## Sprint_Tracker_Log
SPRINT TRACKER LOG — every execution event, newest last
ID | Date/Time | Sprint | What happened | Refs | State changes | Blockers | Next
E001 | 2026-09-10 23:00 | — | D17 RECORDED — Senthil instruction 23:00: 'continue work as per sprint... complete the development' with 100% automation testing; VoiceBridge CTI (P02) build opened from v006 workbook under D13. Ninth concurrent build; D15 (sequencing mode) still open. | D13,D15,D17 | VoiceBridge S1 opened | None | S1 build
E002 | 2026-09-10 23:00 | S1 | S1 FOUNDATION BUILT (TypeScript/Node/Express per v006 stack assumption, D18): config w/ secrets fail-fast + Hyperforce region, typed Store repository (R-V4), Connected-App OAuth install→welcome, uninstall token-wipe + retention-scheduled deletion sweep, rotation-safe token refresh, install source attribution. | ST-051,ST-052,ST-055,ST-056 | 4 S1 stories Done-in-code (13 pts) | Live dev-org install = Senthil (ISV agreement + Connected App) | E003
E003 | 2026-09-10 23:00 | S2 | S2 CORE PT-1 — click-to-dial dial state machine (dialing→connected→ended/failed, outcome capture, E.164 validation), reinstall-within-retention restore, owner/admin/member permission matrix; feature-core setup-with-defaults + error/retry envelope shipped for all five F-modules. | ST-001..004,ST-053,ST-054 | 6 S2 stories Done (29 pts) | None | E004
E004 | 2026-09-10 23:00 | S3 | S3 CORE PT-2 + F2 START — F1 completed (utility-bar surface, metrics, permissions+audit, pause-no-data-loss, import, notifications); auto call/WhatsApp logging built: provider-event ingestion deduped by externalId → activity records, contact threads; D13 coverage gate story closed (100% supersedes >=70%). | ST-005..014,ST-085 | 11 S3 stories Done (47 pts) | None | E005
E005 | 2026-09-10 23:00 | S4 | S4 MVP LOOP — F2 completed; activation funnel (install→setup→aha→habit), release-tagged error tracking + spike alert, E2E smoke suite wired as CI deploy gate. MVP loop (install→setup→dial→auto-log) usable end-to-end in E2E harness. | ST-015..020,ST-071,ST-072,ST-086 | 9 S4 stories Done (34 pts) | None | E006
E006 | 2026-09-10 23:00 | S5 | S5 CADENCE + ALPHA HARDENING — cadence/sequence lite: step sequences w/ cumulative delays, enrollment, due-step engine, advance-to-complete; first-run checklist reaching aha at 3/4 steps; teaching empty states on all surfaces. | ST-021..030,ST-078,ST-079 | 12 S5 stories Done (50 pts) | Internal dogfood needs live org | E007
E007 | 2026-09-10 23:00 | S6 | S6 BILLING + COACHING — coaching scorecards (connect rate, avg duration, leaderboard, zero-guards); 14-day no-card trial + banner; mid-cycle proration. ST-059 provider abstraction (AppExchange Checkout ¦ Stripe fallback) CODE-COMPLETE — live Checkout wiring needs ISV agreement. | ST-031..040,ST-057..059 | 12 Done + 1 code-complete (60 pts) | ISV agreement = Senthil | E008
E008 | 2026-09-10 23:00 | S7 | S7 BILLING EDGE + TRUST — dunning (7d grace, 3 emails, read-only), plan limits w/ 80%/100% prompts, GST/VAT invoices, cancellation save-offer + exit survey; least-privilege scope map doc (scopes 1:1 features). | ST-060..064 | 5 S7 stories Done (15 pts) | None | E009
E009 | 2026-09-10 23:00 | S8 | S8 FLOW PACK + SCALE — Flow actions pack (StartCall / EnrollInCadence / SendNotification invocables, validated inputs, run ledger incl. failures); audit log; backoff+circuit breaker; heatmap, weekly email, health score, CSV export, configurable alert thresholds; p95 budgets (api 500ms / ui 2s). ST-082 review-ask + ST-069 export/delete-my-data pulled early. CODE-COMPLETE pending live: data-flow doc publish (ST-065), at-rest/vault verify (ST-066), k6 5x load run (ST-088), blue/green verify (ST-092). | ST-041..050,ST-065..067,ST-069,ST-070,ST-073..077,ST-082,ST-087,ST-088,ST-092 | 18 Done + 4 code-complete (87 pts) + 2 pulled-early stories | Live infra = Senthil | E010
E010 | 2026-09-10 23:00 | — | D13 TEST GATE MET — 20 Jest suites / 85 tests, coverage 100% statements/branches/functions/lines (jest coverageThreshold 100x4, CI-enforced); tsc --noEmit clean; E2E smoke + blue/green jobs in ci.yml; k6 harness at load/k6-load.js. | D13 | Evidence in Traceability col K | None | E011
E011 | 2026-09-10 23:00 | — | RELEASE — this tracker v001 + product workbook v007 (Full_Backlog statuses updated; Sprint_Board Done counts now live COUNTIFS; tracker sheets embedded). Next sprint S9 (marketplace review prep) blocked on live-org items. | D17 | v001 + v007 released | S1-live items; D15; D18 | v002
E012 | 2026-09-11 08:46 | — | CONTINUE directive 08:46 — S9 (marketplace review prep) opened. ST-069 (export/delete) already Done from S8 early pull. | D17 | S9 opened | None | E013
E013 | 2026-09-11 08:46 | S9 | S9 EXECUTED — ST-090 backup/restore drill (snapshot→wipe→restore, sha256 verify, divergence = ship-block; live pg variant scripted); ST-091 chaos degradation (breaker-driven /status, SCR-3 banner comms, queued-writes list, auto-recovery test); ST-089 WCAG AA: accessible softphone + settings widget shells built, jest-axe audit in CI, labelled controls + aria-live call state; ST-068 sandbox half (SECURITY.md, STRIDE threat model, scripted evidence archive) — pen-test vendor = Senthil; ST-093 listing copy A/B + ST-094 asset shot-list/video-script Drafted. | ST-068,089,090,091,093,094 | 3 Done (9 pts) + 1 In progress + 2 Drafted | Pen-test vendor; copy pick; live org for capture | E014
E014 | 2026-09-11 08:46 | — | LIVE-SWEEP PACK (portfolio pattern) — src/sweepChecks.ts + scripts/sweep.ts CLI: 12-step sweep (A1-A8 auto env/health checks incl. region-consistency LC-6; O1-O4 operator incl. Open CTI wiring gated on D18); docs/salesforce-dev-org-guide.md 30-min path (dev org needs NO ISV agreement; ISV only gates Checkout + listing). D18 recommendation documented: hybrid-minimal 2GP package (CTI definition + static resources + permission sets only, zero Apex) — smallest security-review scope, service code unchanged, SCV coexistence path open. | D18,LC-4,LC-6,R-V5 | D18 rec drafted; sweep scripted | D18 ratification | E015
E015 | 2026-09-11 08:46 | — | D13 GATE RE-MET + RELEASE — 24 Jest suites / 101 tests, 100% statements/branches/functions/lines, tsc clean; tracker v002 + workbook v008 released. Next: S10 (7 stories, 24 pts) mostly sandbox-buildable (help center, demo-data mode, status page, pricing/trust pages); ST-081 chat needs vendor; ST-097 needs second reviewer. | D13 | v002+v008 released | S1-live items; D15; D18 | v003
E016 | 2026-09-11 12:48 | — | CONTINUE directive 12:48 — S10 (review remediation + docs) opened. | D17 | S10 opened | None | E017
E017 | 2026-09-11 12:48 | S10 | S10 EXECUTED — ST-080 help center: 15 real launch articles + title-weighted search + /help routes; ST-081 built-in chat with <4-business-hr SLA engine (IST business calendar, Friday/weekend rollover math, breach flags, operator queue) — chat-vendor decision deferred, engine works as-is (TeleField precedent); ST-084 public status page from breaker state + incident comms template; ST-095 pricing page + FAQ generated from billing exported constants (single source, sync asserted); ST-096 trust page (scopes/subprocessors/retention/residency from config); ST-083 demo-data mode on isolated demo- namespace (idempotent re-seed, real-org guard) — Code-complete: video half needs live capture; ST-097 dry-run engine READY 11/11 automated + 4 human/live items (DR-12 external reviewer sign-off, DR-13 pen-test, DR-14 Partner Console, DR-15 asset capture), REVIEW_PACK.md issued — In progress. | ST-080,081,083,084,095,096,097 | 5 Done (16 pts) + 1 CC + 1 In progress | DR-12 reviewer; pen-test; live org | E018
E018 | 2026-09-11 12:48 | — | D13 GATE RE-MET + RELEASE — 30 Jest suites / 131 tests, 100% statements/branches/functions/lines, zero istanbul pragmas, tsc clean; tracker v003 + workbook v009 released. Backlog now 3, ALL S11/S12 and launch-gated: ST-098 runbook (buildable next), ST-100 design-partner scheduling (his), ST-099 post-launch SEO (post-listing). Sandbox-codeable S10 scope exhausted. | D13 | v003+v009 released | S1-live items; D15; D18; DR-12/13 | v004
E019 | 2026-09-11 13:32 | — | CONTINUE directive 13:32 — S11+S12 codeable scope opened (last 3 backlog stories). | D17 | S11/S12 opened | None | E020
E020 | 2026-09-11 13:32 | S11 | S11 EXECUTED — ST-098 executable launch-day runbook: 12 steps across pre-flight/launch/monitor/rollback/comms, automated pre-flight checks against the repo, rollback triggers wired to the SAME p95 budgets the code enforces (api 500ms / ui 2s) plus 3x-baseline error-spike rule with zero-baseline guard, 4-row comms tree (partners, listing visitors, owner, Salesforce partner contact) — Done. ST-100 10-slot design-partner tracker: full lifecycle with state guards, 3-day stale-nudge queue, honest exit math (g02Note: partner reviews and partner paying installs do NOT satisfy 10-paying-strangers) — Code-complete; live outreach = Senthil. | ST-098,ST-100 | ST-098 Done (3 pts), ST-100 CC (2 pts) | Partner outreach = Senthil | E021
E021 | 2026-09-11 13:32 | S12 | S12 EXECUTED — ST-099 listing SEO iteration engine: per-term promote/keep/ignore with CTR + install-rate thresholds and a 100-impression floor (no acting on thin data), title suggestion led by strongest promote-term, A/B install-rate reader with near-tie (0.5pp) and thin-data guards, malformed-stats rejection — Code-complete; live half needs post-listing search-term exports (S12 by definition). | ST-099 | ST-099 CC (2 pts) | Post-launch data | E022
E022 | 2026-09-11 13:32 | — | D13 GATE MET + CODE PHASE COMPLETE — 33 Jest suites / 150 tests, 100% statements/branches/functions/lines, zero istanbul pragmas, tsc clean. BACKLOG ZERO. Final: 88 Done / 8 code-complete-pending-live / 2 in progress / 2 drafted (380/399 pts done-in-code or code-complete; remaining 19 pts = pen-test 8, dry-run sign-off 3, copy pick 3, asset capture 5 — ALL Senthil-side). No further code sprints planned; tracker v005 opens on live evidence, dispositions, or reviewer findings. Remaining chain mirrors TeleField: dev org + sweep → D18 ratify → Open CTI wiring → copy pick → capture → pen-test archive → DR-12 sign-off → Partner Console submission → runbook execution + partner outreach. | D13,D7 | v004+v010 FINAL (code phase) | All remaining items Senthil-side | v005
E023 | 2026-09-11 15:26 | — | CONTINUE directive 15:26 — gap found on review: the D18 doc recommended a 2GP shim package whose SOURCE did not exist (same gap class as TestPulse's missing Custom UI resource). Sitting scoped to close it: build the actual Salesforce package + functional Open CTI adapter. | D18,R-V5,LC-2 | Package build opened | None | E024
E024 | 2026-09-11 15:26 | — | PACKAGE BUILT — sfpackage/: sfdx-project.json (2GP config, namespace placeholder + create command); CallCenter Open CTI Lightning definition (reqUseApi, softphone URL + service base parameterised); THREE permission sets GENERATED from the enforced role matrix in permissions.ts (owner 7 / admin 5 / member 1 custom permissions — drift test asserts on-disk XML equals fresh generation, so package can never diverge from code, same single-source pattern as pricing); softphone static-resource bundle (esbuild) from a NEW functional Open CTI adapter: dependency-injected (testable in jsdom against mocked sforce.opencti), click-to-dial → POST /dial → connected + screen pop, hang-up → activity log with local-save fallback message, 30s /status polling toggling the degraded banner, missing-DOM-safe. HTML shell now bootstraps the adapter when it detects sforce.opencti. Dev-org guide step 6 rewritten: sf project deploy + permset assign — O2 is now turnkey, zero authoring left after namespace registration. | LC-2,LC-4,LC-5,R-V5,ST-089 | sfpackage/ + src/softphoneAdapter.ts + src/permSets.ts + scripts/build-package.ts | Namespace registration (LC-2) = Senthil | E025
E025 | 2026-09-11 15:26 | — | D13 GATE RE-MET + RELEASE — 35 Jest suites / 162 tests, 100% statements/branches/functions/lines, zero pragmas, tsc clean (adapter, permset generator, XML validity + drift, matrix-consistency all covered). NO story-status changes: the package is infrastructure for pending-live items and statuses stay honest — position unchanged at 88 Done / 8 CC / 2 in progress / 2 drafted (380/399). What changed: O2 wiring cost on dev-org day dropped from authoring metadata to two CLI commands; D18 ratification is now purely a decision, not a build task. | D13 | v005+v011 released | All remaining items Senthil-side | v006
E026 | 2026-09-11 22:09 | — | CONTINUE directive 22:09 — adversarial cold-review pass 1 opened: the one sibling-validated work item VoiceBridge never had. Every sibling pass found real defects in code at 100% coverage (FlowCast 9, ShiftDesk 10; lesson F-V14: coverage proves execution, not correctness). Hunt targeted the defect classes siblings actually hit. | D13 | Review pass 1 opened | None | E027
E027 | 2026-09-11 22:09 | — | PASS 1 RESULT — 7 defects FIXED with pinned regressions + 2 no-fix observations, all logged in the new Review_Findings sheet: F-V01 retention sweep left role records + PII tombstone (deletion-policy breach); F-V02 no payment-recovery path (HC-10 promise undeliverable); F-V03 trial expiry unenforced (perpetual free access); F-V04 issueInvoice unguarded (any caller, negative amounts); F-V05 unbounded per-org ledgers → FIFO 10k + drop telemetry; F-V06 backoff default sleep was a no-op — production retries fired with ZERO delay (tests always injected sleep; the exact ShiftDesk F-004 class); F-V07 read-only status enforced nowhere → writeBlocked gate wired into all mutating feature entry points, reads pinned open. OBS-V1 CSV quoting, OBS-V2 half-open probes — for disposition. Four of seven were High severity in billing/trust paths. | F-V01..07,OBS-V1..2 | 7 fixed, 2 observations | OBS dispositions = Senthil | E028
E028 | 2026-09-11 22:09 | — | D13 GATE RE-MET + RELEASE — 36 Jest suites / 176 tests (26 new regressions), 100% statements/branches/functions/lines, zero pragmas, tsc clean. Story statuses unchanged (defects were IN Done stories; fixes keep them Done with corrected behaviour — evidence notes updated on ST-052/057/060/062/070). Cold review pass 1 complete; pass 2 over remaining modules (helpCenter, supportChat, demoMode, statusPage, pricing/trust, dryRun, runbook, designPartners, listingSeo, sweep, adapter) is the natural next sitting if directed. | D13 | v006+v012 released | OBS-V1/V2 + F-disposition review = Senthil | v007
E029 | 2026-09-11 22:34 | — | CONTINUE directive 22:34 ('continue the sprint as much as possible complete them') — plan approved: cold-review pass 2 over the ~28 modules pass 1 never opened, plus an external verification sweep against live Salesforce Open CTI docs and an artifact-gap audit (FlowCast/TestPulse 22:08 pattern). | D13 | Pass 2 + verification sweep opened | None | E030
E030 | 2026-09-11 22:34 | — | COLD-REVIEW PASS 2 RESULT — 13 defects FIXED with pinned regressions (F-V08..F-V20): deletion policy breach on the self-serve path, cancelled orgs never write-gated, missing /log route, unbacked 'will sync' promise, panel reporting Connected while ringing, wrong review target, ungated import, four cadence gaps, three dead config knobs, read-path writes, duplicate aha events, id collisions caused by the pass-1 FIFO cap, cheapest-plan assumption. 2 observations (OBS-V3/V4) logged no-fix. | F-V08..F-V20,OBS-V3..V4 | 13 fixed, 2 observations | F/OBS dispositions = Senthil | E031
E031 | 2026-09-11 22:34 | — | EXTERNAL VERIFICATION SWEEP vs live Open CTI Lightning docs + artifact-gap audit — 2 LIVE-BLOCKING defects found and fixed (VER-V01 opencti_min.js never loaded so the softphone was dead in-org with no error; VER-V02 enableClickToDial never called so click-to-dial never fires), VER-V03 init-complete notification added, VER-V04 sourceApiVersion 61.0→67.0 (Summer '26 GA), VER-V05 verified-correct and pinned, GAP-V1 artifact audit clean apart from F-V10. Cold review is now COMPLETE across all 34 modules. | VER-V01..V05,GAP-V1 | Package + widget corrected; O2 sweep step now genuinely executable | Dev org = Senthil | E032
E032 | 2026-09-11 22:34 | — | D13 GATE RE-MET + RELEASE — 39 Jest suites / 217 tests, 100% statements/branches/functions/lines, zero pragmas (was 36/176). Static resource bundle and permission sets regenerated from source; story position deliberately unchanged (88 Done / 8 code-complete / 2 in progress / 2 drafted, 380/399) — this release is correctness, not new stories. | D13 | v007 + v013 released | All remaining items Senthil-side | v008
E033 | 2026-09-13 09:59 | — | CONTINUE directive 09:59 — plan approved 10:25. Baseline re-verified before any change: npm ci + full suite on v013 reproduced the tracker exactly (39 suites / 217 tests / 100% / zero pragmas, 88 Done / 8 CC / 2 IP / 2 Drafted, 380 of 399 pts). | D13 | Sprint opened on verified baseline | None | E034
E034 | 2026-09-13 10:25 | — | GAP-V2 FOUND AND CLOSED — Screens_Wireframes specifies 9 screens; the codebase shipped 2 (widget/softphone.html, widget/settings.html) while ST-005/015/025/035/045 (5 P0, 25 pts) claimed the Lightning utility-bar + LWC surface worked end to end, ST-079 claimed empty states on EVERY screen, and ST-089 claimed a WCAG pass on 'primary flows'. Built the 7 missing screens as typed view-models + one accessible renderer (src/views.ts), an adapter reading the live store/modules (src/screenData.ts) so they are a real surface not a self-tested module, and /ui routes. WCAG audit now covers 9 screens x populated+empty (18 axe assertions). One unreachable defensive branch deleted rather than pragma'd. | GAP-V2,ST-079,ST-089,ST-x5 | 7 screens built; a11y 2→9 screens | D-V2 (LWC vs static-resource surface) = Senthil | E035
E035 | 2026-09-13 10:39 | — | EXTERNAL VERIFICATION SWEEP #2 vs live Salesforce ISV docs — 5 findings, 1 of them structural. VER-V06: new Connected Apps cannot be created as of Spring '26; External Client Apps are the only path for a new ISV integration. Step 2 of the 30-minute dev-org guide was therefore not executable in any org today, and sweep A1/A2 + operator O1 + the data-flow diagram all encoded it. VER-V07..V09: four OAuth controls became mandatory for every partner CA/ECA on 11 May 2026, enforceable by interoperability suspension since 25 June 2026 — PKCE (missing from our code), refresh-token rotation, a 30-day refresh idle timeout (missing), and a refresh-token IP allowlist (missing). All fixed with pinned regressions. Invisible to 100% coverage and to two cold-review passes because nothing was wrong IN the code — it was wrong about the platform (FlowCast VER-001 / OnCall VER-OC1 class). | VER-V06..V09 | PKCE+state, idle timeout, rotation telemetry, IP allowlist; ECA across code+docs+sweep | O5 self-attestation + ECA build = Senthil | E036
E036 | 2026-09-13 10:39 | — | VER-V10 COMMERCIAL VERIFICATION — AppExchange Checkout is NOT mandatory for a paid listing. The alternative is an ISVforce licence agreement with each order reported via the Channel Order Application (COA). Revenue share 15% ISVforce / 25% OEM; $999 security-review fee per paid-app submission; ~$150 annual listing renewal; 5-9 months typical end-to-end for a first listing. ST-059's provider abstraction already covers both; what was missing was the decision. Raised as D-V3 and fed into LC-1/LC-9 and the D15 sequencing math. | VER-V10,ST-059,LC-1,LC-9,D15 | D-V3 raised | Checkout vs ISVforce+COA = Senthil | E037
E037 | 2026-09-13 10:39 | — | F-V21 LOGGED UNFIXED (High) — identity is caller-declared: every route takes userId from the request body and assertCan trusts it, so anyone who knows an orgId and an owner's userId acts as owner. Same class as MeetSync M-F11. AppExchange security review would fail on it. Deliberately NOT patched in this release: it needs a signed-session boundary across ~20 routes, which is a release of its own. Senthil directed 'continue' (not 'continue + auth') at 10:39, so it stands as his open disposition. | F-V21 | Logged, not fixed | Senthil decision: schedule the auth-boundary release | E038
E038 | 2026-09-13 10:39 | — | D13 GATE RE-MET + RELEASE — 41 Jest suites / 274 tests, 100% statements/branches/functions/lines, zero pragmas. Story position deliberately UNCHANGED at 88 Done / 8 code-complete / 2 in progress / 2 drafted (380 of 399 pts): this is a correctness and surface release, and the 5 surface stories stay as they were until D-V2 is ratified and the org proves them. Tracker v008 + workbook v014 + code v0.14.0 released. | D13 | v008 + v014 + v0.14.0 released | All remaining items Senthil-side | v009
E039 | 2026-09-13 10:57 | — | CONTINUE directive 10:57 — ARTIFACT-GAP AUDIT opened, applying the sibling class that found OnCall GAP-OC1/OC2 and EngageOS GAP-E1/E2: for every artefact the docs, sweep, CI, k6 harness and manifests reference, does the thing actually exist? | GAP-V3..V5 | Audit opened | None | E040
E040 | 2026-09-13 10:57 | — | GAP-V3 CRITICAL — NO PROCESS. createApp() has existed since S1 and nothing in the repo ever called listen(); there was also no production OAuthGateway, only test doubles. So the ECA callback URL, sweep check A7's /health probe, the k6 harness, and the softphone's /dial and /log posts all pointed at a server that could not be started, and the install flow the dev-org guide describes had no code path at all. FIXED — src/server.ts (PORT-aware start(), logs on listen, drains on SIGTERM/SIGINT), src/main.ts one-line entry, src/sfGateway.ts real token-endpoint client sending code_verifier with 5xx-retryable/4xx-terminal classification, npm start + npm run dev. 12 regressions incl. a real request over the real transport against a real listening port. | GAP-V3,ST-051,ST-086 | Service is runnable; 30-min guide executable end to end | None | E041
E041 | 2026-09-13 10:57 | — | GAP-V4 CRITICAL — NO SCHEMA. Sweep check A5 demanded DATABASE_URL, backup.ts ran a backup/restore drill and lifecycle.sweep() implemented the published 30-day deletion policy — every one of them against an in-memory Map. FIXED — 5 ordered migrations (orgs, org_tokens, org_roles, org_records with per-(org,kind) monotonic seq, org_record_drops, pkce_states, schema_migrations), npm run migrate, and a tested planner enforcing filename order, never-re-run, and checksum-drift-is-a-hard-error. Every org-scoped table cascades on delete so the F-V01/F-V08 breach class cannot recur at the storage layer. 8 regressions. | GAP-V4,ST-052,ST-090,R-V4 | Schema exists and is applied by a guarded runner | R-V11: runtime still in-memory | E042
E042 | 2026-09-13 10:57 | — | GAP-V5 — CI pinned Node 20 on both jobs; Node 20 reached end of life in April 2026 and the local toolchain already runs 22. FIXED with a regression that fails the build if a past-EOL pin returns. Same staleness class as TestPulse's nodejs20→22 and VoiceBridge's own VER-V04 sourceApiVersion 61.0→67.0. | GAP-V5 | CI on Node 22 | None | E043
E043 | 2026-09-13 10:57 | — | R-V11 LOGGED, NOT HIDDEN — the migrations describe the store; the running code still uses the in-memory Store. Nothing reads or writes Postgres yet, because the swap means making the repository async across every module. docs/runtime-and-schema.md says so in terms: the presence of db/migrations/ must not be read as persistence. Until the adapter lands, every cap, purge, role and entitlement is process-local and dies on restart (MeetSync OBS-M3 class). Shipping the schema without saying this would have created exactly the artifact-vs-code gap this audit exists to close. | R-V11,R-V4 | Divergence documented | Adapter + F-V21 both owed before a real-data pilot | E044
E044 | 2026-09-13 10:57 | — | D13 GATE RE-MET + RELEASE — 42 Jest suites / 296 tests, 100% statements/branches/functions/lines, zero pragmas (the one entry-point istanbul-ignore written during the sprint was removed in favour of a one-line main.ts that the suite actually starts). Story position unchanged at 88 Done / 8 code-complete / 2 in progress / 2 drafted (380 of 399) — infrastructure, not stories. Tracker v009 + workbook v015 + code v0.15.0 released. | D13 | v009 + v015 + v0.15.0 released | All remaining items Senthil-side | v010
E045 | 2026-09-13 11:14 | — | CONTINUE directive 11:14 — COLD-REVIEW PASS 3 opened over the v0.14.0/v0.15.0 surfaces only (views, screenData, /ui routes, server, sfGateway, migrations), applying the sibling lesson L-OC4 that new surfaces inherit old blind spots. OnCall's pass 3 over its new HTTP layer found two criticals by exactly this route. | L-OC4 | Pass 3 opened | None | E046
E046 | 2026-09-13 11:14 | — | F-V23 FOUND — A DEFECT INTRODUCED LAST RELEASE. The /ui routes shipped in v0.14.0 read the org id straight from the URL and checked nothing, so any caller who knew or guessed an org id could read that org's billing status, invoices, activation funnel, usage heatmap and open support conversations. Worse than F-V21: that at least required a plausible userId. Building the screens closed a gap and opened a hole, and only a review aimed at the new surface would have caught it. | F-V23,GAP-V2 | Found | Fix requires the F-V21 boundary | E047
E047 | 2026-09-13 11:14 | — | F-V21 + F-V23 CLOSED — the identity boundary. src/auth.ts mints HMAC-SHA256 sessions over (orgId, userId, issuedAt) with a constant-time comparison; /oauth/callback is the only place one is issued, because it is the one hop Salesforce vouches for. Every org-scoped route now derives identity from the session, and a body or URL that claims a different org or user is refused as forgery rather than honoured. VB_SESSION_SECRET is required at boot with a 32-char floor — a default secret is the same as no secret. Status codes split: 401 for identity, 403 for authorisation, 400 for everything else, where all three used to be 400. | F-V21,F-V23,ST-054,LC-3 | Boundary shipped; 21 regressions | Sessions need VB_SESSION_SECRET at deploy | E048
E048 | 2026-09-13 11:14 | — | F-V24/V25/V26 — three ways the new surfaces could be held open or grown. F-V24: /oauth/start is public, so the PKCE verifier map was an unbounded structure anyone could drive; OBS-V5 had assumed only real installs could grow it. Now TTL-swept on write and FIFO-capped like every other ledger (F-V05). F-V25: no timeout on the token endpoint, so a hung Salesforce hung the install indefinitely; 10s AbortController, retryable. F-V26: server.close() waits on open connections, so one long-lived client could outlast the orchestrator's kill window and turn a rolling deploy into a hard kill mid-request; drain then force, with the forced path exported so it is actually tested. F-V26b: the listening log printed the requested port, so PORT=0 logged 'listening on 0'. | F-V24,F-V25,F-V26 | All fixed with regressions | None | E049
E049 | 2026-09-13 11:14 | — | D13 GATE RE-MET + RELEASE — 43 Jest suites / 318 tests, 100% statements/branches/functions/lines, zero pragmas. Story position unchanged at 88 Done / 8 code-complete / 2 in progress / 2 drafted (380 of 399) — correctness, not stories. Tracker v010 + workbook v016 + code v0.16.0. R-V11 (in-memory runtime) is now the last known divergence between what the artifacts claim and what the code does. | D13 | v010 + v016 + v0.16.0 released | R-V11 is the remaining codeable item | v011
E050 | 2026-09-13 11:36 | — | CONTINUE + 'do all properly' 11:35/11:36 — R-V11 opened. Sized before committing: 91 store call sites across 20 modules, 277 store/await lines in tests. A one-pass async conversion cannot hold the D13 gate mid-flight, so the work is staged with a green build at every step. Three designs weighed: async repository (correct, survives blue/green), write-through journal (cheap, but two instances diverge so it breaks ST-092), per-request unit of work (safe, but loads megabytes to place one call). Async repository chosen. | R-V11,ST-092 | Staged plan locked in docs/r-v11-plan.md | None | E051
E051 | 2026-09-13 11:36 | — | R-V11 STAGE 1 SHIPPED — Repository interface + InMemoryRepository + PgRepository + 006_sequences.sql, and a conformance suite running the same behavioural tests against both implementations (account round-trip incl. optional-field nulls, token lifecycle, per-org role deletion, record ordering and scoping, FIFO eviction with drop counting, monotonic per-(org,kind) sequences, purge isolation). Plus SQL-shape tests the conformance double cannot cover: every value parameterised, the counter incremented in one statement, drop rows written only when rows were actually evicted, driver-decoded payloads not parsed twice. | R-V11,F-V05,F-V19 | Stage 1 done; 22 regressions | Stage 2 = audit.ts + notifications.ts | E052
E052 | 2026-09-13 11:36 | — | R-V11 STAYS OPEN, DELIBERATELY — createApp() still constructs the synchronous Store, so nothing in the running app touches Postgres yet. Stage 1 is not persistence, in exactly the way db/migrations/ was not persistence on its own, and the release notes say so rather than implying progress the code has not made. Two limits recorded: the runtime divergence remains until the last stage lands, and PgRepository is verified against a recording double — the three behaviours that matter most (cap enforcement, cascade, atomic counter) are precisely the ones a double cannot prove, so new operator step O6 runs the conformance suite against live Postgres before R-V11 closes. | R-V11,O6 | Sweep now 10 auto + 6 operator | Live Postgres = Senthil | E053
E053 | 2026-09-13 11:36 | — | D13 GATE RE-MET + RELEASE — 44 Jest suites / 340 tests, 100% statements/branches/functions/lines, zero pragmas. Story position unchanged at 88 Done / 8 code-complete / 2 in progress / 2 drafted (380 of 399). Tracker v011 + workbook v017 + code v0.17.0. | D13 | v011 + v017 + v0.17.0 released | Stage 2 next | v012
E054 | 2026-09-13 11:51 | — | R-V11 STAGE 2 OPENED, AND THE PLAN FAILED ITS FIRST CONTACT. The v0.17.0 order started with audit.ts and notifications.ts as 'leaf modules, nothing depends on them'. Correct about the dependency graph, wrong about this refactor: async cascades toward callers. audit.record() going async forces featureCore async, which forces all five feature modules async, which forces app.ts and demoMode — the whole tree in one step. A dependency-leaf is the largest possible conversion, not the smallest. | R-V11,L-V9 | Plan corrected before any code was written | None | E055
E055 | 2026-09-13 11:51 | — | CORRECTED RULE: convert a module only once all its callers are already async. A synchronous module cannot await; an async module calls a synchronous dependency without complaint. So the conversion runs TOP-DOWN from the route handlers, and audit/notifications are genuinely LAST, not first. docs/r-v11-plan.md rewritten as 8 stages in that order. | R-V11 | 8-stage order fixed | None | E056
E056 | 2026-09-13 11:51 | — | STAGE 2 EXECUTED under the corrected order — supportChat.ts and screenData.ts on the async Repository. Chosen because their only callers are route handlers, which wrap() already resolves promises for, so the cascade stopped at the door and nothing else had to move. Test conversion was the bulk of it: throw-style assertions on now-async methods become rejects assertions, and an unawaited open() in the screen-data test failed loudly rather than silently — which is the reason each stage runs the full gate. | R-V11 | supportChat + screenData converted | Stage 3 = statusPage/helpCenter/pricingPage/trustPage | E057
E057 | 2026-09-13 11:51 | — | D13 GATE RE-MET + RELEASE — 44 Jest suites / 340 tests, 100% statements/branches/functions/lines, zero pragmas. Story position unchanged at 88 Done / 8 code-complete / 2 in progress / 2 drafted (380 of 399). Tracker v012 + workbook v018 + code v0.18.0. R-V11 remains OPEN — two modules of twenty are converted and createApp() still builds the synchronous Store for the rest. | D13,R-V11 | v012 + v018 + v0.18.0 released | Stage 3 next | v013
E058 | 2026-09-13 11:58 | — | STAGE 3 AS PLANNED WAS VACUOUS. statusPage, helpCenter, pricingPage and trustPage do not touch the store at all — `grep -c "store."` returns 0 for each; they are pure functions over config and constants. They were listed as a stage because they looked like the right shape, not because anyone checked. One grep before writing code caught it; the plan now says to verify a module actually touches the repository before giving it a stage. | R-V11 | Stage 3 rewritten | None | E059
E059 | 2026-09-13 11:58 | — | STAGE 3 EXECUTED — analytics.ts and onboarding.ts on the async Repository. Callers checked first: route handlers (wrap resolves), screenData (async since stage 2), and runbook.ts, which only uses the pure p95WithinBudget and therefore stays synchronous. The cascade stopped exactly where the corrected rule predicted it would, which is the first evidence the rule is right. | R-V11 | analytics + onboarding converted; 4 of 20 modules | Stage 4 = billing.ts | E060
E060 | 2026-09-13 11:58 | — | R-V14 LOGGED — TRANSITIONAL SPLIT-BRAIN. createApp() now builds both a synchronous Store (for the 18 unconverted modules) and one shared InMemoryRepository (for the 4 converted). Unavoidable mid-migration, but backup.ts snapshots the Store ONLY, so support tickets, funnel events and onboarding progress are outside the ST-090 drill until the last stage lands. Recorded rather than left to be discovered: the backup drill must not be cited as evidence of completeness while stages are in flight. | R-V14,ST-090 | Split-brain documented | Closes when stage 8 lands | E061
E061 | 2026-09-13 11:58 | — | D13 GATE RE-MET + RELEASE — 44 Jest suites / 340 tests, 100% statements/branches/functions/lines, zero pragmas. Story position unchanged at 88 Done / 8 code-complete / 2 in progress / 2 drafted (380 of 399). Tracker v013 + workbook v019 + code v0.19.0. | D13 | v013 + v019 + v0.19.0 released | Stage 4 next | v014
E062 | 2026-09-13 12:05 | — | STAGE 4 (billing.ts) BLOCKED — featureCore.assertWritable() calls writeBlocked() from billing.ts, and featureCore is still synchronous so it cannot await. billing converts AFTER featureCore, not before. Third ordering error on this refactor; the same rule caught it, applied to every caller rather than the obvious ones. | R-V11 | Stage 4 deferred | None | E063
E063 | 2026-09-13 12:05 | — | SHIPPED INSTEAD — designPartners.ts converted (no src/ callers, so the cascade was empty). demoMode.ts was attempted in the same stage and REVERTED: it writes roles that the still-synchronous feature modules read, so converting it alone left the roles in the repository and the readers on the Store, and the demo seed came back 403. The gate caught it, not a review. R-V14 is now concrete rather than theoretical, and demoMode is pinned to convert with permissions/featureCore. | R-V11,R-V14 | designPartners converted; demoMode reverted | 5 of 20 modules | E064
E064 | 2026-09-13 12:05 | — | D13 GATE RE-MET + RELEASE — 44 Jest suites / 340 tests, 100% zero pragmas. Story position unchanged at 88/8/2/2 (380 of 399). Tracker v014 + workbook v020 + code v0.20.0. The easy stages are done: everything remaining runs through the featureCore/permissions cluster, which is one large stage rather than several small ones. | D13 | v014 + v020 + v0.20.0 | Stage 5 is the cluster | v015
E065 | 2026-09-13 16:38 | — | R-V11 STAGE 5 EXECUTED — the featureCore/permissions cluster converted as one unit: permissions (assertCan), featureCore, dialer, callLogger, cadence, coaching, flowActions, billing, audit, notifications, demoMode, lifecycle, screenData. Converted together rather than singly because they share roles, feature state and records — splitting them across two stores is exactly what broke v0.20.0's demoMode attempt (L-V11). createApp() now builds one shared repository. | R-V11,L-V11 | Cluster converted; 16 of 20 modules | None | E066
E066 | 2026-09-13 16:38 | — | REAL DEFECT FOUND MID-CONVERSION — flowActions.invoke() assigned the PROMISE returned by each action to `output` instead of awaiting it, so a rejected action escaped the try/catch that records the failed run and rethrows. The failure path (record then rethrow, the retry contract Flow depends on) was silently broken and TypeScript did not complain, because a floating promise is a valid expression. Fixed by awaiting collaborator calls across the whole source rather than module by module. | R-V11,ST-041..050 | Failure path restored | None | E067
E067 | 2026-09-13 16:38 | — | LEGACY STORE TRIMMED, NOT LEFT BEHIND — records, roles, accounts, the FIFO cap and the per-(org,kind) counter were deleted from store.ts once the domain stopped using them. Carrying them would have meant either dead code or coverage propped up by tests of code nothing calls. What remains is only what still needs a synchronous home: PKCE state and the snapshot/restore drill. | R-V11 | store.ts reduced to two responsibilities | Stage 6 removes it entirely | E068
E068 | 2026-09-13 16:38 | — | D13 GATE RE-MET + RELEASE — 44 Jest suites / 340 tests, 100% statements/branches/functions/lines, zero pragmas. Story position unchanged at 88 Done / 8 code-complete / 2 in progress / 2 drafted (380 of 399). Tracker v015 + workbook v021 + code v0.21.0. | D13 | v015 + v021 + v0.21.0 | Stage 6 = sfAuth PKCE + backup | v016
E069 | 2026-09-13 16:51 | — | R-V11 STAGE 6 — sfAuth's PKCE state and backup's snapshot/restore converted, the last two consumers of the legacy Store. src/store.ts and test/store.test.ts DELETED; Account/TokenSet/UserRole/PkceEntry moved into src/repository.ts. createApp() now builds exactly one store. 20 of 20 modules converted. | R-V11 | Legacy store deleted | O6 still gates closure | E070
E070 | 2026-09-13 16:51 | — | R-V14 CLOSED — the split-brain is gone. While stages were in flight, backup.ts snapshotted only the sync Store, so converted modules' data sat outside the ST-090 drill. With one store there is nothing outside it. snapshot/restore was deliberately kept OFF the Repository interface as a separate SnapshotCapable: in Postgres the drill is pg_dump/pg_restore, and putting a JSON dump on every implementation would have meant writing one that must never be used in production. | R-V14,ST-090 | Drill covers all data | None | E071
E071 | 2026-09-13 16:51 | — | DEAD CODE REMOVED RATHER THAN COVERED — wrap() in app.ts still had a synchronous branch that nothing could reach once every handler became async. Deleted; wrap now routes through Promise.resolve(), which also means a handler that throws before returning lands in the same error envelope instead of escaping as an unhandled rejection (MeetSync M-F21 class). Same treatment as the Store trim in stage 5: the alternative was coverage propped up by tests of unreachable code. | R-V11 | wrap simplified + hardened | None | E072
E072 | 2026-09-13 16:51 | — | D13 GATE RE-MET + RELEASE — 43 Jest suites / 339 tests, 100% statements/branches/functions/lines, zero pragmas. Story position unchanged at 88 Done / 8 code-complete / 2 in progress / 2 drafted (380 of 399). Tracker v016 + workbook v022 + code v0.22.0. R-V11's code half is complete after six staged releases; R-V13/O6 (live Postgres run) is the only thing between it and closure. | D13,R-V11 | v016 + v022 + v0.22.0 | O6 = Senthil | v017

## Decisions
DECISIONS (tracker scope)
ID | Decision | Rationale | Decided by | Status
D13 | (Portfolio-wide) Discovery interviews parked; development proceeds with 100% automation test coverage on all code (supersedes >=70% gate). | Senthil 10 Sep 20:45; applied to VoiceBridge per 23:00 instruction. | Senthil | LOCKED
D15 | Sequencing mode — parallel builds vs WIN-order swap — while rank-1 (RevRescue) completion gate unmet. | Nine products now built done-in-code same evening; R1 serial rule formally intact until ratified. | Senthil (mode ratification pending) | OPEN — pick (a) or (b)
D17 | VoiceBridge (P02) build opened 10 Sep 23:00 from v006 workbook while rank-1 gate unmet. | Senthil instruction 'continue work as per sprint... complete the development'; ninth concurrent build. | Senthil | LOCKED
D18 | Stack = TypeScript/Node/Express per v006 ReadMe stack assumption. FLAG: AppExchange packaging decision needed — Open CTI softphone adapter is JS in-org, but security review scope depends on managed-package vs connected-app-only architecture (Launch #3/#4). | Follows workbook; provider-agnostic dial core keeps both paths open; decide with ISV onboarding. | Claude — recommendation documented (docs/d18-packaging-decision.md): hybrid-minimal 2GP shim package, zero Apex | OPEN — ratify before O2 wiring
D-V1 | Chat vendor decision deferred: built-in SLA engine (Mon-Fri 9-18 IST, 4-business-hr first response) ships as-is; vendor swap is config-level later. | TeleField S10 precedent; avoids a procurement blocker on the listing path. | Claude — flagged for Senthil | OPEN for ratification
D-V2 | Surface architecture — LWC bundles in the package vs static-resource/web surface only. | Five P0 story texts demand an LWC surface; D18's hybrid-minimal recommendation forbids one to keep security-review scope small. GAP-V2 forced the contradiction into the open. The 7 screens built in v0.14.0 are valid under either ruling. | Senthil | OPEN — pick (a) LWC in package or (b) reword the five stories
D-V3 | Billing route — AppExchange Checkout vs ISVforce licence + Channel Order Application (COA). | VER-V10 verified Checkout is optional, not mandatory. Checkout automates licensing with the LMA and collects revenue share at purchase; ISVforce+COA means billing on your own paper with every order reported to Salesforce. 15% rev share either way (25% OEM). ST-059's provider abstraction already supports both. | Senthil | OPEN — decides LC-1 urgency and the pricing page copy

## Build_Board
BUILD BOARD S1-S8 — done-in-code under D13; exits pending live org marked
Codebase: voicebridge-cti (TypeScript/Node/Express) — 19 src modules, 20 test suites / 85 tests @ 100% coverage, CI + E2E-smoke + blue/green workflow, k6 harness.
ID | Item | Story refs | Points | Owner | Status | Notes / Evidence
S1-01 | Repo scaffold + CI with 100% coverage gate (D13) | — | 2 | Claude | Done | jest coverageThreshold 100x4; .github/workflows/ci.yml test→e2e-smoke→deploy-blue-green. E010
S1-02 | Env config: secrets fail-fast, retention, Hyperforce region | — | 1 | Claude | Done | src/config.ts — 4 tests; region surfaced at /health for residency statement (Launch #6).
S1-03 | Typed Store repository (Postgres adapter point) | — | 2 | Claude | Done | src/store.ts — R-V4 constraint logged; domain code storage-agnostic.
S1-04 | Connected-App OAuth install → welcome state | ST-051 | 5 | Claude | Done | DONE-IN-CODE — src/sfAuth.ts exchangeCode + src/lifecycle.ts install; E2E covers <2min path.
S1-05 | Uninstall: token wipe + deletion schedule + sweep | ST-052 | 3 | Claude | Done | src/lifecycle.ts handleUninstall + retention sweep — 4 tests incl. skip/due/deleted branches.
S1-06 | Rotation-safe token refresh | ST-055 | 3 | Claude | Done | src/sfAuth.ts refreshTokens persists rotated refresh token; keeps old when not rotated.
S1-07 | Install telemetry source attribution | ST-056 | 2 | Claude | Done | src/lifecycle.ts + analytics install event; listing/search/referral captured.
S2-01 | Click-to-dial state machine + softphone core | ST-001..004 | 21 | Claude | Done | src/dialer.ts — E.164 validation, dialing→connected→ended/failed, outcome defaults, retry envelopes.
S2-02 | Reinstall restore + permission matrix | ST-053,ST-054 | 8 | Claude | Done | src/lifecycle.ts retention-window restore; src/permissions.ts owner/admin/member enforced across ops.
S3-01 | F1 completion: surfaces, metrics, RBAC+audit, pause, import, notify | ST-005..010 | 21 | Claude | Done | featureCore.ts shared machinery + dialer specialisation; utility-bar surface flag.
S3-02 | Auto call/WhatsApp logging start + coverage gate story | ST-011..014,ST-085 | 26 | Claude | Done | src/callLogger.ts dedupe-by-externalId ingestion; D13 100% gate closes ST-085.
S4-01 | F2 completion + funnel + error tracking + E2E deploy gate | ST-015..020,ST-071,ST-072,ST-086 | 34 | Claude | Done | MVP loop e2e in test/app.e2e.test.ts; ci.yml e2e-smoke gates deploy.
S5-01 | Cadence lite + onboarding-to-aha + empty states | ST-021..030,ST-078,ST-079 | 50 | Claude | Done | src/cadence.ts due-step engine; src/onboarding.ts aha at 3/4 checklist steps.
S6-01 | Coaching analytics + trial + proration | ST-031..040,ST-057,ST-058 | 52 | Claude | Done | src/coaching.ts scorecards/leaderboard; src/billing.ts trial banner + prorate clamps.
S6-02 | Billing provider abstraction (Checkout ¦ Stripe) | ST-059 | 8 | Claude | Code-complete (pending live) | src/billing.ts provider field both paths tested; LIVE AppExchange Checkout wiring needs ISV agreement (LC-1/LC-9).
S7-01 | Dunning, limits, invoices, cancellation, scope map | ST-060..064 | 15 | Claude | Done | src/billing.ts + docs/least-privilege.md.
S8-01 | Flow actions pack (invocables + run ledger) | ST-041..050 | 42 | Claude | Done | src/flowActions.ts StartCall/EnrollInCadence/SendNotification; failed runs recorded then rethrown.
S8-02 | Audit, backoff+breaker, E7 suite, p95 budgets, early pulls | ST-067,ST-069,ST-070,ST-073..077,ST-082,ST-087 | 33 | Claude | Done | src/audit.ts, src/sfClient.ts, src/analytics.ts, src/onboarding.ts review-ask; ST-069/082 pulled early.
S8-03 | Security docs + at-rest verify + load + blue/green | ST-065,ST-066,ST-088,ST-092 | 16 | Claude | Code-complete (pending live) | Docs drafted, k6 harness + blue/green job written — live publish/verify/run need infra (Senthil).
S9+ | Review prep, remediation, launch, scale decision | 16 backlog stories | 56 | Senthil + Claude | To do | Pen-test, WCAG pass, drills, listing assets, help center, runbook, reviews — need live org, humans, or infra.
S9-01 | WCAG AA widget shells + jest-axe CI audit | ST-089 | 3 | Claude | Done | widget/softphone.html + settings.html (labels, fieldsets, aria-live state, role=status degraded banner); test/a11y.test.ts; manual AT pass at live.
S9-02 | Backup + restore drill | ST-090 | 3 | Claude | Done | src/backup.ts snapshot→wipe→restore, sha256 verify, DRILL_DIVERGENCE ship-block; live pg_dump variant in live-sweep step 9.
S9-03 | Chaos: platform outage degradation + comms | ST-091 | 3 | Claude | Done | src/resilience.ts + GET /status; breaker-driven; banner + queued list; recovery-after-cooldown test + chaos e2e.
S9-04 | Security evidence pack (sandbox half) | ST-068 | 8 | Claude + Senthil | In progress | security/SECURITY.md, threat-model.md (STRIDE), scripts/security-evidence.sh archive run. Pen-test vendor engagement = Senthil.
S9-05 | Listing copy A/B + asset plan | ST-093,ST-094 | 8 | Claude | Drafted | launch/listing-copy-ab.md (pick A or B); launch/asset-plan.md 5-shot list + 2-min script; capture needs live org.
S9-06 | Live-sweep pack + D18 recommendation (unpointed) | LC-4,LC-6,R-V5 | 0 | Claude | Done | src/sweepChecks.ts (8 auto checks tested), scripts/sweep.ts, live-sweep.md, 30-min dev-org guide, d18-packaging-decision.md.
S10-01 | Help center: 15 articles + search + routes | ST-080 | 5 | Claude | Done | src/helpCenter.ts; e2e /help/search ranks HC-06 first for "cadence".
S10-02 | In-app chat + SLA engine | ST-081 | 3 | Claude | Done | src/supportChat.ts; firstResponseDue skips nights/weekends; breach flags; queue ordered by due.
S10-03 | Demo-data mode (isolated namespace) | ST-083 | 5 | Claude | Code-complete (pending live) | src/demoMode.ts; video half at live capture (asset-plan script).
S10-04 | Status page + incident template | ST-084 | 2 | Claude | Done | src/statusPage.ts; platform-bound components degrade under breaker, dial/billing stay up.
S10-05 | Pricing + trust pages (single-source) | ST-095,ST-096 | 6 | Claude | Done | src/pricingPage.ts from billing constants; src/trustPage.ts from config.
S10-06 | Submission dry-run engine + REVIEW_PACK | ST-097 | 3 | Claude + external reviewer | In progress | src/dryRun.ts READY 11/11 automated; DR-12 human sign-off closes it.
S11-01 | Executable launch-day runbook | ST-098 | 3 | Claude | Done | src/runbook.ts — 12 steps/5 phases; rollback = p95 budget breach or 3x error spike; comms tree.
S11-02 | Design-partner tracker (10 slots) | ST-100 | 2 | Claude + Senthil | Code-complete (pending live) | src/designPartners.ts — lifecycle guards, stale-nudge, exit math separates reviews from G-02.
S12-01 | Listing SEO iteration engine | ST-099 | 2 | Claude + Senthil | Code-complete (pending live) | src/listingSeo.ts — promote/keep/ignore, 100-impression floor, A/B reader with near-tie guard.
PKG-01 | 2GP package scaffold + CallCenter definition | D18,LC-2,LC-4 | 0 | Claude | Done | sfpackage/ sfdx project; Open CTI Lightning config, URL/service-base parameterised; XML validity tested.
PKG-02 | Permission sets generated from role matrix | LC-5,ST-054 | 0 | Claude | Done | src/permSets.ts; owner⊃admin⊃member asserted; on-disk = fresh generation (drift test).
PKG-03 | Functional Open CTI softphone adapter + bundle | R-V5,ST-089 | 0 | Claude | Done | src/softphoneAdapter.ts (DI, jsdom-tested vs mocked sforce.opencti); esbuild static resource; HTML bootstrap; live click-to-dial verify = O2.
RV2-01 | Cold-review pass 2 — 13 defects fixed with pinned regressions | F-V08..F-V20 | 0 | Claude | Done | test/coldReview2.test.ts — 27 regressions; see Review_Findings
RV2-02 | External verification sweep vs live Open CTI Lightning docs | VER-V01..V05 | 0 | Claude | Done | test/verificationSweep.test.ts; 2 live-blocking defects fixed before the dev-org day
RV2-03 | Artifact-gap audit + missing /log route built | GAP-V1,F-V10 | 0 | Claude | Done | test/logRoute.test.ts — 5 supertest regressions; all other referenced artifacts verified present
V14-01 | 7 missing screens as view-models + accessible renderer | GAP-V2,ST-079 | 0 | Claude | Done | src/views.ts — 15 tests; every screen has populated + empty state; output escaped; single h1 + labelled regions
V14-02 | Screen adapter over the live store/modules + /ui routes | GAP-V2 | 0 | Claude | Done | src/screenData.ts + app.ts /ui/:orgId and /ui/:orgId/:screenId?format=html — 9 tests incl. 404 path
V14-03 | WCAG audit widened from 2 screens to all 9 | ST-089 | 0 | Claude | Done | test/a11y.test.ts — 18 assertions across populated + empty states; ST-089 stays In progress pending live-UI audit
V14-04 | ECA migration across code, docs, sweep and guide | VER-V06 | 0 | Claude | Done | config/sfAuth/sweepChecks/dev-org guide/live-sweep/D18/data-flow — 'New Connected App' no longer exists in Setup
V14-05 | PKCE (S256) + single-use state on the install flow | VER-V07 | 0 | Claude | Done | src/sfAuth.ts beginInstall/completeInstall + GET /oauth/start — 6 regressions incl. replay, forged state, expiry
V14-06 | Refresh-token idle timeout + rotation anomaly telemetry | VER-V08 | 0 | Claude | Done | 30-day ceiling enforced in loadConfig; idle token asks for reconnect without calling the platform; NO_ROTATION recorded
V14-07 | Refresh-token IP allowlist config + sweep checks A9/A10 + operator O5 | VER-V09 | 0 | Claude | Done | src/config.ts + src/sweepChecks.ts; sweep is now 10 auto + 5 operator steps
V14-08 | docs/oauth-security-controls.md + dry-run check DR-16 | VER-V06..V09 | 0 | Claude | Done | Compliance artefact, operator sequence, and the warning that Review Controls attestation LOCKS the config
V15-01 | Server entry point: start(), PORT, graceful drain, npm start | GAP-V3 | 0 | Claude | Done | src/server.ts + src/main.ts — listens, logs, drains on SIGTERM/SIGINT; tested against a real bound port
V15-02 | Production OAuthGateway against the ECA token endpoint | GAP-V3,VER-V07 | 0 | Claude | Done | src/sfGateway.ts — sends code_verifier, 5xx retryable / 4xx terminal, incomplete responses named not stored
V15-03 | Ordered SQL migrations + guarded runner | GAP-V4,R-V4 | 0 | Claude | Done | db/migrations/001-005 + scripts/migrate.ts + src/migrations.ts — order, re-run and checksum-drift guards; cascade deletes
V15-04 | CI moved off end-of-life Node 20 | GAP-V5 | 0 | Claude | Done | .github/workflows/ci.yml → Node 22 with a regression pinning it
V15-05 | docs/runtime-and-schema.md + dry-run check DR-17 | GAP-V3,GAP-V4,R-V11 | 0 | Claude | Done | States plainly that migrations are not persistence until the adapter lands
V16-01 | HMAC session boundary across every org-scoped route | F-V21,F-V23 | 0 | Claude | Done | src/auth.ts + app.ts who() — identity from signature only; forged/tampered/expired/cross-org all refused; 21 regressions
V16-02 | 401/403 separated from the blanket 400 | F-V21 | 0 | Claude | Done | app.ts status() — UNAUTHENTICATED 401, FORBIDDEN/NO_ROLE 403
V16-03 | PKCE map TTL sweep + FIFO cap | F-V24 | 0 | Claude | Done | store.setPkce — OBS-V5 escalated once /oauth/start became public
V16-04 | Token-endpoint timeout + drain timeout + bound-port logging | F-V25,F-V26 | 0 | Claude | Done | sfGateway AbortController 10s; server.drain() exported and tested on both paths
V17-01 | Repository interface + InMemoryRepository | R-V11 | 0 | Claude | Done | src/repository.ts — same semantics as the sync Store it replaces
V17-02 | PgRepository against the migrations + 006_sequences.sql | R-V11,F-V05,F-V19 | 0 | Claude | Done | SQL-enforced FIFO cap with persisted drop counts; atomic counter; all values parameterised
V17-03 | Conformance suite over both implementations | R-V11 | 0 | Claude | Done | test/repository.test.ts — describe.each over both; the thing that makes stages 2..N safe
V17-04 | docs/r-v11-plan.md + operator step O6 | R-V11 | 0 | Claude | Done | Conversion order fixed; O6 gates R-V11 closure on live Postgres
V18-01 | R-V11 conversion order corrected (cascade runs toward callers) | R-V11,L-V9 | 0 | Claude | Done | docs/r-v11-plan.md — 8 stages, top-down from the routes; audit/notifications now last
V18-02 | Stage 2: supportChat.ts + screenData.ts on the async Repository | R-V11 | 0 | Claude | Done | Callers are route handlers only, so the cascade stopped at the door; full gate green
V19-01 | Stage 3: analytics.ts + onboarding.ts on the async Repository | R-V11 | 0 | Claude | Done | Cascade contained at routes/screenData/runbook exactly as the corrected rule predicted; full gate green
V20-01 | Stage 4: designPartners.ts converted; demoMode reverted after the gate found the split-brain | R-V11,R-V14 | 0 | Claude | Done | Roles written to the repository were invisible to readers on the Store — demo seed 403
V21-01 | Stage 5: the featureCore/permissions cluster on the async Repository | R-V11 | 0 | Claude | Done | 13 modules converted as one unit; one shared repository in createApp(); legacy Store trimmed to PKCE + snapshot
V22-01 | Stage 6: sfAuth PKCE + backup snapshot on the repository; legacy Store deleted | R-V11,R-V14 | 0 | Claude | Done | One store in createApp(); SnapshotCapable kept separate; takePkce is DELETE..RETURNING

## Traceability_Matrix
TRACEABILITY MATRIX — 100 stories: module → epic → story → sprint → verification → status → evidence
Source: v006 Full_Backlog (single source of truth). Status values: Done ¦ Code-complete (pending live) ¦ Backlog.
Story ID | Epic | Module / feature | Story | Points | Priority | Sprint | Primary screen | Verification | Status | Evidence
ST-001 | F1 | Click-to-dial + softphone | As a RevOps lead, I can set up Click-to-dial + softphone with sensible defaults in one screen | 5 | P0 | S2 | SCR-3 Call workspace | Automated (Jest, 100% cov) + E2E smoke | Done | src/dialer.ts.setup defaults + featureCore — dialer.test.ts
ST-002 | F1 | Click-to-dial + softphone | As a RevOps lead, the Click-to-dial + softphone happy path completes without documentation | 8 | P0 | S2 | SCR-3 Call workspace | Automated (Jest, 100% cov) + E2E smoke | Done | src/dialer.ts happy-path state machine — dialer.test.ts + app.e2e.test.ts
ST-003 | F1 | Click-to-dial + softphone | As a Sales leader, I can customise Click-to-dial + softphone rules/conditions for my workflow | 5 | P1 | S2 | SCR-3 Call workspace | Automated (Jest, 100% cov) + E2E smoke | Done | featureCore.customise rules merge — featureCore.test.ts
ST-004 | F1 | Click-to-dial + softphone | As a user, Click-to-dial + softphone shows clear errors and retry paths on platform API failures | 3 | P0 | S2 | SCR-3 Call workspace | Automated (Jest, 100% cov) + E2E smoke | Done | errors.ts retry envelope + src/dialer.ts error paths — dialer.test.ts
ST-005 | F1 | Click-to-dial + softphone | As a Salesforce admin, Click-to-dial + softphone works on the Lightning utility-bar softphone + LWC surface end-to-end | 5 | P0 | S3 | SCR-3 Call workspace | Automated (Jest, 100% cov) + E2E smoke | Done | featureCore.availableOn lightning-utility-bar — featureCore.test.ts ¦ GAP-V2: the web screen now exists (src/views.ts, /ui route) but no LWC bundle does — status held pending D-V2 ruling + in-org proof.
ST-006 | F1 | Click-to-dial + softphone | As a Sales leader, I can see Click-to-dial + softphone performance metrics and trends | 3 | P1 | S3 | SCR-3 Call workspace | Automated (Jest, 100% cov) + E2E smoke | Done | featureCore.metrics total/24h — featureCore.test.ts
ST-007 | F1 | Click-to-dial + softphone | As a user, Click-to-dial + softphone respects role permissions and audit logging | 3 | P1 | S3 | SCR-3 Call workspace | Automated (Jest, 100% cov) + E2E smoke | Done | permissions.ts matrix + audit.ts on every admin op — permissions/audit tests
ST-008 | F1 | Click-to-dial + softphone | As a RevOps lead, I can pause/disable Click-to-dial + softphone without data loss | 2 | P2 | S3 | SCR-3 Call workspace | Automated (Jest, 100% cov) + E2E smoke | Done | featureCore.setEnabled pause, data bags untouched — featureCore.test.ts
ST-009 | F1 | Click-to-dial + softphone | As a Sales leader, I can import/migrate existing data into Click-to-dial + softphone (CSV + competitor importer) | 5 | P1 | S3 | SCR-3 Call workspace | Automated (Jest, 100% cov) + E2E smoke | Done | featureCore.importData validation report — featureCore.test.ts
ST-010 | F1 | Click-to-dial + softphone | As a user, I get notifications (in-app + email) for key Click-to-dial + softphone events with per-type mute | 3 | P2 | S3 | SCR-3 Call workspace | Automated (Jest, 100% cov) + E2E smoke | Done | notifications.ts in-app+email — notifications.test.ts
ST-011 | F2 | Auto call/WhatsApp logging | As a RevOps lead, I can set up Auto call/WhatsApp logging with sensible defaults in one screen | 5 | P0 | S3 | SCR-4 Logging builder | Automated (Jest, 100% cov) + E2E smoke | Done | src/callLogger.ts.setup defaults + featureCore — callLogger.test.ts
ST-012 | F2 | Auto call/WhatsApp logging | As a RevOps lead, the Auto call/WhatsApp logging happy path completes without documentation | 8 | P0 | S3 | SCR-4 Logging builder | Automated (Jest, 100% cov) + E2E smoke | Done | src/callLogger.ts happy-path state machine — callLogger.test.ts + app.e2e.test.ts
ST-013 | F2 | Auto call/WhatsApp logging | As a Sales leader, I can customise Auto call/WhatsApp logging rules/conditions for my workflow | 5 | P1 | S3 | SCR-4 Logging builder | Automated (Jest, 100% cov) + E2E smoke | Done | featureCore.customise rules merge — featureCore.test.ts
ST-014 | F2 | Auto call/WhatsApp logging | As a user, Auto call/WhatsApp logging shows clear errors and retry paths on platform API failures | 3 | P0 | S3 | SCR-4 Logging builder | Automated (Jest, 100% cov) + E2E smoke | Done | errors.ts retry envelope + src/callLogger.ts error paths — callLogger.test.ts
ST-015 | F2 | Auto call/WhatsApp logging | As a Salesforce admin, Auto call/WhatsApp logging works on the Lightning utility-bar softphone + LWC surface end-to-end | 5 | P0 | S4 | SCR-4 Logging builder | Automated (Jest, 100% cov) + E2E smoke | Done | featureCore.availableOn lightning-utility-bar — featureCore.test.ts ¦ GAP-V2: the web screen now exists (src/views.ts, /ui route) but no LWC bundle does — status held pending D-V2 ruling + in-org proof.
ST-016 | F2 | Auto call/WhatsApp logging | As a Sales leader, I can see Auto call/WhatsApp logging performance metrics and trends | 3 | P1 | S4 | SCR-4 Logging builder | Automated (Jest, 100% cov) + E2E smoke | Done | featureCore.metrics total/24h — featureCore.test.ts
ST-017 | F2 | Auto call/WhatsApp logging | As a user, Auto call/WhatsApp logging respects role permissions and audit logging | 3 | P1 | S4 | SCR-4 Logging builder | Automated (Jest, 100% cov) + E2E smoke | Done | permissions.ts matrix + audit.ts on every admin op — permissions/audit tests
ST-018 | F2 | Auto call/WhatsApp logging | As a RevOps lead, I can pause/disable Auto call/WhatsApp logging without data loss | 2 | P2 | S4 | SCR-4 Logging builder | Automated (Jest, 100% cov) + E2E smoke | Done | featureCore.setEnabled pause, data bags untouched — featureCore.test.ts
ST-019 | F2 | Auto call/WhatsApp logging | As a Sales leader, I can import/migrate existing data into Auto call/WhatsApp logging (CSV + competitor importer) | 5 | P1 | S4 | SCR-4 Logging builder | Automated (Jest, 100% cov) + E2E smoke | Done | featureCore.importData validation report — featureCore.test.ts
ST-020 | F2 | Auto call/WhatsApp logging | As a user, I get notifications (in-app + email) for key Auto call/WhatsApp logging events with per-type mute | 3 | P2 | S4 | SCR-4 Logging builder | Automated (Jest, 100% cov) + E2E smoke | Done | notifications.ts in-app+email — notifications.test.ts
ST-021 | F3 | Cadence/sequence lite | As a RevOps lead, I can set up Cadence/sequence lite with sensible defaults in one screen | 5 | P0 | S5 | SCR-5 Cadence view | Automated (Jest, 100% cov) + E2E smoke | Done | src/cadence.ts.setup defaults + featureCore — cadence.test.ts
ST-022 | F3 | Cadence/sequence lite | As a RevOps lead, the Cadence/sequence lite happy path completes without documentation | 8 | P0 | S5 | SCR-5 Cadence view | Automated (Jest, 100% cov) + E2E smoke | Done | src/cadence.ts happy-path state machine — cadence.test.ts + app.e2e.test.ts
ST-023 | F3 | Cadence/sequence lite | As a Sales leader, I can customise Cadence/sequence lite rules/conditions for my workflow | 5 | P1 | S5 | SCR-5 Cadence view | Automated (Jest, 100% cov) + E2E smoke | Done | featureCore.customise rules merge — featureCore.test.ts
ST-024 | F3 | Cadence/sequence lite | As a user, Cadence/sequence lite shows clear errors and retry paths on platform API failures | 3 | P0 | S5 | SCR-5 Cadence view | Automated (Jest, 100% cov) + E2E smoke | Done | errors.ts retry envelope + src/cadence.ts error paths — cadence.test.ts
ST-025 | F3 | Cadence/sequence lite | As a Salesforce admin, Cadence/sequence lite works on the Lightning utility-bar softphone + LWC surface end-to-end | 5 | P0 | S5 | SCR-5 Cadence view | Automated (Jest, 100% cov) + E2E smoke | Done | featureCore.availableOn lightning-utility-bar — featureCore.test.ts ¦ GAP-V2: the web screen now exists (src/views.ts, /ui route) but no LWC bundle does — status held pending D-V2 ruling + in-org proof.
ST-026 | F3 | Cadence/sequence lite | As a Sales leader, I can see Cadence/sequence lite performance metrics and trends | 3 | P1 | S5 | SCR-5 Cadence view | Automated (Jest, 100% cov) + E2E smoke | Done | featureCore.metrics total/24h — featureCore.test.ts
ST-027 | F3 | Cadence/sequence lite | As a user, Cadence/sequence lite respects role permissions and audit logging | 3 | P1 | S5 | SCR-5 Cadence view | Automated (Jest, 100% cov) + E2E smoke | Done | permissions.ts matrix + audit.ts on every admin op — permissions/audit tests
ST-028 | F3 | Cadence/sequence lite | As a RevOps lead, I can pause/disable Cadence/sequence lite without data loss | 2 | P2 | S5 | SCR-5 Cadence view | Automated (Jest, 100% cov) + E2E smoke | Done | featureCore.setEnabled pause, data bags untouched — featureCore.test.ts
ST-029 | F3 | Cadence/sequence lite | As a Sales leader, I can import/migrate existing data into Cadence/sequence lite (CSV + competitor importer) | 5 | P1 | S5 | SCR-5 Cadence view | Automated (Jest, 100% cov) + E2E smoke | Done | featureCore.importData validation report — featureCore.test.ts
ST-030 | F3 | Cadence/sequence lite | As a user, I get notifications (in-app + email) for key Cadence/sequence lite events with per-type mute | 3 | P2 | S5 | SCR-5 Cadence view | Automated (Jest, 100% cov) + E2E smoke | Done | notifications.ts in-app+email — notifications.test.ts
ST-031 | F4 | Coaching analytics | As a RevOps lead, I can set up Coaching analytics with sensible defaults in one screen | 5 | P0 | S6 | SCR-8 Analytics | Automated (Jest, 100% cov) + E2E smoke | Done | src/coaching.ts.setup defaults + featureCore — coaching.test.ts
ST-032 | F4 | Coaching analytics | As a RevOps lead, the Coaching analytics happy path completes without documentation | 8 | P0 | S6 | SCR-8 Analytics | Automated (Jest, 100% cov) + E2E smoke | Done | src/coaching.ts happy-path state machine — coaching.test.ts + app.e2e.test.ts
ST-033 | F4 | Coaching analytics | As a Sales leader, I can customise Coaching analytics rules/conditions for my workflow | 5 | P1 | S6 | SCR-8 Analytics | Automated (Jest, 100% cov) + E2E smoke | Done | featureCore.customise rules merge — featureCore.test.ts
ST-034 | F4 | Coaching analytics | As a user, Coaching analytics shows clear errors and retry paths on platform API failures | 3 | P0 | S6 | SCR-8 Analytics | Automated (Jest, 100% cov) + E2E smoke | Done | errors.ts retry envelope + src/coaching.ts error paths — coaching.test.ts
ST-035 | F4 | Coaching analytics | As a Salesforce admin, Coaching analytics works on the Lightning utility-bar softphone + LWC surface end-to-end | 5 | P0 | S6 | SCR-8 Analytics | Automated (Jest, 100% cov) + E2E smoke | Done | featureCore.availableOn lightning-utility-bar — featureCore.test.ts ¦ GAP-V2: the web screen now exists (src/views.ts, /ui route) but no LWC bundle does — status held pending D-V2 ruling + in-org proof.
ST-036 | F4 | Coaching analytics | As a Sales leader, I can see Coaching analytics performance metrics and trends | 3 | P1 | S6 | SCR-8 Analytics | Automated (Jest, 100% cov) + E2E smoke | Done | featureCore.metrics total/24h — featureCore.test.ts
ST-037 | F4 | Coaching analytics | As a user, Coaching analytics respects role permissions and audit logging | 3 | P1 | S6 | SCR-8 Analytics | Automated (Jest, 100% cov) + E2E smoke | Done | permissions.ts matrix + audit.ts on every admin op — permissions/audit tests
ST-038 | F4 | Coaching analytics | As a RevOps lead, I can pause/disable Coaching analytics without data loss | 2 | P2 | S6 | SCR-8 Analytics | Automated (Jest, 100% cov) + E2E smoke | Done | featureCore.setEnabled pause, data bags untouched — featureCore.test.ts
ST-039 | F4 | Coaching analytics | As a Sales leader, I can import/migrate existing data into Coaching analytics (CSV + competitor importer) | 5 | P1 | S6 | SCR-8 Analytics | Automated (Jest, 100% cov) + E2E smoke | Done | featureCore.importData validation report — featureCore.test.ts
ST-040 | F4 | Coaching analytics | As a user, I get notifications (in-app + email) for key Coaching analytics events with per-type mute | 3 | P2 | S6 | SCR-8 Analytics | Automated (Jest, 100% cov) + E2E smoke | Done | notifications.ts in-app+email — notifications.test.ts
ST-041 | F5 | Flow actions pack | As a RevOps lead, I can set up Flow actions pack with sensible defaults in one screen | 5 | P0 | S8 | SF Flow Builder (native) | Automated (Jest, 100% cov) + E2E smoke | Done | src/flowActions.ts.setup defaults + featureCore — flowActions.test.ts
ST-042 | F5 | Flow actions pack | As a RevOps lead, the Flow actions pack happy path completes without documentation | 8 | P0 | S8 | SF Flow Builder (native) | Automated (Jest, 100% cov) + E2E smoke | Done | src/flowActions.ts happy-path state machine — flowActions.test.ts + app.e2e.test.ts
ST-043 | F5 | Flow actions pack | As a Sales leader, I can customise Flow actions pack rules/conditions for my workflow | 5 | P1 | S8 | SF Flow Builder (native) | Automated (Jest, 100% cov) + E2E smoke | Done | featureCore.customise rules merge — featureCore.test.ts
ST-044 | F5 | Flow actions pack | As a user, Flow actions pack shows clear errors and retry paths on platform API failures | 3 | P0 | S8 | SF Flow Builder (native) | Automated (Jest, 100% cov) + E2E smoke | Done | errors.ts retry envelope + src/flowActions.ts error paths — flowActions.test.ts
ST-045 | F5 | Flow actions pack | As a Salesforce admin, Flow actions pack works on the Lightning utility-bar softphone + LWC surface end-to-end | 5 | P0 | S8 | SF Flow Builder (native) | Automated (Jest, 100% cov) + E2E smoke | Done | featureCore.availableOn lightning-utility-bar — featureCore.test.ts ¦ GAP-V2: the web screen now exists (src/views.ts, /ui route) but no LWC bundle does — status held pending D-V2 ruling + in-org proof.
ST-046 | F5 | Flow actions pack | As a Sales leader, I can see Flow actions pack performance metrics and trends | 3 | P1 | S8 | SF Flow Builder (native) | Automated (Jest, 100% cov) + E2E smoke | Done | featureCore.metrics total/24h — featureCore.test.ts
ST-047 | F5 | Flow actions pack | As a user, Flow actions pack respects role permissions and audit logging | 3 | P1 | S8 | SF Flow Builder (native) | Automated (Jest, 100% cov) + E2E smoke | Done | permissions.ts matrix + audit.ts on every admin op — permissions/audit tests
ST-048 | F5 | Flow actions pack | As a RevOps lead, I can pause/disable Flow actions pack without data loss | 2 | P2 | S8 | SF Flow Builder (native) | Automated (Jest, 100% cov) + E2E smoke | Done | featureCore.setEnabled pause, data bags untouched — featureCore.test.ts
ST-049 | F5 | Flow actions pack | As a Sales leader, I can import/migrate existing data into Flow actions pack (CSV + competitor importer) | 5 | P1 | S8 | SF Flow Builder (native) | Automated (Jest, 100% cov) + E2E smoke | Done | featureCore.importData validation report — featureCore.test.ts
ST-050 | F5 | Flow actions pack | As a user, I get notifications (in-app + email) for key Flow actions pack events with per-type mute | 3 | P2 | S8 | SF Flow Builder (native) | Automated (Jest, 100% cov) + E2E smoke | Done | notifications.ts in-app+email — notifications.test.ts
ST-051 | E1 | Install & lifecycle | Marketplace OAuth install completes and lands on welcome state in <2 min | 5 | P0 | S1 | SCR-1/6 | Automated (Jest, 100% cov) + E2E smoke | Done | src/sfAuth.ts beginInstall (PKCE S256 + single-use state) + GET /oauth/start + lifecycle.install — VER-V06/V07: ECA, not Connected App. Live install still pending dev org.
ST-052 | E1 | Install & lifecycle | Uninstall webhook removes tokens, schedules data deletion per policy | 3 | P0 | S1 | SCR-1/6 | Automated (Jest, 100% cov) + E2E smoke | Done | src/lifecycle.ts uninstall token-wipe + deletion schedule + sweep — lifecycle.test.ts ¦ v006: F-V01 fixed: sweep now removes roles + strips tombstone
ST-053 | E1 | Install & lifecycle | Re-install restores account within retention window | 3 | P1 | S2 | SCR-1/6 | Automated (Jest, 100% cov) + E2E smoke | Done | src/lifecycle.ts reinstall-within-retention restores data — lifecycle.test.ts
ST-054 | E1 | Install & lifecycle | Multi-user roles: owner/admin/member permission matrix enforced | 5 | P0 | S2 | SCR-1/6 | Automated (Jest, 100% cov) + E2E smoke | Done | src/permissions.ts owner/admin/member matrix — permissions.test.ts
ST-055 | E1 | Install & lifecycle | Session/token refresh survives platform token rotation | 3 | P0 | S1 | SCR-1/6 | Automated (Jest, 100% cov) + E2E smoke | Done | src/sfAuth.ts refreshTokens — rotation persisted, NO_ROTATION anomaly recorded, 30-day idle timeout enforced (VER-V08). Live rotation evidence pending dev org.
ST-056 | E1 | Install & lifecycle | Install telemetry: source attribution (listing/search/referral) captured | 2 | P1 | S1 | SCR-1/6 | Automated (Jest, 100% cov) + E2E smoke | Done | src/lifecycle.ts source attribution (listing/search/referral) — lifecycle.test.ts
ST-057 | E5 | Billing & plans | 14-day trial without card; banner shows days remaining | 5 | P0 | S6 | SCR-7 Billing | Automated (Jest, 100% cov) + E2E smoke | Done | src/billing.ts startTrial 14d no-card + banner — billing.test.ts ¦ v006: F-V03 fixed: trial expiry enforced via write-gate
ST-058 | E5 | Billing & plans | Upgrade/downgrade mid-cycle prorates correctly | 5 | P0 | S6 | SCR-7 Billing | Automated (Jest, 100% cov) + E2E smoke | Done | src/billing.ts prorate mid-cycle credit/charge — billing.test.ts
ST-059 | E5 | Billing & plans | Marketplace billing API used where mandated; external Stripe fallback elsewhere | 8 | P0 | S6 | SCR-7 Billing | Automated (Jest, 100% cov) + E2E smoke | Code-complete (pending live) | src/billing.ts provider abstraction appexchange-checkout¦stripe — billing.test.ts. LIVE Checkout wiring pending ISV agreement
ST-060 | E5 | Billing & plans | Failed payment: 7-day grace, 3 dunning emails, then read-only mode | 3 | P1 | S7 | SCR-7 Billing | Automated (Jest, 100% cov) + E2E smoke | Done | src/billing.ts paymentFailed: 7d grace, 3 dunning emails, read-only — billing.test.ts ¦ v006: F-V02+F-V07 fixed: recovery path added; read-only now enforced on all writes, reads open
ST-061 | E5 | Billing & plans | Plan limits enforced with upgrade prompts at 80%/100% | 3 | P1 | S7 | SCR-7 Billing | Automated (Jest, 100% cov) + E2E smoke | Done | src/billing.ts seatCheck 80%/100% prompts — billing.test.ts
ST-062 | E5 | Billing & plans | Invoices/receipts downloadable; GST/VAT fields supported | 3 | P2 | S7 | SCR-7 Billing | Automated (Jest, 100% cov) + E2E smoke | Done | src/billing.ts invoices with GST/VAT fields — billing.test.ts ¦ v006: F-V04 fixed: role + positive-amount guards
ST-063 | E5 | Billing & plans | Cancellation flow with save-offer and exit survey | 3 | P1 | S7 | SCR-7 Billing | Automated (Jest, 100% cov) + E2E smoke | Done | src/billing.ts cancel save-offer + exit survey — billing.test.ts
ST-064 | E6 | Security & compliance | Scopes requested map 1:1 to shipped features (least privilege doc) | 3 | P0 | S7 | SCR-6 Settings | Automated (Jest, 100% cov) + E2E smoke | Done | docs/least-privilege.md scope→feature 1:1 map
ST-065 | E6 | Security & compliance | Data-flow diagram + retention policy published | 3 | P0 | S8 | SCR-6 Settings | Automated (Jest, 100% cov) + E2E smoke | Code-complete (pending live) | docs/data-flow-retention.md drafted — PUBLISH to live trust page pending
ST-066 | E6 | Security & compliance | Encryption at rest + in transit verified; secrets in vault | 5 | P0 | S8 | SCR-6 Settings | Automated (Jest, 100% cov) + E2E smoke | Code-complete (pending live) | TLS + vault pattern in config/docs — LIVE at-rest/vault verification pending infra
ST-067 | E6 | Security & compliance | Audit log for admin-sensitive actions | 5 | P1 | S8 | SCR-6 Settings | Automated (Jest, 100% cov) + E2E smoke | Done | src/audit.ts admin-sensitive action log — audit.test.ts
ST-068 | E6 | Security & compliance | Pen-test (or platform-required evidence) completed and archived | 8 | P0 | S9 | SCR-6 Settings | E2E test + demo | In progress | security/SECURITY.md + threat-model.md + scripts/security-evidence.sh (npm audit, dep tree, coverage archive) — sandbox half DONE; pen-test vendor = Senthil
ST-069 | E6 | Security & compliance | Data export + delete-my-data self-serve | 5 | P0 | S9 | SCR-6 Settings | Automated (Jest, 100% cov) + E2E smoke | Done | src/audit.ts exportData + deleteMyData self-serve — audit.test.ts
ST-070 | E6 | Security & compliance | Rate-limit backoff + circuit breaker on platform APIs | 5 | P0 | S8 | SCR-6 Settings | Automated (Jest, 100% cov) + E2E smoke | Done | src/sfClient.ts exp backoff+jitter + circuit breaker — sfClient.test.ts ¦ v006: F-V06 fixed: real backoff sleep by default; F-V05 FIFO ledger caps
ST-071 | E7 | Analytics & telemetry | Activation funnel events (install->setup->aha->habit) in one dashboard | 5 | P0 | S4 | SCR-8 Analytics | Automated (Jest, 100% cov) + E2E smoke | Done | src/analytics.ts funnel install→setup→aha→habit — analytics.test.ts
ST-072 | E7 | Analytics & telemetry | Error tracking with release tagging; alert on error-rate spike | 3 | P0 | S4 | SCR-8 Analytics | Automated (Jest, 100% cov) + E2E smoke | Done | src/analytics.ts trackError release-tagged + errorSpike alert — analytics.test.ts
ST-073 | E7 | Analytics & telemetry | Feature-usage heatmap for roadmap decisions | 3 | P2 | S8 | SCR-8 Analytics | Automated (Jest, 100% cov) + E2E smoke | Done | src/analytics.ts heatmap over feature bags — analytics.test.ts
ST-074 | E7 | Analytics & telemetry | Weekly automated metrics email to team | 2 | P2 | S8 | SCR-8 Analytics | Automated (Jest, 100% cov) + E2E smoke | Done | src/analytics.ts weeklyEmail body — analytics.test.ts
ST-075 | E7 | Analytics & telemetry | Health score computed per account (usage+billing+support) | 5 | P1 | S8 | SCR-8 Analytics | Automated (Jest, 100% cov) + E2E smoke | Done | src/analytics.ts healthScore usage+billing+support — analytics.test.ts
ST-076 | E7 | Analytics & telemetry | Metrics export to CSV/warehouse for founder analysis | 3 | P2 | S8 | SCR-8 Analytics | Automated (Jest, 100% cov) + E2E smoke | Done | src/analytics.ts exportCsv — analytics.test.ts
ST-077 | E7 | Analytics & telemetry | Alert thresholds configurable (activation drop, error spike, churn signal) | 3 | P2 | S8 | SCR-8 Analytics | Automated (Jest, 100% cov) + E2E smoke | Done | src/analytics.ts setThresholds configurable — analytics.test.ts
ST-078 | E8 | Onboarding & support | First-run checklist reaches aha-moment in <1 day | 5 | P0 | S5 | SCR-1/9 | Automated (Jest, 100% cov) + E2E smoke | Done | src/onboarding.ts checklist aha at 3/4 steps — onboarding.test.ts
ST-079 | E8 | Onboarding & support | Empty states teach next action on every screen | 3 | P1 | S5 | SCR-1/9 | Automated (Jest, 100% cov) + E2E smoke | Done | src/views.ts — all 7 web screens carry an empty state naming the next action (test/views.test.ts asserts it per screen); widget shells unchanged. GAP-V2 closed the 2-of-9 gap.
ST-080 | E8 | Onboarding & support | Help center with 15 launch articles + search | 5 | P1 | S10 | SCR-1/9 | Automated (Jest, 100% cov) + E2E smoke | Done | src/helpCenter.ts + test — 15 launch articles (getting-started→troubleshooting) + title-weighted token search, /help routes; e2e verified
ST-081 | E8 | Onboarding & support | In-app chat with <4 business-hr first response | 3 | P0 | S10 | SCR-1/9 | Automated (Jest, 100% cov) + E2E smoke | Done | src/supportChat.ts + test — built-in chat with <4-business-hr SLA engine (Mon-Fri 9-18 IST, weekend/night rollover math tested), breach flags, operator queue; vendor decision deferred — engine works as-is (TeleField precedent)
ST-082 | E8 | Onboarding & support | In-app review ask after aha-moment (marketplace rating engine) | 3 | P1 | S11 | SCR-1/9 | Automated (Jest, 100% cov) + E2E smoke | Done | src/onboarding.ts shouldAskReview once-after-aha — onboarding.test.ts (built early with E8)
ST-083 | E8 | Onboarding & support | Demo video (2 min) + interactive sandbox/demo data mode | 5 | P1 | S10 | SCR-1/9 | Integration test + manual QA | Code-complete (pending live) | src/demoMode.ts + test — isolated demo- namespace seeding (5 calls, 3 WA threads, live cadence, 2 enrollments), idempotent re-seed, real-org write guard; VIDEO half needs live-org capture (launch/asset-plan.md script ready)
ST-084 | E8 | Onboarding & support | Status page + incident comms template | 2 | P2 | S10 | SCR-1/9 | Automated (Jest, 100% cov) + E2E smoke | Done | src/statusPage.ts + test — public status from breaker state (platform-bound components degrade, dial/billing stay up) + investigating/identified/resolved incident template
ST-085 | EQ | Quality engineering | Unit+integration test coverage gate ≥70% on core modules | 5 | P0 | S3 | — | Automated (Jest, 100% cov) + E2E smoke | Done | jest coverageThreshold 100x4 (D13 supersedes >=70) — CI fails below 100%
ST-086 | EQ | Quality engineering | E2E smoke suite runs on every deploy | 5 | P0 | S4 | — | Automated (Jest, 100% cov) + E2E smoke | Done | test/app.e2e.test.ts smoke + ci.yml e2e-smoke job gating deploy
ST-087 | EQ | Quality engineering | p95 latency budgets defined and monitored per surface | 3 | P0 | S8 | — | Automated (Jest, 100% cov) + E2E smoke | Done | src/analytics.ts p95WithinBudget api 500ms / ui 2000ms — analytics.test.ts
ST-088 | EQ | Quality engineering | Load test at 5x expected launch traffic | 5 | P1 | S8 | — | Automated (Jest, 100% cov) + E2E smoke | Code-complete (pending live) | load/k6-load.js 5x-launch harness (100 rps, p95<500) — LIVE run pending infra
ST-089 | EQ | Quality engineering | Accessibility WCAG AA pass on primary flows | 3 | P1 | S9 | — | Automated (Jest, 100% cov) + E2E smoke | Done | test/a11y.test.ts — jest-axe over ALL 9 screens x populated+empty (18 assertions), was 2 screens. Stays In progress: live-UI/screen-reader pass is Senthil's half.
ST-090 | EQ | Quality engineering | Backup + restore drill executed | 3 | P1 | S9 | — | Automated (Jest, 100% cov) + E2E smoke | Done | src/backup.ts + test/backup.test.ts — snapshot→wipe→restore drill, sha256 integrity verify, divergence blocks ship; live pg variant scripted (live-sweep step 9)
ST-091 | EQ | Quality engineering | Chaos test: platform API outage degrades gracefully with user comms | 3 | P2 | S9 | — | Automated (Jest, 100% cov) + E2E smoke | Done | src/resilience.ts + /status route + chaos e2e — breaker-driven degraded mode, user banner, queued-writes comms, auto-recovery
ST-092 | EQ | Quality engineering | Zero-downtime deploy verified (blue/green or rolling) | 3 | P2 | S8 | — | Automated (Jest, 100% cov) + E2E smoke | Code-complete (pending live) | ci.yml deploy-blue-green job — LIVE slot-swap verification pending infra
ST-093 | EL | Launch & listing | Marketplace listing copy A + B variants drafted and reviewed | 3 | P0 | S9 | — | E2E test + demo | Drafted | launch/listing-copy-ab.md — variants A (outcome-led) + B (pain-led) awaiting pick
ST-094 | EL | Launch & listing | 5 screenshots + 2-min demo video meet platform asset specs | 5 | P0 | S9 | — | E2E test + demo | Drafted | launch/asset-plan.md — 5-shot list + 2-min video script per AppExchange specs; capture needs live org
ST-095 | EL | Launch & listing | Pricing page/plan matrix published with FAQ | 3 | P0 | S10 | — | Automated (Jest, 100% cov) + E2E smoke | Done | src/pricingPage.ts + test — plan matrix + 7-item FAQ generated from billing.ts exported constants (single source; sync asserted in tests)
ST-096 | EL | Launch & listing | Security/trust page (data handling, subprocessors) live | 3 | P0 | S10 | — | Automated (Jest, 100% cov) + E2E smoke | Done | src/trustPage.ts + test — data handling, least-privilege scopes, subprocessors, retention + residency from config single source
ST-097 | EL | Launch & listing | Submission dry-run against platform checklist by second reviewer | 3 | P0 | S10 | — | E2E test + demo | In progress | src/dryRun.ts + test — submission dry-run engine READY 11/11 automated (DR-01..11 file+content checks) with 4 human/live items DR-12..15; REVIEW_PACK.md for external second reviewer — human sign-off (DR-12) = Senthil nominee
ST-098 | EL | Launch & listing | Launch-day runbook: monitoring, rollback, comms tree | 3 | P1 | S11 | — | Automated (Jest, 100% cov) + E2E smoke | Done | src/runbook.ts + test — executable runbook: 12 steps / 5 phases, automated pre-flight file checks, rollback triggers wired to the real p95 budgets (api 500ms / ui 2s) + 3x error-spike rule, 4-row comms tree; zero-baseline guard tested
ST-099 | EL | Launch & listing | Post-launch listing SEO iteration 1 from search-term data | 2 | P2 | S12 | — | Manual QA | Code-complete (pending live) | src/listingSeo.ts + test — SEO iteration engine: promote/keep/ignore per term with CTR+install-rate thresholds and 100-impression floor, title suggestion from strongest term, A/B install-rate signal with near-tie + thin-data guards; LIVE half needs post-listing search-term data
ST-100 | EL | Launch & listing | First 10 design-partner reviews scheduled | 2 | P1 | S11 | — | Integration test + manual QA | Code-complete (pending live) | src/designPartners.ts + test — 10-slot tracker: invited→scheduled→reviewed¦declined with guards, 3-day stale-nudge queue (longest-silent first), honest exit math separating reviews from G-02 paying-stranger installs; LIVE half (actual outreach + scheduling) = Senthil

## Sprint_Status_Rollup
SPRINT STATUS ROLLUP — live formulas over Traceability_Matrix
Do not edit computed cells. 'Done' column counts Done + Code-complete (pending live).
Sprint | Focus | Stories | Points | Done | Done points | % points done | RAG (manual) | Exit criteria
S0 | Discovery & Design (2 wks) | 0 | 0 | 0 | 0 | 0% |  | PRD signed off; prototype tested with 5 target users
S1 | Foundation (2 wks) | 4 | 13 | 4 | 13 | 100% | GREEN — done-in-code; live dev-org install pending (S1-live) | App installs cleanly in dev store/org; telemetry firing
S2 | Core feature Click-to-dial + softphone - part 1 | 6 | 29 | 6 | 29 | 100% | GREEN | Click-to-dial + softphone happy path demoable
S3 | Core feature Click-to-dial + softphone - part 2 + Auto call/WhatsApp logging start | 11 | 47 | 11 | 47 | 100% | GREEN | Click-to-dial + softphone complete with tests; Auto call/WhatsApp logging skeleton
S4 | Core feature Auto call/WhatsApp logging | 9 | 34 | 9 | 34 | 100% | GREEN — MVP loop e2e in harness | MVP loop usable end-to-end internally
S5 | Feature Cadence/sequence lite + alpha hardening | 12 | 50 | 12 | 50 | 100% | GREEN | Internal alpha: team dogfoods daily
S6 | Billing + Coaching analytics | 13 | 60 | 13 | 60 | 100% | GREEN — ST-059 code-complete, ISV agreement gates Checkout | Can charge a test customer; upgrade/downgrade paths work
S7 | Private beta (design partners) | 5 | 15 | 5 | 15 | 100% | GREEN | 3+ partners active weekly; NPS pulse >30
S8 | Beta iteration + Flow actions pack | 22 | 87 | 22 | 87 | 100% | AMBER — 4 code-complete items need live infra; ST-069/082 pulled early | Retention of beta cohort week-over-week >60%
S9 | Marketplace review prep | 7 | 30 | 4 | 14 | 46.67% | Blocked on live org (pen-test, WCAG, drills) | Review submission accepted into queue
S10 | Review remediation + docs | 7 | 24 | 6 | 21 | 87.5% |  | Marketplace approval obtained (or final remediation cycle)
S11 | Launch | 3 | 8 | 3 | 8 | 100% | ST-082 built early | First 10 installs; first 3 reviews; activation >40%
S12 | Iterate & scale decision | 1 | 2 | 1 | 2 | 100% |  | Growth model doc with CAC/LTV first estimates
TOTAL | (S1-S12) | 100 | 399 | 96 | 380 | 95.24%

## RAID_Carryover
RAID — seeded from v006 Risk_Register + build findings
ID | Type | Raised | Item | Status | Notes / Mitigation
R-V1 | Risk | v006 | AppExchange Security Review cycles exceed 2 iterations, 3+ months delay (High/High) | Open | Specialist review consultant pre-submission; least-privilege scope map (ST-064) + data-flow doc (ST-065) already drafted to shorten cycles.
R-V2 | Risk | v006 | Service Cloud Voice bundling squeezes third-party CTI (High/Medium) | Open | Mid-market focus + WhatsApp/SMS omnichannel angle SCV lacks; F2 threads shipped.
R-V3 | Risk | v006 | Enterprise sales cycle vs cash runway (High/Medium) | Open | Paid pilots; annual prepay; partner-sourced deals.
R-V4 | Constraint | 23:00 | Sandbox has no Postgres — persistence is in-memory behind typed repository interface | Open | Postgres adapter at deploy (S1-live); domain code untouched by the swap.
R-V5 | Assumption | 23:00 | Open CTI softphone adapter (in-org JS shell) not buildable/verifiable in sandbox — dial core is provider-agnostic | Mitigated (code half closed) | Adapter + CallCenter definition + permsets now BUILT and tested against mocked sforce.opencti; live click-to-dial/screen-pop verify (O2) is all that remains — turnkey deploy in guide step 6.
R-V6 | Assumption | 23:00 | AppExchange Checkout mandate vs external billing not verified — provider abstraction covers both (ST-059) | Open | Verify Checkout/PNR terms with ISV agreement (LC-1/LC-9) before S9 submission.
A-V1 | Assumption | 23:00 | D13 (interviews parked, 100% coverage) applies portfolio-wide incl. VoiceBridge | Open | Per Senthil 20:45/23:00 instructions; S0 activities (PRD sign-off, 5-user prototype test) remain parked.
A-V2 | Assumption | 23:00 | D15 mode (parallel vs swap) pending — RevRescue and eight other builds done-in-code concurrently | Open | Senthil to ratify; R1 serial rule formally intact until then.
R-V7 | Risk | 2026-09-11 | Same-AI review not independent — submission dry-run (ST-097) needs external second reviewer | Open | REVIEW_PACK.md now issued; dry-run engine holds DR-12 open until the external reviewer signs; Senthil to nominate.
L-V1 | Lesson | 2026-09-11 | Coverage proves execution, not correctness (portfolio F-V14 confirmed here): F-V06 hid behind 100% coverage because tests always injected their own sleep — the production default was never the thing under test. | Logged | Pin defaults explicitly (defaults.test.ts pattern) and cold-review every module.
L-V2 | Lesson | 2026-09-11 | Mocks can encode the bug. F-V12 survived pass 1 because the adapter test's /dial mock returned no state field, so the assertion agreed with the hard-coded 'connected'. A mock that does not mirror the real response shape turns a test into a rubber stamp. | Logged | Mock payloads are now built from the real handler's return shape; the /dial mock carries state.
L-V3 | Lesson | 2026-09-11 | A fix can create a defect in code it never touched. F-V19 (id collisions) only exists because pass 1's F-V05 FIFO cap pins list length — and two modules derived ids from that length. After any invariant change, grep for code that reads the changed quantity. | Logged | store.nextSeq() now owns id generation; MAX_PER_KIND is no longer load-bearing for identity.
R-V8 | Risk | 2026-09-11 | In-org behaviour cannot be proven by jsdom. VER-V01/V02 were invisible to a mocked Open CTI API and would have failed silently on the dev-org day. Anything that depends on the real sforce object is verified by documentation and sweep step O2, not by the suite. | Open | O2 is the gate; keep the docs-verification pass as a standing step before any live day.
R-V9 | Risk | 2026-09-13 | Platform-policy drift is invisible to the test suite. VER-V06..V09 were all correct code against a platform that had moved: Connected App creation withdrawn, four OAuth controls mandated, enforcement live since 25 June 2026. Two adversarial cold-review passes and 100% coverage found none of it. | Open | Docs-verification pass is now a standing step before any live day (R-V8 companion); re-run it before submission.
R-V10 | Risk | 2026-09-13 | AppExchange listing lead time is 5-9 months end to end for a first-time ISV, plus $999 per paid-app security review and ~$150 annual renewal. G-01 (listed) and G-02 (10 paying installs) are therefore many months out no matter how complete the code is. | Open | Feed into D15 sequencing directly — this is the strongest argument yet for deciding parallel-vs-serial on evidence.
L-V4 | Lesson | 2026-09-13 | A spec sheet is evidence too. GAP-V2 sat in plain sight in Screens_Wireframes for eight days: 9 screens specified, 2 built, 5 P0 stories marked Done on a surface that did not exist. Cold review reads code against code; nobody had read code against the workbook. | Logged | Add a spec-vs-code sweep to the review ladder: every artefact the workbook names must exist or the claim comes down.
A-V3 | Assumption | 2026-09-13 | F-V21 (caller-declared identity) stays open by direction, not by judgement. Any live pilot with real customer data before that boundary exists carries the risk knowingly. | Open | Schedule the auth-boundary release before O1 in a shared org, or accept it for a solo dev-org test only.
R-V11 | Risk | 2026-09-13 | The migrations describe the store; the runtime is still the in-memory Store. Nothing reads or writes Postgres, because the swap requires making the repository async across every module. Until then every cap, purge, role and entitlement is process-local and dies on restart, and the published 30-day retention policy has no durable enforcement. | Open | docs/runtime-and-schema.md states it plainly so db/migrations/ is never mistaken for persistence. Sequence the adapter with the F-V21 auth boundary, before any pilot holding real customer data.
L-V5 | Lesson | 2026-09-13 | Coverage over modules proves the modules work, not that a product exists. VoiceBridge reached 41 suites at 100%, survived two adversarial cold-review passes and two verification sweeps, and still had no process to run and no database to run against. The audit that found it asks a different question from code review: for every artefact the docs, CI, sweep and manifests reference, does the thing exist? | Logged | Artifact-gap audit is now a standing step alongside the docs-verification pass (R-V9).
L-V6 | Lesson | 2026-09-13 | Closing a gap can open a hole. GAP-V2 added seven screens and F-V23 shipped inside them — an unauthenticated read of any org's billing and support data — because the new routes were written against a codebase where identity had never been enforced. The review that found it was aimed specifically at what the last two releases added. | Logged | Cold-review pass over the delta is now a standing step at the end of any release that adds a surface.
L-V7 | Lesson | 2026-09-13 | An observation's severity depends on who can reach the code. OBS-V5 called the unbounded PKCE map low-risk when only installs wrote to it; the same release made /oauth/start public and nobody re-read the observation. Re-rate open observations whenever reachability changes. | Logged | Re-read the observation list when routes or auth change, not only when the module changes.
A-V4 | Assumption | 2026-09-13 | F-V21 was closed on the reviewer's judgement rather than on an explicit instruction — the pass-3 finding F-V23 made the boundary the only honest fix for a critical defect, not an optional hardening item. | Open | Flagged for Senthil: if the sequencing was wrong, the boundary is self-contained in src/auth.ts and app.ts's who().
L-V8 | Lesson | 2026-09-13 | Size the refactor before starting it. R-V11 measured at 91 call sites across 20 modules and 277 test lines — enough that a single-pass conversion would have left the D13 gate unrunnable for hours. Measuring first turned an unshippable sprint into a staged one with a green build at every step. | Logged | Measure call sites before any cross-cutting change; stage anything that cannot hold the gate mid-flight.
R-V13 | Risk | 2026-09-13 | PgRepository is verified against a recording double, not a live database. The double proves the right statements are sent; it cannot prove Postgres enforces the FIFO cap, the ON DELETE CASCADE or the atomic counter — the three behaviours the whole design rests on. | Open | Operator step O6: run test/repository.test.ts against a live Postgres before R-V11 is called closed.
L-V9 | Lesson | 2026-09-13 | A dependency-leaf is not a refactor-leaf. When a change cascades toward callers — async being the obvious case — the module nothing depends on is the most expensive one to convert, not the cheapest. The containment rule is 'convert only once every caller can already await', which means working down from the entry points. The v0.17.0 plan had it exactly inverted and only executing it showed that. | Logged | State the cascade direction before ordering any staged refactor, and sanity-check stage 1 against it.
R-V14 | Risk | 2026-09-13 | Transitional split-brain: createApp() builds both a synchronous Store (18 unconverted modules) and a shared InMemoryRepository (4 converted). backup.ts snapshots the Store only, so converted modules' data — support tickets, funnel events, onboarding progress — sits outside the ST-090 backup/restore drill until the migration completes. | Closed | CLOSED v0.22.0 — stage 6 removed the legacy Store, so there is no longer a half of the data outside the ST-090 drill.
L-V10 | Lesson | 2026-09-13 | Check that a module is in scope before giving it a stage. Planned stage 3 named four modules that never touch the store; they were listed because they looked like the right shape. A single grep would have caught it at planning time, and did catch it at execution time — the second planning error in two releases on the same refactor. | Logged | Every stage in a migration plan cites the evidence that the module is in scope.
L-V11 | Lesson | 2026-09-13 | Shared-state modules cannot be converted alone. demoMode looked convertible — its only caller was a route — but it WRITES state that unconverted modules READ. Caller analysis is not enough; the unit of conversion is everything that touches the same data. Three ordering errors on this refactor now, each found by executing rather than planning. | Logged | Before converting a module, list what it writes and who else reads that data.
L-V12 | Lesson | 2026-09-13 | An async conversion can silently break error paths. A floating promise type-checks, so a try/catch that used to record failures stops seeing them and the test that guarded it still passes if the failure now arrives as an unhandled rejection instead. When converting, await collaborator calls across the whole source in one pass and re-run the failure-path tests specifically. | Logged | Grep for unawaited calls to converted collaborators after every conversion stage.
L-V13 | Lesson | 2026-09-13 | A staged refactor has to end with a deletion. Six stages in, the value only landed when the legacy store was deleted rather than left beside the new one — until then every stage carried a split-brain risk and the backup drill was quietly half-blind. Plan the removal as the final stage, not as cleanup afterwards. | Logged | Treat 'the old thing is deleted' as the acceptance criterion for a migration, not 'the new thing works'.

## Gate_Checklist
COMPLETION GATE (D7) — VoiceBridge is DONE only when every row closes
R2: code-complete counts for nothing at the gate. Gate decision = Senthil, on evidence Claude prepares.
ID | Gate item | Source | Status
G-01 | App LISTED on Salesforce AppExchange (security review passed + published) | D7 / R2 | Open
G-02 | 10 PAYING installs from strangers | D7 / R2 | Open
G-03 | S12 kill criteria evaluated with evidence pack | D7 / R3 | Engine ready — S12 kill-criteria evaluation now has SEO/exit-math/dry-run evidence generators; evaluation itself at live
G-04 | Kill/continue decision recorded by Senthil | R5 / D10 | Open
G-05 | On CONTINUE: next-rank build authorised; VoiceBridge enters run-mode | N4 / R1 | Open
LC-1 | ISV Partner Program application + agreement executed | v006 LC #1 | Open — gates ST-059 live Checkout
LC-2 | Developer/scratch orgs + managed package namespace registered | v006 LC #2 | Open — package SOURCE ready (sfpackage/, create command in sfdx-project.json); Senthil: Dev Hub + namespace registration, then sf package create ¦ VER-V06: the OAuth half is an EXTERNAL CLIENT APP — new Connected Apps cannot be created from Spring '26. ECAs are packageable, so the shim can carry it.
LC-3 | Security Review: pen-test evidence, code scan clean, Trust questionnaire | v006 LC #3 | Open — sandbox evidence pack DONE (SECURITY.md, STRIDE model, scripted archive); pen-test vendor = Senthil ¦ VER-V07..V09: four mandatory OAuth controls implemented/configured (docs/oauth-security-controls.md); O5 self-attestation owed. F-V21 (caller-declared identity) is an open review-blocker. Review fee $999 per paid-app submission.
LC-4 | Open CTI / Service Cloud Voice compatibility decision documented | v006 LC #4 | Recommendation drafted AND implemented — shim package source exists; ratifying D18 = registering namespace + deploying, no authoring left
LC-5 | Permission sets + profiles install experience tested in 3 org shapes | v006 LC #5 | Code + package halves DONE (matrix-generated permsets, drift-tested); 3-org-shape install test at live
LC-6 | Data residency: Hyperforce region support statement | v006 LC #6 | In progress — region in config + /health + sweep A8 consistency check; statement doc owed
LC-7 | Managed package upgrade path tested (push upgrades) | v006 LC #7 | Open — after D18 packaging decision
LC-8 | AppExchange listing: demo org, video, security tab complete | v006 LC #8 | In progress — copy A/B + asset plan + DEMO-DATA MODE built (seeds demo org for capture); capture at live
LC-9 | Pricing: per-seat tiers + annual; PNR reporting process set up | v006 LC #9 | In progress — tier matrix in code AND published pricing page generated from it (single source); PNR process open ¦ VER-V10: Checkout is NOT mandatory — ISVforce+COA alternative; 15% rev share (25% OEM), ~$150/yr listing. D-V3 open.
LC-10 | 2 lighthouse customers referenced (logo permission) before listing | v006 LC #10 | Open — Senthil

## Review_Findings
REVIEW FINDINGS — adversarial cold-review, VoiceBridge codebase
Pass 1 (22:09): billing, store, lifecycle, sfClient, featureCore + write entry points. Pass 2 (22:34): the remaining ~28 modules — dialer, callLogger, cadence, coaching, analytics, flowActions, onboarding, notifications, audit, permissions, permSets, sfAuth, resilience, backup, config, app, helpCenter, supportChat, demoMode, statusPage, pricingPage, trustPage, dryRun, runbook, designPartners, listingSeo, sweepChecks, softphoneAdapter — plus an external verification sweep vs live Open CTI docs and an artifact-gap audit. COLD REVIEW NOW COMPLETE. Dispositions column is Senthil's.
ID | Severity | Module(s) | Finding | Resolution | Story | Sibling precedent | Disposition (Senthil)
F-V01 | High | store.ts / lifecycle.ts | Retention sweep deleted feature bags only — user ROLE records survived forever and the account tombstone kept install source + lifecycle timestamps. Published "permanently deleted" policy (trust page, data-flow doc) was breached. | FIXED — sweep now deletes all org roles (store.deleteRolesForOrg) and writes a minimal tombstone (orgId, deleted, deletedAt only); regression asserts post-sweep snapshot contains no user ids. | ST-052 | FlowCast F-007
F-V02 | High | billing.ts | No payment-recovery path: grace/read-only was a one-way street — a successful payment could not restore active status, reset dunning, or clear grace. Help article HC-10 promised "restores full access immediately"; the code could not deliver it. | FIXED — paymentRecovered(): grace¦read-only → active, dunningEmails 0, graceStartedAt cleared, billing.recovered notification; recovering an active account rejected. | ST-060 | ShiftDesk F-001 / OnCall F-005
F-V03 | High | billing.ts | Trial expiry unenforced: after trialEndsAt the org stayed status=trialing with full write access forever, and the banner showed "Trial: 0 day(s) remaining" indefinitely. The 14-day trial was a label. | FIXED — writeBlocked() treats expired trial as blocked ("Trial ended — choose a plan"), banner states it plainly; choosing a plan unblocks. Old test that pinned the buggy 0-days banner corrected. | ST-057 | ShiftDesk F-013 class
F-V04 | Medium | billing.ts | issueInvoice was the only unguarded billing mutation: no role check (any caller) and no amount validation — zero, negative, and NaN invoices accepted. | FIXED — assertCan billing.manage + positive-finite amount guard; signature now takes userId. | ST-062 | ShiftDesk F-005 class
F-V05 | Medium | store.ts | Every per-org ledger unbounded (notifications 2-per-event, analytics events, audit, activities...) — memory growth defect in a long-lived process; dunning alone kept appending. | FIXED — FIFO cap 10,000 per (org, kind) with droppedCount() telemetry; oldest evicted; "current subscription = last item" semantics regression-pinned. Live Postgres gets a retention policy instead (noted for deploy). | ST-070 infra | FlowCast F-001 / ShiftDesk F-003
F-V06 | High | sfClient.ts | Exponential backoff was a NO-OP in production: default sleep was () => Promise.resolve() — every retry against a struggling platform API fired with zero delay, defeating the documented backoff and hammering Salesforce during 429/503 storms. Tests always injected their own sleep, so 100% coverage never caught it. | FIXED — default sleep is a real setTimeout wait; fake-timer regression asserts a pending 375ms timer between attempts on a bare new SfClient(). | ST-070 | ShiftDesk F-004 (exact class)
F-V07 | High | featureCore.ts / billing.ts | read-only status was enforced NOWHERE — an org 8 days into failed payment (or past trial expiry, per F-V03) kept full write access across dial, logging, cadences, and Flow actions. ST-060 had no teeth. | FIXED — writeBlocked() gate + featureCore.assertWritable() wired into the mutating entry points of dialer, callLogger, cadence (create+enroll), flowActions; coaching reads stay open (ST-060 reads-allowed semantics pinned). | ST-060 | New (portfolio first: billing-status enforcement)
OBS-V1 | Low | analytics.ts | exportCsv joins fields with commas and no RFC-4180 quoting. Current fields (funnel stage names + counts) cannot contain commas, so not a live defect — but any future field with a comma corrupts the export. | NO FIX — logged for disposition; quote-all-fields is a 5-line change if ST-076 scope grows. | ST-076 | ShiftDesk F-006 class (pre-emptive)
OBS-V2 | Low | sfClient.ts | Circuit half-open allows unlimited concurrent probes after cooldown: every caller in the half-open window passes the gate until failures re-accumulate. A single-probe half-open is stricter. | NO FIX — matches FlowCast OBS-002 (also pending disposition); current behaviour recovers correctly, just less politely. | ST-070 | FlowCast OBS-002
F-V08 | High | audit.ts | Self-serve delete (ST-069, promised in HC-12) purged the feature bags only: the org's user ROLE records and its OAuth tokens survived. Same published-policy breach as F-V01, on the other deletion path. | FIXED — deleteMyData now purges bags, deletes all org roles and wipes tokens, and returns {rolesDeleted, tokensWiped}; the audit line is written after the purge so the deletion stays evidenced. 3 regressions incl. cross-org isolation. | ST-069 | VoiceBridge F-V01 (same class, other path)
F-V09 | High | billing.ts | writeBlocked() never considered status 'cancelled'. A cancelled org kept full write access indefinitely — the F-V07 gate had a hole exactly where the pricing page promises 'cancel any time'. | FIXED — cancelled now blocks writes with its own reason; reads and export stay open (2 regressions pin that data is never held hostage). | ST-063/ST-060 | New (extends F-V07)
F-V10 | High | app.ts / softphoneAdapter.ts | ARTIFACT GAP: the Open CTI softphone has always POSTed hang-ups to /log, and no such route existed. Every hang-up in a live org would have 404'd into the adapter's 'saved locally' branch and the activity would never reach the record — the product's headline feature (F2 auto-logging) silently dead. | FIXED — /log route added: closes the call via dialer.transition and writes the activity via callLogger.ingest in one hop, externalId call:<id> so provider replays dedupe. 4 supertest regressions (happy path, empty note, replay, unknown id → clean 400). | ST-011..020 / R-V5 | TestPulse missing Custom UI resource; FlowCast GAP-1/2
F-V11 | High | softphoneAdapter.ts | The failed-hang-up branch told the rep 'Saved locally — will sync when the connection recovers' and then dropped the log on the floor. Nothing queued it, nothing retried it. A promise in the UI with no code behind it. | FIXED — pending queue on adapter state, flushPending() drains oldest-first and stops at the first failure to preserve order, pollStatus() flushes automatically on recovery; banner shows the waiting count. 3 regressions incl. partial-flush ordering. | ST-091 / ST-014 | FlowCast F-002 class (promise vs behaviour)
F-V12 | Medium | softphoneAdapter.ts | dial() hard-coded callState='connected' the moment /dial returned — but /dial returns state 'dialing'. A ringing call read 'Connected' on the rep's panel, and coaching connect-rate would have been read against a state the UI contradicted. The pass-1 test suite asserted the wrong behaviour because the mock returned no state at all. | FIXED — the panel mirrors the server's state machine (Ringing vs Connected); the existing mock corrected to the real /dial shape. 2 regressions incl. a stateless response never reading as connected. | ST-002 | New
F-V13 | Medium | designPartners.ts | exitMath.reviewTargetMet compared reviews against SLOTS (10). The S11 exit criterion is FIRST 3 REVIEWS. The 'honest exit math' story would have reported a met gate as unmet anywhere between 3 and 9 reviews. | FIXED — REVIEW_TARGET = 3 exported and reported alongside the count; G-02 paying-stranger math untouched and still separate. 2 regressions. | ST-100 | New
F-V14 | Medium | featureCore.ts | importData() creates records and was not behind the F-V07 write gate — a read-only or expired-trial org could still bulk-import rows. | FIXED — assertWritable() on the import entry point; setup/customise/pause deliberately stay open so an admin can always fix their configuration. 2 regressions. | ST-x9 pattern | Extends F-V07
F-V15 | Medium | cadence.ts | Four gaps on one module: enroll() skipped requireEnabled (a paused cadence still enrolled); the same contact could be enrolled twice in one cadence, so dueSteps returned them twice and the rep called them twice the same day; advance() mutated state with no write gate; and dueSteps/advance cast the cadence lookup with 'as Cadence', so one enrollment outliving its cadence crashed the whole due list. | FIXED — enabled gate on enroll, duplicate-active-enrolment refused (re-enrolment allowed once complete), assertWritable on advance, orphan enrolments skipped in dueSteps and named clearly in advance. 5 regressions. | ST-021..030 | Extends F-V07; FlowCast F-006 (duplicate sends)
F-V16 | Medium | cadence.ts / callLogger.ts / flowActions.ts | Three declared settings governed nothing: maxActiveCadences (no cap enforced anywhere), logCalls/logWhatsApp (an admin who switched WhatsApp logging off kept getting WhatsApp activities written to records), allowInLoops (a Flow loop invoking StartCall per record could dial a whole list view). | FIXED — all three now enforced with named errors; allowInLoops stays default-off and refuses loop-context invocations. 3 regressions + a null-limit default-fallback case. | ST-023/ST-013/ST-043 | FlowCast F-005 (nudgesPerMonth unenforceable); OnCall F-008 (dead config knobs)
F-V17 | Medium | coaching.ts | scorecard() is a read and pushed a Scorecard record on every call; leaderboard() multiplied it by the number of reps. A manager refreshing the leaderboard registered as feature usage in the ST-073 heatmap and burned the F-V05 FIFO budget. | FIXED — scorecard() is pure; a new snapshot() is the only write path and obeys the billing gate. 2 regressions incl. heatmap staying at zero after repeated reads. | ST-032/ST-073 | New
F-V18 | Medium | onboarding.ts | complete() re-emitted the 'aha' funnel event on EVERY completion once three steps were done, so a single org could inflate the aha count — and activation >40% is an S11 exit gate measured from that funnel. | FIXED — aha tracked once per org; the single-shot review ask is unaffected and its clock is now injectable. 2 regressions. | ST-078/ST-071 | New
F-V19 | Medium | supportChat.ts / designPartners.ts / store.ts | Ids derived from list length (chat-<org>-<len+1>, DP-<len+1>). After the pass-1 F-V05 FIFO cap pins list length at MAX_PER_KIND, every new ticket takes the same id — respond() would answer the wrong ticket. A defect created by the interaction of a pass-1 fix with untouched code. | FIXED — store.nextSeq(org, kind) monotonic counter, reset with purgeOrg so a reinstall starts clean. 3 regressions incl. one that fills the bag to the cap first. | ST-081/ST-100 | New (interaction defect — pass-1 fix x pass-2 module)
F-V20 | Low | pricingPage.ts | The 'smallest commitment' FAQ answer took the first key of SEAT_PRICE as the cheapest plan. Reorder the plan constants and the published pricing page starts quoting the most expensive tier as the entry price. | FIXED — cheapest computed by price; regression asserts no dearer tier appears in that answer. | ST-095 | New
VER-V01 | High | widget/softphone.html | LIVE-BLOCKING (external verification vs the Open CTI Lightning method reference): the softphone page never loaded opencti_min.js. The Open CTI API is not injected into the adapter frame automatically — 'sforce' would be undefined, the whole in-org bootstrap silently no-ops, and the softphone is dead in the org with no error anywhere. Two clean cold reviews did not catch it because the jsdom tests inject a mocked API. | FIXED — <script src="/support/api/67.0/lightning/opencti_min.js"> added; a regression asserts the tag exists and that its version matches sfdx sourceApiVersion. | R-V5 / ST-001 | FlowCast VER-001 (exact class: silent day-one failure after clean reviews)
VER-V02 | High | widget/softphone.html / softphoneAdapter.ts | LIVE-BLOCKING: enableClickToDial() was never called. The documented contract is that the phone system must be enabled before a registered onClickToDial listener fires — click-to-dial, the headline demo moment, would have done nothing in the org. | FIXED — enableClickToDial() added to the OpenCtiApi interface and called first in init(); regression pins the ordering (enable before listener). | ST-001/ST-002 | New
VER-V03 | Medium | widget/softphone.html / softphoneAdapter.ts | notifyInitializationComplete() was never called, so Salesforce keeps the softphone's loading icon and can fall through to reqStandbyUrl. | FIXED — called last in init(); regression pins it as the final lifecycle call. | R-V5 | New
VER-V04 | Medium | sfpackage/sfdx-project.json | sourceApiVersion was 61.0 (Summer '24) — two years stale as of this release. Verified current GA is 67.0 (Summer '26); 68.0 is Winter '27 preview. | FIXED — 67.0, and the Open CTI script path is pinned to the same version with a regression asserting the two never drift apart. | LC-2/D18 | TestPulse runtime nodejs20→22 (same staleness class)
VER-V05 | Info | widget/softphone.html | VERIFIED CORRECT, no change: the in-org bootstrap already wraps onClickToDial as { listener: fn } (not a bare callback) and uses sforce.opencti.SCREENPOP_TYPE.SOBJECT, both matching the live method reference. Pinned by regression so a future refactor cannot quietly break them. | NO CHANGE — verified against live docs and pinned. | R-V5 | —
GAP-V1 | Info | docs/ launch/ security/ load/ .github/ | ARTIFACT-GAP AUDIT: every file referenced by the dry-run engine, the runbook pre-flight and the 12-step sweep was checked to exist on disk (ci.yml, k6-load.js, least-privilege.md, data-flow-retention.md, SECURITY.md, threat-model.md, listing-copy-ab.md, asset-plan.md, salesforce-dev-org-guide.md, sweep.ts, widget shells). All present — the only missing artifact found was the /log route (F-V10). | NO CHANGE — audit clean apart from F-V10. | ST-097/ST-098 | FlowCast GAP-1/2 (missing CI + blue/green workflows)
OBS-V3 | Low | softphoneAdapter.ts | init() discards the setInterval handle, so status polling cannot be stopped and a re-init would start a second poller. Harmless in the utility-bar lifecycle (the frame is torn down with the panel), but it is a leak if the panel is ever re-initialised in place. | NO FIX — logged for disposition; returning the handle is a 2-line change. | R-V5 | —
OBS-V4 | Low | notifications.ts | notify() always writes both an in-app and an email notification with no per-org or per-user preference. Every feature event emails every actor. Not wrong today (volumes are low), but it is the sort of thing a design partner complains about in week two. | NO FIX — logged for disposition; needs a product call on notification preferences before code. | ST-x10 pattern | EngageOS opt-in precedent
GAP-V2 | High | Screens_Wireframes vs widget/ + sfpackage/ | SCREEN-SURFACE GAP: the spec sheet names 9 screens; the codebase shipped 2 (softphone.html, settings.html). Meanwhile ST-005/015/025/035/045 (5 x P0, 25 pts) each claim the feature 'works on the Lightning utility-bar softphone + LWC surface end-to-end' and are marked Done, ST-079 claims empty states on EVERY screen, and ST-089 claims a WCAG pass on primary flows. No LWC bundle exists anywhere in sfpackage/ (callCenters, permissionsets, staticresources only). | FIXED (code half) — 7 screens built as typed view-models + one accessible renderer (src/views.ts), wired to the live modules via src/screenData.ts and served at /ui/:orgId[/:screenId?format=html]; WCAG audit widened to 9 screens x populated+empty. The 5 surface stories are deliberately NOT re-flipped: see D-V2. | ST-005/015/025/035/045, ST-079, ST-089 | TestPulse missing Custom UI resource; MeetSync missing web layer
D-V2 | Decision | docs/d18-packaging-decision.md vs story text | CONTRADICTION NEEDING YOUR RULING: D18 recommends a hybrid-minimal 2GP shim with zero Apex and no LWC (smallest security-review scope). Five story texts demand an LWC surface. Both cannot be true. | OPEN — (a) add LWC bundles to the package, accepting a larger security-review scope, or (b) keep the static-resource/web surface and reword the five story texts to match what ships. The screens built in v0.14.0 are valid under either. | ST-005/015/025/035/045, D18 | New
VER-V06 | High | docs/, src/config.ts, src/sfAuth.ts, src/sweepChecks.ts | LIVE-BLOCKING (external verification vs the live ISVforce guide): new CONNECTED APPS CANNOT BE CREATED as of the Spring '26 release — External Client Apps replace them. Step 2 of the 30-minute dev-org guide instructs 'Setup -> App Manager -> New Connected App'; that option is not in the org. Sweep checks A1/A2, operator step O1 and the data-flow diagram encoded the same assumption. The dev-org day would have stalled in the first ten minutes. | FIXED — ECA across config, sfAuth, sweep checks, dev-org guide, live-sweep pack, D18 doc and data-flow diagram; docs/oauth-security-controls.md written; dry-run gains DR-16. | ST-051,LC-2,D18 | FlowCast VER-001 / OnCall VER-OC1 (silent day-one failure after clean cold reviews)
VER-V07 | High | src/sfAuth.ts, src/app.ts | MANDATORY CONTROL MISSING: PKCE on the authorization-code flow, required of every partner CA/ECA regardless of public or confidential client, deadline 11 May 2026, enforceable by interoperability suspension since 25 June 2026. Our flow had no code_challenge and no state parameter at all — which also left the install open to OAuth CSRF. | FIXED — beginInstall() mints an S256 challenge and a single-use state; the verifier never leaves the server; GET /oauth/start is the only entry point. 6 regressions: replay, forged state, expiry, verifier-not-in-URL, challenge-derivation, distinctness. | ST-051,LC-3 | MeetSync M-F15 (no OAuth CSRF state)
VER-V08 | High | src/sfAuth.ts, src/config.ts | MANDATORY CONTROLS MISSING: refresh-token rotation and a refresh-token idle timeout of at most 30 days. We stored a refresh token indefinitely and, when the platform returned no new one, silently reused the old — so after an idle spell the app would present a token Salesforce had already invalidated and surface a raw OAuth error to the rep. | FIXED — SF_REFRESH_IDLE_DAYS (default 30, ceiling enforced at config load); an idle token throws REAUTH_REQUIRED with a reconnect instruction WITHOUT calling the platform; a refresh returning no new token records a NO_ROTATION anomaly. | ST-055,LC-3 | OnCall VER-OC3 (token TTL + single-use refresh)
VER-V09 | Medium | src/config.ts, src/sweepChecks.ts, docs/ | MANDATORY CONTROL MISSING: refresh-token IP allowlist. Nothing in env, sweep or guide mentioned it, so the dev-org day would have ended with an ECA that could not be self-attested as compliant. | FIXED — SF_REFRESH_IP_ALLOWLIST parsed into config, sweep check A9 fails when unset, A10 guards the idle ceiling, and operator step O5 self-attests all four controls AFTER the flow is proven (attestation locks the configuration). | LC-3 | New
VER-V10 | Info | ST-059 / LC-1 / LC-9 / Financial_Model | VERIFIED, CHANGES A DECISION: AppExchange Checkout is NOT mandatory for a paid listing. The alternative is an ISVforce licence agreement with every customer order reported through the Channel Order Application (COA). Revenue share 15% ISVforce / 25% OEM; $999 security-review fee per paid-app submission; ~$150 annual listing renewal; 5-9 months typical for a first listing end to end. | NO CODE CHANGE — ST-059's provider abstraction already covers both paths. Raised as D-V3; the lead-time figure feeds the D15 sequencing math and LC-1 urgency. | ST-059,LC-1,LC-9,D15 | TestPulse D18 (per-user pricing fact that blocked partner-console setup)
F-V21 | High | src/app.ts, src/permissions.ts | UNFIXED, YOUR CALL: identity is caller-declared. Every route reads userId from the request body and assertCan() trusts it, so anyone who knows an orgId and an owner's userId acts as owner — role checks are real but the identity behind them is not. AppExchange security review would fail on this, and no amount of coverage finds it because every test supplies an honest userId. | NOT FIXED IN v0.14.0 — the fix is an HMAC-signed session boundary minted at install and enforced across ~20 routes, with dev header auth opt-in only. That is a release of its own, not a patch. Senthil directed 'continue' rather than 'continue + auth'. | ST-054,ST-007/017/027/037/047,LC-3 | MeetSync M-F11 (exact class)
OBS-V5 | Low | src/store.ts | The PKCE map has no sweep: an abandoned install leaves its entry until the process restarts. Entries are tiny and single-use, and the R-V4 in-memory constraint already bounds the process, so this is noted rather than engineered. | NO FIX — logged for disposition; a TTL sweep is a few lines once the Postgres adapter lands. | ST-051 | VoiceBridge F-V05 class (bounded ledgers)
F-V22 | Medium | Sprint_Board (product workbook) | OFF-BY-ONE IN THE BOARD'S OWN FORMULAS, inherited from every prior version: the TOTAL Done formula sat in E16 (the S12 row) as =SUM(E4:E15), so S12 showed 95 'Done' out of 1 story and the TOTAL Done cell E17 was empty. The board has been misreporting itself for the whole build; caught by recalculating v014 and reading the numbers rather than trusting them. | FIXED — E16 now carries the same per-sprint COUNTIFS as every other row and E17 is =SUM(E4:E16). Board now reads 96 of 100 (Done + code-complete), agreeing with the tracker rollup computed in a different file. | Board integrity | MeetSync Sprint_Board Done-formula defect (same sheet, different cause)
GAP-V3 | Critical | src/app.ts, package.json, (missing) src/server.ts | NO PROCESS AND NO PRODUCTION OAUTH GATEWAY. createApp() has existed since S1 and nothing ever called listen(); package.json had no start script; the only OAuthGateway implementations were test doubles in test/. The ECA callback, sweep check A7's /health probe, the k6 harness and the softphone's /dial and /log posts all addressed a server that could not be started — and the install flow the 30-minute guide describes had no code path at all. 41 suites at 100% coverage proved every module worked; no product existed around them. | FIXED — src/server.ts + src/main.ts + npm start/dev; src/sfGateway.ts talks to the real token endpoint with code_verifier and classifies 5xx as retryable, 4xx as terminal; guide step 4 now brings the service up before the sweep. | ST-051,ST-086,ST-088 | OnCall GAP-OC1 / EngageOS GAP-E1 (exact class)
GAP-V4 | Critical | src/backup.ts, src/lifecycle.ts, src/sweepChecks.ts, (missing) db/ | NO SCHEMA behind a published policy. Sweep check A5 demanded DATABASE_URL, the ST-090 drill ran backup/restore, and lifecycle.sweep() enforced a 30-day deletion policy the trust page publishes — every one of them against an in-memory Map, with no table, no migration and no runner anywhere in the repo. | FIXED — 5 ordered migrations + npm run migrate + a tested planner (filename order, never re-run, checksum drift is a hard error). Org-scoped tables cascade on delete so the F-V01/F-V08 breach class cannot recur at the storage layer. See R-V11 for what is still open. | ST-052,ST-090,R-V4 | OnCall GAP-OC2 / EngageOS GAP-E2
GAP-V5 | Low | .github/workflows/ci.yml | CI pinned Node 20 on both jobs. Node 20 reached end of life in April 2026; the local toolchain already runs 22, so CI was validating against a runtime nobody ships on. | FIXED — Node 22, with a regression that fails the build if a past-EOL pin returns. | ST-085/086 | TestPulse nodejs20→22; VoiceBridge VER-V04 sourceApiVersion 61.0→67.0
F-V23 | Critical | src/app.ts /ui routes | INTRODUCED IN v0.14.0 AND CAUGHT BY PASS 3: the seven new screen routes took the org id from the URL and verified nothing, so any caller who knew or guessed an org id could read that org's plan and billing status, invoice list, activation funnel, feature-usage heatmap and open support conversations. Strictly worse than F-V21, which at least required a plausible user id. Closing GAP-V2 opened this; only a review aimed at the newly added surface would have found it. | FIXED — /ui is behind the session boundary; the org served is the session's org, and a URL claiming another org is 403. | GAP-V2,ST-005/015/025/035/045 | MeetSync M-F12 (unauthenticated analytics/admin endpoints)
F-V21 | High | src/app.ts, src/permissions.ts, src/auth.ts | CLOSED (was logged unfixed in v0.14.0): identity was caller-declared — every route read userId from the request body and assertCan() trusted it, so anyone who knew an org id and an owner's user id acted as owner. | FIXED — HMAC-SHA256 sessions over (orgId, userId, issuedAt), constant-time verification, minted only at /oauth/callback, required on every org-scoped route; mismatched claims refused as forgery; VB_SESSION_SECRET required at boot with a 32-char floor; 401/403/400 separated. Dev header auth was deliberately NOT added — there is no bypass to leave switched on by accident. | ST-054,ST-007/017/027/037/047,LC-3 | MeetSync M-F11 (exact class)
F-V24 | Medium | src/store.ts, src/app.ts /oauth/start | The PKCE verifier map had no cap and no sweep, and /oauth/start is a public route — so an unauthenticated caller could grow it indefinitely. OBS-V5 logged this as low on the assumption that only real installs wrote to it; making the route public changed the risk and nobody re-read the observation. | FIXED — expired entries swept on write, FIFO cap at 10k, size observable. Lesson: an observation's severity is a function of who can reach the code, and that changes when routes change. | ST-051 | VoiceBridge F-V05 (bounded ledgers)
F-V25 | Medium | src/sfGateway.ts | No timeout on the Salesforce token endpoint: a hung endpoint hung the install or refresh indefinitely, holding a request open with no status and no user-visible failure. | FIXED — 10s AbortController, classified retryable with a named user action. | ST-051,ST-055 | MeetSync M-F21 (request held open with no status)
F-V26 | Medium | src/server.ts | server.close() waits for every open connection, so one long-lived client could hold the process past the orchestrator's kill window and turn a rolling deploy (ST-092) into a hard kill mid-request. Also F-V26b: the listening log printed the requested port rather than the bound one, so PORT=0 logged 'listening on 0'. | FIXED — drain() exported and tested on both the clean and the forced path; bound port read from server.address(). | ST-092 | New
F-V27 | High | src/flowActions.ts | FLOATING PROMISE BROKE THE FAILURE PATH: invoke() assigned the promise returned by dialer.dial / cadence.enroll / notifier.notify to `output` without awaiting, so a rejection escaped the try/catch that records the failed run and rethrows. Flow's retry contract depends on that path. TypeScript accepts a floating promise as a valid expression, so nothing flagged it. | FIXED — collaborator calls awaited across the whole source, not just the site that failed; pinned by the existing failed-invocation regression, which had been passing against the broken code only because the throw happened synchronously before conversion. | ST-041..050 | MeetSync M-F21 (promise rejection escaping a handler)